## Bands
schedule | band | level | start | finish | activities | work_days | activity_ids
Baseline | Structure | 2 | 2026-03-24 | 2026-04-03 | 6 | 12 | C-02-ST-100 ¦ C-02-ST-110 ¦ C-02-MP-120 ¦ C-02-ST-130 ¦ C-02-ST-140 ¦ C-02-ST-150
Baseline | Structure | 3 | 2026-04-06 | 2026-04-16 | 6 | 12 | C-03-ST-100 ¦ C-03-ST-110 ¦ C-03-MP-120 ¦ C-03-ST-130 ¦ C-03-ST-140 ¦ C-03-ST-150
Baseline | Structure | 4 | 2026-04-17 | 2026-04-29 | 6 | 12 | C-04-ST-100 ¦ C-04-ST-110 ¦ C-04-MP-120 ¦ C-04-ST-130 ¦ C-04-ST-140 ¦ C-04-ST-150
Baseline | Structure | 5 | 2026-04-30 | 2026-05-12 | 6 | 12 | C-05-ST-100 ¦ C-05-ST-110 ¦ C-05-MP-120 ¦ C-05-ST-130 ¦ C-05-ST-140 ¦ C-05-ST-150
Baseline | Structure | 6 | 2026-05-13 | 2026-05-26 | 6 | 12 | C-06-ST-100 ¦ C-06-ST-110 ¦ C-06-MP-120 ¦ C-06-ST-130 ¦ C-06-ST-140 ¦ C-06-ST-150
Baseline | Structure | 7 | 2026-05-27 | 2026-06-08 | 6 | 12 | C-07-ST-100 ¦ C-07-ST-110 ¦ C-07-MP-120 ¦ C-07-ST-130 ¦ C-07-ST-140 ¦ C-07-ST-150
Baseline | Structure | 8 | 2026-06-09 | 2026-06-18 | 6 | 11 | C-08-ST-100 ¦ C-08-ST-110 ¦ C-08-MP-120 ¦ C-08-ST-130 ¦ C-08-ST-140 ¦ C-08-ST-150
Baseline | Structure | 9 | 2026-06-18 | 2026-06-29 | 6 | 11 | C-09-ST-100 ¦ C-09-ST-110 ¦ C-09-MP-120 ¦ C-09-ST-130 ¦ C-09-ST-140 ¦ C-09-ST-150
Baseline | Structure | 10 | 2026-06-29 | 2026-07-09 | 6 | 11 | C-10-ST-100 ¦ C-10-ST-110 ¦ C-10-MP-120 ¦ C-10-ST-130 ¦ C-10-ST-140 ¦ C-10-ST-150
Baseline | Structure | 11 | 2026-07-09 | 2026-07-20 | 6 | 11 | C-11-ST-100 ¦ C-11-ST-110 ¦ C-11-MP-120 ¦ C-11-ST-130 ¦ C-11-ST-140 ¦ C-11-ST-150
Baseline | Structure | 12 | 2026-07-20 | 2026-07-29 | 6 | 11 | C-12-ST-100 ¦ C-12-ST-110 ¦ C-12-MP-120 ¦ C-12-ST-130 ¦ C-12-ST-140 ¦ C-12-ST-150
Baseline | Structure | 14 | 2026-07-30 | 2026-08-10 | 6 | 11 | C-14-ST-100 ¦ C-14-ST-110 ¦ C-14-MP-120 ¦ C-14-ST-130 ¦ C-14-ST-140 ¦ C-14-ST-150
Baseline | Structure | 15 | 2026-08-10 | 2026-08-19 | 6 | 11 | C-15-ST-100 ¦ C-15-ST-110 ¦ C-15-MP-120 ¦ C-15-ST-130 ¦ C-15-ST-140 ¦ C-15-ST-150
Baseline | Structure | 16 | 2026-08-19 | 2026-08-26 | 6 | 9 | C-16-ST-100 ¦ C-16-ST-110 ¦ C-16-MP-120 ¦ C-16-ST-130 ¦ C-16-ST-140 ¦ C-16-ST-150
Baseline | Structure | 17 | 2026-08-26 | 2026-09-02 | 6 | 9 | C-17-ST-100 ¦ C-17-ST-110 ¦ C-17-MP-120 ¦ C-17-ST-130 ¦ C-17-ST-140 ¦ C-17-ST-150
Baseline | Structure | 18 | 2026-09-02 | 2026-09-10 | 6 | 9 | C-18-ST-100 ¦ C-18-ST-110 ¦ C-18-MP-120 ¦ C-18-ST-130 ¦ C-18-ST-140 ¦ C-18-ST-150
Baseline | Structure | 19 | 2026-09-10 | 2026-09-17 | 6 | 9 | C-19-ST-100 ¦ C-19-ST-110 ¦ C-19-MP-120 ¦ C-19-ST-130 ¦ C-19-ST-140 ¦ C-19-ST-150
Baseline | Structure | 20 | 2026-09-17 | 2026-09-24 | 6 | 9 | C-20-ST-100 ¦ C-20-ST-110 ¦ C-20-MP-120 ¦ C-20-ST-130 ¦ C-20-ST-140 ¦ C-20-ST-150
Baseline | Structure | 21 | 2026-09-24 | 2026-10-01 | 6 | 9 | C-21-ST-100 ¦ C-21-ST-110 ¦ C-21-MP-120 ¦ C-21-ST-130 ¦ C-21-ST-140 ¦ C-21-ST-150
Baseline | Structure | 22 | 2026-10-01 | 2026-10-08 | 6 | 9 | C-22-ST-100 ¦ C-22-ST-110 ¦ C-22-MP-120 ¦ C-22-ST-130 ¦ C-22-ST-140 ¦ C-22-ST-150
Baseline | Structure | 23 | 2026-10-08 | 2026-10-15 | 6 | 9 | C-23-ST-100 ¦ C-23-ST-110 ¦ C-23-MP-120 ¦ C-23-ST-130 ¦ C-23-ST-140 ¦ C-23-ST-150
Baseline | Structure | 24 | 2026-10-15 | 2026-10-22 | 6 | 9 | C-24-ST-100 ¦ C-24-ST-110 ¦ C-24-MP-120 ¦ C-24-ST-130 ¦ C-24-ST-140 ¦ C-24-ST-150
Baseline | Structure | 25 | 2026-10-22 | 2026-10-29 | 6 | 9 | C-25-ST-100 ¦ C-25-ST-110 ¦ C-25-MP-120 ¦ C-25-ST-130 ¦ C-25-ST-140 ¦ C-25-ST-150
Baseline | Structure | 26 | 2026-10-29 | 2026-11-05 | 6 | 9 | C-26-ST-100 ¦ C-26-ST-110 ¦ C-26-MP-120 ¦ C-26-ST-130 ¦ C-26-ST-140 ¦ C-26-ST-150
Baseline | Structure | 27 | 2026-11-05 | 2026-11-12 | 6 | 9 | C-27-ST-100 ¦ C-27-ST-110 ¦ C-27-MP-120 ¦ C-27-ST-130 ¦ C-27-ST-140 ¦ C-27-ST-150
Baseline | Structure | 28 | 2026-11-12 | 2026-11-19 | 6 | 9 | C-28-ST-100 ¦ C-28-ST-110 ¦ C-28-MP-120 ¦ C-28-ST-130 ¦ C-28-ST-140 ¦ C-28-ST-150
Baseline | Structure | 29 | 2026-11-19 | 2026-11-30 | 6 | 9 | C-29-ST-100 ¦ C-29-ST-110 ¦ C-29-MP-120 ¦ C-29-ST-130 ¦ C-29-ST-140 ¦ C-29-ST-150
Baseline | Structure | 30 | 2026-11-30 | 2026-12-07 | 6 | 9 | C-30-ST-100 ¦ C-30-ST-110 ¦ C-30-MP-120 ¦ C-30-ST-130 ¦ C-30-ST-140 ¦ C-30-ST-150
Baseline | Structure | 31 | 2026-12-07 | 2026-12-14 | 6 | 9 | C-31-ST-100 ¦ C-31-ST-110 ¦ C-31-MP-120 ¦ C-31-ST-130 ¦ C-31-ST-140 ¦ C-31-ST-150
Baseline | Structure | 32 | 2026-12-14 | 2026-12-23 | 6 | 11 | C-32-ST-100 ¦ C-32-ST-110 ¦ C-32-MP-120 ¦ C-32-ST-130 ¦ C-32-ST-140 ¦ C-32-ST-150
Baseline | Structure | 33 | 2026-12-23 | 2027-01-06 | 6 | 11 | C-33-ST-100 ¦ C-33-MP-120 ¦ C-33-ST-110 ¦ C-33-ST-130 ¦ C-33-ST-140 ¦ C-33-ST-150
Baseline | Structure | 34 | 2027-01-06 | 2027-01-18 | 6 | 11 | C-34-ST-100 ¦ C-34-ST-110 ¦ C-34-MP-120 ¦ C-34-ST-130 ¦ C-34-ST-140 ¦ C-34-ST-150
Baseline | Structure | 35 | 2027-01-18 | 2027-01-27 | 6 | 11 | C-35-ST-100 ¦ C-35-ST-110 ¦ C-35-MP-120 ¦ C-35-ST-130 ¦ C-35-ST-140 ¦ C-35-ST-150
Baseline | Structure | 36 | 2027-01-27 | 2027-02-12 | 9 | 19 | C-36-ST-100 ¦ C-36-MP-120 ¦ C-36-ST-110 ¦ C-36-ST-130 ¦ C-36-ST-140 ¦ C-36-ST-150 ¦ C-36-ST-170 ¦ C-36-ST-180 ¦ C-36-ST-190
Baseline | Structure | 37 | 2027-02-18 | 2027-03-22 | 7 | 14 | C-37-ST-100 ¦ C-37-ST-110 ¦ C-37-MP-120 ¦ C-37-ST-130 ¦ C-37-ST-140 ¦ C-37-ST-150 ¦ C-37-ST-190
Baseline | Structure | 38 | 2027-03-02 | 2027-03-05 | 4 | 6 | C-38-ST-100 ¦ C-38-ST-110 ¦ C-38-MP-120 ¦ C-38-ST-130
Baseline | Envelope | 1 | 2027-04-14 | 2027-07-19 | 2 | 30 | C-01-ST-400 ¦ C-01-EX-100
Baseline | Envelope | 2 | 2026-05-28 | 2026-07-17 | 2 | 16 | C-02-ST-400 ¦ C-02-EX-100
Baseline | Envelope | 3 | 2026-06-11 | 2026-07-31 | 2 | 16 | C-03-ST-400 ¦ C-03-EX-100
Baseline | Envelope | 4 | 2026-06-25 | 2026-08-14 | 2 | 16 | C-04-ST-400 ¦ C-04-EX-100
Baseline | Envelope | 5 | 2026-07-10 | 2026-08-28 | 2 | 16 | C-05-ST-400 ¦ C-05-EX-100
Baseline | Envelope | 6 | 2026-07-24 | 2026-09-09 | 2 | 16 | C-06-ST-400 ¦ C-06-EX-100
Baseline | Envelope | 7 | 2026-08-07 | 2026-09-21 | 2 | 17 | C-07-ST-400 ¦ C-07-EX-100
Baseline | Envelope | 8 | 2026-08-21 | 2026-09-30 | 2 | 14 | C-08-ST-400 ¦ C-08-EX-100
Baseline | Envelope | 9 | 2026-09-01 | 2026-10-09 | 2 | 14 | C-09-ST-400 ¦ C-09-EX-100
Baseline | Envelope | 10 | 2026-09-11 | 2026-10-20 | 2 | 14 | C-10-ST-400 ¦ C-10-EX-100
Baseline | Envelope | 11 | 2026-09-22 | 2026-10-29 | 2 | 14 | C-11-ST-400 ¦ C-11-EX-100
Baseline | Envelope | 12 | 2026-10-01 | 2026-11-09 | 2 | 14 | C-12-ST-400 ¦ C-12-EX-100
Baseline | Envelope | 14 | 2026-10-12 | 2026-11-18 | 2 | 14 | C-14-ST-400 ¦ C-14-EX-100
Baseline | Envelope | 15 | 2026-10-21 | 2026-12-01 | 2 | 14 | C-15-ST-400 ¦ C-15-EX-100
Baseline | Envelope | 16 | 2026-10-30 | 2026-12-10 | 2 | 14 | C-16-ST-400 ¦ C-16-EX-100
Baseline | Envelope | 17 | 2026-11-10 | 2026-12-21 | 2 | 14 | C-17-ST-400 ¦ C-17-EX-100
Baseline | Envelope | 18 | 2026-11-19 | 2026-12-31 | 2 | 14 | C-18-ST-400 ¦ C-18-EX-100
Baseline | Envelope | 19 | 2026-12-02 | 2027-01-12 | 2 | 14 | C-19-ST-400 ¦ C-19-EX-100
Baseline | Envelope | 20 | 2026-12-11 | 2027-01-21 | 2 | 14 | C-20-ST-400 ¦ C-20-EX-100
Baseline | Envelope | 21 | 2026-12-22 | 2027-02-01 | 2 | 14 | C-21-ST-400 ¦ C-21-EX-100
Baseline | Envelope | 22 | 2027-01-04 | 2027-02-10 | 2 | 14 | C-22-ST-400 ¦ C-22-EX-100
Baseline | Envelope | 23 | 2027-01-13 | 2027-02-19 | 2 | 14 | C-23-ST-400 ¦ C-23-EX-100
Baseline | Envelope | 24 | 2027-01-22 | 2027-03-02 | 2 | 14 | C-24-ST-400 ¦ C-24-EX-100
Baseline | Envelope | 25 | 2027-02-02 | 2027-03-11 | 2 | 14 | C-25-ST-400 ¦ C-25-EX-100
Baseline | Envelope | 26 | 2027-02-11 | 2027-03-22 | 2 | 14 | C-26-ST-400 ¦ C-26-EX-100
Baseline | Envelope | 27 | 2027-02-22 | 2027-03-31 | 2 | 14 | C-27-ST-400 ¦ C-27-EX-100
Baseline | Envelope | 28 | 2027-03-03 | 2027-04-09 | 2 | 14 | C-28-ST-400 ¦ C-28-EX-100
Baseline | Envelope | 29 | 2027-03-12 | 2027-04-20 | 2 | 14 | C-29-ST-400 ¦ C-29-EX-100
Baseline | Envelope | 30 | 2027-03-23 | 2027-04-29 | 2 | 14 | C-30-ST-400 ¦ C-30-EX-100
Baseline | Envelope | 31 | 2027-04-01 | 2027-05-10 | 2 | 14 | C-31-ST-400 ¦ C-31-EX-100
Baseline | Envelope | 32 | 2027-04-12 | 2027-05-19 | 2 | 14 | C-32-ST-400 ¦ C-32-EX-100
Baseline | Envelope | 33 | 2027-04-21 | 2027-05-28 | 2 | 14 | C-33-ST-400 ¦ C-33-EX-100
Baseline | Envelope | 34 | 2027-04-30 | 2027-06-09 | 2 | 14 | C-34-ST-400 ¦ C-34-EX-100
Baseline | Envelope | 35 | 2027-05-11 | 2027-06-18 | 2 | 14 | C-35-ST-400 ¦ C-35-EX-100
Baseline | Envelope | 36 | 2027-03-18 | 2027-03-24 | 1 | 5 | C-36-ST-400
Baseline | Framing and MEP rough-in | 1 | 2027-04-28 | 2027-07-14 | 9 | 96 | C-01-UC-FN-100 ¦ C-01-UC-FN-120 ¦ C-01-UC-MP-140 ¦ C-01-UC-MP-150 ¦ C-01-UC-FN-130 ¦ C-01-UC-MP-160 ¦ C-01-UC-MP-170 ¦ C-01-UC-MP-180 ¦ C-01-UC-MP-190
Baseline | Framing and MEP rough-in | 2 | 2026-06-11 | 2026-08-05 | 14 | 78 | C-02-UC-FN-100 ¦ C-02-UC-FN-110 ¦ C-02-UC-MP-100 ¦ C-02-UC-FN-120 ¦ C-02-UC-MP-120 ¦ C-02-UC-MP-130 ¦ C-02-UC-MP-140 ¦ C-02-UC-MP-150 ¦ C-02-UC-FN-130 ¦ C-02-UC-MP-160 ¦ C-02-UC-MP-110 ¦ C-02-UC-MP-170 ¦ C-02-UC-MP-180 ¦ C-02-UC-MP-190
Baseline | Framing and MEP rough-in | 3 | 2026-06-25 | 2026-08-14 | 14 | 86 | C-03-U-FN-100 ¦ C-03-U-MP-100 ¦ C-03-U-FN-110 ¦ C-03-U-FN-120 ¦ C-03-U-MP-120 ¦ C-03-U-MP-130 ¦ C-03-U-MP-140 ¦ C-03-U-MP-150 ¦ C-03-U-FN-130 ¦ C-03-U-MP-110 ¦ C-03-U-MP-160 ¦ C-03-U-MP-170 ¦ C-03-U-MP-180 ¦ C-03-U-MP-190
Baseline | Framing and MEP rough-in | 4 | 2026-07-10 | 2026-08-28 | 14 | 86 | C-04-U-FN-100 ¦ C-04-U-MP-100 ¦ C-04-U-FN-110 ¦ C-04-U-FN-120 ¦ C-04-U-MP-120 ¦ C-04-U-MP-130 ¦ C-04-U-MP-110 ¦ C-04-U-MP-140 ¦ C-04-U-MP-150 ¦ C-04-U-FN-130 ¦ C-04-U-MP-160 ¦ C-04-U-MP-170 ¦ C-04-U-MP-180 ¦ C-04-U-MP-190
Baseline | Framing and MEP rough-in | 5 | 2026-07-24 | 2026-09-14 | 14 | 86 | C-05-U-FN-100 ¦ C-05-U-MP-100 ¦ C-05-U-FN-110 ¦ C-05-U-FN-120 ¦ C-05-U-MP-110 ¦ C-05-U-MP-120 ¦ C-05-U-MP-130 ¦ C-05-U-MP-140 ¦ C-05-U-MP-150 ¦ C-05-U-FN-130 ¦ C-05-U-MP-160 ¦ C-05-U-MP-170 ¦ C-05-U-MP-180 ¦ C-05-U-MP-190
Baseline | Framing and MEP rough-in | 6 | 2026-08-07 | 2026-09-28 | 14 | 86 | C-06-U-FN-100 ¦ C-06-U-MP-100 ¦ C-06-U-FN-110 ¦ C-06-U-FN-120 ¦ C-06-U-MP-110 ¦ C-06-U-MP-120 ¦ C-06-U-MP-130 ¦ C-06-U-MP-140 ¦ C-06-U-MP-150 ¦ C-06-U-FN-130 ¦ C-06-U-MP-160 ¦ C-06-U-MP-170 ¦ C-06-U-MP-180 ¦ C-06-U-MP-190
Baseline | Framing and MEP rough-in | 7 | 2026-08-21 | 2026-10-12 | 14 | 92 | C-07-U-FN-100 ¦ C-07-U-MP-100 ¦ C-07-U-FN-110 ¦ C-07-U-FN-120 ¦ C-07-U-MP-110 ¦ C-07-U-MP-120 ¦ C-07-U-MP-130 ¦ C-07-U-MP-140 ¦ C-07-U-MP-150 ¦ C-07-U-MP-160 ¦ C-07-U-FN-130 ¦ C-07-U-MP-170 ¦ C-07-U-MP-180 ¦ C-07-U-MP-190
Baseline | Framing and MEP rough-in | 8 | 2026-09-01 | 2026-10-26 | 14 | 89 | C-08-U-FN-100 ¦ C-08-U-MP-100 ¦ C-08-U-FN-110 ¦ C-08-U-MP-110 ¦ C-08-U-MP-120 ¦ C-08-U-MP-130 ¦ C-08-U-FN-120 ¦ C-08-U-MP-140 ¦ C-08-U-MP-150 ¦ C-08-U-MP-160 ¦ C-08-U-FN-130 ¦ C-08-U-MP-170 ¦ C-08-U-MP-180 ¦ C-08-U-MP-190
Baseline | Framing and MEP rough-in | 9 | 2026-09-11 | 2026-11-04 | 14 | 89 | C-09-U-FN-100 ¦ C-09-U-MP-100 ¦ C-09-U-FN-110 ¦ C-09-U-MP-110 ¦ C-09-U-MP-120 ¦ C-09-U-MP-130 ¦ C-09-U-FN-120 ¦ C-09-U-MP-140 ¦ C-09-U-MP-150 ¦ C-09-U-MP-160 ¦ C-09-U-FN-130 ¦ C-09-U-MP-170 ¦ C-09-U-MP-180 ¦ C-09-U-MP-190
Baseline | Framing and MEP rough-in | 10 | 2026-09-22 | 2026-11-13 | 14 | 89 | C-10-U-FN-100 ¦ C-10-U-MP-100 ¦ C-10-U-FN-110 ¦ C-10-U-MP-110 ¦ C-10-U-MP-120 ¦ C-10-U-MP-130 ¦ C-10-U-FN-120 ¦ C-10-U-MP-140 ¦ C-10-U-MP-150 ¦ C-10-U-MP-160 ¦ C-10-U-FN-130 ¦ C-10-U-MP-170 ¦ C-10-U-MP-180 ¦ C-10-U-MP-190
Baseline | Framing and MEP rough-in | 11 | 2026-10-01 | 2026-11-24 | 14 | 89 | C-11-U-FN-100 ¦ C-11-U-MP-100 ¦ C-11-U-FN-110 ¦ C-11-U-MP-110 ¦ C-11-U-MP-120 ¦ C-11-U-MP-130 ¦ C-11-U-FN-120 ¦ C-11-U-MP-140 ¦ C-11-U-MP-150 ¦ C-11-U-MP-160 ¦ C-11-U-FN-130 ¦ C-11-U-MP-170 ¦ C-11-U-MP-180 ¦ C-11-U-MP-190
Baseline | Framing and MEP rough-in | 12 | 2026-10-12 | 2026-12-07 | 14 | 89 | C-12-U-FN-100 ¦ C-12-U-MP-100 ¦ C-12-U-FN-110 ¦ C-12-U-MP-110 ¦ C-12-U-MP-120 ¦ C-12-U-MP-130 ¦ C-12-U-FN-120 ¦ C-12-U-MP-140 ¦ C-12-U-MP-150 ¦ C-12-U-MP-160 ¦ C-12-U-FN-130 ¦ C-12-U-MP-170 ¦ C-12-U-MP-180 ¦ C-12-U-MP-190
Baseline | Framing and MEP rough-in | 14 | 2026-10-21 | 2026-12-16 | 14 | 89 | C-14-U-FN-100 ¦ C-14-U-MP-100 ¦ C-14-U-FN-110 ¦ C-14-U-MP-110 ¦ C-14-U-MP-120 ¦ C-14-U-MP-130 ¦ C-14-U-FN-120 ¦ C-14-U-MP-140 ¦ C-14-U-MP-150 ¦ C-14-U-MP-160 ¦ C-14-U-FN-130 ¦ C-14-U-MP-170 ¦ C-14-U-MP-180 ¦ C-14-U-MP-190
Baseline | Framing and MEP rough-in | 15 | 2026-10-30 | 2026-12-28 | 14 | 89 | C-15-U-FN-100 ¦ C-15-U-MP-100 ¦ C-15-U-FN-110 ¦ C-15-U-MP-110 ¦ C-15-U-MP-120 ¦ C-15-U-MP-130 ¦ C-15-U-FN-120 ¦ C-15-U-MP-140 ¦ C-15-U-MP-150 ¦ C-15-U-MP-160 ¦ C-15-U-FN-130 ¦ C-15-U-MP-170 ¦ C-15-U-MP-180 ¦ C-15-U-MP-190
Baseline | Framing and MEP rough-in | 16 | 2026-11-10 | 2027-01-08 | 14 | 89 | C-16-U-FN-100 ¦ C-16-U-MP-100 ¦ C-16-U-FN-110 ¦ C-16-U-MP-110 ¦ C-16-U-MP-120 ¦ C-16-U-MP-130 ¦ C-16-U-FN-120 ¦ C-16-U-MP-140 ¦ C-16-U-MP-150 ¦ C-16-U-MP-160 ¦ C-16-U-FN-130 ¦ C-16-U-MP-170 ¦ C-16-U-MP-180 ¦ C-16-U-MP-190
Baseline | Framing and MEP rough-in | 17 | 2026-11-19 | 2027-01-20 | 14 | 89 | C-17-U-FN-100 ¦ C-17-U-MP-100 ¦ C-17-U-FN-110 ¦ C-17-U-MP-110 ¦ C-17-U-MP-120 ¦ C-17-U-MP-130 ¦ C-17-U-FN-120 ¦ C-17-U-MP-140 ¦ C-17-U-MP-150 ¦ C-17-U-MP-160 ¦ C-17-U-FN-130 ¦ C-17-U-MP-170 ¦ C-17-U-MP-180 ¦ C-17-U-MP-190
Baseline | Framing and MEP rough-in | 18 | 2026-12-02 | 2027-02-01 | 14 | 89 | C-18-U-FN-100 ¦ C-18-U-MP-100 ¦ C-18-U-FN-110 ¦ C-18-U-MP-110 ¦ C-18-U-MP-120 ¦ C-18-U-MP-130 ¦ C-18-U-FN-120 ¦ C-18-U-MP-140 ¦ C-18-U-MP-150 ¦ C-18-U-MP-160 ¦ C-18-U-FN-130 ¦ C-18-U-MP-170 ¦ C-18-U-MP-180 ¦ C-18-U-MP-190
Baseline | Framing and MEP rough-in | 19 | 2026-12-11 | 2027-02-11 | 14 | 89 | C-19-U-FN-100 ¦ C-19-U-MP-100 ¦ C-19-U-FN-110 ¦ C-19-U-MP-110 ¦ C-19-U-MP-120 ¦ C-19-U-MP-130 ¦ C-19-U-FN-120 ¦ C-19-U-MP-140 ¦ C-19-U-MP-150 ¦ C-19-U-MP-160 ¦ C-19-U-FN-130 ¦ C-19-U-MP-170 ¦ C-19-U-MP-180 ¦ C-19-U-MP-190
Baseline | Framing and MEP rough-in | 20 | 2026-12-22 | 2027-02-23 | 14 | 89 | C-20-U-FN-100 ¦ C-20-U-MP-100 ¦ C-20-U-FN-110 ¦ C-20-U-MP-110 ¦ C-20-U-MP-120 ¦ C-20-U-MP-130 ¦ C-20-U-FN-120 ¦ C-20-U-MP-140 ¦ C-20-U-MP-150 ¦ C-20-U-MP-160 ¦ C-20-U-FN-130 ¦ C-20-U-MP-170 ¦ C-20-U-MP-180 ¦ C-20-U-MP-190
Baseline | Framing and MEP rough-in | 21 | 2027-01-04 | 2027-03-05 | 14 | 89 | C-21-U-FN-100 ¦ C-21-U-MP-100 ¦ C-21-U-FN-110 ¦ C-21-U-MP-110 ¦ C-21-U-MP-120 ¦ C-21-U-MP-130 ¦ C-21-U-FN-120 ¦ C-21-U-MP-140 ¦ C-21-U-MP-150 ¦ C-21-U-MP-160 ¦ C-21-U-FN-130 ¦ C-21-U-MP-170 ¦ C-21-U-MP-180 ¦ C-21-U-MP-190
Baseline | Framing and MEP rough-in | 22 | 2027-01-13 | 2027-03-17 | 14 | 89 | C-22-U-FN-100 ¦ C-22-U-MP-100 ¦ C-22-U-FN-110 ¦ C-22-U-MP-110 ¦ C-22-U-MP-120 ¦ C-22-U-MP-130 ¦ C-22-U-FN-120 ¦ C-22-U-MP-140 ¦ C-22-U-MP-150 ¦ C-22-U-MP-160 ¦ C-22-U-FN-130 ¦ C-22-U-MP-170 ¦ C-22-U-MP-180 ¦ C-22-U-MP-190
Baseline | Framing and MEP rough-in | 23 | 2027-01-22 | 2027-03-29 | 14 | 89 | C-23-U-FN-100 ¦ C-23-U-MP-100 ¦ C-23-U-FN-110 ¦ C-23-U-MP-110 ¦ C-23-U-MP-120 ¦ C-23-U-MP-130 ¦ C-23-U-FN-120 ¦ C-23-U-MP-140 ¦ C-23-U-MP-150 ¦ C-23-U-MP-160 ¦ C-23-U-FN-130 ¦ C-23-U-MP-170 ¦ C-23-U-MP-180 ¦ C-23-U-MP-190
Baseline | Framing and MEP rough-in | 24 | 2027-02-02 | 2027-04-08 | 14 | 89 | C-24-U-FN-100 ¦ C-24-U-MP-100 ¦ C-24-U-FN-110 ¦ C-24-U-MP-110 ¦ C-24-U-MP-120 ¦ C-24-U-MP-130 ¦ C-24-U-FN-120 ¦ C-24-U-MP-140 ¦ C-24-U-MP-150 ¦ C-24-U-MP-160 ¦ C-24-U-FN-130 ¦ C-24-U-MP-170 ¦ C-24-U-MP-180 ¦ C-24-U-MP-190
Baseline | Framing and MEP rough-in | 25 | 2027-02-11 | 2027-04-20 | 14 | 89 | C-25-U-FN-100 ¦ C-25-U-MP-100 ¦ C-25-U-FN-110 ¦ C-25-U-MP-110 ¦ C-25-U-MP-120 ¦ C-25-U-MP-130 ¦ C-25-U-FN-120 ¦ C-25-U-MP-140 ¦ C-25-U-MP-150 ¦ C-25-U-MP-160 ¦ C-25-U-FN-130 ¦ C-25-U-MP-170 ¦ C-25-U-MP-180 ¦ C-25-U-MP-190
Baseline | Framing and MEP rough-in | 26 | 2027-02-22 | 2027-04-29 | 14 | 89 | C-26-U-FN-100 ¦ C-26-U-MP-100 ¦ C-26-U-FN-110 ¦ C-26-U-MP-110 ¦ C-26-U-MP-120 ¦ C-26-U-MP-130 ¦ C-26-U-FN-120 ¦ C-26-U-MP-140 ¦ C-26-U-MP-150 ¦ C-26-U-MP-160 ¦ C-26-U-FN-130 ¦ C-26-U-MP-170 ¦ C-26-U-MP-180 ¦ C-26-U-MP-190
Baseline | Framing and MEP rough-in | 27 | 2027-03-03 | 2027-05-10 | 14 | 89 | C-27-U-FN-100 ¦ C-27-U-MP-100 ¦ C-27-U-FN-110 ¦ C-27-U-MP-110 ¦ C-27-U-MP-120 ¦ C-27-U-MP-130 ¦ C-27-U-FN-120 ¦ C-27-U-MP-140 ¦ C-27-U-MP-150 ¦ C-27-U-MP-160 ¦ C-27-U-FN-130 ¦ C-27-U-MP-170 ¦ C-27-U-MP-180 ¦ C-27-U-MP-190
Baseline | Framing and MEP rough-in | 28 | 2027-03-12 | 2027-05-19 | 14 | 89 | C-28-U-FN-100 ¦ C-28-U-MP-100 ¦ C-28-U-FN-110 ¦ C-28-U-MP-110 ¦ C-28-U-MP-120 ¦ C-28-U-MP-130 ¦ C-28-U-FN-120 ¦ C-28-U-MP-140 ¦ C-28-U-MP-150 ¦ C-28-U-MP-160 ¦ C-28-U-FN-130 ¦ C-28-U-MP-170 ¦ C-28-U-MP-180 ¦ C-28-U-MP-190
Baseline | Framing and MEP rough-in | 29 | 2027-03-23 | 2027-05-28 | 14 | 89 | C-29-U-FN-100 ¦ C-29-U-MP-100 ¦ C-29-U-FN-110 ¦ C-29-U-MP-110 ¦ C-29-U-MP-120 ¦ C-29-U-MP-130 ¦ C-29-U-FN-120 ¦ C-29-U-MP-140 ¦ C-29-U-MP-150 ¦ C-29-U-MP-160 ¦ C-29-U-FN-130 ¦ C-29-U-MP-170 ¦ C-29-U-MP-180 ¦ C-29-U-MP-190
Baseline | Framing and MEP rough-in | 30 | 2027-04-01 | 2027-06-09 | 14 | 89 | C-30-U-FN-100 ¦ C-30-U-MP-100 ¦ C-30-U-FN-110 ¦ C-30-U-MP-110 ¦ C-30-U-MP-120 ¦ C-30-U-MP-130 ¦ C-30-U-FN-120 ¦ C-30-U-MP-140 ¦ C-30-U-MP-150 ¦ C-30-U-MP-160 ¦ C-30-U-FN-130 ¦ C-30-U-MP-170 ¦ C-30-U-MP-180 ¦ C-30-U-MP-190
Baseline | Framing and MEP rough-in | 31 | 2027-04-12 | 2027-06-18 | 14 | 89 | C-31-U-FN-100 ¦ C-31-U-MP-100 ¦ C-31-U-FN-110 ¦ C-31-U-MP-110 ¦ C-31-U-MP-120 ¦ C-31-U-MP-130 ¦ C-31-U-FN-120 ¦ C-31-U-MP-140 ¦ C-31-U-MP-150 ¦ C-31-U-MP-160 ¦ C-31-U-FN-130 ¦ C-31-U-MP-170 ¦ C-31-U-MP-180 ¦ C-31-U-MP-190
Baseline | Framing and MEP rough-in | 32 | 2027-04-21 | 2027-06-29 | 14 | 89 | C-32-U-FN-100 ¦ C-32-U-MP-100 ¦ C-32-U-FN-110 ¦ C-32-U-MP-110 ¦ C-32-U-MP-120 ¦ C-32-U-MP-130 ¦ C-32-U-FN-120 ¦ C-32-U-MP-140 ¦ C-32-U-MP-150 ¦ C-32-U-MP-160 ¦ C-32-U-FN-130 ¦ C-32-U-MP-170 ¦ C-32-U-MP-180 ¦ C-32-U-MP-190
Baseline | Framing and MEP rough-in | 33 | 2027-04-30 | 2027-07-09 | 14 | 89 | C-33-U-FN-100 ¦ C-33-U-MP-100 ¦ C-33-U-FN-110 ¦ C-33-U-MP-110 ¦ C-33-U-MP-120 ¦ C-33-U-MP-130 ¦ C-33-U-FN-120 ¦ C-33-U-MP-140 ¦ C-33-U-MP-150 ¦ C-33-U-MP-160 ¦ C-33-U-FN-130 ¦ C-33-U-MP-170 ¦ C-33-U-MP-180 ¦ C-33-U-MP-190
Baseline | Framing and MEP rough-in | 34 | 2027-05-11 | 2027-07-20 | 14 | 89 | C-34-U-FN-100 ¦ C-34-U-MP-100 ¦ C-34-U-FN-110 ¦ C-34-U-MP-110 ¦ C-34-U-MP-120 ¦ C-34-U-MP-130 ¦ C-34-U-FN-120 ¦ C-34-U-MP-140 ¦ C-34-U-MP-150 ¦ C-34-U-MP-160 ¦ C-34-U-FN-130 ¦ C-34-U-MP-170 ¦ C-34-U-MP-180 ¦ C-34-U-MP-190
Baseline | Framing and MEP rough-in | 35 | 2027-05-20 | 2027-07-29 | 14 | 89 | C-35-U-FN-100 ¦ C-35-U-MP-100 ¦ C-35-U-FN-110 ¦ C-35-U-MP-110 ¦ C-35-U-MP-120 ¦ C-35-U-MP-130 ¦ C-35-U-FN-120 ¦ C-35-U-MP-140 ¦ C-35-U-MP-150 ¦ C-35-U-MP-160 ¦ C-35-U-FN-130 ¦ C-35-U-MP-170 ¦ C-35-U-MP-180 ¦ C-35-U-MP-190
Baseline | Framing and MEP rough-in | 36 | 2027-03-25 | 2027-07-21 | 13 | 60 | C-36-IN-MP-100 ¦ C-36-IN-MP-110 ¦ C-36-IN-MP-120 ¦ C-36-IN-MP-130 ¦ C-36-IN-FN-100 ¦ C-36-IN-FN-110 ¦ C-36-IN-FN-120 ¦ C-36-IN-FN-130 ¦ C-36-IN-MP-140 ¦ C-36-IN-MP-150 ¦ C-36-IN-MP-160 ¦ C-36-IN-MP-170 ¦ C-36-IN-MP-180
Baseline | Drywall and prime paint | 1 | 2027-07-20 | 2027-08-13 | 5 | 26 | C-01-UC-FN-200 ¦ C-01-UC-FN-210 ¦ C-01-UC-FN-230 ¦ C-01-UC-FN-270 ¦ C-01-UC-FN-260
Baseline | Drywall and prime paint | 2 | 2026-08-06 | 2026-09-18 | 8 | 48 | C-02-UC-FN-200 ¦ C-02-UC-FN-210 ¦ C-02-UC-FN-220 ¦ C-02-UC-FN-230 ¦ C-02-UC-FN-240 ¦ C-02-UC-FN-250 ¦ C-02-UC-FN-260 ¦ C-02-UC-FN-270
Baseline | Drywall and prime paint | 3 | 2026-08-17 | 2026-09-29 | 8 | 48 | C-03-U-FN-200 ¦ C-03-U-FN-210 ¦ C-03-U-FN-220 ¦ C-03-U-FN-230 ¦ C-03-U-FN-240 ¦ C-03-U-FN-250 ¦ C-03-U-FN-260 ¦ C-03-U-FN-270
Baseline | Drywall and prime paint | 4 | 2026-08-31 | 2026-10-13 | 8 | 48 | C-04-U-FN-200 ¦ C-04-U-FN-210 ¦ C-04-U-FN-220 ¦ C-04-U-FN-230 ¦ C-04-U-FN-240 ¦ C-04-U-FN-250 ¦ C-04-U-FN-260 ¦ C-04-U-FN-270
Baseline | Drywall and prime paint | 5 | 2026-09-15 | 2026-10-27 | 8 | 48 | C-05-U-FN-200 ¦ C-05-U-FN-210 ¦ C-05-U-FN-220 ¦ C-05-U-FN-230 ¦ C-05-U-FN-240 ¦ C-05-U-FN-250 ¦ C-05-U-FN-260 ¦ C-05-U-FN-270
Baseline | Drywall and prime paint | 6 | 2026-09-29 | 2026-11-10 | 8 | 48 | C-06-U-FN-200 ¦ C-06-U-FN-210 ¦ C-06-U-FN-220 ¦ C-06-U-FN-230 ¦ C-06-U-FN-240 ¦ C-06-U-FN-250 ¦ C-06-U-FN-260 ¦ C-06-U-FN-270
Baseline | Drywall and prime paint | 7 | 2026-10-13 | 2026-12-14 | 8 | 62 | C-07-U-FN-200 ¦ C-07-U-FN-210 ¦ C-07-U-FN-220 ¦ C-07-U-FN-230 ¦ C-07-U-FN-240 ¦ C-07-U-FN-250 ¦ C-07-U-FN-260 ¦ C-07-U-FN-270
Baseline | Drywall and prime paint | 8 | 2026-10-27 | 2026-12-29 | 8 | 62 | C-08-U-FN-200 ¦ C-08-U-FN-210 ¦ C-08-U-FN-220 ¦ C-08-U-FN-230 ¦ C-08-U-FN-240 ¦ C-08-U-FN-250 ¦ C-08-U-FN-260 ¦ C-08-U-FN-270
Baseline | Drywall and prime paint | 9 | 2026-11-05 | 2027-01-08 | 8 | 62 | C-09-U-FN-200 ¦ C-09-U-FN-210 ¦ C-09-U-FN-220 ¦ C-09-U-FN-230 ¦ C-09-U-FN-240 ¦ C-09-U-FN-250 ¦ C-09-U-FN-260 ¦ C-09-U-FN-270
Baseline | Drywall and prime paint | 10 | 2026-11-16 | 2027-01-19 | 8 | 62 | C-10-U-FN-200 ¦ C-10-U-FN-210 ¦ C-10-U-FN-220 ¦ C-10-U-FN-230 ¦ C-10-U-FN-240 ¦ C-10-U-FN-250 ¦ C-10-U-FN-260 ¦ C-10-U-FN-270
Baseline | Drywall and prime paint | 11 | 2026-11-25 | 2027-01-28 | 8 | 62 | C-11-U-FN-200 ¦ C-11-U-FN-210 ¦ C-11-U-FN-220 ¦ C-11-U-FN-230 ¦ C-11-U-FN-240 ¦ C-11-U-FN-250 ¦ C-11-U-FN-260 ¦ C-11-U-FN-270
Baseline | Drywall and prime paint | 12 | 2026-12-08 | 2027-02-08 | 8 | 62 | C-12-U-FN-200 ¦ C-12-U-FN-210 ¦ C-12-U-FN-220 ¦ C-12-U-FN-230 ¦ C-12-U-FN-240 ¦ C-12-U-FN-250 ¦ C-12-U-FN-260 ¦ C-12-U-FN-270
Baseline | Drywall and prime paint | 14 | 2026-12-17 | 2027-02-17 | 8 | 62 | C-14-U-FN-200 ¦ C-14-U-FN-210 ¦ C-14-U-FN-220 ¦ C-14-U-FN-230 ¦ C-14-U-FN-240 ¦ C-14-U-FN-250 ¦ C-14-U-FN-260 ¦ C-14-U-FN-270
Baseline | Drywall and prime paint | 15 | 2026-12-29 | 2027-02-26 | 8 | 62 | C-15-U-FN-200 ¦ C-15-U-FN-210 ¦ C-15-U-FN-220 ¦ C-15-U-FN-230 ¦ C-15-U-FN-240 ¦ C-15-U-FN-250 ¦ C-15-U-FN-260 ¦ C-15-U-FN-270
Baseline | Drywall and prime paint | 16 | 2027-01-11 | 2027-03-10 | 8 | 62 | C-16-U-FN-200 ¦ C-16-U-FN-210 ¦ C-16-U-FN-220 ¦ C-16-U-FN-230 ¦ C-16-U-FN-240 ¦ C-16-U-FN-250 ¦ C-16-U-FN-260 ¦ C-16-U-FN-270
Baseline | Drywall and prime paint | 17 | 2027-01-21 | 2027-03-22 | 8 | 62 | C-17-U-FN-200 ¦ C-17-U-FN-210 ¦ C-17-U-FN-220 ¦ C-17-U-FN-230 ¦ C-17-U-FN-240 ¦ C-17-U-FN-250 ¦ C-17-U-FN-260 ¦ C-17-U-FN-270
Baseline | Drywall and prime paint | 18 | 2027-02-02 | 2027-04-01 | 8 | 62 | C-18-U-FN-200 ¦ C-18-U-FN-210 ¦ C-18-U-FN-220 ¦ C-18-U-FN-230 ¦ C-18-U-FN-240 ¦ C-18-U-FN-250 ¦ C-18-U-FN-260 ¦ C-18-U-FN-270
Baseline | Drywall and prime paint | 19 | 2027-02-12 | 2027-04-13 | 8 | 62 | C-19-U-FN-200 ¦ C-19-U-FN-210 ¦ C-19-U-FN-220 ¦ C-19-U-FN-230 ¦ C-19-U-FN-240 ¦ C-19-U-FN-250 ¦ C-19-U-FN-260 ¦ C-19-U-FN-270
Baseline | Drywall and prime paint | 20 | 2027-02-24 | 2027-04-23 | 8 | 62 | C-20-U-FN-200 ¦ C-20-U-FN-210 ¦ C-20-U-FN-220 ¦ C-20-U-FN-230 ¦ C-20-U-FN-240 ¦ C-20-U-FN-250 ¦ C-20-U-FN-260 ¦ C-20-U-FN-270
Baseline | Drywall and prime paint | 21 | 2027-03-08 | 2027-05-05 | 8 | 62 | C-21-U-FN-200 ¦ C-21-U-FN-210 ¦ C-21-U-FN-220 ¦ C-21-U-FN-230 ¦ C-21-U-FN-240 ¦ C-21-U-FN-250 ¦ C-21-U-FN-260 ¦ C-21-U-FN-270
Baseline | Drywall and prime paint | 22 | 2027-03-18 | 2027-05-17 | 8 | 62 | C-22-U-FN-200 ¦ C-22-U-FN-210 ¦ C-22-U-FN-220 ¦ C-22-U-FN-230 ¦ C-22-U-FN-240 ¦ C-22-U-FN-250 ¦ C-22-U-FN-260 ¦ C-22-U-FN-270
Baseline | Drywall and prime paint | 23 | 2027-03-30 | 2027-05-27 | 8 | 62 | C-23-U-FN-200 ¦ C-23-U-FN-210 ¦ C-23-U-FN-220 ¦ C-23-U-FN-230 ¦ C-23-U-FN-240 ¦ C-23-U-FN-250 ¦ C-23-U-FN-260 ¦ C-23-U-FN-270
Baseline | Drywall and prime paint | 24 | 2027-04-09 | 2027-06-09 | 8 | 62 | C-24-U-FN-200 ¦ C-24-U-FN-210 ¦ C-24-U-FN-220 ¦ C-24-U-FN-230 ¦ C-24-U-FN-240 ¦ C-24-U-FN-250 ¦ C-24-U-FN-260 ¦ C-24-U-FN-270
Baseline | Drywall and prime paint | 25 | 2027-04-21 | 2027-06-21 | 8 | 62 | C-25-U-FN-200 ¦ C-25-U-FN-210 ¦ C-25-U-FN-220 ¦ C-25-U-FN-230 ¦ C-25-U-FN-240 ¦ C-25-U-FN-250 ¦ C-25-U-FN-260 ¦ C-25-U-FN-270
Baseline | Drywall and prime paint | 26 | 2027-04-30 | 2027-06-30 | 8 | 62 | C-26-U-FN-200 ¦ C-26-U-FN-210 ¦ C-26-U-FN-220 ¦ C-26-U-FN-230 ¦ C-26-U-FN-240 ¦ C-26-U-FN-250 ¦ C-26-U-FN-260 ¦ C-26-U-FN-270
Baseline | Drywall and prime paint | 27 | 2027-05-11 | 2027-07-12 | 8 | 62 | C-27-U-FN-200 ¦ C-27-U-FN-210 ¦ C-27-U-FN-220 ¦ C-27-U-FN-230 ¦ C-27-U-FN-240 ¦ C-27-U-FN-250 ¦ C-27-U-FN-260 ¦ C-27-U-FN-270
Baseline | Drywall and prime paint | 28 | 2027-05-20 | 2027-07-21 | 8 | 62 | C-28-U-FN-200 ¦ C-28-U-FN-210 ¦ C-28-U-FN-220 ¦ C-28-U-FN-230 ¦ C-28-U-FN-240 ¦ C-28-U-FN-250 ¦ C-28-U-FN-260 ¦ C-28-U-FN-270
Baseline | Drywall and prime paint | 29 | 2027-06-01 | 2027-07-30 | 8 | 62 | C-29-U-FN-200 ¦ C-29-U-FN-210 ¦ C-29-U-FN-220 ¦ C-29-U-FN-230 ¦ C-29-U-FN-240 ¦ C-29-U-FN-250 ¦ C-29-U-FN-260 ¦ C-29-U-FN-270
Baseline | Drywall and prime paint | 30 | 2027-06-10 | 2027-08-10 | 8 | 62 | C-30-U-FN-200 ¦ C-30-U-FN-210 ¦ C-30-U-FN-220 ¦ C-30-U-FN-230 ¦ C-30-U-FN-240 ¦ C-30-U-FN-250 ¦ C-30-U-FN-260 ¦ C-30-U-FN-270
Baseline | Drywall and prime paint | 31 | 2027-06-21 | 2027-08-19 | 8 | 62 | C-31-U-FN-200 ¦ C-31-U-FN-210 ¦ C-31-U-FN-220 ¦ C-31-U-FN-230 ¦ C-31-U-FN-240 ¦ C-31-U-FN-250 ¦ C-31-U-FN-260 ¦ C-31-U-FN-270
Baseline | Drywall and prime paint | 32 | 2027-06-30 | 2027-08-30 | 8 | 62 | C-32-U-FN-200 ¦ C-32-U-FN-210 ¦ C-32-U-FN-220 ¦ C-32-U-FN-230 ¦ C-32-U-FN-240 ¦ C-32-U-FN-250 ¦ C-32-U-FN-260 ¦ C-32-U-FN-270
Baseline | Drywall and prime paint | 33 | 2027-07-12 | 2027-09-09 | 8 | 62 | C-33-U-FN-200 ¦ C-33-U-FN-210 ¦ C-33-U-FN-220 ¦ C-33-U-FN-230 ¦ C-33-U-FN-240 ¦ C-33-U-FN-250 ¦ C-33-U-FN-260 ¦ C-33-U-FN-270
Baseline | Drywall and prime paint | 34 | 2027-07-21 | 2027-09-20 | 8 | 62 | C-34-U-FN-200 ¦ C-34-U-FN-210 ¦ C-34-U-FN-220 ¦ C-34-U-FN-230 ¦ C-34-U-FN-240 ¦ C-34-U-FN-250 ¦ C-34-U-FN-260 ¦ C-34-U-FN-270
Baseline | Drywall and prime paint | 35 | 2027-07-30 | 2027-10-05 | 8 | 62 | C-35-U-FN-200 ¦ C-35-U-FN-210 ¦ C-35-U-FN-230 ¦ C-35-U-FN-220 ¦ C-35-U-FN-240 ¦ C-35-U-FN-250 ¦ C-35-U-FN-260 ¦ C-35-U-FN-270
Baseline | Drywall and prime paint | 36 | 2027-07-26 | 2027-08-24 | 8 | 27 | C-36-IN-FN-200 ¦ C-36-IN-FN-210 ¦ C-36-IN-FN-220 ¦ C-36-IN-FN-230 ¦ C-36-IN-FN-240 ¦ C-36-IN-FN-250 ¦ C-36-IN-FN-260 ¦ C-36-IN-FN-270
Baseline | Finishes and equipment | 1 | 2027-08-12 | 2027-09-24 | 24 | 92 | C-01-C-FN-100 ¦ C-01-UC-MP-200 ¦ C-01-UC-FN-310 ¦ C-01-C-FN-110 ¦ C-01-UC-FN-320 ¦ C-01-UC-FN-330 ¦ C-01-UC-FN-370 ¦ C-01-UC-MP-400 ¦ C-01-UC-MP-410 ¦ C-01-UC-MP-420 ¦ C-01-C-FN-120 ¦ C-01-UC-MP-430 ¦ C-01-UC-MP-440 ¦ C-01-C-FN-140 ¦ C-01-UC-FN-400 ¦ C-01-C-FN-150 ¦ C-01-C-FN-160 ¦ C-01-C-FN-170 ¦ C-01-C-MP-120 ¦ C-01-C-MP-130 ¦ C-01-C-MP-150 ¦ C-01-C-MP-160 ¦ C-01-C-MP-140 ¦ C-01-C-FN-180
Baseline | Finishes and equipment | 2 | 2026-09-17 | 2026-11-04 | 36 | 147 | C-02-UC-FN-280 ¦ C-02-C-FN-100 ¦ C-02-UC-MP-200 ¦ C-02-C-FN-110 ¦ C-02-UC-FN-290 ¦ C-02-UC-FN-300 ¦ C-02-UC-MP-210 ¦ C-02-C-FN-120 ¦ C-02-C-FN-130 ¦ C-02-C-FN-140 ¦ C-02-C-MP-100 ¦ C-02-UC-FN-310 ¦ C-02-C-FN-150 ¦ C-02-UC-FN-320 ¦ C-02-UC-FN-330 ¦ C-02-UC-FN-340 ¦ C-02-UC-FN-350 ¦ C-02-UC-FN-360 ¦ C-02-UC-MP-400 ¦ C-02-UC-MP-410 ¦ C-02-C-FN-160 ¦ C-02-C-FN-170 ¦ C-02-C-MP-110 ¦ C-02-C-MP-120 ¦ C-02-UC-MP-420 ¦ C-02-C-MP-140 ¦ C-02-UC-MP-430 ¦ C-02-UC-MP-440 ¦ C-02-UC-FN-370 ¦ C-02-UC-FN-390 ¦ C-02-C-MP-130 ¦ C-02-C-MP-150 ¦ C-02-C-MP-160 ¦ C-02-C-FN-180 ¦ C-02-UC-FN-450 ¦ C-02-UC-FN-400
Baseline | Finishes and equipment | 3 | 2026-09-28 | 2026-11-24 | 34 | 132 | C-03-U-FN-280 ¦ C-03-C-FN-100 ¦ C-03-U-MP-200 ¦ C-03-C-FN-110 ¦ C-03-U-FN-290 ¦ C-03-U-FN-300 ¦ C-03-U-MP-210 ¦ C-03-C-FN-120 ¦ C-03-C-FN-130 ¦ C-03-C-MP-100 ¦ C-03-C-FN-140 ¦ C-03-C-FN-150 ¦ C-03-U-FN-310 ¦ C-03-C-FN-160 ¦ C-03-C-FN-170 ¦ C-03-C-MP-110 ¦ C-03-C-MP-120 ¦ C-03-C-MP-140 ¦ C-03-U-FN-330 ¦ C-03-U-FN-340 ¦ C-03-U-FN-350 ¦ C-03-U-MP-400 ¦ C-03-U-MP-410 ¦ C-03-C-MP-130 ¦ C-03-U-MP-420 ¦ C-03-C-MP-150 ¦ C-03-U-MP-430 ¦ C-03-U-MP-440 ¦ C-03-C-MP-160 ¦ C-03-C-FN-180 ¦ C-03-U-FN-370 ¦ C-03-U-FN-390 ¦ C-03-U-FN-400 ¦ C-03-U-FN-410
Baseline | Finishes and equipment | 4 | 2026-10-12 | 2026-12-08 | 34 | 127 | C-04-U-FN-280 ¦ C-04-C-FN-100 ¦ C-04-U-MP-200 ¦ C-04-C-FN-110 ¦ C-04-U-FN-290 ¦ C-04-U-FN-300 ¦ C-04-U-MP-210 ¦ C-04-C-FN-120 ¦ C-04-C-FN-130 ¦ C-04-C-MP-100 ¦ C-04-C-FN-140 ¦ C-04-U-FN-310 ¦ C-04-C-FN-150 ¦ C-04-U-FN-330 ¦ C-04-U-FN-340 ¦ C-04-U-MP-400 ¦ C-04-U-MP-410 ¦ C-04-C-FN-160 ¦ C-04-C-FN-170 ¦ C-04-C-MP-110 ¦ C-04-C-MP-120 ¦ C-04-U-MP-420 ¦ C-04-C-MP-140 ¦ C-04-U-FN-350 ¦ C-04-U-MP-430 ¦ C-04-U-MP-440 ¦ C-04-C-MP-130 ¦ C-04-C-MP-150 ¦ C-04-C-MP-160 ¦ C-04-U-FN-370 ¦ C-04-U-FN-390 ¦ C-04-C-FN-180 ¦ C-04-U-FN-400 ¦ C-04-U-FN-410
Baseline | Finishes and equipment | 5 | 2026-10-26 | 2026-12-18 | 34 | 127 | C-05-U-FN-280 ¦ C-05-C-FN-100 ¦ C-05-U-MP-200 ¦ C-05-C-FN-110 ¦ C-05-U-FN-290 ¦ C-05-U-FN-300 ¦ C-05-U-MP-210 ¦ C-05-C-FN-120 ¦ C-05-C-FN-130 ¦ C-05-C-MP-100 ¦ C-05-C-FN-140 ¦ C-05-U-FN-310 ¦ C-05-C-FN-150 ¦ C-05-U-FN-330 ¦ C-05-U-FN-340 ¦ C-05-U-MP-400 ¦ C-05-U-MP-410 ¦ C-05-C-FN-160 ¦ C-05-C-FN-170 ¦ C-05-C-MP-110 ¦ C-05-C-MP-120 ¦ C-05-U-FN-350 ¦ C-05-U-MP-420 ¦ C-05-C-MP-140 ¦ C-05-U-MP-430 ¦ C-05-U-MP-440 ¦ C-05-C-MP-130 ¦ C-05-C-MP-150 ¦ C-05-U-FN-370 ¦ C-05-U-FN-390 ¦ C-05-C-MP-160 ¦ C-05-C-FN-180 ¦ C-05-U-FN-400 ¦ C-05-U-FN-410
Baseline | Finishes and equipment | 6 | 2026-11-09 | 2027-01-04 | 34 | 127 | C-06-U-FN-280 ¦ C-06-C-FN-100 ¦ C-06-U-MP-200 ¦ C-06-C-FN-110 ¦ C-06-U-FN-290 ¦ C-06-U-FN-300 ¦ C-06-U-MP-210 ¦ C-06-C-FN-120 ¦ C-06-C-FN-130 ¦ C-06-C-MP-100 ¦ C-06-C-FN-140 ¦ C-06-U-FN-310 ¦ C-06-C-FN-150 ¦ C-06-U-FN-330 ¦ C-06-U-FN-340 ¦ C-06-U-FN-350 ¦ C-06-U-MP-400 ¦ C-06-U-MP-410 ¦ C-06-C-FN-160 ¦ C-06-C-FN-170 ¦ C-06-C-MP-110 ¦ C-06-C-MP-120 ¦ C-06-U-MP-420 ¦ C-06-C-MP-140 ¦ C-06-U-MP-430 ¦ C-06-U-MP-440 ¦ C-06-C-MP-130 ¦ C-06-U-FN-370 ¦ C-06-U-FN-390 ¦ C-06-C-MP-150 ¦ C-06-C-MP-160 ¦ C-06-C-FN-180 ¦ C-06-U-FN-400 ¦ C-06-U-FN-410
Baseline | Finishes and equipment | 7 | 2026-12-11 | 2027-02-12 | 36 | 163 | C-07-U-FN-280 ¦ C-07-C-FN-100 ¦ C-07-U-MP-200 ¦ C-07-C-FN-110 ¦ C-07-U-FN-290 ¦ C-07-U-FN-300 ¦ C-07-U-MP-210 ¦ C-07-C-FN-120 ¦ C-07-C-FN-130 ¦ C-07-C-MP-100 ¦ C-07-C-FN-140 ¦ C-07-U-FN-310 ¦ C-07-C-FN-150 ¦ C-07-U-FN-320 ¦ C-07-U-FN-330 ¦ C-07-U-FN-340 ¦ C-07-U-FN-350 ¦ C-07-U-MP-400 ¦ C-07-U-MP-410 ¦ C-07-U-FN-360 ¦ C-07-C-FN-160 ¦ C-07-C-FN-170 ¦ C-07-C-MP-110 ¦ C-07-C-MP-120 ¦ C-07-U-MP-420 ¦ C-07-U-MP-430 ¦ C-07-U-MP-440 ¦ C-07-C-MP-130 ¦ C-07-C-MP-140 ¦ C-07-C-MP-150 ¦ C-07-C-MP-160 ¦ C-07-U-FN-370 ¦ C-07-U-FN-390 ¦ C-07-C-FN-180 ¦ C-07-U-FN-400 ¦ C-07-U-FN-410
Baseline | Finishes and equipment | 8 | 2026-12-28 | 2027-02-26 | 34 | 151 | C-08-U-FN-280 ¦ C-08-C-FN-100 ¦ C-08-U-MP-200 ¦ C-08-C-FN-110 ¦ C-08-U-FN-290 ¦ C-08-U-FN-300 ¦ C-08-U-MP-210 ¦ C-08-C-FN-120 ¦ C-08-C-FN-130 ¦ C-08-C-MP-100 ¦ C-08-C-FN-140 ¦ C-08-U-FN-310 ¦ C-08-C-FN-150 ¦ C-08-U-FN-330 ¦ C-08-U-FN-340 ¦ C-08-U-FN-350 ¦ C-08-U-MP-400 ¦ C-08-U-MP-410 ¦ C-08-C-FN-160 ¦ C-08-C-FN-170 ¦ C-08-C-MP-110 ¦ C-08-C-MP-120 ¦ C-08-U-MP-420 ¦ C-08-U-MP-430 ¦ C-08-U-MP-440 ¦ C-08-C-MP-130 ¦ C-08-C-MP-140 ¦ C-08-C-MP-150 ¦ C-08-U-FN-390 ¦ C-08-C-MP-160 ¦ C-08-U-FN-370 ¦ C-08-C-FN-180 ¦ C-08-U-FN-400 ¦ C-08-U-FN-410
Baseline | Finishes and equipment | 9 | 2027-01-07 | 2027-03-12 | 34 | 151 | C-09-U-FN-280 ¦ C-09-C-FN-100 ¦ C-09-U-MP-200 ¦ C-09-C-FN-110 ¦ C-09-U-FN-290 ¦ C-09-U-FN-300 ¦ C-09-U-MP-210 ¦ C-09-C-FN-120 ¦ C-09-C-FN-130 ¦ C-09-C-MP-100 ¦ C-09-C-FN-140 ¦ C-09-U-FN-310 ¦ C-09-C-FN-150 ¦ C-09-U-FN-330 ¦ C-09-U-FN-340 ¦ C-09-U-MP-400 ¦ C-09-U-MP-410 ¦ C-09-U-FN-350 ¦ C-09-C-FN-160 ¦ C-09-C-FN-170 ¦ C-09-C-MP-110 ¦ C-09-C-MP-120 ¦ C-09-U-MP-420 ¦ C-09-U-MP-430 ¦ C-09-U-MP-440 ¦ C-09-C-MP-130 ¦ C-09-C-MP-140 ¦ C-09-C-MP-150 ¦ C-09-C-MP-160 ¦ C-09-U-FN-390 ¦ C-09-C-FN-180 ¦ C-09-U-FN-370 ¦ C-09-U-FN-400 ¦ C-09-U-FN-410
Baseline | Finishes and equipment | 10 | 2027-01-18 | 2027-03-26 | 34 | 151 | C-10-U-FN-280 ¦ C-10-C-FN-100 ¦ C-10-U-MP-200 ¦ C-10-C-FN-110 ¦ C-10-U-FN-290 ¦ C-10-U-FN-300 ¦ C-10-U-MP-210 ¦ C-10-C-FN-120 ¦ C-10-C-FN-130 ¦ C-10-C-MP-100 ¦ C-10-C-FN-140 ¦ C-10-U-FN-310 ¦ C-10-C-FN-150 ¦ C-10-U-FN-330 ¦ C-10-U-FN-340 ¦ C-10-U-MP-410 ¦ C-10-U-FN-350 ¦ C-10-C-FN-160 ¦ C-10-C-FN-170 ¦ C-10-C-MP-110 ¦ C-10-C-MP-130 ¦ C-10-U-MP-420 ¦ C-10-C-MP-150 ¦ C-10-U-MP-430 ¦ C-10-U-MP-440 ¦ C-10-C-MP-120 ¦ C-10-C-MP-160 ¦ C-10-U-MP-400 ¦ C-10-C-MP-140 ¦ C-10-U-FN-390 ¦ C-10-C-FN-180 ¦ C-10-U-FN-370 ¦ C-10-U-FN-400 ¦ C-10-U-FN-410
Baseline | Finishes and equipment | 11 | 2027-01-27 | 2027-04-09 | 34 | 151 | C-11-U-FN-280 ¦ C-11-C-FN-100 ¦ C-11-U-MP-200 ¦ C-11-C-FN-110 ¦ C-11-U-FN-290 ¦ C-11-U-FN-300 ¦ C-11-U-MP-210 ¦ C-11-C-FN-120 ¦ C-11-C-FN-130 ¦ C-11-C-MP-100 ¦ C-11-C-FN-140 ¦ C-11-U-FN-310 ¦ C-11-C-FN-150 ¦ C-11-U-FN-330 ¦ C-11-U-FN-340 ¦ C-11-U-MP-400 ¦ C-11-U-MP-410 ¦ C-11-C-FN-160 ¦ C-11-C-FN-170 ¦ C-11-C-MP-110 ¦ C-11-C-MP-120 ¦ C-11-U-FN-350 ¦ C-11-U-MP-420 ¦ C-11-U-MP-430 ¦ C-11-U-MP-440 ¦ C-11-C-MP-130 ¦ C-11-C-MP-140 ¦ C-11-C-MP-150 ¦ C-11-C-MP-160 ¦ C-11-U-FN-390 ¦ C-11-C-FN-180 ¦ C-11-U-FN-370 ¦ C-11-U-FN-400 ¦ C-11-U-FN-410
Baseline | Finishes and equipment | 12 | 2027-02-05 | 2027-04-23 | 34 | 151 | C-12-U-FN-280 ¦ C-12-C-FN-100 ¦ C-12-U-MP-200 ¦ C-12-C-FN-110 ¦ C-12-U-FN-290 ¦ C-12-U-FN-300 ¦ C-12-U-MP-210 ¦ C-12-C-FN-120 ¦ C-12-C-FN-130 ¦ C-12-C-MP-100 ¦ C-12-C-FN-140 ¦ C-12-U-FN-310 ¦ C-12-C-FN-150 ¦ C-12-U-FN-330 ¦ C-12-U-FN-340 ¦ C-12-U-MP-400 ¦ C-12-U-MP-410 ¦ C-12-C-FN-160 ¦ C-12-C-FN-170 ¦ C-12-C-MP-110 ¦ C-12-C-MP-120 ¦ C-12-U-MP-420 ¦ C-12-U-FN-350 ¦ C-12-U-MP-430 ¦ C-12-U-MP-440 ¦ C-12-C-MP-130 ¦ C-12-C-MP-140 ¦ C-12-C-MP-150 ¦ C-12-C-MP-160 ¦ C-12-C-FN-180 ¦ C-12-U-FN-390 ¦ C-12-U-FN-370 ¦ C-12-U-FN-400 ¦ C-12-U-FN-410
Baseline | Finishes and equipment | 14 | 2027-02-16 | 2027-05-07 | 34 | 151 | C-14-U-FN-280 ¦ C-14-C-FN-100 ¦ C-14-U-MP-200 ¦ C-14-C-FN-110 ¦ C-14-U-FN-290 ¦ C-14-U-FN-300 ¦ C-14-U-MP-210 ¦ C-14-C-FN-120 ¦ C-14-C-FN-130 ¦ C-14-C-MP-100 ¦ C-14-C-FN-140 ¦ C-14-U-FN-310 ¦ C-14-C-FN-150 ¦ C-14-U-FN-330 ¦ C-14-U-FN-340 ¦ C-14-U-MP-410 ¦ C-14-C-FN-160 ¦ C-14-C-FN-170 ¦ C-14-C-MP-110 ¦ C-14-C-MP-130 ¦ C-14-U-MP-420 ¦ C-14-C-MP-150 ¦ C-14-U-FN-350 ¦ C-14-U-MP-430 ¦ C-14-U-MP-440 ¦ C-14-C-MP-120 ¦ C-14-C-MP-160 ¦ C-14-U-MP-400 ¦ C-14-C-MP-140 ¦ C-14-C-FN-180 ¦ C-14-U-FN-390 ¦ C-14-U-FN-370 ¦ C-14-U-FN-400 ¦ C-14-U-FN-410
Baseline | Finishes and equipment | 15 | 2027-02-25 | 2027-05-21 | 34 | 151 | C-15-U-FN-280 ¦ C-15-C-FN-100 ¦ C-15-U-MP-200 ¦ C-15-C-FN-110 ¦ C-15-U-FN-290 ¦ C-15-U-FN-300 ¦ C-15-U-MP-210 ¦ C-15-C-FN-120 ¦ C-15-C-FN-130 ¦ C-15-C-MP-100 ¦ C-15-C-FN-140 ¦ C-15-U-FN-310 ¦ C-15-C-FN-150 ¦ C-15-U-FN-330 ¦ C-15-U-FN-340 ¦ C-15-U-MP-400 ¦ C-15-U-MP-410 ¦ C-15-C-FN-160 ¦ C-15-C-FN-170 ¦ C-15-C-MP-110 ¦ C-15-C-MP-120 ¦ C-15-U-MP-420 ¦ C-15-U-MP-430 ¦ C-15-U-MP-440 ¦ C-15-C-MP-130 ¦ C-15-U-FN-350 ¦ C-15-C-MP-140 ¦ C-15-C-MP-150 ¦ C-15-C-MP-160 ¦ C-15-C-FN-180 ¦ C-15-U-FN-390 ¦ C-15-U-FN-370 ¦ C-15-U-FN-400 ¦ C-15-U-FN-410
Baseline | Finishes and equipment | 16 | 2027-03-09 | 2027-06-07 | 34 | 151 | C-16-U-FN-280 ¦ C-16-C-FN-100 ¦ C-16-U-MP-200 ¦ C-16-C-FN-110 ¦ C-16-U-FN-290 ¦ C-16-U-FN-300 ¦ C-16-U-MP-210 ¦ C-16-C-FN-120 ¦ C-16-C-FN-130 ¦ C-16-C-MP-100 ¦ C-16-C-FN-140 ¦ C-16-U-FN-310 ¦ C-16-C-FN-150 ¦ C-16-U-FN-330 ¦ C-16-U-FN-340 ¦ C-16-U-MP-400 ¦ C-16-U-MP-410 ¦ C-16-C-FN-160 ¦ C-16-C-FN-170 ¦ C-16-C-MP-110 ¦ C-16-C-MP-120 ¦ C-16-U-MP-420 ¦ C-16-U-MP-430 ¦ C-16-U-MP-440 ¦ C-16-C-MP-130 ¦ C-16-U-FN-350 ¦ C-16-C-MP-140 ¦ C-16-C-MP-150 ¦ C-16-C-MP-160 ¦ C-16-C-FN-180 ¦ C-16-U-FN-390 ¦ C-16-U-FN-370 ¦ C-16-U-FN-400 ¦ C-16-U-FN-410
Baseline | Finishes and equipment | 17 | 2027-03-19 | 2027-06-18 | 34 | 151 | C-17-U-FN-280 ¦ C-17-C-FN-100 ¦ C-17-U-MP-200 ¦ C-17-C-FN-110 ¦ C-17-U-FN-290 ¦ C-17-U-FN-300 ¦ C-17-U-MP-210 ¦ C-17-C-FN-120 ¦ C-17-C-FN-130 ¦ C-17-C-MP-100 ¦ C-17-C-FN-140 ¦ C-17-U-FN-310 ¦ C-17-C-FN-150 ¦ C-17-U-FN-330 ¦ C-17-U-FN-340 ¦ C-17-U-MP-410 ¦ C-17-C-FN-160 ¦ C-17-C-FN-170 ¦ C-17-C-MP-110 ¦ C-17-C-MP-130 ¦ C-17-U-MP-420 ¦ C-17-C-MP-150 ¦ C-17-U-MP-430 ¦ C-17-U-MP-440 ¦ C-17-C-MP-120 ¦ C-17-C-MP-160 ¦ C-17-U-FN-350 ¦ C-17-U-MP-400 ¦ C-17-C-MP-140 ¦ C-17-C-FN-180 ¦ C-17-U-FN-390 ¦ C-17-U-FN-370 ¦ C-17-U-FN-400 ¦ C-17-U-FN-410
Baseline | Finishes and equipment | 18 | 2027-03-31 | 2027-07-01 | 34 | 151 | C-18-U-FN-280 ¦ C-18-C-FN-100 ¦ C-18-U-MP-200 ¦ C-18-C-FN-110 ¦ C-18-U-FN-290 ¦ C-18-U-FN-300 ¦ C-18-U-MP-210 ¦ C-18-C-FN-120 ¦ C-18-C-FN-130 ¦ C-18-C-MP-100 ¦ C-18-C-FN-140 ¦ C-18-U-FN-310 ¦ C-18-C-FN-150 ¦ C-18-U-FN-330 ¦ C-18-U-FN-340 ¦ C-18-U-MP-400 ¦ C-18-U-MP-410 ¦ C-18-C-FN-160 ¦ C-18-C-FN-170 ¦ C-18-C-MP-110 ¦ C-18-C-MP-120 ¦ C-18-U-MP-420 ¦ C-18-U-MP-430 ¦ C-18-U-MP-440 ¦ C-18-C-MP-130 ¦ C-18-U-FN-350 ¦ C-18-C-MP-140 ¦ C-18-C-MP-150 ¦ C-18-C-MP-160 ¦ C-18-C-FN-180 ¦ C-18-U-FN-390 ¦ C-18-U-FN-370 ¦ C-18-U-FN-400 ¦ C-18-U-FN-410
Baseline | Finishes and equipment | 19 | 2027-04-12 | 2027-07-15 | 34 | 151 | C-19-U-FN-280 ¦ C-19-C-FN-100 ¦ C-19-U-MP-200 ¦ C-19-C-FN-110 ¦ C-19-U-FN-290 ¦ C-19-U-FN-300 ¦ C-19-U-MP-210 ¦ C-19-C-FN-120 ¦ C-19-C-FN-130 ¦ C-19-C-MP-100 ¦ C-19-C-FN-140 ¦ C-19-U-FN-310 ¦ C-19-C-FN-150 ¦ C-19-U-FN-330 ¦ C-19-U-FN-340 ¦ C-19-U-MP-400 ¦ C-19-U-MP-410 ¦ C-19-C-FN-160 ¦ C-19-C-FN-170 ¦ C-19-C-MP-110 ¦ C-19-C-MP-120 ¦ C-19-U-MP-420 ¦ C-19-U-MP-430 ¦ C-19-U-MP-440 ¦ C-19-C-MP-130 ¦ C-19-U-FN-350 ¦ C-19-C-MP-140 ¦ C-19-C-MP-150 ¦ C-19-C-MP-160 ¦ C-19-C-FN-180 ¦ C-19-U-FN-390 ¦ C-19-U-FN-370 ¦ C-19-U-FN-400 ¦ C-19-U-FN-410
Baseline | Finishes and equipment | 20 | 2027-04-22 | 2027-07-28 | 34 | 151 | C-20-U-FN-280 ¦ C-20-C-FN-100 ¦ C-20-U-MP-200 ¦ C-20-C-FN-110 ¦ C-20-U-FN-290 ¦ C-20-U-FN-300 ¦ C-20-U-MP-210 ¦ C-20-C-FN-120 ¦ C-20-C-FN-130 ¦ C-20-C-MP-100 ¦ C-20-C-FN-140 ¦ C-20-U-FN-310 ¦ C-20-C-FN-150 ¦ C-20-U-FN-330 ¦ C-20-U-FN-340 ¦ C-20-U-MP-410 ¦ C-20-C-FN-160 ¦ C-20-C-FN-170 ¦ C-20-C-MP-110 ¦ C-20-C-MP-130 ¦ C-20-U-MP-420 ¦ C-20-C-MP-150 ¦ C-20-U-MP-430 ¦ C-20-U-MP-440 ¦ C-20-C-MP-120 ¦ C-20-C-MP-160 ¦ C-20-U-FN-350 ¦ C-20-U-MP-400 ¦ C-20-C-MP-140 ¦ C-20-C-FN-180 ¦ C-20-U-FN-390 ¦ C-20-U-FN-370 ¦ C-20-U-FN-400 ¦ C-20-U-FN-410
Baseline | Finishes and equipment | 21 | 2027-05-04 | 2027-08-10 | 34 | 151 | C-21-U-FN-280 ¦ C-21-C-FN-100 ¦ C-21-U-MP-200 ¦ C-21-C-FN-110 ¦ C-21-U-FN-290 ¦ C-21-U-FN-300 ¦ C-21-U-MP-210 ¦ C-21-C-FN-120 ¦ C-21-C-FN-130 ¦ C-21-C-MP-100 ¦ C-21-C-FN-140 ¦ C-21-U-FN-310 ¦ C-21-C-FN-150 ¦ C-21-U-FN-330 ¦ C-21-U-FN-340 ¦ C-21-U-MP-400 ¦ C-21-U-MP-410 ¦ C-21-C-FN-160 ¦ C-21-C-FN-170 ¦ C-21-C-MP-110 ¦ C-21-C-MP-120 ¦ C-21-U-MP-420 ¦ C-21-U-MP-430 ¦ C-21-U-MP-440 ¦ C-21-C-MP-130 ¦ C-21-U-FN-350 ¦ C-21-C-MP-140 ¦ C-21-C-MP-150 ¦ C-21-C-MP-160 ¦ C-21-C-FN-180 ¦ C-21-U-FN-390 ¦ C-21-U-FN-370 ¦ C-21-U-FN-400 ¦ C-21-U-FN-410
Baseline | Finishes and equipment | 22 | 2027-05-14 | 2027-08-23 | 34 | 151 | C-22-U-FN-280 ¦ C-22-C-FN-100 ¦ C-22-U-MP-200 ¦ C-22-C-FN-110 ¦ C-22-U-FN-290 ¦ C-22-U-FN-300 ¦ C-22-U-MP-210 ¦ C-22-C-FN-120 ¦ C-22-C-FN-130 ¦ C-22-C-MP-100 ¦ C-22-C-FN-140 ¦ C-22-U-FN-310 ¦ C-22-C-FN-150 ¦ C-22-U-FN-330 ¦ C-22-U-FN-340 ¦ C-22-U-MP-400 ¦ C-22-U-MP-410 ¦ C-22-C-FN-160 ¦ C-22-C-FN-170 ¦ C-22-C-MP-110 ¦ C-22-C-MP-120 ¦ C-22-U-MP-420 ¦ C-22-U-MP-430 ¦ C-22-U-MP-440 ¦ C-22-C-MP-130 ¦ C-22-U-FN-350 ¦ C-22-C-MP-140 ¦ C-22-C-MP-150 ¦ C-22-C-MP-160 ¦ C-22-C-FN-180 ¦ C-22-U-FN-390 ¦ C-22-U-FN-370 ¦ C-22-U-FN-400 ¦ C-22-U-FN-410
Baseline | Finishes and equipment | 23 | 2027-05-26 | 2027-09-03 | 34 | 151 | C-23-U-FN-280 ¦ C-23-C-FN-100 ¦ C-23-U-MP-200 ¦ C-23-C-FN-110 ¦ C-23-U-FN-290 ¦ C-23-U-FN-300 ¦ C-23-U-MP-210 ¦ C-23-C-FN-120 ¦ C-23-C-FN-130 ¦ C-23-C-MP-100 ¦ C-23-C-FN-140 ¦ C-23-U-FN-310 ¦ C-23-C-FN-150 ¦ C-23-U-FN-330 ¦ C-23-U-FN-340 ¦ C-23-U-MP-410 ¦ C-23-C-FN-160 ¦ C-23-C-FN-170 ¦ C-23-C-MP-110 ¦ C-23-C-MP-130 ¦ C-23-U-MP-420 ¦ C-23-C-MP-150 ¦ C-23-U-MP-430 ¦ C-23-U-MP-440 ¦ C-23-C-MP-120 ¦ C-23-C-MP-160 ¦ C-23-U-FN-350 ¦ C-23-U-MP-400 ¦ C-23-C-MP-140 ¦ C-23-C-FN-180 ¦ C-23-U-FN-390 ¦ C-23-U-FN-370 ¦ C-23-U-FN-400 ¦ C-23-U-FN-410
Baseline | Finishes and equipment | 24 | 2027-06-08 | 2027-09-17 | 34 | 151 | C-24-U-FN-280 ¦ C-24-C-FN-100 ¦ C-24-U-MP-200 ¦ C-24-C-FN-110 ¦ C-24-U-FN-290 ¦ C-24-U-FN-300 ¦ C-24-U-MP-210 ¦ C-24-C-FN-120 ¦ C-24-C-FN-130 ¦ C-24-C-MP-100 ¦ C-24-C-FN-140 ¦ C-24-U-FN-310 ¦ C-24-C-FN-150 ¦ C-24-U-FN-330 ¦ C-24-U-FN-340 ¦ C-24-U-MP-400 ¦ C-24-U-MP-410 ¦ C-24-C-FN-160 ¦ C-24-C-FN-170 ¦ C-24-C-MP-110 ¦ C-24-C-MP-120 ¦ C-24-U-MP-420 ¦ C-24-U-MP-430 ¦ C-24-U-MP-440 ¦ C-24-C-MP-130 ¦ C-24-U-FN-350 ¦ C-24-C-MP-140 ¦ C-24-C-MP-150 ¦ C-24-C-MP-160 ¦ C-24-C-FN-180 ¦ C-24-U-FN-390 ¦ C-24-U-FN-370 ¦ C-24-U-FN-400 ¦ C-24-U-FN-410
Baseline | Finishes and equipment | 25 | 2027-06-18 | 2027-09-29 | 34 | 151 | C-25-U-FN-280 ¦ C-25-C-FN-100 ¦ C-25-U-MP-200 ¦ C-25-C-FN-110 ¦ C-25-U-FN-290 ¦ C-25-U-FN-300 ¦ C-25-U-MP-210 ¦ C-25-C-FN-120 ¦ C-25-C-FN-130 ¦ C-25-C-MP-100 ¦ C-25-C-FN-140 ¦ C-25-U-FN-310 ¦ C-25-C-FN-150 ¦ C-25-U-FN-330 ¦ C-25-U-FN-340 ¦ C-25-U-MP-400 ¦ C-25-U-MP-410 ¦ C-25-C-FN-160 ¦ C-25-C-FN-170 ¦ C-25-C-MP-110 ¦ C-25-C-MP-120 ¦ C-25-U-MP-420 ¦ C-25-U-MP-430 ¦ C-25-U-MP-440 ¦ C-25-C-MP-130 ¦ C-25-U-FN-350 ¦ C-25-C-MP-140 ¦ C-25-C-MP-150 ¦ C-25-C-MP-160 ¦ C-25-C-FN-180 ¦ C-25-U-FN-390 ¦ C-25-U-FN-370 ¦ C-25-U-FN-400 ¦ C-25-U-FN-410
Baseline | Finishes and equipment | 26 | 2027-06-29 | 2027-09-07 | 34 | 151 | C-26-U-FN-280 ¦ C-26-C-FN-100 ¦ C-26-U-MP-200 ¦ C-26-C-FN-110 ¦ C-26-U-FN-290 ¦ C-26-U-FN-300 ¦ C-26-U-MP-210 ¦ C-26-C-FN-120 ¦ C-26-C-FN-130 ¦ C-26-C-MP-100 ¦ C-26-C-FN-140 ¦ C-26-U-FN-310 ¦ C-26-C-FN-150 ¦ C-26-U-FN-330 ¦ C-26-U-FN-340 ¦ C-26-U-MP-410 ¦ C-26-C-FN-160 ¦ C-26-C-FN-170 ¦ C-26-C-MP-110 ¦ C-26-C-MP-130 ¦ C-26-U-MP-420 ¦ C-26-C-MP-150 ¦ C-26-U-MP-430 ¦ C-26-U-MP-440 ¦ C-26-C-MP-120 ¦ C-26-C-MP-160 ¦ C-26-U-MP-400 ¦ C-26-U-FN-350 ¦ C-26-C-MP-140 ¦ C-26-C-FN-180 ¦ C-26-U-FN-370 ¦ C-26-U-FN-390 ¦ C-26-U-FN-400 ¦ C-26-U-FN-410
Baseline | Finishes and equipment | 27 | 2027-07-09 | 2027-09-17 | 34 | 151 | C-27-U-FN-280 ¦ C-27-C-FN-100 ¦ C-27-U-MP-200 ¦ C-27-C-FN-110 ¦ C-27-U-FN-290 ¦ C-27-U-FN-300 ¦ C-27-U-MP-210 ¦ C-27-C-FN-120 ¦ C-27-C-FN-130 ¦ C-27-C-MP-100 ¦ C-27-C-FN-140 ¦ C-27-U-FN-310 ¦ C-27-C-FN-150 ¦ C-27-U-FN-330 ¦ C-27-U-FN-340 ¦ C-27-U-MP-400 ¦ C-27-U-MP-410 ¦ C-27-C-FN-160 ¦ C-27-C-FN-170 ¦ C-27-C-MP-110 ¦ C-27-C-MP-120 ¦ C-27-U-MP-420 ¦ C-27-U-MP-430 ¦ C-27-U-MP-440 ¦ C-27-C-MP-130 ¦ C-27-C-MP-140 ¦ C-27-C-MP-150 ¦ C-27-U-FN-350 ¦ C-27-C-MP-160 ¦ C-27-C-FN-180 ¦ C-27-U-FN-370 ¦ C-27-U-FN-390 ¦ C-27-U-FN-400 ¦ C-27-U-FN-410
Baseline | Finishes and equipment | 28 | 2027-07-20 | 2027-09-29 | 34 | 151 | C-28-U-FN-280 ¦ C-28-C-FN-100 ¦ C-28-U-MP-200 ¦ C-28-C-FN-110 ¦ C-28-U-FN-290 ¦ C-28-U-FN-300 ¦ C-28-U-MP-210 ¦ C-28-C-FN-120 ¦ C-28-C-FN-130 ¦ C-28-C-MP-100 ¦ C-28-C-FN-140 ¦ C-28-U-FN-310 ¦ C-28-C-FN-150 ¦ C-28-U-FN-330 ¦ C-28-U-FN-340 ¦ C-28-U-MP-400 ¦ C-28-U-MP-410 ¦ C-28-C-FN-160 ¦ C-28-C-FN-170 ¦ C-28-C-MP-110 ¦ C-28-C-MP-120 ¦ C-28-U-MP-420 ¦ C-28-U-MP-430 ¦ C-28-U-MP-440 ¦ C-28-C-MP-130 ¦ C-28-C-MP-140 ¦ C-28-C-MP-150 ¦ C-28-C-MP-160 ¦ C-28-U-FN-350 ¦ C-28-C-FN-180 ¦ C-28-U-FN-370 ¦ C-28-U-FN-390 ¦ C-28-U-FN-400 ¦ C-28-U-FN-410
Baseline | Finishes and equipment | 29 | 2027-07-29 | 2027-10-11 | 34 | 151 | C-29-U-FN-280 ¦ C-29-C-FN-100 ¦ C-29-U-MP-200 ¦ C-29-C-FN-110 ¦ C-29-U-FN-290 ¦ C-29-U-FN-300 ¦ C-29-U-MP-210 ¦ C-29-C-FN-120 ¦ C-29-C-FN-130 ¦ C-29-C-MP-100 ¦ C-29-C-FN-140 ¦ C-29-U-FN-310 ¦ C-29-C-FN-150 ¦ C-29-U-FN-330 ¦ C-29-U-FN-340 ¦ C-29-U-MP-410 ¦ C-29-C-FN-160 ¦ C-29-C-FN-170 ¦ C-29-C-MP-110 ¦ C-29-C-MP-130 ¦ C-29-U-MP-420 ¦ C-29-C-MP-150 ¦ C-29-U-MP-430 ¦ C-29-U-MP-440 ¦ C-29-C-MP-120 ¦ C-29-C-MP-160 ¦ C-29-U-MP-400 ¦ C-29-C-MP-140 ¦ C-29-U-FN-350 ¦ C-29-C-FN-180 ¦ C-29-U-FN-370 ¦ C-29-U-FN-390 ¦ C-29-U-FN-400 ¦ C-29-U-FN-410
Baseline | Finishes and equipment | 30 | 2027-08-09 | 2027-10-21 | 34 | 151 | C-30-U-FN-280 ¦ C-30-C-FN-100 ¦ C-30-U-MP-200 ¦ C-30-C-FN-110 ¦ C-30-U-FN-290 ¦ C-30-U-FN-300 ¦ C-30-U-MP-210 ¦ C-30-C-FN-120 ¦ C-30-C-FN-130 ¦ C-30-C-MP-100 ¦ C-30-C-FN-140 ¦ C-30-U-FN-310 ¦ C-30-C-FN-150 ¦ C-30-U-FN-330 ¦ C-30-U-FN-340 ¦ C-30-U-MP-400 ¦ C-30-U-MP-410 ¦ C-30-C-FN-160 ¦ C-30-C-FN-170 ¦ C-30-C-MP-110 ¦ C-30-C-MP-120 ¦ C-30-U-MP-420 ¦ C-30-U-MP-430 ¦ C-30-U-MP-440 ¦ C-30-C-MP-130 ¦ C-30-C-MP-140 ¦ C-30-C-MP-150 ¦ C-30-C-MP-160 ¦ C-30-U-FN-350 ¦ C-30-C-FN-180 ¦ C-30-U-FN-370 ¦ C-30-U-FN-390 ¦ C-30-U-FN-400 ¦ C-30-U-FN-410
Baseline | Finishes and equipment | 31 | 2027-08-18 | 2027-11-02 | 34 | 151 | C-31-U-FN-280 ¦ C-31-C-FN-100 ¦ C-31-U-MP-200 ¦ C-31-C-FN-110 ¦ C-31-U-FN-290 ¦ C-31-U-FN-300 ¦ C-31-U-MP-210 ¦ C-31-C-FN-120 ¦ C-31-C-FN-130 ¦ C-31-C-MP-100 ¦ C-31-C-FN-140 ¦ C-31-U-FN-310 ¦ C-31-C-FN-150 ¦ C-31-U-FN-330 ¦ C-31-U-FN-340 ¦ C-31-U-MP-400 ¦ C-31-U-MP-410 ¦ C-31-C-FN-160 ¦ C-31-C-FN-170 ¦ C-31-C-MP-110 ¦ C-31-C-MP-120 ¦ C-31-U-MP-420 ¦ C-31-U-MP-430 ¦ C-31-U-MP-440 ¦ C-31-C-MP-130 ¦ C-31-C-MP-140 ¦ C-31-C-MP-150 ¦ C-31-C-MP-160 ¦ C-31-C-FN-180 ¦ C-31-U-FN-350 ¦ C-31-U-FN-370 ¦ C-31-U-FN-390 ¦ C-31-U-FN-400 ¦ C-31-U-FN-410
Baseline | Finishes and equipment | 32 | 2027-08-27 | 2027-11-08 | 34 | 151 | C-32-U-FN-280 ¦ C-32-C-FN-100 ¦ C-32-U-MP-200 ¦ C-32-C-FN-110 ¦ C-32-U-FN-290 ¦ C-32-U-FN-300 ¦ C-32-U-MP-210 ¦ C-32-C-FN-120 ¦ C-32-C-FN-130 ¦ C-32-C-MP-100 ¦ C-32-C-FN-140 ¦ C-32-U-FN-310 ¦ C-32-C-FN-150 ¦ C-32-U-FN-330 ¦ C-32-U-FN-340 ¦ C-32-U-MP-410 ¦ C-32-C-FN-160 ¦ C-32-C-FN-170 ¦ C-32-C-MP-110 ¦ C-32-C-MP-130 ¦ C-32-U-MP-420 ¦ C-32-C-MP-150 ¦ C-32-U-MP-430 ¦ C-32-U-MP-440 ¦ C-32-C-MP-120 ¦ C-32-C-MP-160 ¦ C-32-U-MP-400 ¦ C-32-C-MP-140 ¦ C-32-C-FN-180 ¦ C-32-U-FN-350 ¦ C-32-U-FN-370 ¦ C-32-U-FN-390 ¦ C-32-U-FN-400 ¦ C-32-U-FN-410
Baseline | Finishes and equipment | 33 | 2027-09-08 | 2027-11-17 | 34 | 151 | C-33-U-FN-280 ¦ C-33-C-FN-100 ¦ C-33-U-MP-200 ¦ C-33-C-FN-110 ¦ C-33-U-FN-290 ¦ C-33-U-FN-300 ¦ C-33-U-MP-210 ¦ C-33-C-FN-120 ¦ C-33-C-FN-130 ¦ C-33-C-MP-100 ¦ C-33-C-FN-140 ¦ C-33-U-FN-310 ¦ C-33-C-FN-150 ¦ C-33-U-FN-330 ¦ C-33-U-FN-340 ¦ C-33-U-MP-400 ¦ C-33-U-MP-410 ¦ C-33-C-FN-160 ¦ C-33-C-FN-170 ¦ C-33-C-MP-110 ¦ C-33-C-MP-120 ¦ C-33-U-MP-420 ¦ C-33-U-MP-430 ¦ C-33-U-MP-440 ¦ C-33-C-MP-130 ¦ C-33-C-MP-140 ¦ C-33-C-MP-150 ¦ C-33-C-MP-160 ¦ C-33-C-FN-180 ¦ C-33-U-FN-350 ¦ C-33-U-FN-370 ¦ C-33-U-FN-390 ¦ C-33-U-FN-400 ¦ C-33-U-FN-410
Baseline | Finishes and equipment | 34 | 2027-09-17 | 2027-11-30 | 34 | 151 | C-34-U-FN-280 ¦ C-34-C-FN-100 ¦ C-34-U-MP-200 ¦ C-34-C-FN-110 ¦ C-34-U-FN-290 ¦ C-34-U-FN-300 ¦ C-34-U-MP-210 ¦ C-34-C-FN-120 ¦ C-34-C-FN-130 ¦ C-34-C-MP-100 ¦ C-34-C-FN-140 ¦ C-34-U-FN-310 ¦ C-34-C-FN-150 ¦ C-34-U-FN-330 ¦ C-34-U-FN-340 ¦ C-34-U-MP-400 ¦ C-34-U-MP-410 ¦ C-34-U-MP-420 ¦ C-34-C-FN-160 ¦ C-34-C-FN-170 ¦ C-34-C-MP-110 ¦ C-34-C-MP-120 ¦ C-34-U-MP-430 ¦ C-34-U-MP-440 ¦ C-34-C-MP-130 ¦ C-34-C-MP-140 ¦ C-34-C-MP-150 ¦ C-34-C-MP-160 ¦ C-34-C-FN-180 ¦ C-34-U-FN-350 ¦ C-34-U-FN-370 ¦ C-34-U-FN-390 ¦ C-34-U-FN-400 ¦ C-34-U-FN-410
Baseline | Finishes and equipment | 35 | 2027-10-06 | 2027-12-07 | 34 | 146 | C-35-C-FN-100 ¦ C-35-U-FN-280 ¦ C-35-U-MP-200 ¦ C-35-C-FN-110 ¦ C-35-U-FN-290 ¦ C-35-C-FN-120 ¦ C-35-C-FN-130 ¦ C-35-C-MP-100 ¦ C-35-U-FN-300 ¦ C-35-U-MP-210 ¦ C-35-C-FN-140 ¦ C-35-U-FN-310 ¦ C-35-U-MP-400 ¦ C-35-U-MP-410 ¦ C-35-C-FN-150 ¦ C-35-U-MP-420 ¦ C-35-U-FN-330 ¦ C-35-U-FN-340 ¦ C-35-U-MP-430 ¦ C-35-U-MP-440 ¦ C-35-C-FN-160 ¦ C-35-C-FN-170 ¦ C-35-C-MP-110 ¦ C-35-C-MP-120 ¦ C-35-C-MP-130 ¦ C-35-C-MP-140 ¦ C-35-C-MP-150 ¦ C-35-U-FN-350 ¦ C-35-C-MP-160 ¦ C-35-C-FN-180 ¦ C-35-U-FN-390 ¦ C-35-U-FN-370 ¦ C-35-U-FN-400 ¦ C-35-U-FN-410
Baseline | Finishes and equipment | 36 | 2027-07-22 | 2027-10-01 | 16 | 50 | C-36-IN-MP-200 ¦ C-36-IN-MP-400 ¦ C-36-IN-FN-280 ¦ C-36-IN-FN-290 ¦ C-36-IN-FN-310 ¦ C-36-IN-MP-410 ¦ C-36-IN-FN-330 ¦ C-36-IN-FN-340 ¦ C-36-IN-FN-350 ¦ C-36-IN-MP-420 ¦ C-36-IN-MP-430 ¦ C-36-IN-MP-440 ¦ C-36-IN-MP-450 ¦ C-36-IN-MP-460 ¦ C-36-IN-MP-470 ¦ C-36-IN-FN-400
Baseline | Inspection and contractor punch | 1 | 2027-09-27 | 2027-11-12 | 3 | 35 | C-01-U-PC-900 ¦ C-01-U-PC-910 ¦ C-01-U-PC-920
Baseline | Inspection and contractor punch | 2 | 2027-03-30 | 2027-05-05 | 3 | 27 | C-02-U-PC-900 ¦ C-02-U-PC-910 ¦ C-02-U-PC-920
Baseline | Inspection and contractor punch | 3 | 2027-04-08 | 2027-05-14 | 3 | 27 | C-03-U-PC-900 ¦ C-03-U-PC-910 ¦ C-03-U-PC-920
Baseline | Inspection and contractor punch | 4 | 2027-04-19 | 2027-05-25 | 3 | 27 | C-04-U-PC-900 ¦ C-04-U-PC-910 ¦ C-04-U-PC-920
Baseline | Inspection and contractor punch | 5 | 2027-04-28 | 2027-06-04 | 3 | 27 | C-05-U-PC-900 ¦ C-05-U-PC-910 ¦ C-05-U-PC-920
Baseline | Inspection and contractor punch | 6 | 2027-05-07 | 2027-06-15 | 3 | 27 | C-06-U-PC-900 ¦ C-06-U-PC-910 ¦ C-06-U-PC-920
Baseline | Inspection and contractor punch | 7 | 2027-05-18 | 2027-06-24 | 3 | 27 | C-07-U-PC-900 ¦ C-07-U-PC-910 ¦ C-07-U-PC-920
Baseline | Inspection and contractor punch | 8 | 2027-05-27 | 2027-07-06 | 3 | 27 | C-08-U-PC-900 ¦ C-08-U-PC-910 ¦ C-08-U-PC-920
Baseline | Inspection and contractor punch | 9 | 2027-06-08 | 2027-07-15 | 3 | 27 | C-09-U-PC-900 ¦ C-09-U-PC-910 ¦ C-09-U-PC-920
Baseline | Inspection and contractor punch | 10 | 2027-06-17 | 2027-07-19 | 3 | 22 | C-10-U-PC-900 ¦ C-10-U-PC-910 ¦ C-10-U-PC-920
Baseline | Inspection and contractor punch | 11 | 2027-06-28 | 2027-07-28 | 3 | 22 | C-11-U-PC-900 ¦ C-11-U-PC-910 ¦ C-11-U-PC-920
Baseline | Inspection and contractor punch | 12 | 2027-07-08 | 2027-08-06 | 3 | 22 | C-12-U-PC-900 ¦ C-12-U-PC-910 ¦ C-12-U-PC-920
Baseline | Inspection and contractor punch | 14 | 2027-07-19 | 2027-08-17 | 3 | 22 | C-14-U-PC-900 ¦ C-14-U-PC-910 ¦ C-14-U-PC-920
Baseline | Inspection and contractor punch | 15 | 2027-07-23 | 2027-08-19 | 3 | 22 | C-15-U-PC-900 ¦ C-15-U-PC-910 ¦ C-15-U-PC-920
Baseline | Inspection and contractor punch | 16 | 2027-08-03 | 2027-08-30 | 3 | 20 | C-16-U-PC-900 ¦ C-16-U-PC-910 ¦ C-16-U-PC-920
Baseline | Inspection and contractor punch | 17 | 2027-08-09 | 2027-09-03 | 3 | 20 | C-17-U-PC-900 ¦ C-17-U-PC-910 ¦ C-17-U-PC-920
Baseline | Inspection and contractor punch | 18 | 2027-08-13 | 2027-09-10 | 3 | 20 | C-18-U-PC-900 ¦ C-18-U-PC-910 ¦ C-18-U-PC-920
Baseline | Inspection and contractor punch | 19 | 2027-08-19 | 2027-09-16 | 3 | 20 | C-19-U-PC-900 ¦ C-19-U-PC-910 ¦ C-19-U-PC-920
Baseline | Inspection and contractor punch | 20 | 2027-08-25 | 2027-09-22 | 3 | 20 | C-20-U-PC-900 ¦ C-20-U-PC-910 ¦ C-20-U-PC-920
Baseline | Inspection and contractor punch | 21 | 2027-08-31 | 2027-09-28 | 3 | 20 | C-21-U-PC-900 ¦ C-21-U-PC-910 ¦ C-21-U-PC-920
Baseline | Inspection and contractor punch | 22 | 2027-09-07 | 2027-10-04 | 3 | 20 | C-22-U-PC-900 ¦ C-22-U-PC-910 ¦ C-22-U-PC-920
Baseline | Inspection and contractor punch | 23 | 2027-09-13 | 2027-10-08 | 3 | 20 | C-23-U-PC-900 ¦ C-23-U-PC-910 ¦ C-23-U-PC-920
Baseline | Inspection and contractor punch | 24 | 2027-09-17 | 2027-10-14 | 3 | 20 | C-24-U-PC-900 ¦ C-24-U-PC-910 ¦ C-24-U-PC-920
Baseline | Inspection and contractor punch | 25 | 2027-09-28 | 2027-10-21 | 3 | 20 | C-25-U-PC-900 ¦ C-25-U-PC-910 ¦ C-25-U-PC-920
Baseline | Inspection and contractor punch | 26 | 2027-10-05 | 2027-11-01 | 3 | 20 | C-26-U-PC-900 ¦ C-26-U-PC-910 ¦ C-26-U-PC-920
Baseline | Inspection and contractor punch | 27 | 2027-10-07 | 2027-11-03 | 3 | 20 | C-27-U-PC-900 ¦ C-27-U-PC-910 ¦ C-27-U-PC-920
Baseline | Inspection and contractor punch | 28 | 2027-10-11 | 2027-11-05 | 3 | 20 | C-28-U-PC-900 ¦ C-28-U-PC-910 ¦ C-28-U-PC-920
Baseline | Inspection and contractor punch | 29 | 2027-10-13 | 2027-11-09 | 3 | 20 | C-29-U-PC-900 ¦ C-29-U-PC-910 ¦ C-29-U-PC-920
Baseline | Inspection and contractor punch | 30 | 2027-10-20 | 2027-11-16 | 3 | 20 | C-30-U-PC-900 ¦ C-30-U-PC-910 ¦ C-30-U-PC-920
Baseline | Inspection and contractor punch | 31 | 2027-11-01 | 2027-11-30 | 3 | 20 | C-31-U-PC-900 ¦ C-31-U-PC-910 ¦ C-31-U-PC-920
Baseline | Inspection and contractor punch | 32 | 2027-11-08 | 2027-12-07 | 3 | 20 | C-32-U-PC-900 ¦ C-32-U-PC-910 ¦ C-32-U-PC-920
Baseline | Inspection and contractor punch | 33 | 2027-11-11 | 2027-12-10 | 3 | 20 | C-33-U-PC-900 ¦ C-33-U-PC-910 ¦ C-33-U-PC-920
Baseline | Inspection and contractor punch | 34 | 2027-11-22 | 2027-12-21 | 3 | 20 | C-34-U-PC-900 ¦ C-34-U-PC-910 ¦ C-34-U-PC-920
Baseline | Inspection and contractor punch | 35 | 2027-11-29 | 2027-12-21 | 3 | 20 | C-35-U-PC-900 ¦ C-35-U-PC-910 ¦ C-35-U-PC-920
Baseline | Inspection and contractor punch | 36 | 2027-10-04 | 2027-11-05 | 3 | 25 | C-36-IN-PC-900 ¦ C-36-IN-PC-910 ¦ C-36-IN-PC-920
Baseline | Final clean and Owner punch | 1 | 2027-09-27 | 2027-12-02 | 4 | 13 | C-01-C-FN-190 ¦ C-01-U-PC-930 ¦ C-01-U-PC-940 ¦ C-01-U-PC-950
Baseline | Final clean and Owner punch | 2 | 2027-05-06 | 2027-05-20 | 3 | 11 | C-02-U-PC-930 ¦ C-02-C-FN-190 ¦ C-02-U-PC-950
Baseline | Final clean and Owner punch | 3 | 2027-05-17 | 2027-06-01 | 3 | 11 | C-03-U-PC-930 ¦ C-03-C-FN-190 ¦ C-03-U-PC-950
Baseline | Final clean and Owner punch | 4 | 2027-05-26 | 2027-06-10 | 3 | 11 | C-04-U-PC-930 ¦ C-04-C-FN-190 ¦ C-04-U-PC-950
Baseline | Final clean and Owner punch | 5 | 2027-06-07 | 2027-06-21 | 3 | 11 | C-05-U-PC-930 ¦ C-05-C-FN-190 ¦ C-05-U-PC-950
Baseline | Final clean and Owner punch | 6 | 2027-06-16 | 2027-06-30 | 3 | 11 | C-06-U-PC-930 ¦ C-06-C-FN-190 ¦ C-06-U-PC-950
Baseline | Final clean and Owner punch | 7 | 2027-06-25 | 2027-07-12 | 3 | 11 | C-07-U-PC-930 ¦ C-07-C-FN-190 ¦ C-07-U-PC-950
Baseline | Final clean and Owner punch | 8 | 2027-07-07 | 2027-07-21 | 3 | 11 | C-08-U-PC-930 ¦ C-08-C-FN-190 ¦ C-08-U-PC-950
Baseline | Final clean and Owner punch | 9 | 2027-07-16 | 2027-07-30 | 3 | 11 | C-09-U-PC-930 ¦ C-09-C-FN-190 ¦ C-09-U-PC-950
Baseline | Final clean and Owner punch | 10 | 2027-07-23 | 2027-08-06 | 3 | 11 | C-10-U-PC-930 ¦ C-10-C-FN-190 ¦ C-10-U-PC-950
Baseline | Final clean and Owner punch | 11 | 2027-07-30 | 2027-08-13 | 3 | 11 | C-11-U-PC-930 ¦ C-11-C-FN-190 ¦ C-11-U-PC-950
Baseline | Final clean and Owner punch | 12 | 2027-08-09 | 2027-08-23 | 3 | 11 | C-12-U-PC-930 ¦ C-12-C-FN-190 ¦ C-12-U-PC-950
Baseline | Final clean and Owner punch | 14 | 2027-08-18 | 2027-09-01 | 3 | 11 | C-14-U-PC-930 ¦ C-14-C-FN-190 ¦ C-14-U-PC-950
Baseline | Final clean and Owner punch | 15 | 2027-08-25 | 2027-09-09 | 3 | 11 | C-15-U-PC-930 ¦ C-15-C-FN-190 ¦ C-15-U-PC-950
Baseline | Final clean and Owner punch | 16 | 2027-09-01 | 2027-09-16 | 3 | 11 | C-16-U-PC-930 ¦ C-16-C-FN-190 ¦ C-16-U-PC-950
Baseline | Final clean and Owner punch | 17 | 2027-09-09 | 2027-09-23 | 3 | 11 | C-17-U-PC-930 ¦ C-17-C-FN-190 ¦ C-17-U-PC-950
Baseline | Final clean and Owner punch | 18 | 2027-09-16 | 2027-09-30 | 3 | 11 | C-18-U-PC-930 ¦ C-18-C-FN-190 ¦ C-18-U-PC-950
Baseline | Final clean and Owner punch | 19 | 2027-09-23 | 2027-10-07 | 3 | 11 | C-19-U-PC-930 ¦ C-19-C-FN-190 ¦ C-19-U-PC-950
Baseline | Final clean and Owner punch | 20 | 2027-09-30 | 2027-10-14 | 3 | 11 | C-20-U-PC-930 ¦ C-20-C-FN-190 ¦ C-20-U-PC-950
Baseline | Final clean and Owner punch | 21 | 2027-10-07 | 2027-10-21 | 3 | 11 | C-21-U-PC-930 ¦ C-21-C-FN-190 ¦ C-21-U-PC-950
Baseline | Final clean and Owner punch | 22 | 2027-10-14 | 2027-10-28 | 3 | 11 | C-22-U-PC-930 ¦ C-22-C-FN-190 ¦ C-22-U-PC-950
Baseline | Final clean and Owner punch | 23 | 2027-10-21 | 2027-11-04 | 3 | 11 | C-23-U-PC-930 ¦ C-23-C-FN-190 ¦ C-23-U-PC-950
Baseline | Final clean and Owner punch | 24 | 2027-10-28 | 2027-11-11 | 3 | 11 | C-24-U-PC-930 ¦ C-24-C-FN-190 ¦ C-24-U-PC-950
Baseline | Final clean and Owner punch | 25 | 2027-11-04 | 2027-11-18 | 3 | 11 | C-25-U-PC-930 ¦ C-25-C-FN-190 ¦ C-25-U-PC-950
Baseline | Final clean and Owner punch | 26 | 2027-11-11 | 2027-11-29 | 3 | 11 | C-26-U-PC-930 ¦ C-26-C-FN-190 ¦ C-26-U-PC-950
Baseline | Final clean and Owner punch | 27 | 2027-11-18 | 2027-12-06 | 3 | 11 | C-27-U-PC-930 ¦ C-27-C-FN-190 ¦ C-27-U-PC-950
Baseline | Final clean and Owner punch | 28 | 2027-11-29 | 2027-12-13 | 3 | 11 | C-28-U-PC-930 ¦ C-28-C-FN-190 ¦ C-28-U-PC-950
Baseline | Final clean and Owner punch | 29 | 2027-12-06 | 2027-12-20 | 3 | 11 | C-29-U-PC-930 ¦ C-29-C-FN-190 ¦ C-29-U-PC-950
Baseline | Final clean and Owner punch | 30 | 2027-12-13 | 2027-12-28 | 3 | 11 | C-30-U-PC-930 ¦ C-30-C-FN-190 ¦ C-30-U-PC-950
Baseline | Final clean and Owner punch | 31 | 2027-12-20 | 2028-01-05 | 3 | 11 | C-31-U-PC-930 ¦ C-31-C-FN-190 ¦ C-31-U-PC-950
Baseline | Final clean and Owner punch | 32 | 2027-12-28 | 2028-01-12 | 3 | 11 | C-32-U-PC-930 ¦ C-32-C-FN-190 ¦ C-32-U-PC-950
Baseline | Final clean and Owner punch | 33 | 2028-01-05 | 2028-01-19 | 3 | 11 | C-33-U-PC-930 ¦ C-33-C-FN-190 ¦ C-33-U-PC-950
Baseline | Final clean and Owner punch | 34 | 2028-01-12 | 2028-01-26 | 3 | 11 | C-34-U-PC-930 ¦ C-34-C-FN-190 ¦ C-34-U-PC-950
Baseline | Final clean and Owner punch | 35 | 2028-01-19 | 2028-02-02 | 3 | 11 | C-35-U-PC-930 ¦ C-35-C-FN-190 ¦ C-35-U-PC-950
Baseline | Final clean and Owner punch | 36 | 2027-11-08 | 2027-11-23 | 3 | 12 | C-36-IN-PC-930 ¦ C-36-IN-PC-940 ¦ C-36-IN-PC-950
Phased TCO | Structure | 2 | 2026-03-24 | 2026-04-03 | 6 | 13 | C-02-ST-100 ¦ C-02-ST-110 ¦ C-02-MP-120 ¦ C-02-ST-130 ¦ C-02-ST-140 ¦ C-02-ST-150
Phased TCO | Structure | 3 | 2026-04-06 | 2026-04-16 | 6 | 13 | C-03-ST-100 ¦ C-03-ST-110 ¦ C-03-MP-120 ¦ C-03-ST-130 ¦ C-03-ST-140 ¦ C-03-ST-150
Phased TCO | Structure | 4 | 2026-04-17 | 2026-05-01 | 6 | 15 | C-04-ST-100 ¦ C-04-ST-110 ¦ C-04-MP-120 ¦ C-04-ST-130 ¦ C-04-ST-140 ¦ C-04-ST-150
Phased TCO | Structure | 5 | 2026-05-04 | 2026-05-18 | 6 | 15 | C-05-ST-100 ¦ C-05-ST-110 ¦ C-05-MP-120 ¦ C-05-ST-130 ¦ C-05-ST-140 ¦ C-05-ST-150
Phased TCO | Structure | 6 | 2026-05-19 | 2026-06-03 | 6 | 15 | C-06-ST-100 ¦ C-06-ST-110 ¦ C-06-MP-120 ¦ C-06-ST-130 ¦ C-06-ST-140 ¦ C-06-ST-150
Phased TCO | Structure | 7 | 2026-06-04 | 2026-06-17 | 6 | 14 | C-07-ST-100 ¦ C-07-ST-110 ¦ C-07-MP-120 ¦ C-07-ST-130 ¦ C-07-ST-140 ¦ C-07-ST-150
Phased TCO | Structure | 8 | 2026-06-18 | 2026-06-29 | 6 | 11 | C-08-ST-100 ¦ C-08-ST-110 ¦ C-08-MP-120 ¦ C-08-ST-130 ¦ C-08-ST-140 ¦ C-08-ST-150
Phased TCO | Structure | 9 | 2026-06-29 | 2026-07-07 | 6 | 9 | C-09-ST-100 ¦ C-09-ST-110 ¦ C-09-MP-120 ¦ C-09-ST-130 ¦ C-09-ST-140 ¦ C-09-ST-150
Phased TCO | Structure | 10 | 2026-07-07 | 2026-07-14 | 6 | 9 | C-10-ST-100 ¦ C-10-ST-110 ¦ C-10-MP-120 ¦ C-10-ST-130 ¦ C-10-ST-140 ¦ C-10-ST-150
Phased TCO | Structure | 11 | 2026-07-14 | 2026-07-21 | 6 | 9 | C-11-ST-100 ¦ C-11-ST-110 ¦ C-11-MP-120 ¦ C-11-ST-130 ¦ C-11-ST-140 ¦ C-11-ST-150
Phased TCO | Structure | 12 | 2026-07-21 | 2026-07-28 | 6 | 9 | C-12-ST-100 ¦ C-12-ST-110 ¦ C-12-MP-120 ¦ C-12-ST-130 ¦ C-12-ST-140 ¦ C-12-ST-150
Phased TCO | Structure | 14 | 2026-07-29 | 2026-08-05 | 6 | 9 | C-14-ST-100 ¦ C-14-ST-110 ¦ C-14-MP-120 ¦ C-14-ST-130 ¦ C-14-ST-140 ¦ C-14-ST-150
Phased TCO | Structure | 15 | 2026-08-05 | 2026-08-12 | 6 | 9 | C-15-ST-100 ¦ C-15-ST-110 ¦ C-15-MP-120 ¦ C-15-ST-130 ¦ C-15-ST-140 ¦ C-15-ST-150
Phased TCO | Structure | 16 | 2026-08-12 | 2026-08-19 | 6 | 9 | C-16-ST-100 ¦ C-16-ST-110 ¦ C-16-MP-120 ¦ C-16-ST-130 ¦ C-16-ST-140 ¦ C-16-ST-150
Phased TCO | Structure | 17 | 2026-08-19 | 2026-08-26 | 6 | 9 | C-17-ST-100 ¦ C-17-ST-110 ¦ C-17-MP-120 ¦ C-17-ST-130 ¦ C-17-ST-140 ¦ C-17-ST-150
Phased TCO | Structure | 18 | 2026-08-26 | 2026-09-02 | 6 | 9 | C-18-ST-100 ¦ C-18-ST-110 ¦ C-18-MP-120 ¦ C-18-ST-130 ¦ C-18-ST-140 ¦ C-18-ST-150
Phased TCO | Structure | 19 | 2026-09-02 | 2026-09-10 | 6 | 9 | C-19-ST-100 ¦ C-19-ST-110 ¦ C-19-MP-120 ¦ C-19-ST-130 ¦ C-19-ST-140 ¦ C-19-ST-150
Phased TCO | Structure | 20 | 2026-09-10 | 2026-09-17 | 6 | 9 | C-20-ST-100 ¦ C-20-ST-110 ¦ C-20-MP-120 ¦ C-20-ST-130 ¦ C-20-ST-140 ¦ C-20-ST-150
Phased TCO | Structure | 21 | 2026-09-17 | 2026-09-24 | 6 | 9 | C-21-ST-100 ¦ C-21-ST-110 ¦ C-21-MP-120 ¦ C-21-ST-130 ¦ C-21-ST-140 ¦ C-21-ST-150
Phased TCO | Structure | 22 | 2026-09-24 | 2026-10-01 | 6 | 9 | C-22-ST-100 ¦ C-22-ST-110 ¦ C-22-MP-120 ¦ C-22-ST-130 ¦ C-22-ST-140 ¦ C-22-ST-150
Phased TCO | Structure | 23 | 2026-10-01 | 2026-10-08 | 6 | 9 | C-23-ST-100 ¦ C-23-ST-110 ¦ C-23-MP-120 ¦ C-23-ST-130 ¦ C-23-ST-140 ¦ C-23-ST-150
Phased TCO | Structure | 24 | 2026-10-08 | 2026-10-15 | 6 | 9 | C-24-ST-100 ¦ C-24-ST-110 ¦ C-24-MP-120 ¦ C-24-ST-130 ¦ C-24-ST-140 ¦ C-24-ST-150
Phased TCO | Structure | 25 | 2026-10-15 | 2026-10-22 | 6 | 9 | C-25-ST-100 ¦ C-25-ST-110 ¦ C-25-MP-120 ¦ C-25-ST-130 ¦ C-25-ST-140 ¦ C-25-ST-150
Phased TCO | Structure | 26 | 2026-10-22 | 2026-10-29 | 6 | 9 | C-26-ST-100 ¦ C-26-ST-110 ¦ C-26-MP-120 ¦ C-26-ST-130 ¦ C-26-ST-140 ¦ C-26-ST-150
Phased TCO | Structure | 27 | 2026-10-29 | 2026-11-05 | 6 | 9 | C-27-ST-100 ¦ C-27-ST-110 ¦ C-27-MP-120 ¦ C-27-ST-130 ¦ C-27-ST-140 ¦ C-27-ST-150
Phased TCO | Structure | 28 | 2026-11-05 | 2026-11-12 | 6 | 9 | C-28-ST-100 ¦ C-28-ST-110 ¦ C-28-MP-120 ¦ C-28-ST-130 ¦ C-28-ST-140 ¦ C-28-ST-150
Phased TCO | Structure | 29 | 2026-11-12 | 2026-11-19 | 6 | 9 | C-29-ST-100 ¦ C-29-ST-110 ¦ C-29-MP-120 ¦ C-29-ST-130 ¦ C-29-ST-140 ¦ C-29-ST-150
Phased TCO | Structure | 30 | 2026-11-19 | 2026-11-30 | 6 | 9 | C-30-ST-100 ¦ C-30-ST-110 ¦ C-30-MP-120 ¦ C-30-ST-130 ¦ C-30-ST-140 ¦ C-30-ST-150
Phased TCO | Structure | 31 | 2026-11-30 | 2026-12-07 | 6 | 9 | C-31-ST-100 ¦ C-31-ST-110 ¦ C-31-MP-120 ¦ C-31-ST-130 ¦ C-31-ST-140 ¦ C-31-ST-150
Phased TCO | Structure | 32 | 2026-12-07 | 2026-12-14 | 6 | 9 | C-32-ST-100 ¦ C-32-ST-110 ¦ C-32-MP-120 ¦ C-32-ST-130 ¦ C-32-ST-140 ¦ C-32-ST-150
Phased TCO | Structure | 33 | 2026-12-14 | 2026-12-22 | 6 | 9 | C-33-ST-100 ¦ C-33-MP-120 ¦ C-33-ST-110 ¦ C-33-ST-130 ¦ C-33-ST-140 ¦ C-33-ST-150
Phased TCO | Structure | 34 | 2026-12-22 | 2026-12-31 | 6 | 9 | C-34-ST-100 ¦ C-34-ST-110 ¦ C-34-MP-120 ¦ C-34-ST-130 ¦ C-34-ST-140 ¦ C-34-ST-150
Phased TCO | Structure | 35 | 2026-12-31 | 2027-01-08 | 6 | 9 | C-35-ST-100 ¦ C-35-ST-110 ¦ C-35-MP-120 ¦ C-35-ST-130 ¦ C-35-ST-140 ¦ C-35-ST-150
Phased TCO | Structure | 36 | 2027-01-08 | 2027-01-21 | 9 | 15 | C-36-ST-100 ¦ C-36-MP-120 ¦ C-36-ST-110 ¦ C-36-ST-130 ¦ C-36-ST-140 ¦ C-36-ST-150 ¦ C-36-ST-170 ¦ C-36-ST-180 ¦ C-36-ST-190
Phased TCO | Structure | 37 | 2027-01-27 | 2027-02-23 | 7 | 12 | C-37-ST-100 ¦ C-37-ST-110 ¦ C-37-MP-120 ¦ C-37-ST-130 ¦ C-37-ST-140 ¦ C-37-ST-150 ¦ C-37-ST-190
Phased TCO | Structure | 38 | 2027-02-04 | 2027-02-08 | 4 | 5 | C-38-ST-100 ¦ C-38-ST-110 ¦ C-38-MP-120 ¦ C-38-ST-130
Phased TCO | Envelope | 1 | 2027-03-19 | 2027-04-14 | 2 | 19 | C-01-ST-400 ¦ C-01-EX-100
Phased TCO | Envelope | 2 | 2026-06-04 | 2026-07-07 | 2 | 12 | C-02-ST-400 ¦ C-02-EX-100
Phased TCO | Envelope | 3 | 2026-06-19 | 2026-07-17 | 2 | 12 | C-03-ST-400 ¦ C-03-EX-100
Phased TCO | Envelope | 4 | 2026-07-01 | 2026-07-28 | 2 | 12 | C-04-ST-400 ¦ C-04-EX-100
Phased TCO | Envelope | 5 | 2026-07-13 | 2026-08-06 | 2 | 12 | C-05-ST-400 ¦ C-05-EX-100
Phased TCO | Envelope | 6 | 2026-07-22 | 2026-08-14 | 2 | 12 | C-06-ST-400 ¦ C-06-EX-100
Phased TCO | Envelope | 7 | 2026-07-31 | 2026-08-21 | 2 | 11 | C-07-ST-400 ¦ C-07-EX-100
Phased TCO | Envelope | 8 | 2026-08-10 | 2026-08-28 | 2 | 10 | C-08-ST-400 ¦ C-08-EX-100
Phased TCO | Envelope | 9 | 2026-08-17 | 2026-09-04 | 2 | 10 | C-09-ST-400 ¦ C-09-EX-100
Phased TCO | Envelope | 10 | 2026-08-24 | 2026-09-14 | 2 | 10 | C-10-ST-400 ¦ C-10-EX-100
Phased TCO | Envelope | 11 | 2026-08-31 | 2026-09-21 | 2 | 10 | C-11-ST-400 ¦ C-11-EX-100
Phased TCO | Envelope | 12 | 2026-09-08 | 2026-09-28 | 2 | 10 | C-12-ST-400 ¦ C-12-EX-100
Phased TCO | Envelope | 14 | 2026-09-15 | 2026-10-05 | 2 | 10 | C-14-ST-400 ¦ C-14-EX-100
Phased TCO | Envelope | 15 | 2026-09-22 | 2026-10-12 | 2 | 10 | C-15-ST-400 ¦ C-15-EX-100
Phased TCO | Envelope | 16 | 2026-09-29 | 2026-10-19 | 2 | 10 | C-16-ST-400 ¦ C-16-EX-100
Phased TCO | Envelope | 17 | 2026-10-06 | 2026-10-26 | 2 | 10 | C-17-ST-400 ¦ C-17-EX-100
Phased TCO | Envelope | 18 | 2026-10-13 | 2026-11-02 | 2 | 10 | C-18-ST-400 ¦ C-18-EX-100
Phased TCO | Envelope | 19 | 2026-10-20 | 2026-11-09 | 2 | 10 | C-19-ST-400 ¦ C-19-EX-100
Phased TCO | Envelope | 20 | 2026-10-27 | 2026-11-16 | 2 | 10 | C-20-ST-400 ¦ C-20-EX-100
Phased TCO | Envelope | 21 | 2026-11-03 | 2026-11-23 | 2 | 10 | C-21-ST-400 ¦ C-21-EX-100
Phased TCO | Envelope | 22 | 2026-11-10 | 2026-12-02 | 2 | 10 | C-22-ST-400 ¦ C-22-EX-100
Phased TCO | Envelope | 23 | 2026-11-17 | 2026-12-09 | 2 | 10 | C-23-ST-400 ¦ C-23-EX-100
Phased TCO | Envelope | 24 | 2026-11-24 | 2026-12-16 | 2 | 10 | C-24-ST-400 ¦ C-24-EX-100
Phased TCO | Envelope | 25 | 2026-12-03 | 2026-12-23 | 2 | 10 | C-25-ST-400 ¦ C-25-EX-100
Phased TCO | Envelope | 26 | 2026-12-10 | 2026-12-31 | 2 | 10 | C-26-ST-400 ¦ C-26-EX-100
Phased TCO | Envelope | 27 | 2026-12-17 | 2027-01-08 | 2 | 10 | C-27-ST-400 ¦ C-27-EX-100
Phased TCO | Envelope | 28 | 2026-12-24 | 2027-01-15 | 2 | 10 | C-28-ST-400 ¦ C-28-EX-100
Phased TCO | Envelope | 29 | 2027-01-04 | 2027-01-22 | 2 | 10 | C-29-ST-400 ¦ C-29-EX-100
Phased TCO | Envelope | 30 | 2027-01-11 | 2027-01-29 | 2 | 10 | C-30-ST-400 ¦ C-30-EX-100
Phased TCO | Envelope | 31 | 2027-01-18 | 2027-02-05 | 2 | 10 | C-31-ST-400 ¦ C-31-EX-100
Phased TCO | Envelope | 32 | 2027-01-25 | 2027-02-12 | 2 | 10 | C-32-ST-400 ¦ C-32-EX-100
Phased TCO | Envelope | 33 | 2027-02-01 | 2027-02-19 | 2 | 10 | C-33-ST-400 ¦ C-33-EX-100
Phased TCO | Envelope | 34 | 2027-02-08 | 2027-02-26 | 2 | 10 | C-34-ST-400 ¦ C-34-EX-100
Phased TCO | Envelope | 35 | 2027-02-15 | 2027-03-05 | 2 | 10 | C-35-ST-400 ¦ C-35-EX-100
Phased TCO | Envelope | 36 | 2027-02-22 | 2027-02-25 | 1 | 4 | C-36-ST-400
Phased TCO | Framing and MEP rough-in | 1 | 2027-03-30 | 2027-05-28 | 8 | 69 | C-01-UC-FN-100 ¦ C-01-UC-FN-120 ¦ C-01-UC-MP-140 ¦ C-01-UC-MP-150 ¦ C-01-UC-MP-160 ¦ C-01-UC-MP-170 ¦ C-01-UC-MP-180 ¦ C-01-UC-MP-190
Phased TCO | Framing and MEP rough-in | 2 | 2026-04-29 | 2026-06-26 | 13 | 41 | C-02-UC-MP-100 ¦ C-02-UC-MP-120 ¦ C-02-UC-MP-130 ¦ C-02-UC-FN-100 ¦ C-02-UC-FN-110 ¦ C-02-UC-FN-120 ¦ C-02-UC-MP-110 ¦ C-02-UC-MP-150 ¦ C-02-UC-MP-160 ¦ C-02-UC-MP-140 ¦ C-02-UC-MP-170 ¦ C-02-UC-MP-180 ¦ C-02-UC-MP-190
Phased TCO | Framing and MEP rough-in | 3 | 2026-05-14 | 2026-07-14 | 13 | 41 | C-03-U-MP-100 ¦ C-03-U-MP-120 ¦ C-03-U-MP-130 ¦ C-03-U-FN-100 ¦ C-03-U-FN-110 ¦ C-03-U-FN-120 ¦ C-03-U-MP-110 ¦ C-03-U-MP-150 ¦ C-03-U-MP-160 ¦ C-03-U-MP-140 ¦ C-03-U-MP-170 ¦ C-03-U-MP-180 ¦ C-03-U-MP-190
Phased TCO | Framing and MEP rough-in | 4 | 2026-06-01 | 2026-07-24 | 13 | 41 | C-04-U-MP-100 ¦ C-04-U-MP-120 ¦ C-04-U-MP-130 ¦ C-04-U-FN-100 ¦ C-04-U-FN-110 ¦ C-04-U-FN-120 ¦ C-04-U-MP-110 ¦ C-04-U-MP-150 ¦ C-04-U-MP-160 ¦ C-04-U-MP-140 ¦ C-04-U-MP-170 ¦ C-04-U-MP-180 ¦ C-04-U-MP-190
Phased TCO | Framing and MEP rough-in | 5 | 2026-06-16 | 2026-07-31 | 13 | 41 | C-05-U-MP-100 ¦ C-05-U-MP-120 ¦ C-05-U-MP-130 ¦ C-05-U-FN-100 ¦ C-05-U-FN-110 ¦ C-05-U-FN-120 ¦ C-05-U-MP-110 ¦ C-05-U-MP-150 ¦ C-05-U-MP-160 ¦ C-05-U-MP-140 ¦ C-05-U-MP-170 ¦ C-05-U-MP-180 ¦ C-05-U-MP-190
Phased TCO | Framing and MEP rough-in | 6 | 2026-06-26 | 2026-08-07 | 13 | 41 | C-06-U-MP-100 ¦ C-06-U-MP-120 ¦ C-06-U-MP-130 ¦ C-06-U-FN-100 ¦ C-06-U-FN-110 ¦ C-06-U-FN-120 ¦ C-06-U-MP-110 ¦ C-06-U-MP-150 ¦ C-06-U-MP-160 ¦ C-06-U-MP-140 ¦ C-06-U-MP-170 ¦ C-06-U-MP-180 ¦ C-06-U-MP-190
Phased TCO | Framing and MEP rough-in | 7 | 2026-07-06 | 2026-08-18 | 13 | 48 | C-07-U-MP-100 ¦ C-07-U-MP-120 ¦ C-07-U-MP-130 ¦ C-07-U-FN-100 ¦ C-07-U-FN-110 ¦ C-07-U-FN-120 ¦ C-07-U-MP-110 ¦ C-07-U-MP-150 ¦ C-07-U-MP-160 ¦ C-07-U-MP-140 ¦ C-07-U-MP-170 ¦ C-07-U-MP-180 ¦ C-07-U-MP-190
Phased TCO | Framing and MEP rough-in | 8 | 2026-07-29 | 2026-08-31 | 13 | 48 | C-08-U-FN-100 ¦ C-08-U-FN-110 ¦ C-08-U-MP-110 ¦ C-08-U-FN-120 ¦ C-08-U-MP-100 ¦ C-08-U-MP-120 ¦ C-08-U-MP-140 ¦ C-08-U-MP-130 ¦ C-08-U-MP-150 ¦ C-08-U-MP-170 ¦ C-08-U-MP-160 ¦ C-08-U-MP-180 ¦ C-08-U-MP-190
Phased TCO | Framing and MEP rough-in | 9 | 2026-08-06 | 2026-09-03 | 13 | 48 | C-09-U-FN-100 ¦ C-09-U-FN-110 ¦ C-09-U-MP-110 ¦ C-09-U-FN-120 ¦ C-09-U-MP-100 ¦ C-09-U-MP-120 ¦ C-09-U-MP-130 ¦ C-09-U-MP-140 ¦ C-09-U-MP-150 ¦ C-09-U-MP-160 ¦ C-09-U-MP-170 ¦ C-09-U-MP-180 ¦ C-09-U-MP-190
Phased TCO | Framing and MEP rough-in | 10 | 2026-08-13 | 2026-09-14 | 13 | 48 | C-10-U-FN-100 ¦ C-10-U-FN-110 ¦ C-10-U-MP-110 ¦ C-10-U-MP-100 ¦ C-10-U-FN-120 ¦ C-10-U-MP-120 ¦ C-10-U-MP-130 ¦ C-10-U-MP-150 ¦ C-10-U-MP-160 ¦ C-10-U-MP-140 ¦ C-10-U-MP-170 ¦ C-10-U-MP-180 ¦ C-10-U-MP-190
Phased TCO | Framing and MEP rough-in | 11 | 2026-08-20 | 2026-09-22 | 13 | 48 | C-11-U-FN-100 ¦ C-11-U-FN-110 ¦ C-11-U-MP-100 ¦ C-11-U-MP-110 ¦ C-11-U-MP-120 ¦ C-11-U-MP-130 ¦ C-11-U-FN-120 ¦ C-11-U-MP-150 ¦ C-11-U-MP-160 ¦ C-11-U-MP-140 ¦ C-11-U-MP-170 ¦ C-11-U-MP-180 ¦ C-11-U-MP-190
Phased TCO | Framing and MEP rough-in | 12 | 2026-08-24 | 2026-09-30 | 13 | 48 | C-12-U-MP-100 ¦ C-12-U-MP-120 ¦ C-12-U-FN-100 ¦ C-12-U-FN-110 ¦ C-12-U-MP-130 ¦ C-12-U-MP-110 ¦ C-12-U-FN-120 ¦ C-12-U-MP-150 ¦ C-12-U-MP-160 ¦ C-12-U-MP-140 ¦ C-12-U-MP-170 ¦ C-12-U-MP-180 ¦ C-12-U-MP-190
Phased TCO | Framing and MEP rough-in | 14 | 2026-08-26 | 2026-10-08 | 13 | 48 | C-14-U-MP-100 ¦ C-14-U-MP-120 ¦ C-14-U-MP-130 ¦ C-14-U-FN-100 ¦ C-14-U-FN-110 ¦ C-14-U-MP-110 ¦ C-14-U-FN-120 ¦ C-14-U-MP-150 ¦ C-14-U-MP-160 ¦ C-14-U-MP-140 ¦ C-14-U-MP-170 ¦ C-14-U-MP-180 ¦ C-14-U-MP-190
Phased TCO | Framing and MEP rough-in | 15 | 2026-08-28 | 2026-10-16 | 13 | 48 | C-15-U-MP-100 ¦ C-15-U-MP-120 ¦ C-15-U-MP-130 ¦ C-15-U-FN-100 ¦ C-15-U-FN-110 ¦ C-15-U-MP-110 ¦ C-15-U-FN-120 ¦ C-15-U-MP-150 ¦ C-15-U-MP-160 ¦ C-15-U-MP-140 ¦ C-15-U-MP-170 ¦ C-15-U-MP-180 ¦ C-15-U-MP-190
Phased TCO | Framing and MEP rough-in | 16 | 2026-09-01 | 2026-10-26 | 13 | 48 | C-16-U-MP-100 ¦ C-16-U-MP-120 ¦ C-16-U-MP-130 ¦ C-16-U-FN-100 ¦ C-16-U-FN-110 ¦ C-16-U-MP-110 ¦ C-16-U-FN-120 ¦ C-16-U-MP-150 ¦ C-16-U-MP-160 ¦ C-16-U-MP-140 ¦ C-16-U-MP-170 ¦ C-16-U-MP-180 ¦ C-16-U-MP-190
Phased TCO | Framing and MEP rough-in | 17 | 2026-09-09 | 2026-11-03 | 13 | 48 | C-17-U-MP-100 ¦ C-17-U-MP-120 ¦ C-17-U-MP-130 ¦ C-17-U-FN-100 ¦ C-17-U-FN-110 ¦ C-17-U-MP-110 ¦ C-17-U-FN-120 ¦ C-17-U-MP-150 ¦ C-17-U-MP-160 ¦ C-17-U-MP-140 ¦ C-17-U-MP-170 ¦ C-17-U-MP-180 ¦ C-17-U-MP-190
Phased TCO | Framing and MEP rough-in | 18 | 2026-09-16 | 2026-11-11 | 13 | 48 | C-18-U-MP-100 ¦ C-18-U-MP-120 ¦ C-18-U-MP-130 ¦ C-18-U-FN-100 ¦ C-18-U-FN-110 ¦ C-18-U-MP-110 ¦ C-18-U-FN-120 ¦ C-18-U-MP-150 ¦ C-18-U-MP-160 ¦ C-18-U-MP-140 ¦ C-18-U-MP-170 ¦ C-18-U-MP-180 ¦ C-18-U-MP-190
Phased TCO | Framing and MEP rough-in | 19 | 2026-09-23 | 2026-11-19 | 13 | 48 | C-19-U-MP-100 ¦ C-19-U-MP-120 ¦ C-19-U-MP-130 ¦ C-19-U-FN-100 ¦ C-19-U-FN-110 ¦ C-19-U-MP-110 ¦ C-19-U-FN-120 ¦ C-19-U-MP-150 ¦ C-19-U-MP-160 ¦ C-19-U-MP-140 ¦ C-19-U-MP-170 ¦ C-19-U-MP-180 ¦ C-19-U-MP-190
Phased TCO | Framing and MEP rough-in | 20 | 2026-09-30 | 2026-12-01 | 13 | 48 | C-20-U-MP-100 ¦ C-20-U-MP-120 ¦ C-20-U-MP-130 ¦ C-20-U-FN-100 ¦ C-20-U-FN-110 ¦ C-20-U-MP-110 ¦ C-20-U-FN-120 ¦ C-20-U-MP-150 ¦ C-20-U-MP-160 ¦ C-20-U-MP-140 ¦ C-20-U-MP-170 ¦ C-20-U-MP-180 ¦ C-20-U-MP-190
Phased TCO | Framing and MEP rough-in | 21 | 2026-10-07 | 2026-12-09 | 13 | 48 | C-21-U-MP-100 ¦ C-21-U-MP-120 ¦ C-21-U-MP-130 ¦ C-21-U-FN-100 ¦ C-21-U-FN-110 ¦ C-21-U-MP-110 ¦ C-21-U-FN-120 ¦ C-21-U-MP-150 ¦ C-21-U-MP-160 ¦ C-21-U-MP-140 ¦ C-21-U-MP-170 ¦ C-21-U-MP-180 ¦ C-21-U-MP-190
Phased TCO | Framing and MEP rough-in | 22 | 2026-10-14 | 2026-12-17 | 13 | 48 | C-22-U-MP-100 ¦ C-22-U-MP-120 ¦ C-22-U-MP-130 ¦ C-22-U-FN-100 ¦ C-22-U-FN-110 ¦ C-22-U-MP-110 ¦ C-22-U-FN-120 ¦ C-22-U-MP-150 ¦ C-22-U-MP-160 ¦ C-22-U-MP-140 ¦ C-22-U-MP-170 ¦ C-22-U-MP-180 ¦ C-22-U-MP-190
Phased TCO | Framing and MEP rough-in | 23 | 2026-10-21 | 2026-12-28 | 13 | 48 | C-23-U-MP-100 ¦ C-23-U-MP-120 ¦ C-23-U-MP-130 ¦ C-23-U-FN-100 ¦ C-23-U-FN-110 ¦ C-23-U-MP-110 ¦ C-23-U-FN-120 ¦ C-23-U-MP-150 ¦ C-23-U-MP-160 ¦ C-23-U-MP-140 ¦ C-23-U-MP-170 ¦ C-23-U-MP-180 ¦ C-23-U-MP-190
Phased TCO | Framing and MEP rough-in | 24 | 2026-10-28 | 2027-01-06 | 13 | 48 | C-24-U-MP-100 ¦ C-24-U-MP-120 ¦ C-24-U-MP-130 ¦ C-24-U-FN-100 ¦ C-24-U-FN-110 ¦ C-24-U-MP-110 ¦ C-24-U-FN-120 ¦ C-24-U-MP-150 ¦ C-24-U-MP-160 ¦ C-24-U-MP-140 ¦ C-24-U-MP-170 ¦ C-24-U-MP-180 ¦ C-24-U-MP-190
Phased TCO | Framing and MEP rough-in | 25 | 2026-11-04 | 2027-01-14 | 13 | 48 | C-25-U-MP-100 ¦ C-25-U-MP-120 ¦ C-25-U-MP-130 ¦ C-25-U-FN-100 ¦ C-25-U-FN-110 ¦ C-25-U-MP-110 ¦ C-25-U-FN-120 ¦ C-25-U-MP-150 ¦ C-25-U-MP-160 ¦ C-25-U-MP-140 ¦ C-25-U-MP-170 ¦ C-25-U-MP-180 ¦ C-25-U-MP-190
Phased TCO | Framing and MEP rough-in | 26 | 2026-11-11 | 2027-01-22 | 13 | 48 | C-26-U-MP-100 ¦ C-26-U-MP-120 ¦ C-26-U-MP-130 ¦ C-26-U-FN-100 ¦ C-26-U-FN-110 ¦ C-26-U-MP-110 ¦ C-26-U-FN-120 ¦ C-26-U-MP-150 ¦ C-26-U-MP-160 ¦ C-26-U-MP-140 ¦ C-26-U-MP-170 ¦ C-26-U-MP-180 ¦ C-26-U-MP-190
Phased TCO | Framing and MEP rough-in | 27 | 2026-11-18 | 2027-02-01 | 13 | 48 | C-27-U-MP-100 ¦ C-27-U-MP-120 ¦ C-27-U-MP-130 ¦ C-27-U-FN-100 ¦ C-27-U-FN-110 ¦ C-27-U-MP-110 ¦ C-27-U-FN-120 ¦ C-27-U-MP-150 ¦ C-27-U-MP-160 ¦ C-27-U-MP-140 ¦ C-27-U-MP-170 ¦ C-27-U-MP-180 ¦ C-27-U-MP-190
Phased TCO | Framing and MEP rough-in | 28 | 2026-11-25 | 2027-02-09 | 13 | 48 | C-28-U-MP-100 ¦ C-28-U-MP-120 ¦ C-28-U-MP-130 ¦ C-28-U-FN-100 ¦ C-28-U-FN-110 ¦ C-28-U-MP-110 ¦ C-28-U-FN-120 ¦ C-28-U-MP-150 ¦ C-28-U-MP-160 ¦ C-28-U-MP-140 ¦ C-28-U-MP-170 ¦ C-28-U-MP-180 ¦ C-28-U-MP-190
Phased TCO | Framing and MEP rough-in | 29 | 2026-12-04 | 2027-02-17 | 13 | 48 | C-29-U-MP-100 ¦ C-29-U-MP-120 ¦ C-29-U-MP-130 ¦ C-29-U-FN-100 ¦ C-29-U-FN-110 ¦ C-29-U-MP-110 ¦ C-29-U-FN-120 ¦ C-29-U-MP-150 ¦ C-29-U-MP-160 ¦ C-29-U-MP-140 ¦ C-29-U-MP-170 ¦ C-29-U-MP-180 ¦ C-29-U-MP-190
Phased TCO | Framing and MEP rough-in | 30 | 2026-12-11 | 2027-02-25 | 13 | 48 | C-30-U-MP-100 ¦ C-30-U-MP-120 ¦ C-30-U-MP-130 ¦ C-30-U-FN-100 ¦ C-30-U-FN-110 ¦ C-30-U-MP-110 ¦ C-30-U-FN-120 ¦ C-30-U-MP-150 ¦ C-30-U-MP-160 ¦ C-30-U-MP-140 ¦ C-30-U-MP-170 ¦ C-30-U-MP-180 ¦ C-30-U-MP-190
Phased TCO | Framing and MEP rough-in | 31 | 2026-12-21 | 2027-03-05 | 13 | 48 | C-31-U-MP-100 ¦ C-31-U-MP-120 ¦ C-31-U-MP-130 ¦ C-31-U-FN-100 ¦ C-31-U-FN-110 ¦ C-31-U-MP-110 ¦ C-31-U-FN-120 ¦ C-31-U-MP-150 ¦ C-31-U-MP-160 ¦ C-31-U-MP-140 ¦ C-31-U-MP-170 ¦ C-31-U-MP-180 ¦ C-31-U-MP-190
Phased TCO | Framing and MEP rough-in | 32 | 2026-12-30 | 2027-03-15 | 13 | 48 | C-32-U-MP-100 ¦ C-32-U-MP-120 ¦ C-32-U-MP-130 ¦ C-32-U-FN-100 ¦ C-32-U-FN-110 ¦ C-32-U-MP-110 ¦ C-32-U-FN-120 ¦ C-32-U-MP-150 ¦ C-32-U-MP-160 ¦ C-32-U-MP-140 ¦ C-32-U-MP-170 ¦ C-32-U-MP-180 ¦ C-32-U-MP-190
Phased TCO | Framing and MEP rough-in | 33 | 2027-01-07 | 2027-03-23 | 13 | 48 | C-33-U-MP-100 ¦ C-33-U-MP-120 ¦ C-33-U-MP-130 ¦ C-33-U-FN-100 ¦ C-33-U-FN-110 ¦ C-33-U-MP-110 ¦ C-33-U-FN-120 ¦ C-33-U-MP-150 ¦ C-33-U-MP-160 ¦ C-33-U-MP-140 ¦ C-33-U-MP-170 ¦ C-33-U-MP-180 ¦ C-33-U-MP-190
Phased TCO | Framing and MEP rough-in | 34 | 2027-01-14 | 2027-03-31 | 13 | 48 | C-34-U-MP-100 ¦ C-34-U-MP-120 ¦ C-34-U-MP-130 ¦ C-34-U-FN-100 ¦ C-34-U-FN-110 ¦ C-34-U-MP-110 ¦ C-34-U-FN-120 ¦ C-34-U-MP-150 ¦ C-34-U-MP-160 ¦ C-34-U-MP-140 ¦ C-34-U-MP-170 ¦ C-34-U-MP-180 ¦ C-34-U-MP-190
Phased TCO | Framing and MEP rough-in | 35 | 2027-02-01 | 2027-04-08 | 13 | 48 | C-35-U-MP-100 ¦ C-35-U-MP-120 ¦ C-35-U-MP-130 ¦ C-35-U-FN-100 ¦ C-35-U-FN-110 ¦ C-35-U-MP-110 ¦ C-35-U-FN-120 ¦ C-35-U-MP-150 ¦ C-35-U-MP-160 ¦ C-35-U-MP-140 ¦ C-35-U-MP-170 ¦ C-35-U-MP-180 ¦ C-35-U-MP-190
Phased TCO | Framing and MEP rough-in | 36 | 2027-02-09 | 2027-05-18 | 12 | 38 | C-36-IN-MP-100 ¦ C-36-IN-MP-120 ¦ C-36-IN-MP-130 ¦ C-36-IN-FN-100 ¦ C-36-IN-FN-110 ¦ C-36-IN-FN-120 ¦ C-36-IN-MP-110 ¦ C-36-IN-MP-150 ¦ C-36-IN-MP-140 ¦ C-36-IN-MP-160 ¦ C-36-IN-MP-170 ¦ C-36-IN-MP-180
Phased TCO | Drywall and prime paint | 1 | 2027-06-01 | 2027-06-18 | 5 | 21 | C-01-UC-FN-200 ¦ C-01-UC-FN-210 ¦ C-01-UC-FN-230 ¦ C-01-UC-FN-270 ¦ C-01-UC-FN-260
Phased TCO | Drywall and prime paint | 2 | 2026-06-09 | 2026-08-07 | 8 | 38 | C-02-UC-FN-220 ¦ C-02-UC-FN-200 ¦ C-02-UC-FN-210 ¦ C-02-UC-FN-230 ¦ C-02-UC-FN-240 ¦ C-02-UC-FN-250 ¦ C-02-UC-FN-260 ¦ C-02-UC-FN-270
Phased TCO | Drywall and prime paint | 3 | 2026-06-24 | 2026-08-19 | 8 | 38 | C-03-U-FN-220 ¦ C-03-U-FN-200 ¦ C-03-U-FN-210 ¦ C-03-U-FN-230 ¦ C-03-U-FN-240 ¦ C-03-U-FN-250 ¦ C-03-U-FN-260 ¦ C-03-U-FN-270
Phased TCO | Drywall and prime paint | 4 | 2026-07-07 | 2026-08-28 | 8 | 38 | C-04-U-FN-220 ¦ C-04-U-FN-200 ¦ C-04-U-FN-210 ¦ C-04-U-FN-230 ¦ C-04-U-FN-240 ¦ C-04-U-FN-250 ¦ C-04-U-FN-260 ¦ C-04-U-FN-270
Phased TCO | Drywall and prime paint | 5 | 2026-07-14 | 2026-09-09 | 8 | 38 | C-05-U-FN-220 ¦ C-05-U-FN-200 ¦ C-05-U-FN-210 ¦ C-05-U-FN-230 ¦ C-05-U-FN-240 ¦ C-05-U-FN-250 ¦ C-05-U-FN-260 ¦ C-05-U-FN-270
Phased TCO | Drywall and prime paint | 6 | 2026-07-21 | 2026-09-17 | 8 | 38 | C-06-U-FN-220 ¦ C-06-U-FN-200 ¦ C-06-U-FN-210 ¦ C-06-U-FN-230 ¦ C-06-U-FN-240 ¦ C-06-U-FN-250 ¦ C-06-U-FN-260 ¦ C-06-U-FN-270
Phased TCO | Drywall and prime paint | 7 | 2026-07-28 | 2026-09-24 | 8 | 42 | C-07-U-FN-220 ¦ C-07-U-FN-200 ¦ C-07-U-FN-210 ¦ C-07-U-FN-240 ¦ C-07-U-FN-230 ¦ C-07-U-FN-250 ¦ C-07-U-FN-260 ¦ C-07-U-FN-270
Phased TCO | Drywall and prime paint | 8 | 2026-08-05 | 2026-10-02 | 8 | 42 | C-08-U-FN-220 ¦ C-08-U-FN-200 ¦ C-08-U-FN-210 ¦ C-08-U-FN-240 ¦ C-08-U-FN-230 ¦ C-08-U-FN-250 ¦ C-08-U-FN-260 ¦ C-08-U-FN-270
Phased TCO | Drywall and prime paint | 9 | 2026-08-13 | 2026-10-08 | 8 | 42 | C-09-U-FN-220 ¦ C-09-U-FN-200 ¦ C-09-U-FN-210 ¦ C-09-U-FN-240 ¦ C-09-U-FN-230 ¦ C-09-U-FN-250 ¦ C-09-U-FN-260 ¦ C-09-U-FN-270
Phased TCO | Drywall and prime paint | 10 | 2026-08-21 | 2026-10-15 | 8 | 42 | C-10-U-FN-220 ¦ C-10-U-FN-200 ¦ C-10-U-FN-210 ¦ C-10-U-FN-240 ¦ C-10-U-FN-230 ¦ C-10-U-FN-250 ¦ C-10-U-FN-260 ¦ C-10-U-FN-270
Phased TCO | Drywall and prime paint | 11 | 2026-08-31 | 2026-10-23 | 8 | 42 | C-11-U-FN-220 ¦ C-11-U-FN-200 ¦ C-11-U-FN-210 ¦ C-11-U-FN-240 ¦ C-11-U-FN-230 ¦ C-11-U-FN-250 ¦ C-11-U-FN-260 ¦ C-11-U-FN-270
Phased TCO | Drywall and prime paint | 12 | 2026-09-09 | 2026-11-02 | 8 | 42 | C-12-U-FN-220 ¦ C-12-U-FN-200 ¦ C-12-U-FN-210 ¦ C-12-U-FN-240 ¦ C-12-U-FN-230 ¦ C-12-U-FN-250 ¦ C-12-U-FN-260 ¦ C-12-U-FN-270
Phased TCO | Drywall and prime paint | 14 | 2026-09-17 | 2026-11-10 | 8 | 42 | C-14-U-FN-220 ¦ C-14-U-FN-200 ¦ C-14-U-FN-210 ¦ C-14-U-FN-240 ¦ C-14-U-FN-230 ¦ C-14-U-FN-250 ¦ C-14-U-FN-260 ¦ C-14-U-FN-270
Phased TCO | Drywall and prime paint | 15 | 2026-09-25 | 2026-11-18 | 8 | 42 | C-15-U-FN-220 ¦ C-15-U-FN-200 ¦ C-15-U-FN-210 ¦ C-15-U-FN-240 ¦ C-15-U-FN-230 ¦ C-15-U-FN-250 ¦ C-15-U-FN-260 ¦ C-15-U-FN-270
Phased TCO | Drywall and prime paint | 16 | 2026-10-05 | 2026-11-30 | 8 | 42 | C-16-U-FN-220 ¦ C-16-U-FN-200 ¦ C-16-U-FN-210 ¦ C-16-U-FN-240 ¦ C-16-U-FN-230 ¦ C-16-U-FN-250 ¦ C-16-U-FN-260 ¦ C-16-U-FN-270
Phased TCO | Drywall and prime paint | 17 | 2026-10-13 | 2026-12-08 | 8 | 42 | C-17-U-FN-220 ¦ C-17-U-FN-200 ¦ C-17-U-FN-210 ¦ C-17-U-FN-240 ¦ C-17-U-FN-230 ¦ C-17-U-FN-250 ¦ C-17-U-FN-260 ¦ C-17-U-FN-270
Phased TCO | Drywall and prime paint | 18 | 2026-10-21 | 2026-12-16 | 8 | 42 | C-18-U-FN-220 ¦ C-18-U-FN-200 ¦ C-18-U-FN-210 ¦ C-18-U-FN-240 ¦ C-18-U-FN-230 ¦ C-18-U-FN-250 ¦ C-18-U-FN-260 ¦ C-18-U-FN-270
Phased TCO | Drywall and prime paint | 19 | 2026-10-29 | 2026-12-24 | 8 | 42 | C-19-U-FN-220 ¦ C-19-U-FN-200 ¦ C-19-U-FN-210 ¦ C-19-U-FN-240 ¦ C-19-U-FN-230 ¦ C-19-U-FN-250 ¦ C-19-U-FN-260 ¦ C-19-U-FN-270
Phased TCO | Drywall and prime paint | 20 | 2026-11-06 | 2027-01-05 | 8 | 42 | C-20-U-FN-220 ¦ C-20-U-FN-200 ¦ C-20-U-FN-210 ¦ C-20-U-FN-240 ¦ C-20-U-FN-230 ¦ C-20-U-FN-250 ¦ C-20-U-FN-260 ¦ C-20-U-FN-270
Phased TCO | Drywall and prime paint | 21 | 2026-11-16 | 2027-01-13 | 8 | 42 | C-21-U-FN-220 ¦ C-21-U-FN-200 ¦ C-21-U-FN-210 ¦ C-21-U-FN-240 ¦ C-21-U-FN-230 ¦ C-21-U-FN-250 ¦ C-21-U-FN-260 ¦ C-21-U-FN-270
Phased TCO | Drywall and prime paint | 22 | 2026-11-24 | 2027-01-21 | 8 | 42 | C-22-U-FN-220 ¦ C-22-U-FN-200 ¦ C-22-U-FN-210 ¦ C-22-U-FN-240 ¦ C-22-U-FN-230 ¦ C-22-U-FN-250 ¦ C-22-U-FN-260 ¦ C-22-U-FN-270
Phased TCO | Drywall and prime paint | 23 | 2026-12-04 | 2027-01-29 | 8 | 42 | C-23-U-FN-220 ¦ C-23-U-FN-200 ¦ C-23-U-FN-210 ¦ C-23-U-FN-240 ¦ C-23-U-FN-230 ¦ C-23-U-FN-250 ¦ C-23-U-FN-260 ¦ C-23-U-FN-270
Phased TCO | Drywall and prime paint | 24 | 2026-12-14 | 2027-02-08 | 8 | 42 | C-24-U-FN-220 ¦ C-24-U-FN-200 ¦ C-24-U-FN-210 ¦ C-24-U-FN-240 ¦ C-24-U-FN-230 ¦ C-24-U-FN-250 ¦ C-24-U-FN-260 ¦ C-24-U-FN-270
Phased TCO | Drywall and prime paint | 25 | 2026-12-22 | 2027-02-16 | 8 | 42 | C-25-U-FN-220 ¦ C-25-U-FN-200 ¦ C-25-U-FN-210 ¦ C-25-U-FN-240 ¦ C-25-U-FN-230 ¦ C-25-U-FN-250 ¦ C-25-U-FN-260 ¦ C-25-U-FN-270
Phased TCO | Drywall and prime paint | 26 | 2026-12-31 | 2027-02-24 | 8 | 42 | C-26-U-FN-220 ¦ C-26-U-FN-200 ¦ C-26-U-FN-210 ¦ C-26-U-FN-240 ¦ C-26-U-FN-230 ¦ C-26-U-FN-250 ¦ C-26-U-FN-260 ¦ C-26-U-FN-270
Phased TCO | Drywall and prime paint | 27 | 2027-01-11 | 2027-03-04 | 8 | 42 | C-27-U-FN-220 ¦ C-27-U-FN-200 ¦ C-27-U-FN-210 ¦ C-27-U-FN-240 ¦ C-27-U-FN-230 ¦ C-27-U-FN-250 ¦ C-27-U-FN-260 ¦ C-27-U-FN-270
Phased TCO | Drywall and prime paint | 28 | 2027-01-19 | 2027-03-12 | 8 | 42 | C-28-U-FN-220 ¦ C-28-U-FN-200 ¦ C-28-U-FN-210 ¦ C-28-U-FN-240 ¦ C-28-U-FN-230 ¦ C-28-U-FN-250 ¦ C-28-U-FN-260 ¦ C-28-U-FN-270
Phased TCO | Drywall and prime paint | 29 | 2027-01-27 | 2027-03-22 | 8 | 42 | C-29-U-FN-220 ¦ C-29-U-FN-200 ¦ C-29-U-FN-210 ¦ C-29-U-FN-240 ¦ C-29-U-FN-230 ¦ C-29-U-FN-250 ¦ C-29-U-FN-260 ¦ C-29-U-FN-270
Phased TCO | Drywall and prime paint | 30 | 2027-02-04 | 2027-03-30 | 8 | 42 | C-30-U-FN-220 ¦ C-30-U-FN-200 ¦ C-30-U-FN-210 ¦ C-30-U-FN-240 ¦ C-30-U-FN-230 ¦ C-30-U-FN-250 ¦ C-30-U-FN-260 ¦ C-30-U-FN-270
Phased TCO | Drywall and prime paint | 31 | 2027-02-12 | 2027-04-07 | 8 | 42 | C-31-U-FN-220 ¦ C-31-U-FN-200 ¦ C-31-U-FN-210 ¦ C-31-U-FN-240 ¦ C-31-U-FN-230 ¦ C-31-U-FN-250 ¦ C-31-U-FN-260 ¦ C-31-U-FN-270
Phased TCO | Drywall and prime paint | 32 | 2027-02-22 | 2027-04-15 | 8 | 42 | C-32-U-FN-220 ¦ C-32-U-FN-200 ¦ C-32-U-FN-210 ¦ C-32-U-FN-240 ¦ C-32-U-FN-230 ¦ C-32-U-FN-250 ¦ C-32-U-FN-260 ¦ C-32-U-FN-270
Phased TCO | Drywall and prime paint | 33 | 2027-03-02 | 2027-04-23 | 8 | 42 | C-33-U-FN-220 ¦ C-33-U-FN-200 ¦ C-33-U-FN-210 ¦ C-33-U-FN-240 ¦ C-33-U-FN-230 ¦ C-33-U-FN-250 ¦ C-33-U-FN-260 ¦ C-33-U-FN-270
Phased TCO | Drywall and prime paint | 34 | 2027-03-10 | 2027-05-03 | 8 | 42 | C-34-U-FN-220 ¦ C-34-U-FN-200 ¦ C-34-U-FN-210 ¦ C-34-U-FN-240 ¦ C-34-U-FN-230 ¦ C-34-U-FN-250 ¦ C-34-U-FN-260 ¦ C-34-U-FN-270
Phased TCO | Drywall and prime paint | 35 | 2027-03-18 | 2027-05-11 | 8 | 42 | C-35-U-FN-220 ¦ C-35-U-FN-200 ¦ C-35-U-FN-210 ¦ C-35-U-FN-240 ¦ C-35-U-FN-230 ¦ C-35-U-FN-250 ¦ C-35-U-FN-260 ¦ C-35-U-FN-270
Phased TCO | Drywall and prime paint | 36 | 2027-05-03 | 2027-06-09 | 8 | 25 | C-36-IN-FN-220 ¦ C-36-IN-FN-200 ¦ C-36-IN-FN-240 ¦ C-36-IN-FN-210 ¦ C-36-IN-FN-250 ¦ C-36-IN-FN-230 ¦ C-36-IN-FN-260 ¦ C-36-IN-FN-270
Phased TCO | Finishes and equipment | 1 | 2027-06-17 | 2027-07-26 | 24 | 83 | C-01-C-FN-100 ¦ C-01-UC-MP-200 ¦ C-01-UC-FN-310 ¦ C-01-C-FN-110 ¦ C-01-UC-FN-320 ¦ C-01-UC-FN-330 ¦ C-01-UC-FN-370 ¦ C-01-UC-MP-400 ¦ C-01-UC-MP-410 ¦ C-01-UC-MP-420 ¦ C-01-C-FN-120 ¦ C-01-UC-MP-430 ¦ C-01-UC-MP-440 ¦ C-01-C-FN-140 ¦ C-01-C-FN-150 ¦ C-01-UC-FN-400 ¦ C-01-C-FN-160 ¦ C-01-C-FN-170 ¦ C-01-C-MP-120 ¦ C-01-C-MP-130 ¦ C-01-C-MP-150 ¦ C-01-C-MP-160 ¦ C-01-C-MP-140 ¦ C-01-C-FN-180
Phased TCO | Finishes and equipment | 2 | 2026-08-07 | 2026-10-23 | 36 | 107 | C-02-UC-FN-280 ¦ C-02-C-FN-100 ¦ C-02-UC-MP-200 ¦ C-02-C-FN-110 ¦ C-02-C-FN-120 ¦ C-02-C-FN-140 ¦ C-02-UC-FN-290 ¦ C-02-UC-FN-370 ¦ C-02-UC-FN-300 ¦ C-02-UC-FN-310 ¦ C-02-UC-FN-320 ¦ C-02-UC-FN-330 ¦ C-02-UC-FN-350 ¦ C-02-UC-FN-360 ¦ C-02-C-FN-130 ¦ C-02-UC-MP-210 ¦ C-02-UC-MP-400 ¦ C-02-C-FN-150 ¦ C-02-UC-FN-340 ¦ C-02-C-FN-160 ¦ C-02-C-FN-170 ¦ C-02-C-MP-110 ¦ C-02-C-MP-120 ¦ C-02-UC-MP-410 ¦ C-02-C-MP-140 ¦ C-02-UC-MP-420 ¦ C-02-UC-MP-430 ¦ C-02-UC-MP-440 ¦ C-02-C-MP-100 ¦ C-02-UC-FN-390 ¦ C-02-UC-FN-450 ¦ C-02-UC-FN-400 ¦ C-02-C-MP-130 ¦ C-02-C-MP-150 ¦ C-02-C-MP-160 ¦ C-02-C-FN-180
Phased TCO | Finishes and equipment | 3 | 2026-08-19 | 2026-09-24 | 33 | 92 | C-03-U-FN-280 ¦ C-03-C-FN-100 ¦ C-03-U-MP-200 ¦ C-03-C-FN-110 ¦ C-03-U-FN-290 ¦ C-03-C-FN-120 ¦ C-03-C-FN-130 ¦ C-03-C-FN-140 ¦ C-03-C-MP-100 ¦ C-03-U-FN-300 ¦ C-03-U-MP-210 ¦ C-03-C-FN-150 ¦ C-03-U-FN-310 ¦ C-03-U-FN-370 ¦ C-03-C-FN-160 ¦ C-03-C-MP-110 ¦ C-03-C-MP-120 ¦ C-03-C-MP-140 ¦ C-03-U-FN-330 ¦ C-03-U-FN-340 ¦ C-03-U-MP-400 ¦ C-03-C-FN-170 ¦ C-03-U-FN-350 ¦ C-03-C-MP-130 ¦ C-03-C-MP-150 ¦ C-03-C-MP-160 ¦ C-03-C-FN-180 ¦ C-03-U-FN-390 ¦ C-03-U-MP-410 ¦ C-03-U-FN-400 ¦ C-03-U-MP-420 ¦ C-03-U-MP-430 ¦ C-03-U-MP-440
Phased TCO | Finishes and equipment | 4 | 2026-08-28 | 2026-10-02 | 33 | 92 | C-04-U-FN-280 ¦ C-04-C-FN-100 ¦ C-04-U-MP-200 ¦ C-04-C-FN-110 ¦ C-04-U-FN-290 ¦ C-04-C-FN-120 ¦ C-04-C-FN-130 ¦ C-04-C-FN-140 ¦ C-04-C-MP-100 ¦ C-04-U-FN-300 ¦ C-04-U-MP-210 ¦ C-04-C-FN-150 ¦ C-04-U-FN-310 ¦ C-04-U-FN-370 ¦ C-04-C-FN-160 ¦ C-04-C-MP-110 ¦ C-04-C-MP-120 ¦ C-04-C-MP-140 ¦ C-04-U-FN-330 ¦ C-04-U-FN-340 ¦ C-04-U-MP-400 ¦ C-04-C-FN-170 ¦ C-04-U-FN-350 ¦ C-04-C-MP-130 ¦ C-04-C-MP-150 ¦ C-04-C-MP-160 ¦ C-04-C-FN-180 ¦ C-04-U-FN-390 ¦ C-04-U-MP-410 ¦ C-04-U-FN-400 ¦ C-04-U-MP-420 ¦ C-04-U-MP-430 ¦ C-04-U-MP-440
Phased TCO | Finishes and equipment | 5 | 2026-09-09 | 2026-10-12 | 33 | 92 | C-05-U-FN-280 ¦ C-05-C-FN-100 ¦ C-05-U-MP-200 ¦ C-05-C-FN-110 ¦ C-05-U-FN-290 ¦ C-05-C-FN-120 ¦ C-05-C-FN-130 ¦ C-05-C-FN-140 ¦ C-05-C-MP-100 ¦ C-05-U-FN-300 ¦ C-05-U-MP-210 ¦ C-05-C-FN-150 ¦ C-05-U-FN-310 ¦ C-05-U-FN-370 ¦ C-05-C-FN-160 ¦ C-05-C-MP-110 ¦ C-05-C-MP-120 ¦ C-05-C-MP-140 ¦ C-05-U-FN-330 ¦ C-05-U-FN-340 ¦ C-05-U-MP-400 ¦ C-05-C-FN-170 ¦ C-05-U-FN-350 ¦ C-05-C-MP-130 ¦ C-05-C-MP-150 ¦ C-05-C-MP-160 ¦ C-05-U-FN-390 ¦ C-05-U-MP-410 ¦ C-05-C-FN-180 ¦ C-05-U-FN-400 ¦ C-05-U-MP-420 ¦ C-05-U-MP-430 ¦ C-05-U-MP-440
Phased TCO | Finishes and equipment | 6 | 2026-09-17 | 2026-10-20 | 33 | 92 | C-06-U-FN-280 ¦ C-06-C-FN-100 ¦ C-06-U-MP-200 ¦ C-06-C-FN-110 ¦ C-06-U-FN-290 ¦ C-06-C-FN-120 ¦ C-06-C-FN-130 ¦ C-06-C-FN-140 ¦ C-06-C-MP-100 ¦ C-06-U-FN-300 ¦ C-06-U-MP-210 ¦ C-06-C-FN-150 ¦ C-06-U-FN-310 ¦ C-06-U-FN-370 ¦ C-06-C-FN-160 ¦ C-06-C-MP-110 ¦ C-06-C-MP-120 ¦ C-06-C-MP-140 ¦ C-06-U-FN-330 ¦ C-06-U-FN-340 ¦ C-06-U-MP-400 ¦ C-06-C-FN-170 ¦ C-06-U-FN-350 ¦ C-06-C-MP-130 ¦ C-06-C-MP-150 ¦ C-06-C-MP-160 ¦ C-06-U-FN-390 ¦ C-06-U-MP-410 ¦ C-06-C-FN-180 ¦ C-06-U-FN-400 ¦ C-06-U-MP-420 ¦ C-06-U-MP-430 ¦ C-06-U-MP-440
Phased TCO | Finishes and equipment | 7 | 2026-09-23 | 2026-11-13 | 36 | 129 | C-07-U-FN-280 ¦ C-07-U-MP-200 ¦ C-07-U-FN-290 ¦ C-07-U-FN-300 ¦ C-07-U-FN-370 ¦ C-07-U-MP-210 ¦ C-07-U-FN-310 ¦ C-07-C-FN-100 ¦ C-07-C-FN-120 ¦ C-07-C-FN-140 ¦ C-07-U-FN-320 ¦ C-07-U-FN-330 ¦ C-07-U-FN-340 ¦ C-07-U-FN-350 ¦ C-07-U-MP-400 ¦ C-07-U-MP-440 ¦ C-07-U-FN-360 ¦ C-07-C-FN-110 ¦ C-07-C-FN-130 ¦ C-07-C-MP-100 ¦ C-07-C-FN-150 ¦ C-07-C-FN-160 ¦ C-07-C-FN-170 ¦ C-07-C-MP-110 ¦ C-07-C-MP-120 ¦ C-07-C-MP-140 ¦ C-07-U-MP-410 ¦ C-07-U-FN-390 ¦ C-07-U-MP-420 ¦ C-07-U-MP-430 ¦ C-07-U-FN-400 ¦ C-07-C-MP-150 ¦ C-07-C-MP-130 ¦ C-07-C-MP-160 ¦ C-07-U-FN-410 ¦ C-07-C-FN-180
Phased TCO | Finishes and equipment | 8 | 2026-10-01 | 2026-11-24 | 34 | 119 | C-08-U-FN-280 ¦ C-08-U-MP-200 ¦ C-08-U-FN-290 ¦ C-08-U-FN-370 ¦ C-08-U-FN-300 ¦ C-08-U-MP-210 ¦ C-08-U-FN-310 ¦ C-08-C-FN-100 ¦ C-08-C-FN-120 ¦ C-08-C-FN-140 ¦ C-08-U-FN-330 ¦ C-08-U-FN-340 ¦ C-08-U-FN-350 ¦ C-08-U-MP-400 ¦ C-08-U-MP-440 ¦ C-08-C-FN-110 ¦ C-08-C-FN-130 ¦ C-08-C-MP-100 ¦ C-08-C-FN-150 ¦ C-08-C-FN-160 ¦ C-08-C-FN-170 ¦ C-08-C-MP-110 ¦ C-08-C-MP-120 ¦ C-08-C-MP-140 ¦ C-08-U-MP-410 ¦ C-08-U-FN-390 ¦ C-08-U-MP-420 ¦ C-08-U-MP-430 ¦ C-08-U-FN-400 ¦ C-08-C-MP-150 ¦ C-08-C-MP-130 ¦ C-08-C-MP-160 ¦ C-08-U-FN-410 ¦ C-08-C-FN-180
Phased TCO | Finishes and equipment | 9 | 2026-10-08 | 2026-12-07 | 34 | 119 | C-09-U-FN-280 ¦ C-09-U-MP-200 ¦ C-09-U-FN-290 ¦ C-09-U-FN-370 ¦ C-09-U-FN-300 ¦ C-09-U-MP-210 ¦ C-09-U-FN-310 ¦ C-09-C-FN-100 ¦ C-09-C-FN-120 ¦ C-09-C-FN-140 ¦ C-09-U-FN-330 ¦ C-09-U-FN-340 ¦ C-09-U-FN-350 ¦ C-09-U-MP-400 ¦ C-09-U-MP-440 ¦ C-09-C-FN-110 ¦ C-09-C-FN-130 ¦ C-09-C-MP-100 ¦ C-09-C-FN-150 ¦ C-09-C-FN-160 ¦ C-09-C-FN-170 ¦ C-09-C-MP-110 ¦ C-09-C-MP-120 ¦ C-09-C-MP-140 ¦ C-09-U-MP-410 ¦ C-09-U-FN-390 ¦ C-09-U-MP-420 ¦ C-09-U-MP-430 ¦ C-09-U-FN-400 ¦ C-09-C-MP-150 ¦ C-09-C-MP-130 ¦ C-09-C-MP-160 ¦ C-09-U-FN-410 ¦ C-09-C-FN-180
Phased TCO | Finishes and equipment | 10 | 2026-10-15 | 2026-12-15 | 34 | 117 | C-10-U-FN-280 ¦ C-10-U-FN-290 ¦ C-10-U-MP-200 ¦ C-10-U-FN-370 ¦ C-10-U-FN-300 ¦ C-10-U-MP-210 ¦ C-10-U-FN-310 ¦ C-10-C-FN-100 ¦ C-10-C-FN-120 ¦ C-10-C-FN-140 ¦ C-10-U-FN-330 ¦ C-10-U-FN-340 ¦ C-10-U-FN-350 ¦ C-10-U-MP-400 ¦ C-10-U-MP-440 ¦ C-10-C-FN-110 ¦ C-10-C-FN-130 ¦ C-10-C-MP-100 ¦ C-10-C-FN-150 ¦ C-10-C-FN-160 ¦ C-10-C-FN-170 ¦ C-10-C-MP-110 ¦ C-10-C-MP-140 ¦ C-10-C-MP-150 ¦ C-10-U-MP-410 ¦ C-10-C-MP-130 ¦ C-10-C-MP-160 ¦ C-10-U-FN-390 ¦ C-10-U-MP-420 ¦ C-10-U-MP-430 ¦ C-10-C-FN-180 ¦ C-10-C-MP-120 ¦ C-10-U-FN-400 ¦ C-10-U-FN-410
Phased TCO | Finishes and equipment | 11 | 2026-10-22 | 2026-12-28 | 34 | 119 | C-11-U-FN-280 ¦ C-11-U-FN-290 ¦ C-11-U-FN-370 ¦ C-11-U-FN-300 ¦ C-11-U-MP-200 ¦ C-11-U-MP-210 ¦ C-11-U-FN-310 ¦ C-11-C-FN-100 ¦ C-11-C-FN-120 ¦ C-11-C-FN-140 ¦ C-11-U-FN-330 ¦ C-11-U-FN-340 ¦ C-11-U-FN-350 ¦ C-11-U-MP-400 ¦ C-11-U-MP-440 ¦ C-11-C-FN-110 ¦ C-11-C-FN-130 ¦ C-11-C-MP-100 ¦ C-11-C-FN-150 ¦ C-11-C-FN-160 ¦ C-11-C-FN-170 ¦ C-11-C-MP-110 ¦ C-11-C-MP-120 ¦ C-11-C-MP-140 ¦ C-11-U-MP-410 ¦ C-11-U-FN-390 ¦ C-11-U-MP-420 ¦ C-11-U-MP-430 ¦ C-11-U-FN-400 ¦ C-11-C-MP-150 ¦ C-11-C-MP-130 ¦ C-11-C-MP-160 ¦ C-11-U-FN-410 ¦ C-11-C-FN-180
Phased TCO | Finishes and equipment | 12 | 2026-10-30 | 2027-01-07 | 34 | 119 | C-12-U-FN-280 ¦ C-12-U-FN-290 ¦ C-12-U-FN-370 ¦ C-12-U-FN-300 ¦ C-12-U-MP-210 ¦ C-12-U-MP-200 ¦ C-12-U-FN-310 ¦ C-12-C-FN-100 ¦ C-12-C-FN-120 ¦ C-12-C-FN-140 ¦ C-12-U-FN-330 ¦ C-12-U-FN-340 ¦ C-12-U-FN-350 ¦ C-12-U-MP-400 ¦ C-12-U-MP-440 ¦ C-12-C-FN-110 ¦ C-12-C-FN-130 ¦ C-12-C-MP-100 ¦ C-12-C-FN-150 ¦ C-12-C-FN-160 ¦ C-12-C-FN-170 ¦ C-12-C-MP-110 ¦ C-12-C-MP-120 ¦ C-12-C-MP-140 ¦ C-12-U-MP-410 ¦ C-12-U-FN-390 ¦ C-12-U-MP-420 ¦ C-12-U-MP-430 ¦ C-12-U-FN-400 ¦ C-12-C-MP-150 ¦ C-12-C-MP-130 ¦ C-12-C-MP-160 ¦ C-12-U-FN-410 ¦ C-12-C-FN-180
Phased TCO | Finishes and equipment | 14 | 2026-11-09 | 2027-01-15 | 34 | 117 | C-14-U-FN-280 ¦ C-14-U-FN-290 ¦ C-14-U-FN-370 ¦ C-14-U-FN-300 ¦ C-14-U-MP-210 ¦ C-14-U-MP-200 ¦ C-14-U-FN-310 ¦ C-14-C-FN-100 ¦ C-14-C-FN-120 ¦ C-14-C-FN-140 ¦ C-14-U-FN-330 ¦ C-14-U-FN-340 ¦ C-14-U-FN-350 ¦ C-14-U-MP-400 ¦ C-14-U-MP-440 ¦ C-14-C-FN-110 ¦ C-14-C-FN-130 ¦ C-14-C-MP-100 ¦ C-14-C-FN-150 ¦ C-14-C-FN-160 ¦ C-14-C-FN-170 ¦ C-14-C-MP-110 ¦ C-14-C-MP-140 ¦ C-14-C-MP-150 ¦ C-14-U-MP-410 ¦ C-14-C-MP-130 ¦ C-14-C-MP-160 ¦ C-14-U-FN-390 ¦ C-14-U-MP-420 ¦ C-14-U-MP-430 ¦ C-14-C-FN-180 ¦ C-14-C-MP-120 ¦ C-14-U-FN-400 ¦ C-14-U-FN-410
Phased TCO | Finishes and equipment | 15 | 2026-11-17 | 2027-01-27 | 34 | 119 | C-15-U-FN-280 ¦ C-15-U-FN-290 ¦ C-15-U-FN-370 ¦ C-15-U-FN-300 ¦ C-15-U-MP-210 ¦ C-15-U-MP-200 ¦ C-15-U-FN-310 ¦ C-15-C-FN-100 ¦ C-15-C-FN-120 ¦ C-15-C-FN-140 ¦ C-15-U-FN-330 ¦ C-15-U-FN-340 ¦ C-15-U-FN-350 ¦ C-15-U-MP-400 ¦ C-15-U-MP-440 ¦ C-15-C-FN-110 ¦ C-15-C-FN-130 ¦ C-15-C-MP-100 ¦ C-15-C-FN-150 ¦ C-15-C-FN-160 ¦ C-15-C-FN-170 ¦ C-15-C-MP-110 ¦ C-15-C-MP-120 ¦ C-15-C-MP-140 ¦ C-15-U-MP-410 ¦ C-15-U-FN-390 ¦ C-15-U-MP-420 ¦ C-15-U-MP-430 ¦ C-15-U-FN-400 ¦ C-15-C-MP-150 ¦ C-15-C-MP-130 ¦ C-15-C-MP-160 ¦ C-15-U-FN-410 ¦ C-15-C-FN-180
Phased TCO | Finishes and equipment | 16 | 2026-11-25 | 2027-02-05 | 34 | 119 | C-16-U-FN-280 ¦ C-16-U-FN-290 ¦ C-16-U-FN-370 ¦ C-16-U-FN-300 ¦ C-16-U-MP-210 ¦ C-16-U-MP-200 ¦ C-16-U-FN-310 ¦ C-16-C-FN-100 ¦ C-16-C-FN-120 ¦ C-16-C-FN-140 ¦ C-16-U-FN-330 ¦ C-16-U-FN-340 ¦ C-16-U-FN-350 ¦ C-16-U-MP-400 ¦ C-16-U-MP-440 ¦ C-16-C-FN-110 ¦ C-16-C-FN-130 ¦ C-16-C-MP-100 ¦ C-16-C-FN-150 ¦ C-16-C-FN-160 ¦ C-16-C-FN-170 ¦ C-16-C-MP-110 ¦ C-16-C-MP-120 ¦ C-16-C-MP-140 ¦ C-16-U-MP-410 ¦ C-16-U-FN-390 ¦ C-16-U-MP-420 ¦ C-16-U-MP-430 ¦ C-16-U-FN-400 ¦ C-16-C-MP-150 ¦ C-16-C-MP-130 ¦ C-16-C-MP-160 ¦ C-16-U-FN-410 ¦ C-16-C-FN-180
Phased TCO | Finishes and equipment | 17 | 2026-12-07 | 2027-02-15 | 34 | 117 | C-17-U-FN-280 ¦ C-17-U-FN-290 ¦ C-17-U-FN-370 ¦ C-17-U-FN-300 ¦ C-17-U-MP-210 ¦ C-17-U-MP-200 ¦ C-17-U-FN-310 ¦ C-17-C-FN-100 ¦ C-17-C-FN-120 ¦ C-17-C-FN-140 ¦ C-17-U-FN-330 ¦ C-17-U-FN-340 ¦ C-17-U-FN-350 ¦ C-17-U-MP-400 ¦ C-17-U-MP-440 ¦ C-17-C-FN-110 ¦ C-17-C-FN-130 ¦ C-17-C-MP-100 ¦ C-17-C-FN-150 ¦ C-17-C-FN-160 ¦ C-17-C-FN-170 ¦ C-17-C-MP-110 ¦ C-17-C-MP-140 ¦ C-17-C-MP-150 ¦ C-17-U-MP-410 ¦ C-17-C-MP-130 ¦ C-17-C-MP-160 ¦ C-17-U-FN-390 ¦ C-17-U-MP-420 ¦ C-17-U-MP-430 ¦ C-17-C-FN-180 ¦ C-17-C-MP-120 ¦ C-17-U-FN-400 ¦ C-17-U-FN-410
Phased TCO | Finishes and equipment | 18 | 2026-12-15 | 2027-02-25 | 34 | 119 | C-18-U-FN-280 ¦ C-18-U-FN-290 ¦ C-18-U-FN-370 ¦ C-18-U-FN-300 ¦ C-18-U-MP-210 ¦ C-18-U-MP-200 ¦ C-18-U-FN-310 ¦ C-18-C-FN-100 ¦ C-18-C-FN-120 ¦ C-18-C-FN-140 ¦ C-18-U-FN-330 ¦ C-18-U-FN-340 ¦ C-18-U-FN-350 ¦ C-18-U-MP-400 ¦ C-18-U-MP-440 ¦ C-18-C-FN-110 ¦ C-18-C-FN-130 ¦ C-18-C-MP-100 ¦ C-18-C-FN-150 ¦ C-18-C-FN-160 ¦ C-18-C-FN-170 ¦ C-18-C-MP-110 ¦ C-18-C-MP-120 ¦ C-18-C-MP-140 ¦ C-18-U-MP-410 ¦ C-18-U-FN-390 ¦ C-18-U-MP-420 ¦ C-18-U-MP-430 ¦ C-18-U-FN-400 ¦ C-18-C-MP-150 ¦ C-18-C-MP-130 ¦ C-18-C-MP-160 ¦ C-18-U-FN-410 ¦ C-18-C-FN-180
Phased TCO | Finishes and equipment | 19 | 2026-12-23 | 2027-03-08 | 34 | 119 | C-19-U-FN-280 ¦ C-19-U-FN-290 ¦ C-19-U-FN-370 ¦ C-19-U-FN-300 ¦ C-19-U-MP-210 ¦ C-19-U-MP-200 ¦ C-19-U-FN-310 ¦ C-19-C-FN-100 ¦ C-19-C-FN-120 ¦ C-19-C-FN-140 ¦ C-19-U-FN-330 ¦ C-19-U-FN-340 ¦ C-19-U-FN-350 ¦ C-19-U-MP-400 ¦ C-19-U-MP-440 ¦ C-19-C-FN-110 ¦ C-19-C-FN-130 ¦ C-19-C-MP-100 ¦ C-19-C-FN-150 ¦ C-19-C-FN-160 ¦ C-19-C-FN-170 ¦ C-19-C-MP-110 ¦ C-19-C-MP-120 ¦ C-19-C-MP-140 ¦ C-19-U-MP-410 ¦ C-19-U-FN-390 ¦ C-19-U-MP-420 ¦ C-19-U-MP-430 ¦ C-19-U-FN-400 ¦ C-19-C-MP-150 ¦ C-19-C-MP-130 ¦ C-19-C-MP-160 ¦ C-19-U-FN-410 ¦ C-19-C-FN-180
Phased TCO | Finishes and equipment | 20 | 2027-01-04 | 2027-03-16 | 34 | 117 | C-20-U-FN-280 ¦ C-20-U-FN-290 ¦ C-20-U-FN-370 ¦ C-20-U-FN-300 ¦ C-20-U-MP-210 ¦ C-20-U-MP-200 ¦ C-20-U-FN-310 ¦ C-20-C-FN-100 ¦ C-20-C-FN-120 ¦ C-20-C-FN-140 ¦ C-20-U-FN-330 ¦ C-20-U-FN-340 ¦ C-20-U-FN-350 ¦ C-20-U-MP-400 ¦ C-20-U-MP-440 ¦ C-20-C-FN-110 ¦ C-20-C-FN-130 ¦ C-20-C-MP-100 ¦ C-20-C-FN-150 ¦ C-20-C-FN-160 ¦ C-20-C-FN-170 ¦ C-20-C-MP-110 ¦ C-20-C-MP-140 ¦ C-20-C-MP-150 ¦ C-20-U-MP-410 ¦ C-20-C-MP-130 ¦ C-20-C-MP-160 ¦ C-20-U-FN-390 ¦ C-20-U-MP-420 ¦ C-20-U-MP-430 ¦ C-20-C-FN-180 ¦ C-20-C-MP-120 ¦ C-20-U-FN-400 ¦ C-20-U-FN-410
Phased TCO | Finishes and equipment | 21 | 2027-01-12 | 2027-03-26 | 34 | 119 | C-21-U-FN-280 ¦ C-21-U-FN-290 ¦ C-21-U-FN-370 ¦ C-21-U-FN-300 ¦ C-21-U-MP-210 ¦ C-21-U-MP-200 ¦ C-21-U-FN-310 ¦ C-21-C-FN-100 ¦ C-21-C-FN-120 ¦ C-21-C-FN-140 ¦ C-21-U-FN-330 ¦ C-21-U-FN-340 ¦ C-21-U-FN-350 ¦ C-21-U-MP-400 ¦ C-21-U-MP-440 ¦ C-21-C-FN-110 ¦ C-21-C-FN-130 ¦ C-21-C-MP-100 ¦ C-21-C-FN-150 ¦ C-21-C-FN-160 ¦ C-21-C-FN-170 ¦ C-21-C-MP-110 ¦ C-21-C-MP-120 ¦ C-21-C-MP-140 ¦ C-21-U-MP-410 ¦ C-21-U-FN-390 ¦ C-21-U-MP-420 ¦ C-21-U-MP-430 ¦ C-21-U-FN-400 ¦ C-21-C-MP-150 ¦ C-21-C-MP-130 ¦ C-21-C-MP-160 ¦ C-21-U-FN-410 ¦ C-21-C-FN-180
Phased TCO | Finishes and equipment | 22 | 2027-01-20 | 2027-04-06 | 34 | 119 | C-22-U-FN-280 ¦ C-22-U-FN-290 ¦ C-22-U-FN-370 ¦ C-22-U-FN-300 ¦ C-22-U-MP-210 ¦ C-22-U-MP-200 ¦ C-22-U-FN-310 ¦ C-22-C-FN-100 ¦ C-22-C-FN-120 ¦ C-22-C-FN-140 ¦ C-22-U-FN-330 ¦ C-22-U-FN-340 ¦ C-22-U-FN-350 ¦ C-22-U-MP-400 ¦ C-22-U-MP-440 ¦ C-22-C-FN-110 ¦ C-22-C-FN-130 ¦ C-22-C-MP-100 ¦ C-22-C-FN-150 ¦ C-22-C-FN-160 ¦ C-22-C-FN-170 ¦ C-22-C-MP-110 ¦ C-22-C-MP-120 ¦ C-22-C-MP-140 ¦ C-22-U-MP-410 ¦ C-22-U-FN-390 ¦ C-22-U-MP-420 ¦ C-22-U-MP-430 ¦ C-22-U-FN-400 ¦ C-22-C-MP-150 ¦ C-22-C-MP-130 ¦ C-22-C-MP-160 ¦ C-22-U-FN-410 ¦ C-22-C-FN-180
Phased TCO | Finishes and equipment | 23 | 2027-01-28 | 2027-04-14 | 34 | 117 | C-23-U-FN-280 ¦ C-23-U-FN-290 ¦ C-23-U-FN-370 ¦ C-23-U-FN-300 ¦ C-23-U-MP-210 ¦ C-23-U-MP-200 ¦ C-23-U-FN-310 ¦ C-23-C-FN-100 ¦ C-23-C-FN-120 ¦ C-23-C-FN-140 ¦ C-23-U-FN-330 ¦ C-23-U-FN-340 ¦ C-23-U-FN-350 ¦ C-23-U-MP-400 ¦ C-23-U-MP-440 ¦ C-23-C-FN-110 ¦ C-23-C-FN-130 ¦ C-23-C-MP-100 ¦ C-23-C-FN-150 ¦ C-23-C-FN-160 ¦ C-23-C-FN-170 ¦ C-23-C-MP-110 ¦ C-23-C-MP-140 ¦ C-23-C-MP-150 ¦ C-23-U-MP-410 ¦ C-23-C-MP-130 ¦ C-23-C-MP-160 ¦ C-23-U-FN-390 ¦ C-23-U-MP-420 ¦ C-23-U-MP-430 ¦ C-23-C-FN-180 ¦ C-23-C-MP-120 ¦ C-23-U-FN-400 ¦ C-23-U-FN-410
Phased TCO | Finishes and equipment | 24 | 2027-02-05 | 2027-04-26 | 34 | 119 | C-24-U-FN-280 ¦ C-24-U-FN-290 ¦ C-24-U-FN-370 ¦ C-24-U-FN-300 ¦ C-24-U-MP-210 ¦ C-24-U-MP-200 ¦ C-24-U-FN-310 ¦ C-24-C-FN-100 ¦ C-24-C-FN-120 ¦ C-24-C-FN-140 ¦ C-24-U-FN-330 ¦ C-24-U-FN-340 ¦ C-24-U-FN-350 ¦ C-24-U-MP-400 ¦ C-24-U-MP-440 ¦ C-24-C-FN-110 ¦ C-24-C-FN-130 ¦ C-24-C-MP-100 ¦ C-24-C-FN-150 ¦ C-24-C-FN-160 ¦ C-24-C-FN-170 ¦ C-24-C-MP-110 ¦ C-24-C-MP-120 ¦ C-24-C-MP-140 ¦ C-24-U-MP-410 ¦ C-24-U-FN-390 ¦ C-24-U-MP-420 ¦ C-24-U-MP-430 ¦ C-24-U-FN-400 ¦ C-24-C-MP-150 ¦ C-24-C-MP-130 ¦ C-24-C-MP-160 ¦ C-24-U-FN-410 ¦ C-24-C-FN-180
Phased TCO | Finishes and equipment | 25 | 2027-02-15 | 2027-05-05 | 34 | 119 | C-25-U-FN-280 ¦ C-25-U-FN-290 ¦ C-25-U-FN-370 ¦ C-25-U-FN-300 ¦ C-25-U-MP-210 ¦ C-25-U-MP-200 ¦ C-25-U-FN-310 ¦ C-25-C-FN-100 ¦ C-25-C-FN-120 ¦ C-25-C-FN-140 ¦ C-25-U-FN-330 ¦ C-25-U-FN-340 ¦ C-25-U-FN-350 ¦ C-25-U-MP-400 ¦ C-25-U-MP-440 ¦ C-25-C-FN-110 ¦ C-25-C-FN-130 ¦ C-25-C-MP-100 ¦ C-25-C-FN-150 ¦ C-25-C-FN-160 ¦ C-25-C-FN-170 ¦ C-25-C-MP-110 ¦ C-25-C-MP-120 ¦ C-25-C-MP-140 ¦ C-25-U-MP-410 ¦ C-25-U-FN-390 ¦ C-25-U-MP-420 ¦ C-25-U-MP-430 ¦ C-25-U-FN-400 ¦ C-25-C-MP-150 ¦ C-25-C-MP-130 ¦ C-25-C-MP-160 ¦ C-25-U-FN-410 ¦ C-25-C-FN-180
Phased TCO | Finishes and equipment | 26 | 2027-02-23 | 2027-05-13 | 34 | 117 | C-26-U-FN-280 ¦ C-26-U-FN-290 ¦ C-26-U-FN-370 ¦ C-26-U-FN-300 ¦ C-26-U-MP-210 ¦ C-26-U-MP-200 ¦ C-26-U-FN-310 ¦ C-26-C-FN-100 ¦ C-26-C-FN-120 ¦ C-26-C-FN-140 ¦ C-26-U-FN-330 ¦ C-26-U-FN-340 ¦ C-26-U-FN-350 ¦ C-26-U-MP-400 ¦ C-26-U-MP-440 ¦ C-26-C-FN-110 ¦ C-26-C-FN-130 ¦ C-26-C-MP-100 ¦ C-26-C-FN-150 ¦ C-26-C-FN-160 ¦ C-26-C-FN-170 ¦ C-26-C-MP-110 ¦ C-26-C-MP-140 ¦ C-26-C-MP-150 ¦ C-26-U-MP-410 ¦ C-26-C-MP-130 ¦ C-26-C-MP-160 ¦ C-26-U-FN-390 ¦ C-26-U-MP-420 ¦ C-26-U-MP-430 ¦ C-26-C-FN-180 ¦ C-26-C-MP-120 ¦ C-26-U-FN-400 ¦ C-26-U-FN-410
Phased TCO | Finishes and equipment | 27 | 2027-03-03 | 2027-05-25 | 34 | 119 | C-27-U-FN-280 ¦ C-27-U-FN-290 ¦ C-27-U-FN-370 ¦ C-27-U-FN-300 ¦ C-27-U-MP-210 ¦ C-27-U-MP-200 ¦ C-27-U-FN-310 ¦ C-27-C-FN-100 ¦ C-27-C-FN-120 ¦ C-27-C-FN-140 ¦ C-27-U-FN-330 ¦ C-27-U-FN-340 ¦ C-27-U-FN-350 ¦ C-27-U-MP-400 ¦ C-27-U-MP-440 ¦ C-27-C-FN-110 ¦ C-27-C-FN-130 ¦ C-27-C-MP-100 ¦ C-27-C-FN-150 ¦ C-27-C-FN-160 ¦ C-27-C-FN-170 ¦ C-27-C-MP-110 ¦ C-27-C-MP-120 ¦ C-27-C-MP-140 ¦ C-27-U-MP-410 ¦ C-27-U-FN-390 ¦ C-27-U-MP-420 ¦ C-27-U-MP-430 ¦ C-27-U-FN-400 ¦ C-27-C-MP-150 ¦ C-27-C-MP-130 ¦ C-27-C-MP-160 ¦ C-27-U-FN-410 ¦ C-27-C-FN-180
Phased TCO | Finishes and equipment | 28 | 2027-03-11 | 2027-06-04 | 34 | 119 | C-28-U-FN-280 ¦ C-28-U-FN-290 ¦ C-28-U-FN-370 ¦ C-28-U-FN-300 ¦ C-28-U-MP-210 ¦ C-28-U-MP-200 ¦ C-28-U-FN-310 ¦ C-28-C-FN-100 ¦ C-28-C-FN-120 ¦ C-28-C-FN-140 ¦ C-28-U-FN-330 ¦ C-28-U-FN-340 ¦ C-28-U-FN-350 ¦ C-28-U-MP-400 ¦ C-28-U-MP-440 ¦ C-28-C-FN-110 ¦ C-28-C-FN-130 ¦ C-28-C-MP-100 ¦ C-28-C-FN-150 ¦ C-28-C-FN-160 ¦ C-28-C-FN-170 ¦ C-28-C-MP-110 ¦ C-28-C-MP-120 ¦ C-28-C-MP-140 ¦ C-28-U-MP-410 ¦ C-28-U-FN-390 ¦ C-28-U-MP-420 ¦ C-28-U-MP-430 ¦ C-28-U-FN-400 ¦ C-28-C-MP-150 ¦ C-28-C-MP-130 ¦ C-28-C-MP-160 ¦ C-28-U-FN-410 ¦ C-28-C-FN-180
Phased TCO | Finishes and equipment | 29 | 2027-03-19 | 2027-06-14 | 34 | 117 | C-29-U-FN-280 ¦ C-29-U-FN-290 ¦ C-29-U-FN-370 ¦ C-29-U-FN-300 ¦ C-29-U-MP-210 ¦ C-29-U-MP-200 ¦ C-29-U-FN-310 ¦ C-29-C-FN-100 ¦ C-29-C-FN-120 ¦ C-29-C-FN-140 ¦ C-29-U-FN-330 ¦ C-29-U-FN-340 ¦ C-29-U-FN-350 ¦ C-29-U-MP-400 ¦ C-29-U-MP-440 ¦ C-29-C-FN-110 ¦ C-29-C-FN-130 ¦ C-29-C-MP-100 ¦ C-29-C-FN-150 ¦ C-29-C-FN-160 ¦ C-29-C-FN-170 ¦ C-29-C-MP-110 ¦ C-29-C-MP-140 ¦ C-29-C-MP-150 ¦ C-29-U-MP-410 ¦ C-29-C-MP-130 ¦ C-29-C-MP-160 ¦ C-29-U-FN-390 ¦ C-29-U-MP-420 ¦ C-29-U-MP-430 ¦ C-29-C-FN-180 ¦ C-29-C-MP-120 ¦ C-29-U-FN-400 ¦ C-29-U-FN-410
Phased TCO | Finishes and equipment | 30 | 2027-03-29 | 2027-06-24 | 34 | 119 | C-30-U-FN-280 ¦ C-30-U-FN-290 ¦ C-30-U-FN-370 ¦ C-30-U-FN-300 ¦ C-30-U-MP-210 ¦ C-30-U-MP-200 ¦ C-30-U-FN-310 ¦ C-30-C-FN-100 ¦ C-30-C-FN-120 ¦ C-30-C-FN-140 ¦ C-30-U-FN-330 ¦ C-30-U-FN-340 ¦ C-30-U-FN-350 ¦ C-30-U-MP-400 ¦ C-30-U-MP-440 ¦ C-30-C-FN-110 ¦ C-30-C-FN-130 ¦ C-30-C-MP-100 ¦ C-30-C-FN-150 ¦ C-30-C-FN-160 ¦ C-30-C-FN-170 ¦ C-30-C-MP-110 ¦ C-30-C-MP-120 ¦ C-30-C-MP-140 ¦ C-30-U-MP-410 ¦ C-30-U-FN-390 ¦ C-30-U-MP-420 ¦ C-30-U-MP-430 ¦ C-30-U-FN-400 ¦ C-30-C-MP-150 ¦ C-30-C-MP-130 ¦ C-30-C-MP-160 ¦ C-30-U-FN-410 ¦ C-30-C-FN-180
Phased TCO | Finishes and equipment | 31 | 2027-04-06 | 2027-07-06 | 34 | 119 | C-31-U-FN-280 ¦ C-31-U-FN-290 ¦ C-31-U-FN-370 ¦ C-31-U-FN-300 ¦ C-31-U-MP-210 ¦ C-31-U-MP-200 ¦ C-31-U-FN-310 ¦ C-31-C-FN-100 ¦ C-31-C-FN-120 ¦ C-31-C-FN-140 ¦ C-31-U-FN-330 ¦ C-31-U-FN-340 ¦ C-31-U-FN-350 ¦ C-31-U-MP-400 ¦ C-31-U-MP-440 ¦ C-31-C-FN-110 ¦ C-31-C-FN-130 ¦ C-31-C-MP-100 ¦ C-31-C-FN-150 ¦ C-31-C-FN-160 ¦ C-31-C-FN-170 ¦ C-31-C-MP-110 ¦ C-31-C-MP-120 ¦ C-31-C-MP-140 ¦ C-31-U-MP-410 ¦ C-31-U-FN-390 ¦ C-31-U-MP-420 ¦ C-31-U-MP-430 ¦ C-31-U-FN-400 ¦ C-31-C-MP-150 ¦ C-31-C-MP-130 ¦ C-31-C-MP-160 ¦ C-31-U-FN-410 ¦ C-31-C-FN-180
Phased TCO | Finishes and equipment | 32 | 2027-04-14 | 2027-07-14 | 34 | 117 | C-32-U-FN-280 ¦ C-32-U-FN-290 ¦ C-32-U-FN-370 ¦ C-32-U-FN-300 ¦ C-32-U-MP-210 ¦ C-32-U-MP-200 ¦ C-32-U-FN-310 ¦ C-32-C-FN-100 ¦ C-32-C-FN-120 ¦ C-32-C-FN-140 ¦ C-32-U-FN-330 ¦ C-32-U-FN-340 ¦ C-32-U-FN-350 ¦ C-32-U-MP-400 ¦ C-32-U-MP-440 ¦ C-32-C-FN-110 ¦ C-32-C-FN-130 ¦ C-32-C-MP-100 ¦ C-32-C-FN-150 ¦ C-32-C-FN-160 ¦ C-32-C-FN-170 ¦ C-32-C-MP-110 ¦ C-32-C-MP-140 ¦ C-32-C-MP-150 ¦ C-32-U-MP-410 ¦ C-32-C-MP-130 ¦ C-32-C-MP-160 ¦ C-32-U-FN-390 ¦ C-32-U-MP-420 ¦ C-32-U-MP-430 ¦ C-32-C-FN-180 ¦ C-32-C-MP-120 ¦ C-32-U-FN-400 ¦ C-32-U-FN-410
Phased TCO | Finishes and equipment | 33 | 2027-04-22 | 2027-07-26 | 34 | 119 | C-33-U-FN-280 ¦ C-33-U-FN-290 ¦ C-33-U-FN-370 ¦ C-33-U-FN-300 ¦ C-33-U-MP-210 ¦ C-33-U-MP-200 ¦ C-33-U-FN-310 ¦ C-33-C-FN-100 ¦ C-33-C-FN-120 ¦ C-33-C-FN-140 ¦ C-33-U-FN-330 ¦ C-33-U-FN-340 ¦ C-33-U-FN-350 ¦ C-33-U-MP-400 ¦ C-33-U-MP-440 ¦ C-33-C-FN-110 ¦ C-33-C-FN-130 ¦ C-33-C-MP-100 ¦ C-33-C-FN-150 ¦ C-33-C-FN-160 ¦ C-33-C-FN-170 ¦ C-33-C-MP-110 ¦ C-33-C-MP-120 ¦ C-33-C-MP-140 ¦ C-33-U-MP-410 ¦ C-33-U-FN-390 ¦ C-33-U-MP-420 ¦ C-33-U-MP-430 ¦ C-33-U-FN-400 ¦ C-33-C-MP-150 ¦ C-33-C-MP-130 ¦ C-33-C-MP-160 ¦ C-33-U-FN-410 ¦ C-33-C-FN-180
Phased TCO | Finishes and equipment | 34 | 2027-04-30 | 2027-08-04 | 34 | 119 | C-34-U-FN-280 ¦ C-34-U-FN-290 ¦ C-34-U-FN-370 ¦ C-34-U-FN-300 ¦ C-34-U-MP-210 ¦ C-34-U-MP-200 ¦ C-34-U-FN-310 ¦ C-34-C-FN-100 ¦ C-34-C-FN-120 ¦ C-34-C-FN-140 ¦ C-34-U-FN-330 ¦ C-34-U-FN-340 ¦ C-34-U-FN-350 ¦ C-34-U-MP-400 ¦ C-34-U-MP-440 ¦ C-34-C-FN-110 ¦ C-34-C-FN-130 ¦ C-34-C-MP-100 ¦ C-34-C-FN-150 ¦ C-34-C-FN-160 ¦ C-34-C-FN-170 ¦ C-34-C-MP-110 ¦ C-34-C-MP-120 ¦ C-34-C-MP-140 ¦ C-34-U-MP-410 ¦ C-34-U-FN-390 ¦ C-34-U-MP-420 ¦ C-34-U-MP-430 ¦ C-34-U-FN-400 ¦ C-34-C-MP-150 ¦ C-34-C-MP-130 ¦ C-34-C-MP-160 ¦ C-34-U-FN-410 ¦ C-34-C-FN-180
Phased TCO | Finishes and equipment | 35 | 2027-05-10 | 2027-08-13 | 34 | 119 | C-35-U-FN-280 ¦ C-35-U-FN-290 ¦ C-35-U-FN-370 ¦ C-35-U-FN-300 ¦ C-35-U-MP-210 ¦ C-35-U-MP-200 ¦ C-35-U-FN-310 ¦ C-35-C-FN-100 ¦ C-35-C-FN-120 ¦ C-35-C-FN-140 ¦ C-35-U-FN-330 ¦ C-35-U-FN-340 ¦ C-35-U-FN-350 ¦ C-35-U-MP-400 ¦ C-35-U-MP-440 ¦ C-35-C-FN-110 ¦ C-35-C-FN-130 ¦ C-35-C-MP-100 ¦ C-35-C-FN-150 ¦ C-35-C-FN-160 ¦ C-35-C-FN-170 ¦ C-35-C-MP-110 ¦ C-35-C-MP-120 ¦ C-35-C-MP-140 ¦ C-35-U-MP-410 ¦ C-35-U-FN-390 ¦ C-35-U-MP-420 ¦ C-35-U-MP-430 ¦ C-35-U-FN-400 ¦ C-35-C-MP-150 ¦ C-35-C-MP-130 ¦ C-35-C-MP-160 ¦ C-35-U-FN-410 ¦ C-35-C-FN-180
Phased TCO | Finishes and equipment | 36 | 2027-05-13 | 2027-07-09 | 15 | 39 | C-36-IN-MP-400 ¦ C-36-IN-MP-200 ¦ C-36-IN-FN-280 ¦ C-36-IN-FN-290 ¦ C-36-IN-FN-310 ¦ C-36-IN-MP-410 ¦ C-36-IN-FN-330 ¦ C-36-IN-FN-340 ¦ C-36-IN-MP-420 ¦ C-36-IN-MP-430 ¦ C-36-IN-MP-440 ¦ C-36-IN-MP-450 ¦ C-36-IN-MP-460 ¦ C-36-IN-MP-470 ¦ C-36-IN-FN-400
Phased TCO | Inspection and contractor punch | 1 | 2027-07-27 | 2027-09-07 | 3 | 30 | C-01-U-PC-900 ¦ C-01-U-PC-910 ¦ C-01-U-PC-920
Phased TCO | Inspection and contractor punch | 2 | 2027-06-28 | 2027-07-26 | 3 | 20 | C-02-U-PC-900 ¦ C-02-U-PC-910 ¦ C-02-U-PC-920
Phased TCO | Inspection and contractor punch | 3 | 2027-07-02 | 2027-07-30 | 3 | 20 | C-03-U-PC-900 ¦ C-03-U-PC-910 ¦ C-03-U-PC-920
Phased TCO | Inspection and contractor punch | 4 | 2027-07-09 | 2027-08-05 | 3 | 20 | C-04-U-PC-900 ¦ C-04-U-PC-910 ¦ C-04-U-PC-920
Phased TCO | Inspection and contractor punch | 5 | 2027-07-15 | 2027-08-11 | 3 | 20 | C-05-U-PC-900 ¦ C-05-U-PC-910 ¦ C-05-U-PC-920
Phased TCO | Inspection and contractor punch | 6 | 2027-07-21 | 2027-08-17 | 3 | 20 | C-06-U-PC-900 ¦ C-06-U-PC-910 ¦ C-06-U-PC-920
Phased TCO | Inspection and contractor punch | 7 | 2027-07-26 | 2027-08-24 | 3 | 22 | C-07-U-PC-900 ¦ C-07-U-PC-910 ¦ C-07-U-PC-920
Phased TCO | Inspection and contractor punch | 8 | 2027-07-30 | 2027-08-30 | 3 | 22 | C-08-U-PC-900 ¦ C-08-U-PC-910 ¦ C-08-U-PC-920
Phased TCO | Inspection and contractor punch | 9 | 2027-08-05 | 2027-09-03 | 3 | 22 | C-09-U-PC-900 ¦ C-09-U-PC-910 ¦ C-09-U-PC-920
Phased TCO | Inspection and contractor punch | 10 | 2027-08-11 | 2027-09-10 | 3 | 22 | C-10-U-PC-900 ¦ C-10-U-PC-910 ¦ C-10-U-PC-920
Phased TCO | Inspection and contractor punch | 11 | 2027-08-17 | 2027-09-16 | 3 | 22 | C-11-U-PC-900 ¦ C-11-U-PC-910 ¦ C-11-U-PC-920
Phased TCO | Inspection and contractor punch | 12 | 2027-08-23 | 2027-09-22 | 3 | 22 | C-12-U-PC-900 ¦ C-12-U-PC-910 ¦ C-12-U-PC-920
Phased TCO | Inspection and contractor punch | 14 | 2027-08-27 | 2027-09-28 | 3 | 22 | C-14-U-PC-900 ¦ C-14-U-PC-910 ¦ C-14-U-PC-920
Phased TCO | Inspection and contractor punch | 15 | 2027-09-02 | 2027-10-04 | 3 | 22 | C-15-U-PC-900 ¦ C-15-U-PC-910 ¦ C-15-U-PC-920
Phased TCO | Inspection and contractor punch | 16 | 2027-09-09 | 2027-10-08 | 3 | 22 | C-16-U-PC-900 ¦ C-16-U-PC-910 ¦ C-16-U-PC-920
Phased TCO | Inspection and contractor punch | 17 | 2027-09-15 | 2027-10-14 | 3 | 22 | C-17-U-PC-900 ¦ C-17-U-PC-910 ¦ C-17-U-PC-920
Phased TCO | Inspection and contractor punch | 18 | 2027-09-21 | 2027-10-20 | 3 | 22 | C-18-U-PC-900 ¦ C-18-U-PC-910 ¦ C-18-U-PC-920
Phased TCO | Inspection and contractor punch | 19 | 2027-09-27 | 2027-10-26 | 3 | 22 | C-19-U-PC-900 ¦ C-19-U-PC-910 ¦ C-19-U-PC-920
Phased TCO | Inspection and contractor punch | 20 | 2027-10-01 | 2027-11-01 | 3 | 22 | C-20-U-PC-900 ¦ C-20-U-PC-910 ¦ C-20-U-PC-920
Phased TCO | Inspection and contractor punch | 21 | 2027-10-07 | 2027-11-05 | 3 | 22 | C-21-U-PC-900 ¦ C-21-U-PC-910 ¦ C-21-U-PC-920
Phased TCO | Inspection and contractor punch | 22 | 2027-10-13 | 2027-11-11 | 3 | 22 | C-22-U-PC-900 ¦ C-22-U-PC-910 ¦ C-22-U-PC-920
Phased TCO | Inspection and contractor punch | 23 | 2027-10-19 | 2027-11-17 | 3 | 22 | C-23-U-PC-900 ¦ C-23-U-PC-910 ¦ C-23-U-PC-920
Phased TCO | Inspection and contractor punch | 24 | 2027-10-25 | 2027-11-23 | 3 | 22 | C-24-U-PC-900 ¦ C-24-U-PC-910 ¦ C-24-U-PC-920
Phased TCO | Inspection and contractor punch | 25 | 2027-10-29 | 2027-12-01 | 3 | 22 | C-25-U-PC-900 ¦ C-25-U-PC-910 ¦ C-25-U-PC-920
Phased TCO | Inspection and contractor punch | 26 | 2027-11-04 | 2027-12-07 | 3 | 22 | C-26-U-PC-900 ¦ C-26-U-PC-910 ¦ C-26-U-PC-920
Phased TCO | Inspection and contractor punch | 27 | 2027-11-10 | 2027-12-13 | 3 | 22 | C-27-U-PC-900 ¦ C-27-U-PC-910 ¦ C-27-U-PC-920
Phased TCO | Inspection and contractor punch | 28 | 2027-11-16 | 2027-12-17 | 3 | 22 | C-28-U-PC-900 ¦ C-28-U-PC-910 ¦ C-28-U-PC-920
Phased TCO | Inspection and contractor punch | 29 | 2027-11-22 | 2027-12-23 | 3 | 22 | C-29-U-PC-900 ¦ C-29-U-PC-910 ¦ C-29-U-PC-920
Phased TCO | Inspection and contractor punch | 30 | 2027-11-30 | 2027-12-30 | 3 | 22 | C-30-U-PC-900 ¦ C-30-U-PC-910 ¦ C-30-U-PC-920
Phased TCO | Inspection and contractor punch | 31 | 2027-12-06 | 2028-01-06 | 3 | 22 | C-31-U-PC-900 ¦ C-31-U-PC-910 ¦ C-31-U-PC-920
Phased TCO | Inspection and contractor punch | 32 | 2027-12-10 | 2028-01-12 | 3 | 22 | C-32-U-PC-900 ¦ C-32-U-PC-910 ¦ C-32-U-PC-920
Phased TCO | Inspection and contractor punch | 33 | 2027-12-16 | 2028-01-18 | 3 | 22 | C-33-U-PC-900 ¦ C-33-U-PC-910 ¦ C-33-U-PC-920
Phased TCO | Inspection and contractor punch | 34 | 2027-12-22 | 2028-01-24 | 3 | 22 | C-34-U-PC-900 ¦ C-34-U-PC-910 ¦ C-34-U-PC-920
Phased TCO | Inspection and contractor punch | 35 | 2027-12-29 | 2028-01-28 | 3 | 22 | C-35-U-PC-900 ¦ C-35-U-PC-910 ¦ C-35-U-PC-920
Phased TCO | Inspection and contractor punch | 36 | 2027-06-25 | 2027-08-06 | 3 | 25 | C-36-IN-PC-900 ¦ C-36-IN-PC-910 ¦ C-36-IN-PC-920
Phased TCO | Final clean and Owner punch | 1 | 2027-07-27 | 2027-09-28 | 4 | 13 | C-01-C-FN-190 ¦ C-01-U-PC-930 ¦ C-01-U-PC-940 ¦ C-01-U-PC-950
Phased TCO | Final clean and Owner punch | 2 | 2027-07-27 | 2027-08-06 | 3 | 9 | C-02-U-PC-930 ¦ C-02-C-FN-190 ¦ C-02-U-PC-950
Phased TCO | Final clean and Owner punch | 3 | 2027-08-02 | 2027-08-12 | 3 | 9 | C-03-U-PC-930 ¦ C-03-C-FN-190 ¦ C-03-U-PC-950
Phased TCO | Final clean and Owner punch | 4 | 2027-08-06 | 2027-08-18 | 3 | 9 | C-04-U-PC-930 ¦ C-04-C-FN-190 ¦ C-04-U-PC-950
Phased TCO | Final clean and Owner punch | 5 | 2027-08-12 | 2027-08-24 | 3 | 9 | C-05-U-PC-930 ¦ C-05-C-FN-190 ¦ C-05-U-PC-950
Phased TCO | Final clean and Owner punch | 6 | 2027-08-18 | 2027-08-30 | 3 | 9 | C-06-U-PC-930 ¦ C-06-C-FN-190 ¦ C-06-U-PC-950
Phased TCO | Final clean and Owner punch | 7 | 2027-08-25 | 2027-09-07 | 3 | 9 | C-07-U-PC-930 ¦ C-07-C-FN-190 ¦ C-07-U-PC-950
Phased TCO | Final clean and Owner punch | 8 | 2027-08-31 | 2027-09-14 | 3 | 9 | C-08-U-PC-930 ¦ C-08-C-FN-190 ¦ C-08-U-PC-950
Phased TCO | Final clean and Owner punch | 9 | 2027-09-07 | 2027-09-21 | 3 | 9 | C-09-U-PC-930 ¦ C-09-C-FN-190 ¦ C-09-U-PC-950
Phased TCO | Final clean and Owner punch | 10 | 2027-09-13 | 2027-09-28 | 3 | 9 | C-10-U-PC-930 ¦ C-10-C-FN-190 ¦ C-10-U-PC-950
Phased TCO | Final clean and Owner punch | 11 | 2027-09-17 | 2027-10-05 | 3 | 9 | C-11-U-PC-930 ¦ C-11-C-FN-190 ¦ C-11-U-PC-950
Phased TCO | Final clean and Owner punch | 12 | 2027-09-23 | 2027-10-12 | 3 | 9 | C-12-U-PC-930 ¦ C-12-C-FN-190 ¦ C-12-U-PC-950
Phased TCO | Final clean and Owner punch | 14 | 2027-09-29 | 2027-10-19 | 3 | 9 | C-14-U-PC-930 ¦ C-14-C-FN-190 ¦ C-14-U-PC-950
Phased TCO | Final clean and Owner punch | 15 | 2027-10-05 | 2027-10-26 | 3 | 9 | C-15-U-PC-930 ¦ C-15-C-FN-190 ¦ C-15-U-PC-950
Phased TCO | Final clean and Owner punch | 16 | 2027-10-11 | 2027-11-02 | 3 | 9 | C-16-U-PC-930 ¦ C-16-C-FN-190 ¦ C-16-U-PC-950
Phased TCO | Final clean and Owner punch | 17 | 2027-10-15 | 2027-11-09 | 3 | 9 | C-17-U-PC-930 ¦ C-17-C-FN-190 ¦ C-17-U-PC-950
Phased TCO | Final clean and Owner punch | 18 | 2027-10-21 | 2027-11-16 | 3 | 9 | C-18-U-PC-930 ¦ C-18-C-FN-190 ¦ C-18-U-PC-950
Phased TCO | Final clean and Owner punch | 19 | 2027-10-27 | 2027-11-23 | 3 | 9 | C-19-U-PC-930 ¦ C-19-C-FN-190 ¦ C-19-U-PC-950
Phased TCO | Final clean and Owner punch | 20 | 2027-11-02 | 2027-12-02 | 3 | 9 | C-20-U-PC-930 ¦ C-20-C-FN-190 ¦ C-20-U-PC-950
Phased TCO | Final clean and Owner punch | 21 | 2027-11-08 | 2027-12-09 | 3 | 9 | C-21-U-PC-930 ¦ C-21-C-FN-190 ¦ C-21-U-PC-950
Phased TCO | Final clean and Owner punch | 22 | 2027-11-12 | 2027-12-16 | 3 | 9 | C-22-U-PC-930 ¦ C-22-C-FN-190 ¦ C-22-U-PC-950
Phased TCO | Final clean and Owner punch | 23 | 2027-11-18 | 2027-12-23 | 3 | 9 | C-23-U-PC-930 ¦ C-23-C-FN-190 ¦ C-23-U-PC-950
Phased TCO | Final clean and Owner punch | 24 | 2027-11-24 | 2028-01-03 | 3 | 9 | C-24-U-PC-930 ¦ C-24-C-FN-190 ¦ C-24-U-PC-950
Phased TCO | Final clean and Owner punch | 25 | 2027-12-02 | 2028-01-10 | 3 | 9 | C-25-U-PC-930 ¦ C-25-C-FN-190 ¦ C-25-U-PC-950
Phased TCO | Final clean and Owner punch | 26 | 2027-12-08 | 2028-01-17 | 3 | 9 | C-26-U-PC-930 ¦ C-26-C-FN-190 ¦ C-26-U-PC-950
Phased TCO | Final clean and Owner punch | 27 | 2027-12-14 | 2028-01-24 | 3 | 9 | C-27-U-PC-930 ¦ C-27-C-FN-190 ¦ C-27-U-PC-950
Phased TCO | Final clean and Owner punch | 28 | 2027-12-20 | 2028-01-31 | 3 | 9 | C-28-U-PC-930 ¦ C-28-C-FN-190 ¦ C-28-U-PC-950
Phased TCO | Final clean and Owner punch | 29 | 2027-12-27 | 2028-02-07 | 3 | 9 | C-29-U-PC-930 ¦ C-29-C-FN-190 ¦ C-29-U-PC-950
Phased TCO | Final clean and Owner punch | 30 | 2028-01-03 | 2028-02-14 | 3 | 9 | C-30-U-PC-930 ¦ C-30-C-FN-190 ¦ C-30-U-PC-950
Phased TCO | Final clean and Owner punch | 31 | 2028-01-07 | 2028-02-21 | 3 | 9 | C-31-U-PC-930 ¦ C-31-C-FN-190 ¦ C-31-U-PC-950
Phased TCO | Final clean and Owner punch | 32 | 2028-01-13 | 2028-02-28 | 3 | 9 | C-32-U-PC-930 ¦ C-32-C-FN-190 ¦ C-32-U-PC-950
Phased TCO | Final clean and Owner punch | 33 | 2028-01-19 | 2028-03-06 | 3 | 9 | C-33-U-PC-930 ¦ C-33-C-FN-190 ¦ C-33-U-PC-950
Phased TCO | Final clean and Owner punch | 34 | 2028-01-25 | 2028-03-13 | 3 | 9 | C-34-U-PC-930 ¦ C-34-C-FN-190 ¦ C-34-U-PC-950
Phased TCO | Final clean and Owner punch | 35 | 2028-01-31 | 2028-03-20 | 3 | 9 | C-35-U-PC-930 ¦ C-35-C-FN-190 ¦ C-35-U-PC-950
Phased TCO | Final clean and Owner punch | 36 | 2027-08-09 | 2027-08-24 | 3 | 12 | C-36-IN-PC-930 ¦ C-36-IN-PC-940 ¦ C-36-IN-PC-950
Formulas:
start = MINIFS(Activities!$K2:K6880,Activities!$A2:A6880,[schedule],Activities!$E2:E6880,[band],Activities!$F2:F6880,[level])
finish = MAXIFS(Activities!$L2:L6880,Activities!$A2:A6880,[schedule],Activities!$E2:E6880,[band],Activities!$F2:F6880,[level])

## WBS crosswalk
WBS area | WBS group (per floor, level removed) | Band | Activity ID pattern (after C-<level>-) | Baseline | Phased TCO | Note
Building Structure | Structure | Structure | MP-120, ST-100–150 | 198 | 198
Building Structure | Structure at High Roof Lvl | Structure | MP-120, ST-100–190 | 5 | 5
Building Structure | Structure at Lower | Structure | MP-120, ST-100–190 | 9 | 9
Building Structure | Structure at Roof Lvl | Structure | MP-120, ST-100–150 | 6 | 6
Building Structure | Exterior & Interior Masonry | Envelope | ST-400 | 35 | 35
Exterior Envelope | Exterior Glazing | Envelope | EX-100 | 34 | 34
Interior MEPs & Finishes | MEP Risers | Framing and MEP rough-in | U-MP-100–130, UC-MP-100–130 | 0 | 132 | Phased TCO only: new WBS sub-group for risers, split out of MEP Rough.
Interior MEPs & Finishes | MEP Risers at Indoor | Framing and MEP rough-in | IN-MP-100–130 | 0 | 4
Interior MEPs & Finishes | MEP Rough | Framing and MEP rough-in | UC-MP-140–190 | 6 | 6
Interior MEPs & Finishes | MEP Rough at Indoor | Framing and MEP rough-in | IN-MP-100–180 | 9 | 5
Interior MEPs & Finishes | MEP Rough at Units & Common Areas | Framing and MEP rough-in | UC-MP-100–190 | 10 | 6
Interior MEPs & Finishes | MEP Rough at Units & Corridors | Framing and MEP rough-in | U-MP-100–190 | 320 | 192
Interior MEPs & Finishes | Wall Layout & Framing | Framing and MEP rough-in | UC-FN-100–130 | 3 | 2
Interior MEPs & Finishes | Wall Layout & Framing at Indoor | Framing and MEP rough-in | IN-FN-100–130 | 4 | 3
Interior MEPs & Finishes | Wall Layout & Framing at Units & Common Areas | Framing and MEP rough-in | UC-FN-100–130 | 4 | 3
Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors | Framing and MEP rough-in | U-FN-100–130 | 128 | 93
Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors at 8t27th h Lvl | Framing and MEP rough-in | U-FN-100–120 | 0 | 3
Interior MEPs & Finishes | Interior Finishes | Drywall and prime paint | UC-FN-200–270 | 5 | 5
Interior MEPs & Finishes | Interior Finishes at Indoor | Drywall and prime paint | IN-FN-200–270 | 8 | 7
Interior MEPs & Finishes | Interior Finishes at Units | Drywall and prime paint | U-FN-200–270 | 256 | 224 | Same WBS group split in two bands: U-FN-200 to 279 go to drywall, the rest to finishes.
Interior MEPs & Finishes | Interior Finishes at Units & Common Areas | Drywall and prime paint | UC-FN-200–270 | 8 | 7
Interior MEPs & Finishes | Wall Layout & Framing at Indoor | Drywall and prime paint | IN-FN-220 | 0 | 1
Interior MEPs & Finishes | Wall Layout & Framing at Units & Common Areas | Drywall and prime paint | UC-FN-220 | 0 | 1
Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors | Drywall and prime paint | U-FN-220 | 0 | 31 | Phased TCO only: the scheduler moved "Frame GWB Drop Ceilings/Soffits" (U-FN-220) into this WBS group; the band rule still treats it as drywall.
Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors at 8t27th h Lvl | Drywall and prime paint | U-FN-220 | 0 | 1
Interior MEPs & Finishes | Interior Finishes | Finishes and equipment | UC-FN-310–400 | 5 | 5
Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor | Finishes and equipment | C-FN-100–180 | 297 | 297
Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridors | Finishes and equipment | C-FN-100–180 | 8 | 8
Interior MEPs & Finishes | Interior Finishes at Indoor | Finishes and equipment | IN-FN-280–400 | 7 | 6
Interior MEPs & Finishes | Interior Finishes at Units | Finishes and equipment | U-FN-280–410 | 354 | 350 | See row above.
Interior MEPs & Finishes | Interior Finishes at Units & Common Areas | Finishes and equipment | UC-FN-280–450 | 13 | 13
Interior MEPs & Finishes | MEP Eqp & Trim | Finishes and equipment | UC-MP-200–440 | 6 | 6
Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor | Finishes and equipment | C-MP-100–160 | 231 | 231
Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridors | Finishes and equipment | C-MP-120–160 | 5 | 5
Interior MEPs & Finishes | MEP Eqp & Trim at Indoor | Finishes and equipment | IN-MP-400–470 | 8 | 8
Interior MEPs & Finishes | MEP Eqp at Units | Finishes and equipment | U-MP-200–210 | 64 | 62
Interior MEPs & Finishes | MEP Eqp at Units & Common Areas | Finishes and equipment | UC-MP-200–210 | 2 | 2
Interior MEPs & Finishes | MEP Eqp at Units t | Finishes and equipment | U-MP-200–210 | 0 | 2
Interior MEPs & Finishes | MEP Rough at Indoor | Finishes and equipment | IN-MP-200 | 1 | 1
Interior MEPs & Finishes | MEP Trim at Units | Finishes and equipment | U-MP-400–440 | 160 | 160
Interior MEPs & Finishes | MEP Trim at Units & Common Areas | Finishes and equipment | UC-MP-400–440 | 5 | 5
Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery | Inspection and contractor punch | U-PC-900–920 | 102 | 102 | Same WBS group split in two bands: PC-900 to 929 here, final cleanup and Owner punch in the next band.
Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery at Indoor | Inspection and contractor punch | IN-PC-900–920 | 3 | 3
Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor | Final clean and Owner punch | C-FN-190 | 33 | 33 | Corridor final cleanup (C-FN-190) goes with the final clean band.
Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridors | Final clean and Owner punch | C-FN-190 | 1 | 1
Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery | Final clean and Owner punch | U-PC-930–950 | 69 | 69 | See row above.
Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery at Indoor | Final clean and Owner punch | IN-PC-930–950 | 3 | 3
Building Structure | FPL Vault SOG - Early Work | (not in a band) | MP-300–340, ST-310–330 | 4 | 8
Building Structure | Foundation Work | (not in a band) | ST-100–600, WL-100 | 13 | 13
Building Structure | Piling Work | (not in a band) | PL-100–300 | 3 | 3
Building Structure | Shoring Removals & Slab Preparation | (not in a band) | ST-300 | 35 | 35
Building Structure | Structure | (not in a band) | ST-200 | 1 | 1
Building Structure | Structure at Lower | (not in a band) | MP-160, ST-200–210 | 3 | 3
Building Structure | Structure at Roof Lvl | (not in a band) | ST-200 | 1 | 1
Building Structure | U/G MEPs & SOG | (not in a band) | MP-100–130, ST-200–210 | 5 | 5
Exterior Envelope | Exterior Balconies | (not in a band) | EX-200–230 | 128 | 0 | Left out on purpose: balconies follow their own sequence.
Exterior Envelope | Exterior Balconies & Elevations (Drops) | (not in a band) | EX-210–230 | 0 | 6
Exterior Envelope | Exterior Balconies & Elevations (Drops) at 15th to | (not in a band) | EX-210–230 | 0 | 12
Exterior Envelope | Exterior Balconies & Elevations (Drops) at 21st to | (not in a band) | EX-210–230 | 0 | 12
Exterior Envelope | Exterior Balconies & Elevations (Drops) at 27th to | (not in a band) | EX-210–230 | 0 | 12
Exterior Envelope | Exterior Balconies & Elevations (Drops) at 3rd to | (not in a band) | EX-210x, EX-230x | 0 | 10
Exterior Envelope | Exterior Balconies & Elevations (Drops) at 8th to | (not in a band) | EX-210–230 | 0 | 12
Exterior Envelope | Finishes & Flooring at Roof Deck | (not in a band) | RD-300–380 | 9 | 9
Exterior Envelope | Jacuzzi | (not in a band) | JC-400–430 | 4 | 4
Exterior Envelope | Jacuzzi Startup | (not in a band) | JC-900–920 | 3 | 3
Exterior Envelope | MEP Rough at Outdoors at th Lvl | (not in a band) | RD-100–110 | 2 | 2
Exterior Envelope | MEP Work at Boiler Rm #3702 at Roof Lvl | (not in a band) | MP-600–640 | 5 | 5
Exterior Envelope | MEP Work at East Mech Eqp Area at Roof Lvl | (not in a band) | MP-100–280 | 8 | 8
Exterior Envelope | MEP Work at Mech Eqp Rm #3611 | (not in a band) | MP-500–560 | 7 | 7
Exterior Envelope | MEP Work at Pool Deck | (not in a band) | PD-800–810 | 2 | 2
Exterior Envelope | MEP Work at Upper Roof Lvl | (not in a band) | MP-100–170 | 7 | 7
Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl | (not in a band) | MP-300–410 | 12 | 12
Exterior Envelope | Planters at Pool Deck | (not in a band) | PD-300–390 | 10 | 10
Exterior Envelope | Planters at Roof Deck | (not in a band) | RD-400–490 | 10 | 10
Exterior Envelope | Pool Deck Finishes | (not in a band) | PD-100–190 | 10 | 10
Exterior Envelope | Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602 | (not in a band) | PL-200–270 | 8 | 8
Exterior Envelope | Roofing & Planter Walls at Roof Deck | (not in a band) | RD-200–260 | 6 | 6
Exterior Envelope | Roofing at North Side at (CL 1-2/D-E) | (not in a band) | RF-100–130 | 4 | 4
Exterior Envelope | Roofing at North Side at (CL 2-5/D-E) | (not in a band) | RF-100–130 | 4 | 4
Exterior Envelope | Roofing at North Side at (CL 7-8/F-G) | (not in a band) | RF-210–230 | 3 | 3
Exterior Envelope | Roofing at Pool Deck | (not in a band) | RF-200–240 | 5 | 5
Exterior Envelope | Roofing at Roof Lvl | (not in a band) | RF-200–230 | 4 | 4
Exterior Envelope | Roofing at Upper Roof Lvl | (not in a band) | RF-200–230 | 4 | 4
Exterior Envelope | Roofing at West Side at (CL 7-8/A-B) | (not in a band) | RF-200–230 | 4 | 4
Exterior Envelope | Swim Spa Pool Work | (not in a band) | PL-100–150 | 5 | 5
Exterior Envelope | Swim Spa Startup & Certification | (not in a band) | PL-700–730 | 4 | 4
Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings | (not in a band) | ES-100–300 | 21 | 21
Interior MEPs & Finishes | Domestic Water Rm #121 | (not in a band) | MP-MP-400–470 | 8 | 8
Interior MEPs & Finishes | FPL Vault #118 | (not in a band) | MP-MP-100–130 | 4 | 4
Interior MEPs & Finishes | Fire Command #112 | (not in a band) | MP-MP-200–280 | 9 | 9
Interior MEPs & Finishes | Fire Pump Rm #116 | (not in a band) | MP-MP-300–370 | 8 | 8
Interior MEPs & Finishes | Generator Room #234 | (not in a band) | MP-MP-200–250 | 6 | 6
Interior MEPs & Finishes | Interior Finishes at Elev Lobby | (not in a band) | LB-FN-100–190 | 10 | 10
Interior MEPs & Finishes | Interior Finishes at Parking | (not in a band) | PG-FN-110–190 | 45 | 45
Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off | (not in a band) | PG-EV-100, PG-FN-110–250 | 16 | 16
Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & MEP Rooms | (not in a band) | LB-MP-200–260 | 7 | 7
Interior MEPs & Finishes | MEP Eqp & Trim at Parking | (not in a band) | PG-MP-190–250 | 27 | 26
Interior MEPs & Finishes | MEP Eqp & Trim at Parking & Drop-Offat | (not in a band) | PG-MP-200–260 | 7 | 7
Interior MEPs & Finishes | MEP Rough at Parking | (not in a band) | PG-MP-100–150 | 30 | 30
Interior MEPs & Finishes | Main Electrical & MDF Room #235 | (not in a band) | MP-MP-100–110 | 2 | 2
Interior MEPs & Finishes | Trash Rms #115 & #122 | (not in a band) | MP-MP-500–540 | 5 | 5
Interior MEPs & Finishes | Work by Others Future Space (Work by Others) - Place Holders | (not in a band) | KT-100, LB-100 | 2 | 0
Interior MEPs & Finishes | Work in Lobby Restaurant- Place Holders | (not in a band) | KT-100, LB-100 | 0 | 2

## Activities
schedule | activity_id | activity_name | in_band | band | level | excluded_reason | wbs_path | activity_type | status | start | finish | original_duration_d | total_float_d | wbs_area | wbs_group
Baseline | C-02-ST-100 | Form Prestressed Elevated Slab @ L2 | yes | Structure | 2 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 2nd Lvl | TT_Task | TK_NotStart | 2026-03-24 | 2026-03-26 | 3 | 0 | Building Structure | Structure
Baseline | C-02-ST-110 | Rebar & PT Tendons for Elevated Slab @ L2 | yes | Structure | 2 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 2nd Lvl | TT_Task | TK_NotStart | 2026-03-26 | 2026-03-30 | 3 | 0 | Building Structure | Structure
Baseline | C-02-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L2 | yes | Structure | 2 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 2nd Lvl | TT_Task | TK_NotStart | 2026-03-27 | 2026-03-27 | 1 | 1 | Building Structure | Structure
Baseline | C-02-ST-130 | Pour Elevated Slab @ L2 | yes | Structure | 2 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 2nd Lvl | TT_Task | TK_NotStart | 2026-03-31 | 2026-03-31 | 1 | 0 | Building Structure | Structure
Baseline | C-02-ST-140 | F/R/P Columns & Shear Walls @ L2 | yes | Structure | 2 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 2nd Lvl | TT_Task | TK_NotStart | 2026-04-01 | 2026-04-03 | 3 | 0 | Building Structure | Structure
Baseline | C-02-ST-150 | Stress PT @ L2 | yes | Structure | 2 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 2nd Lvl | TT_Task | TK_NotStart | 2026-04-02 | 2026-04-02 | 1 | 6 | Building Structure | Structure
Baseline | C-03-ST-100 | Form Prestressed Elevated Slab @ L3 | yes | Structure | 3 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 3rd Lvl | TT_Task | TK_NotStart | 2026-04-06 | 2026-04-08 | 3 | 0 | Building Structure | Structure
Baseline | C-03-ST-110 | Rebar & PT Tendons for Elevated Slab @ L3 | yes | Structure | 3 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 3rd Lvl | TT_Task | TK_NotStart | 2026-04-08 | 2026-04-10 | 3 | 0 | Building Structure | Structure
Baseline | C-03-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L3 | yes | Structure | 3 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 3rd Lvl | TT_Task | TK_NotStart | 2026-04-09 | 2026-04-09 | 1 | 1 | Building Structure | Structure
Baseline | C-03-ST-130 | Pour Elevated Slab @ L3 | yes | Structure | 3 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 3rd Lvl | TT_Task | TK_NotStart | 2026-04-13 | 2026-04-13 | 1 | 0 | Building Structure | Structure
Baseline | C-03-ST-140 | F/R/P Columns & Shear Walls @ L3 | yes | Structure | 3 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 3rd Lvl | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-16 | 3 | 0 | Building Structure | Structure
Baseline | C-03-ST-150 | Stress PT @ L3 | yes | Structure | 3 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 3rd Lvl | TT_Task | TK_NotStart | 2026-04-15 | 2026-04-15 | 1 | 6 | Building Structure | Structure
Baseline | C-04-ST-100 | Form Prestressed Elevated Slab @ L4 | yes | Structure | 4 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 4th Lvl | TT_Task | TK_NotStart | 2026-04-17 | 2026-04-21 | 3 | 0 | Building Structure | Structure
Baseline | C-04-ST-110 | Rebar & PT Tendons for Elevated Slab @ L4 | yes | Structure | 4 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 4th Lvl | TT_Task | TK_NotStart | 2026-04-21 | 2026-04-23 | 3 | 0 | Building Structure | Structure
Baseline | C-04-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L4 | yes | Structure | 4 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 4th Lvl | TT_Task | TK_NotStart | 2026-04-22 | 2026-04-22 | 1 | 1 | Building Structure | Structure
Baseline | C-04-ST-130 | Pour Elevated Slab @ L4 | yes | Structure | 4 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 4th Lvl | TT_Task | TK_NotStart | 2026-04-24 | 2026-04-24 | 1 | 0 | Building Structure | Structure
Baseline | C-04-ST-140 | F/R/P Columns & Shear Walls @ L4 | yes | Structure | 4 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 4th Lvl | TT_Task | TK_NotStart | 2026-04-27 | 2026-04-29 | 3 | 0 | Building Structure | Structure
Baseline | C-04-ST-150 | Stress PT @ L4 | yes | Structure | 4 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 4th Lvl | TT_Task | TK_NotStart | 2026-04-28 | 2026-04-28 | 1 | 6 | Building Structure | Structure
Baseline | C-05-ST-100 | Form Prestressed Elevated Slab @ L5 | yes | Structure | 5 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 5th Lvl | TT_Task | TK_NotStart | 2026-04-30 | 2026-05-04 | 3 | 0 | Building Structure | Structure
Baseline | C-05-ST-110 | Rebar & PT Tendons for Elevated Slab @ L5 | yes | Structure | 5 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 5th Lvl | TT_Task | TK_NotStart | 2026-05-04 | 2026-05-06 | 3 | 0 | Building Structure | Structure
Baseline | C-05-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L5 | yes | Structure | 5 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 5th Lvl | TT_Task | TK_NotStart | 2026-05-05 | 2026-05-05 | 1 | 1 | Building Structure | Structure
Baseline | C-05-ST-130 | Pour Elevated Slab @ L5 | yes | Structure | 5 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 5th Lvl | TT_Task | TK_NotStart | 2026-05-07 | 2026-05-07 | 1 | 0 | Building Structure | Structure
Baseline | C-05-ST-140 | F/R/P Columns & Shear Walls @ L5 | yes | Structure | 5 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 5th Lvl | TT_Task | TK_NotStart | 2026-05-08 | 2026-05-12 | 3 | 0 | Building Structure | Structure
Baseline | C-05-ST-150 | Stress PT @ L5 | yes | Structure | 5 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 5th Lvl | TT_Task | TK_NotStart | 2026-05-11 | 2026-05-11 | 1 | 6 | Building Structure | Structure
Baseline | C-06-ST-100 | Form Prestressed Elevated Slab @ L6 | yes | Structure | 6 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 6th Lvl | TT_Task | TK_NotStart | 2026-05-13 | 2026-05-15 | 3 | 0 | Building Structure | Structure
Baseline | C-06-ST-110 | Rebar & PT Tendons for Elevated Slab @ L6 | yes | Structure | 6 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 6th Lvl | TT_Task | TK_NotStart | 2026-05-15 | 2026-05-19 | 3 | 0 | Building Structure | Structure
Baseline | C-06-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L6 | yes | Structure | 6 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 6th Lvl | TT_Task | TK_NotStart | 2026-05-18 | 2026-05-18 | 1 | 1 | Building Structure | Structure
Baseline | C-06-ST-130 | Pour Elevated Slab @ L6 | yes | Structure | 6 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 6th Lvl | TT_Task | TK_NotStart | 2026-05-20 | 2026-05-20 | 1 | 0 | Building Structure | Structure
Baseline | C-06-ST-140 | F/R/P Columns & Shear Walls @ L6 | yes | Structure | 6 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 6th Lvl | TT_Task | TK_NotStart | 2026-05-21 | 2026-05-26 | 3 | 1 | Building Structure | Structure
Baseline | C-06-ST-150 | Stress PT @ L6 | yes | Structure | 6 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 6th Lvl | TT_Task | TK_NotStart | 2026-05-22 | 2026-05-22 | 1 | 7 | Building Structure | Structure
Baseline | C-07-ST-100 | Form Prestressed Elevated Slab @ L7 | yes | Structure | 7 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 7th Lvl | TT_Task | TK_NotStart | 2026-05-27 | 2026-05-29 | 3 | 1 | Building Structure | Structure
Baseline | C-07-ST-110 | Rebar & PT Tendons for Elevated Slab @ L7 | yes | Structure | 7 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 7th Lvl | TT_Task | TK_NotStart | 2026-05-29 | 2026-06-02 | 3 | 1 | Building Structure | Structure
Baseline | C-07-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L7 | yes | Structure | 7 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 7th Lvl | TT_Task | TK_NotStart | 2026-06-01 | 2026-06-01 | 1 | 2 | Building Structure | Structure
Baseline | C-07-ST-130 | Pour Elevated Slab @ L7 | yes | Structure | 7 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 7th Lvl | TT_Task | TK_NotStart | 2026-06-03 | 2026-06-03 | 1 | 1 | Building Structure | Structure
Baseline | C-07-ST-140 | F/R/P Columns & Shear Walls @ L7 | yes | Structure | 7 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 7th Lvl | TT_Task | TK_NotStart | 2026-06-04 | 2026-06-08 | 3 | 1 | Building Structure | Structure
Baseline | C-07-ST-150 | Stress PT @ L7 | yes | Structure | 7 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 7th Lvl | TT_Task | TK_NotStart | 2026-06-05 | 2026-06-05 | 1 | 7 | Building Structure | Structure
Baseline | C-08-ST-100 | Form Prestressed Elevated Slab @ L8 | yes | Structure | 8 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 8th Lvl | TT_Task | TK_NotStart | 2026-06-09 | 2026-06-11 | 3 | 1 | Building Structure | Structure
Baseline | C-08-ST-110 | Rebar & PT Tendons for Elevated Slab @ L8 | yes | Structure | 8 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 8th Lvl | TT_Task | TK_NotStart | 2026-06-11 | 2026-06-15 | 3 | 1 | Building Structure | Structure
Baseline | C-08-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L8 | yes | Structure | 8 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 8th Lvl | TT_Task | TK_NotStart | 2026-06-12 | 2026-06-12 | 1 | 2 | Building Structure | Structure
Baseline | C-08-ST-130 | Pour Elevated Slab @ L8 | yes | Structure | 8 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 8th Lvl | TT_Task | TK_NotStart | 2026-06-16 | 2026-06-16 | 1 | 1 | Building Structure | Structure
Baseline | C-08-ST-140 | F/R/P Columns & Shear Walls @ L8 | yes | Structure | 8 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 8th Lvl | TT_Task | TK_NotStart | 2026-06-17 | 2026-06-18 | 2 | 1 | Building Structure | Structure
Baseline | C-08-ST-150 | Stress PT @ L8 | yes | Structure | 8 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 8th Lvl | TT_Task | TK_NotStart | 2026-06-18 | 2026-06-18 | 1 | 5 | Building Structure | Structure
Baseline | C-09-ST-100 | Form Prestressed Elevated Slab @ L9 | yes | Structure | 9 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 9th Lvl | TT_Task | TK_NotStart | 2026-06-18 | 2026-06-22 | 3 | 1 | Building Structure | Structure
Baseline | C-09-ST-110 | Rebar & PT Tendons for Elevated Slab @ L9 | yes | Structure | 9 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 9th Lvl | TT_Task | TK_NotStart | 2026-06-22 | 2026-06-24 | 3 | 1 | Building Structure | Structure
Baseline | C-09-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L9 | yes | Structure | 9 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 9th Lvl | TT_Task | TK_NotStart | 2026-06-23 | 2026-06-23 | 1 | 2 | Building Structure | Structure
Baseline | C-09-ST-130 | Pour Elevated Slab @ L9 | yes | Structure | 9 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 9th Lvl | TT_Task | TK_NotStart | 2026-06-25 | 2026-06-25 | 1 | 1 | Building Structure | Structure
Baseline | C-09-ST-140 | F/R/P Columns & Shear Walls @ L9 | yes | Structure | 9 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 9th Lvl | TT_Task | TK_NotStart | 2026-06-26 | 2026-06-29 | 2 | 1 | Building Structure | Structure
Baseline | C-09-ST-150 | Stress PT @ L9 | yes | Structure | 9 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 9th Lvl | TT_Task | TK_NotStart | 2026-06-29 | 2026-06-29 | 1 | 5 | Building Structure | Structure
Baseline | C-10-ST-100 | Form Prestressed Elevated Slab @ L10 | yes | Structure | 10 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 10th Lvl | TT_Task | TK_NotStart | 2026-06-29 | 2026-07-01 | 3 | 1 | Building Structure | Structure
Baseline | C-10-ST-110 | Rebar & PT Tendons for Elevated Slab @ L10 | yes | Structure | 10 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 10th Lvl | TT_Task | TK_NotStart | 2026-07-01 | 2026-07-06 | 3 | 1 | Building Structure | Structure
Baseline | C-10-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L10 | yes | Structure | 10 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 10th Lvl | TT_Task | TK_NotStart | 2026-07-02 | 2026-07-02 | 1 | 2 | Building Structure | Structure
Baseline | C-10-ST-130 | Pour Elevated Slab @ L10 | yes | Structure | 10 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 10th Lvl | TT_Task | TK_NotStart | 2026-07-07 | 2026-07-07 | 1 | 1 | Building Structure | Structure
Baseline | C-10-ST-140 | F/R/P Columns & Shear Walls @ L10 | yes | Structure | 10 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 10th Lvl | TT_Task | TK_NotStart | 2026-07-08 | 2026-07-09 | 2 | 1 | Building Structure | Structure
Baseline | C-10-ST-150 | Stress PT @ L10 | yes | Structure | 10 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 10th Lvl | TT_Task | TK_NotStart | 2026-07-09 | 2026-07-09 | 1 | 5 | Building Structure | Structure
Baseline | C-11-ST-100 | Form Prestressed Elevated Slab @ L11 | yes | Structure | 11 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 11th Lvl | TT_Task | TK_NotStart | 2026-07-09 | 2026-07-13 | 3 | 1 | Building Structure | Structure
Baseline | C-11-ST-110 | Rebar & PT Tendons for Elevated Slab @ L11 | yes | Structure | 11 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 11th Lvl | TT_Task | TK_NotStart | 2026-07-13 | 2026-07-15 | 3 | 1 | Building Structure | Structure
Baseline | C-11-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L11 | yes | Structure | 11 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 11th Lvl | TT_Task | TK_NotStart | 2026-07-14 | 2026-07-14 | 1 | 2 | Building Structure | Structure
Baseline | C-11-ST-130 | Pour Elevated Slab @ L11 | yes | Structure | 11 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 11th Lvl | TT_Task | TK_NotStart | 2026-07-16 | 2026-07-16 | 1 | 1 | Building Structure | Structure
Baseline | C-11-ST-140 | F/R/P Columns & Shear Walls @ L11 | yes | Structure | 11 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 11th Lvl | TT_Task | TK_NotStart | 2026-07-17 | 2026-07-20 | 2 | 1 | Building Structure | Structure
Baseline | C-11-ST-150 | Stress PT @ L11 | yes | Structure | 11 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 11th Lvl | TT_Task | TK_NotStart | 2026-07-20 | 2026-07-20 | 1 | 5 | Building Structure | Structure
Baseline | C-12-ST-100 | Form Prestressed Elevated Slab @ L12 | yes | Structure | 12 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 12th Lvl | TT_Task | TK_NotStart | 2026-07-20 | 2026-07-22 | 3 | 1 | Building Structure | Structure
Baseline | C-12-ST-110 | Rebar & PT Tendons for Elevated Slab @ L12 | yes | Structure | 12 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 12th Lvl | TT_Task | TK_NotStart | 2026-07-22 | 2026-07-24 | 3 | 1 | Building Structure | Structure
Baseline | C-12-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L12 | yes | Structure | 12 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 12th Lvl | TT_Task | TK_NotStart | 2026-07-23 | 2026-07-23 | 1 | 2 | Building Structure | Structure
Baseline | C-12-ST-130 | Pour Elevated Slab @ L12 | yes | Structure | 12 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 12th Lvl | TT_Task | TK_NotStart | 2026-07-27 | 2026-07-27 | 1 | 1 | Building Structure | Structure
Baseline | C-12-ST-140 | F/R/P Columns & Shear Walls @ L12 | yes | Structure | 12 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 12th Lvl | TT_Task | TK_NotStart | 2026-07-28 | 2026-07-29 | 2 | 1 | Building Structure | Structure
Baseline | C-12-ST-150 | Stress PT @ L12 | yes | Structure | 12 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 12th Lvl | TT_Task | TK_NotStart | 2026-07-29 | 2026-07-29 | 1 | 6 | Building Structure | Structure
Baseline | C-14-ST-100 | Form Prestressed Elevated Slab @ L14 | yes | Structure | 14 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 14th Lvl | TT_Task | TK_NotStart | 2026-07-30 | 2026-08-03 | 3 | 1 | Building Structure | Structure
Baseline | C-14-ST-110 | Rebar & PT Tendons for Elevated Slab @ L14 | yes | Structure | 14 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 14th Lvl | TT_Task | TK_NotStart | 2026-08-03 | 2026-08-05 | 3 | 1 | Building Structure | Structure
Baseline | C-14-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L14 | yes | Structure | 14 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 14th Lvl | TT_Task | TK_NotStart | 2026-08-04 | 2026-08-04 | 1 | 2 | Building Structure | Structure
Baseline | C-14-ST-130 | Pour Elevated Slab @ L14 | yes | Structure | 14 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 14th Lvl | TT_Task | TK_NotStart | 2026-08-06 | 2026-08-06 | 1 | 1 | Building Structure | Structure
Baseline | C-14-ST-140 | F/R/P Columns & Shear Walls @ L14 | yes | Structure | 14 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 14th Lvl | TT_Task | TK_NotStart | 2026-08-07 | 2026-08-10 | 2 | 1 | Building Structure | Structure
Baseline | C-14-ST-150 | Stress PT @ L14 | yes | Structure | 14 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 14th Lvl | TT_Task | TK_NotStart | 2026-08-10 | 2026-08-10 | 1 | 5 | Building Structure | Structure
Baseline | C-15-ST-100 | Form Prestressed Elevated Slab @ L15 | yes | Structure | 15 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 15th Lvl | TT_Task | TK_NotStart | 2026-08-10 | 2026-08-12 | 3 | 1 | Building Structure | Structure
Baseline | C-15-ST-110 | Rebar & PT Tendons for Elevated Slab @ L15 | yes | Structure | 15 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 15th Lvl | TT_Task | TK_NotStart | 2026-08-12 | 2026-08-14 | 3 | 1 | Building Structure | Structure
Baseline | C-15-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L15 | yes | Structure | 15 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 15th Lvl | TT_Task | TK_NotStart | 2026-08-13 | 2026-08-13 | 1 | 2 | Building Structure | Structure
Baseline | C-15-ST-130 | Pour Elevated Slab @ L15 | yes | Structure | 15 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 15th Lvl | TT_Task | TK_NotStart | 2026-08-17 | 2026-08-17 | 1 | 1 | Building Structure | Structure
Baseline | C-15-ST-140 | F/R/P Columns & Shear Walls @ L15 | yes | Structure | 15 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 15th Lvl | TT_Task | TK_NotStart | 2026-08-18 | 2026-08-19 | 2 | 1 | Building Structure | Structure
Baseline | C-15-ST-150 | Stress PT @ L15 | yes | Structure | 15 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 15th Lvl | TT_Task | TK_NotStart | 2026-08-19 | 2026-08-19 | 1 | 3 | Building Structure | Structure
Baseline | C-16-ST-100 | Form Prestressed Elevated Slab @ L16 | yes | Structure | 16 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 16th Lvl | TT_Task | TK_NotStart | 2026-08-19 | 2026-08-20 | 2 | 1 | Building Structure | Structure
Baseline | C-16-ST-110 | Rebar & PT Tendons for Elevated Slab @ L16 | yes | Structure | 16 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 16th Lvl | TT_Task | TK_NotStart | 2026-08-20 | 2026-08-21 | 2 | 1 | Building Structure | Structure
Baseline | C-16-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L16 | yes | Structure | 16 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 16th Lvl | TT_Task | TK_NotStart | 2026-08-21 | 2026-08-21 | 1 | 1 | Building Structure | Structure
Baseline | C-16-ST-130 | Pour Elevated Slab @ L16 | yes | Structure | 16 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 16th Lvl | TT_Task | TK_NotStart | 2026-08-24 | 2026-08-24 | 1 | 1 | Building Structure | Structure
Baseline | C-16-ST-140 | F/R/P Columns & Shear Walls @ L16 | yes | Structure | 16 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 16th Lvl | TT_Task | TK_NotStart | 2026-08-25 | 2026-08-26 | 2 | 1 | Building Structure | Structure
Baseline | C-16-ST-150 | Stress PT @ L16 | yes | Structure | 16 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 16th Lvl | TT_Task | TK_NotStart | 2026-08-26 | 2026-08-26 | 1 | 3 | Building Structure | Structure
Baseline | C-17-ST-100 | Form Prestressed Elevated Slab @ L17 | yes | Structure | 17 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 17th Lvl | TT_Task | TK_NotStart | 2026-08-26 | 2026-08-27 | 2 | 1 | Building Structure | Structure
Baseline | C-17-ST-110 | Rebar & PT Tendons for Elevated Slab @ L17 | yes | Structure | 17 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 17th Lvl | TT_Task | TK_NotStart | 2026-08-27 | 2026-08-28 | 2 | 1 | Building Structure | Structure
Baseline | C-17-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L17 | yes | Structure | 17 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 17th Lvl | TT_Task | TK_NotStart | 2026-08-28 | 2026-08-28 | 1 | 1 | Building Structure | Structure
Baseline | C-17-ST-130 | Pour Elevated Slab @ L17 | yes | Structure | 17 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 17th Lvl | TT_Task | TK_NotStart | 2026-08-31 | 2026-08-31 | 1 | 1 | Building Structure | Structure
Baseline | C-17-ST-140 | F/R/P Columns & Shear Walls @ L17 | yes | Structure | 17 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 17th Lvl | TT_Task | TK_NotStart | 2026-09-01 | 2026-09-02 | 2 | 1 | Building Structure | Structure
Baseline | C-17-ST-150 | Stress PT @ L17 | yes | Structure | 17 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 17th Lvl | TT_Task | TK_NotStart | 2026-09-02 | 2026-09-02 | 1 | 3 | Building Structure | Structure
Baseline | C-18-ST-100 | Form Prestressed Elevated Slab @ L18 | yes | Structure | 18 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 18th Lvl | TT_Task | TK_NotStart | 2026-09-02 | 2026-09-03 | 2 | 1 | Building Structure | Structure
Baseline | C-18-ST-110 | Rebar & PT Tendons for Elevated Slab @ L18 | yes | Structure | 18 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 18th Lvl | TT_Task | TK_NotStart | 2026-09-03 | 2026-09-04 | 2 | 1 | Building Structure | Structure
Baseline | C-18-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L18 | yes | Structure | 18 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 18th Lvl | TT_Task | TK_NotStart | 2026-09-04 | 2026-09-04 | 1 | 1 | Building Structure | Structure
Baseline | C-18-ST-130 | Pour Elevated Slab @ L18 | yes | Structure | 18 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 18th Lvl | TT_Task | TK_NotStart | 2026-09-08 | 2026-09-08 | 1 | 1 | Building Structure | Structure
Baseline | C-18-ST-140 | F/R/P Columns & Shear Walls @ L18 | yes | Structure | 18 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 18th Lvl | TT_Task | TK_NotStart | 2026-09-09 | 2026-09-10 | 2 | 1 | Building Structure | Structure
Baseline | C-18-ST-150 | Stress PT @ L18 | yes | Structure | 18 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 18th Lvl | TT_Task | TK_NotStart | 2026-09-10 | 2026-09-10 | 1 | 3 | Building Structure | Structure
Baseline | C-19-ST-100 | Form Prestressed Elevated Slab @ L19 | yes | Structure | 19 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 19th Lvl | TT_Task | TK_NotStart | 2026-09-10 | 2026-09-11 | 2 | 1 | Building Structure | Structure
Baseline | C-19-ST-110 | Rebar & PT Tendons for Elevated Slab @ L19 | yes | Structure | 19 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 19th Lvl | TT_Task | TK_NotStart | 2026-09-11 | 2026-09-14 | 2 | 1 | Building Structure | Structure
Baseline | C-19-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L19 | yes | Structure | 19 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 19th Lvl | TT_Task | TK_NotStart | 2026-09-14 | 2026-09-14 | 1 | 1 | Building Structure | Structure
Baseline | C-19-ST-130 | Pour Elevated Slab @ L19 | yes | Structure | 19 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 19th Lvl | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-15 | 1 | 1 | Building Structure | Structure
Baseline | C-19-ST-140 | F/R/P Columns & Shear Walls @ L19 | yes | Structure | 19 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 19th Lvl | TT_Task | TK_NotStart | 2026-09-16 | 2026-09-17 | 2 | 1 | Building Structure | Structure
Baseline | C-19-ST-150 | Stress PT @ L19 | yes | Structure | 19 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 19th Lvl | TT_Task | TK_NotStart | 2026-09-17 | 2026-09-17 | 1 | 3 | Building Structure | Structure
Baseline | C-20-ST-100 | Form Prestressed Elevated Slab @ L20 | yes | Structure | 20 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 20th Lvl | TT_Task | TK_NotStart | 2026-09-17 | 2026-09-18 | 2 | 1 | Building Structure | Structure
Baseline | C-20-ST-110 | Rebar & PT Tendons for Elevated Slab @ L20 | yes | Structure | 20 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 20th Lvl | TT_Task | TK_NotStart | 2026-09-18 | 2026-09-21 | 2 | 1 | Building Structure | Structure
Baseline | C-20-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L20 | yes | Structure | 20 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 20th Lvl | TT_Task | TK_NotStart | 2026-09-21 | 2026-09-21 | 1 | 1 | Building Structure | Structure
Baseline | C-20-ST-130 | Pour Elevated Slab @ L20 | yes | Structure | 20 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 20th Lvl | TT_Task | TK_NotStart | 2026-09-22 | 2026-09-22 | 1 | 1 | Building Structure | Structure
Baseline | C-20-ST-140 | F/R/P Columns & Shear Walls @ L20 | yes | Structure | 20 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 20th Lvl | TT_Task | TK_NotStart | 2026-09-23 | 2026-09-24 | 2 | 1 | Building Structure | Structure
Baseline | C-20-ST-150 | Stress PT @ L20 | yes | Structure | 20 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 20th Lvl | TT_Task | TK_NotStart | 2026-09-24 | 2026-09-24 | 1 | 3 | Building Structure | Structure
Baseline | C-21-ST-100 | Form Prestressed Elevated Slab @ L21 | yes | Structure | 21 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 21st Lvl | TT_Task | TK_NotStart | 2026-09-24 | 2026-09-25 | 2 | 1 | Building Structure | Structure
Baseline | C-21-ST-110 | Rebar & PT Tendons for Elevated Slab @ L21 | yes | Structure | 21 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 21st Lvl | TT_Task | TK_NotStart | 2026-09-25 | 2026-09-28 | 2 | 1 | Building Structure | Structure
Baseline | C-21-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L21 | yes | Structure | 21 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 21st Lvl | TT_Task | TK_NotStart | 2026-09-28 | 2026-09-28 | 1 | 1 | Building Structure | Structure
Baseline | C-21-ST-130 | Pour Elevated Slab @ L21 | yes | Structure | 21 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 21st Lvl | TT_Task | TK_NotStart | 2026-09-29 | 2026-09-29 | 1 | 1 | Building Structure | Structure
Baseline | C-21-ST-140 | F/R/P Columns & Shear Walls @ L21 | yes | Structure | 21 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 21st Lvl | TT_Task | TK_NotStart | 2026-09-30 | 2026-10-01 | 2 | 1 | Building Structure | Structure
Baseline | C-21-ST-150 | Stress PT @ L21 | yes | Structure | 21 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 21st Lvl | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-01 | 1 | 3 | Building Structure | Structure
Baseline | C-22-ST-100 | Form Prestressed Elevated Slab @ L22 | yes | Structure | 22 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 22nd Lvl | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-02 | 2 | 1 | Building Structure | Structure
Baseline | C-22-ST-110 | Rebar & PT Tendons for Elevated Slab @ L22 | yes | Structure | 22 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 22nd Lvl | TT_Task | TK_NotStart | 2026-10-02 | 2026-10-05 | 2 | 1 | Building Structure | Structure
Baseline | C-22-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L22 | yes | Structure | 22 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 22nd Lvl | TT_Task | TK_NotStart | 2026-10-05 | 2026-10-05 | 1 | 1 | Building Structure | Structure
Baseline | C-22-ST-130 | Pour Elevated Slab @ L22 | yes | Structure | 22 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 22nd Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-06 | 1 | 1 | Building Structure | Structure
Baseline | C-22-ST-140 | F/R/P Columns & Shear Walls @ L22 | yes | Structure | 22 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 22nd Lvl | TT_Task | TK_NotStart | 2026-10-07 | 2026-10-08 | 2 | 1 | Building Structure | Structure
Baseline | C-22-ST-150 | Stress PT @ L22 | yes | Structure | 22 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 22nd Lvl | TT_Task | TK_NotStart | 2026-10-08 | 2026-10-08 | 1 | 3 | Building Structure | Structure
Baseline | C-23-ST-100 | Form Prestressed Elevated Slab @ L23 | yes | Structure | 23 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 23rd Lvl | TT_Task | TK_NotStart | 2026-10-08 | 2026-10-09 | 2 | 1 | Building Structure | Structure
Baseline | C-23-ST-110 | Rebar & PT Tendons for Elevated Slab @ L23 | yes | Structure | 23 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 23rd Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-12 | 2 | 1 | Building Structure | Structure
Baseline | C-23-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L23 | yes | Structure | 23 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 23rd Lvl | TT_Task | TK_NotStart | 2026-10-12 | 2026-10-12 | 1 | 1 | Building Structure | Structure
Baseline | C-23-ST-130 | Pour Elevated Slab @ L23 | yes | Structure | 23 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 23rd Lvl | TT_Task | TK_NotStart | 2026-10-13 | 2026-10-13 | 1 | 1 | Building Structure | Structure
Baseline | C-23-ST-140 | F/R/P Columns & Shear Walls @ L23 | yes | Structure | 23 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 23rd Lvl | TT_Task | TK_NotStart | 2026-10-14 | 2026-10-15 | 2 | 1 | Building Structure | Structure
Baseline | C-23-ST-150 | Stress PT @ L23 | yes | Structure | 23 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 23rd Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-15 | 1 | 3 | Building Structure | Structure
Baseline | C-24-ST-100 | Form Prestressed Elevated Slab @ L24 | yes | Structure | 24 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 24th Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-16 | 2 | 1 | Building Structure | Structure
Baseline | C-24-ST-110 | Rebar & PT Tendons for Elevated Slab @ L24 | yes | Structure | 24 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 24th Lvl | TT_Task | TK_NotStart | 2026-10-16 | 2026-10-19 | 2 | 1 | Building Structure | Structure
Baseline | C-24-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L24 | yes | Structure | 24 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 24th Lvl | TT_Task | TK_NotStart | 2026-10-19 | 2026-10-19 | 1 | 1 | Building Structure | Structure
Baseline | C-24-ST-130 | Pour Elevated Slab @ L24 | yes | Structure | 24 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 24th Lvl | TT_Task | TK_NotStart | 2026-10-20 | 2026-10-20 | 1 | 1 | Building Structure | Structure
Baseline | C-24-ST-140 | F/R/P Columns & Shear Walls @ L24 | yes | Structure | 24 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 24th Lvl | TT_Task | TK_NotStart | 2026-10-21 | 2026-10-22 | 2 | 1 | Building Structure | Structure
Baseline | C-24-ST-150 | Stress PT @ L24 | yes | Structure | 24 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 24th Lvl | TT_Task | TK_NotStart | 2026-10-22 | 2026-10-22 | 1 | 3 | Building Structure | Structure
Baseline | C-25-ST-100 | Form Prestressed Elevated Slab @ L25 | yes | Structure | 25 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 25th Lvl | TT_Task | TK_NotStart | 2026-10-22 | 2026-10-23 | 2 | 1 | Building Structure | Structure
Baseline | C-25-ST-110 | Rebar & PT Tendons for Elevated Slab @ L25 | yes | Structure | 25 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 25th Lvl | TT_Task | TK_NotStart | 2026-10-23 | 2026-10-26 | 2 | 1 | Building Structure | Structure
Baseline | C-25-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L25 | yes | Structure | 25 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 25th Lvl | TT_Task | TK_NotStart | 2026-10-26 | 2026-10-26 | 1 | 1 | Building Structure | Structure
Baseline | C-25-ST-130 | Pour Elevated Slab @ L25 | yes | Structure | 25 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 25th Lvl | TT_Task | TK_NotStart | 2026-10-27 | 2026-10-27 | 1 | 1 | Building Structure | Structure
Baseline | C-25-ST-140 | F/R/P Columns & Shear Walls @ L25 | yes | Structure | 25 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 25th Lvl | TT_Task | TK_NotStart | 2026-10-28 | 2026-10-29 | 2 | 1 | Building Structure | Structure
Baseline | C-25-ST-150 | Stress PT @ L25 | yes | Structure | 25 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 25th Lvl | TT_Task | TK_NotStart | 2026-10-29 | 2026-10-29 | 1 | 3 | Building Structure | Structure
Baseline | C-26-ST-100 | Form Prestressed Elevated Slab @ L26 | yes | Structure | 26 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 26th Lvl | TT_Task | TK_NotStart | 2026-10-29 | 2026-10-30 | 2 | 1 | Building Structure | Structure
Baseline | C-26-ST-110 | Rebar & PT Tendons for Elevated Slab @ L26 | yes | Structure | 26 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 26th Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-02 | 2 | 1 | Building Structure | Structure
Baseline | C-26-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L26 | yes | Structure | 26 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 26th Lvl | TT_Task | TK_NotStart | 2026-11-02 | 2026-11-02 | 1 | 1 | Building Structure | Structure
Baseline | C-26-ST-130 | Pour Elevated Slab @ L26 | yes | Structure | 26 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 26th Lvl | TT_Task | TK_NotStart | 2026-11-03 | 2026-11-03 | 1 | 1 | Building Structure | Structure
Baseline | C-26-ST-140 | F/R/P Columns & Shear Walls @ L26 | yes | Structure | 26 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 26th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-05 | 2 | 1 | Building Structure | Structure
Baseline | C-26-ST-150 | Stress PT @ L26 | yes | Structure | 26 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 26th Lvl | TT_Task | TK_NotStart | 2026-11-05 | 2026-11-05 | 1 | 3 | Building Structure | Structure
Baseline | C-27-ST-100 | Form Prestressed Elevated Slab @ L27 | yes | Structure | 27 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 27th Lvl | TT_Task | TK_NotStart | 2026-11-05 | 2026-11-06 | 2 | 1 | Building Structure | Structure
Baseline | C-27-ST-110 | Rebar & PT Tendons for Elevated Slab @ L27 | yes | Structure | 27 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 27th Lvl | TT_Task | TK_NotStart | 2026-11-06 | 2026-11-09 | 2 | 1 | Building Structure | Structure
Baseline | C-27-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L27 | yes | Structure | 27 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 27th Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-09 | 1 | 1 | Building Structure | Structure
Baseline | C-27-ST-130 | Pour Elevated Slab @ L27 | yes | Structure | 27 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 27th Lvl | TT_Task | TK_NotStart | 2026-11-10 | 2026-11-10 | 1 | 1 | Building Structure | Structure
Baseline | C-27-ST-140 | F/R/P Columns & Shear Walls @ L27 | yes | Structure | 27 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 27th Lvl | TT_Task | TK_NotStart | 2026-11-11 | 2026-11-12 | 2 | 1 | Building Structure | Structure
Baseline | C-27-ST-150 | Stress PT @ L27 | yes | Structure | 27 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 27th Lvl | TT_Task | TK_NotStart | 2026-11-12 | 2026-11-12 | 1 | 3 | Building Structure | Structure
Baseline | C-28-ST-100 | Form Prestressed Elevated Slab @ L28 | yes | Structure | 28 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 28th Lvl | TT_Task | TK_NotStart | 2026-11-12 | 2026-11-13 | 2 | 1 | Building Structure | Structure
Baseline | C-28-ST-110 | Rebar & PT Tendons for Elevated Slab @ L28 | yes | Structure | 28 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 28th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-16 | 2 | 1 | Building Structure | Structure
Baseline | C-28-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L28 | yes | Structure | 28 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 28th Lvl | TT_Task | TK_NotStart | 2026-11-16 | 2026-11-16 | 1 | 1 | Building Structure | Structure
Baseline | C-28-ST-130 | Pour Elevated Slab @ L28 | yes | Structure | 28 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 28th Lvl | TT_Task | TK_NotStart | 2026-11-17 | 2026-11-17 | 1 | 1 | Building Structure | Structure
Baseline | C-28-ST-140 | F/R/P Columns & Shear Walls @ L28 | yes | Structure | 28 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 28th Lvl | TT_Task | TK_NotStart | 2026-11-18 | 2026-11-19 | 2 | 1 | Building Structure | Structure
Baseline | C-28-ST-150 | Stress PT @ L28 | yes | Structure | 28 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 28th Lvl | TT_Task | TK_NotStart | 2026-11-19 | 2026-11-19 | 1 | 3 | Building Structure | Structure
Baseline | C-29-ST-100 | Form Prestressed Elevated Slab @ L29 | yes | Structure | 29 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 29th Lvl | TT_Task | TK_NotStart | 2026-11-19 | 2026-11-20 | 2 | 1 | Building Structure | Structure
Baseline | C-29-ST-110 | Rebar & PT Tendons for Elevated Slab @ L29 | yes | Structure | 29 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 29th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-11-23 | 2 | 1 | Building Structure | Structure
Baseline | C-29-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L29 | yes | Structure | 29 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 29th Lvl | TT_Task | TK_NotStart | 2026-11-23 | 2026-11-23 | 1 | 1 | Building Structure | Structure
Baseline | C-29-ST-130 | Pour Elevated Slab @ L29 | yes | Structure | 29 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 29th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-11-24 | 1 | 1 | Building Structure | Structure
Baseline | C-29-ST-140 | F/R/P Columns & Shear Walls @ L29 | yes | Structure | 29 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 29th Lvl | TT_Task | TK_NotStart | 2026-11-25 | 2026-11-30 | 2 | 1 | Building Structure | Structure
Baseline | C-29-ST-150 | Stress PT @ L29 | yes | Structure | 29 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 29th Lvl | TT_Task | TK_NotStart | 2026-11-30 | 2026-11-30 | 1 | 3 | Building Structure | Structure
Baseline | C-30-ST-100 | Form Prestressed Elevated Slab @ L30 | yes | Structure | 30 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 30th Lvl | TT_Task | TK_NotStart | 2026-11-30 | 2026-12-01 | 2 | 1 | Building Structure | Structure
Baseline | C-30-ST-110 | Rebar & PT Tendons for Elevated Slab @ L30 | yes | Structure | 30 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 30th Lvl | TT_Task | TK_NotStart | 2026-12-01 | 2026-12-02 | 2 | 1 | Building Structure | Structure
Baseline | C-30-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L30 | yes | Structure | 30 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 30th Lvl | TT_Task | TK_NotStart | 2026-12-02 | 2026-12-02 | 1 | 1 | Building Structure | Structure
Baseline | C-30-ST-130 | Pour Elevated Slab @ L30 | yes | Structure | 30 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 30th Lvl | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-03 | 1 | 1 | Building Structure | Structure
Baseline | C-30-ST-140 | F/R/P Columns & Shear Walls @ L30 | yes | Structure | 30 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 30th Lvl | TT_Task | TK_NotStart | 2026-12-04 | 2026-12-07 | 2 | 1 | Building Structure | Structure
Baseline | C-30-ST-150 | Stress PT @ L30 | yes | Structure | 30 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 30th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-07 | 1 | 3 | Building Structure | Structure
Baseline | C-31-ST-100 | Form Prestressed Elevated Slab @ L31 | yes | Structure | 31 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 31st Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-08 | 2 | 1 | Building Structure | Structure
Baseline | C-31-ST-110 | Rebar & PT Tendons for Elevated Slab @ L31 | yes | Structure | 31 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 31st Lvl | TT_Task | TK_NotStart | 2026-12-08 | 2026-12-09 | 2 | 1 | Building Structure | Structure
Baseline | C-31-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L31 | yes | Structure | 31 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 31st Lvl | TT_Task | TK_NotStart | 2026-12-09 | 2026-12-09 | 1 | 1 | Building Structure | Structure
Baseline | C-31-ST-130 | Pour Elevated Slab @ L31 | yes | Structure | 31 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 31st Lvl | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-10 | 1 | 1 | Building Structure | Structure
Baseline | C-31-ST-140 | F/R/P Columns & Shear Walls @ L31 | yes | Structure | 31 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 31st Lvl | TT_Task | TK_NotStart | 2026-12-11 | 2026-12-14 | 2 | 1 | Building Structure | Structure
Baseline | C-31-ST-150 | Stress PT @ L31 | yes | Structure | 31 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 31st Lvl | TT_Task | TK_NotStart | 2026-12-14 | 2026-12-14 | 1 | 5 | Building Structure | Structure
Baseline | C-32-ST-100 | Form Prestressed Elevated Slab @ L32 | yes | Structure | 32 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 32nd Lvl | TT_Task | TK_NotStart | 2026-12-14 | 2026-12-16 | 3 | 1 | Building Structure | Structure
Baseline | C-32-ST-110 | Rebar & PT Tendons for Elevated Slab @ L32 | yes | Structure | 32 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 32nd Lvl | TT_Task | TK_NotStart | 2026-12-16 | 2026-12-18 | 3 | 1 | Building Structure | Structure
Baseline | C-32-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L32 | yes | Structure | 32 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 32nd Lvl | TT_Task | TK_NotStart | 2026-12-17 | 2026-12-17 | 1 | 2 | Building Structure | Structure
Baseline | C-32-ST-130 | Pour Elevated Slab @ L32 | yes | Structure | 32 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 32nd Lvl | TT_Task | TK_NotStart | 2026-12-21 | 2026-12-21 | 1 | 1 | Building Structure | Structure
Baseline | C-32-ST-140 | F/R/P Columns & Shear Walls @ L32 | yes | Structure | 32 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 32nd Lvl | TT_Task | TK_NotStart | 2026-12-22 | 2026-12-23 | 2 | 1 | Building Structure | Structure
Baseline | C-32-ST-150 | Stress PT @ L32 | yes | Structure | 32 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 32nd Lvl | TT_Task | TK_NotStart | 2026-12-23 | 2026-12-23 | 1 | 6 | Building Structure | Structure
Baseline | C-33-ST-100 | Form Prestressed Elevated Slab @ L33 | yes | Structure | 33 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 33rd Lvl | TT_Task | TK_NotStart | 2026-12-23 | 2026-12-28 | 3 | 1 | Building Structure | Structure
Baseline | C-33-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L33 | yes | Structure | 33 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 33rd Lvl | TT_Task | TK_NotStart | 2026-12-29 | 2026-12-29 | 1 | 3 | Building Structure | Structure
Baseline | C-33-ST-110 | Rebar & PT Tendons for Elevated Slab @ L33 | yes | Structure | 33 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 33rd Lvl | TT_Task | TK_NotStart | 2026-12-29 | 2026-12-31 | 3 | 1 | Building Structure | Structure
Baseline | C-33-ST-130 | Pour Elevated Slab @ L33 | yes | Structure | 33 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 33rd Lvl | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-04 | 1 | 1 | Building Structure | Structure
Baseline | C-33-ST-140 | F/R/P Columns & Shear Walls @ L33 | yes | Structure | 33 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 33rd Lvl | TT_Task | TK_NotStart | 2027-01-05 | 2027-01-06 | 2 | 1 | Building Structure | Structure
Baseline | C-33-ST-150 | Stress PT @ L33 | yes | Structure | 33 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 33rd Lvl | TT_Task | TK_NotStart | 2027-01-06 | 2027-01-06 | 1 | 6 | Building Structure | Structure
Baseline | C-34-ST-100 | Form Prestressed Elevated Slab @ L34 | yes | Structure | 34 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 34th Lvl | TT_Task | TK_NotStart | 2027-01-06 | 2027-01-08 | 3 | 1 | Building Structure | Structure
Baseline | C-34-ST-110 | Rebar & PT Tendons for Elevated Slab @ L34 | yes | Structure | 34 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 34th Lvl | TT_Task | TK_NotStart | 2027-01-11 | 2027-01-13 | 3 | 1 | Building Structure | Structure
Baseline | C-34-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L34 | yes | Structure | 34 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 34th Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-12 | 1 | 2 | Building Structure | Structure
Baseline | C-34-ST-130 | Pour Elevated Slab @ L34 | yes | Structure | 34 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 34th Lvl | TT_Task | TK_NotStart | 2027-01-14 | 2027-01-14 | 1 | 1 | Building Structure | Structure
Baseline | C-34-ST-140 | F/R/P Columns & Shear Walls @ L34 | yes | Structure | 34 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 34th Lvl | TT_Task | TK_NotStart | 2027-01-15 | 2027-01-18 | 2 | 1 | Building Structure | Structure
Baseline | C-34-ST-150 | Stress PT @ L34 | yes | Structure | 34 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 34th Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-18 | 1 | 5 | Building Structure | Structure
Baseline | C-35-ST-100 | Form Prestressed Elevated Slab @ L35 | yes | Structure | 35 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 35th Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-20 | 3 | 1 | Building Structure | Structure
Baseline | C-35-ST-110 | Rebar & PT Tendons for Elevated Slab @ L35 | yes | Structure | 35 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 35th Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-01-22 | 3 | 1 | Building Structure | Structure
Baseline | C-35-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L35 | yes | Structure | 35 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 35th Lvl | TT_Task | TK_NotStart | 2027-01-21 | 2027-01-21 | 1 | 2 | Building Structure | Structure
Baseline | C-35-ST-130 | Pour Elevated Slab @ L35 | yes | Structure | 35 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 35th Lvl | TT_Task | TK_NotStart | 2027-01-25 | 2027-01-25 | 1 | 1 | Building Structure | Structure
Baseline | C-35-ST-140 | F/R/P Columns & Shear Walls @ L35 | yes | Structure | 35 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 35th Lvl | TT_Task | TK_NotStart | 2027-01-26 | 2027-01-27 | 2 | 1 | Building Structure | Structure
Baseline | C-35-ST-150 | Stress PT @ L35 | yes | Structure | 35 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 35th Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-01-27 | 1 | 18 | Building Structure | Structure
Baseline | C-36-ST-100 | Form Pool Slab/Beams/Walls @ Low Pool (Interstitial) Lvl | yes | Structure | 36 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-01-29 | 3 | 14 | Building Structure | Structure at Lower
Baseline | C-36-MP-120 | Install MEP Inserts & Sleeves at Pool Slab/Beams/Walls @ Low Pool (Interstitial) Lvl | yes | Structure | 36 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-01-29 | 2027-02-02 | 3 | 14 | Building Structure | Structure at Lower
Baseline | C-36-ST-110 | Rebar Pool Slab/Beams/Walls @ Low Pool (Interstitial) Lvl | yes | Structure | 36 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-01-29 | 2027-02-02 | 3 | 14 | Building Structure | Structure at Lower
Baseline | C-36-ST-130 | Pour Pool Slab/Beams/Walls @ Low Pool Level @ Low Pool (Interstitial) Lvl | yes | Structure | 36 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-02-03 | 2027-02-03 | 1 | 14 | Building Structure | Structure at Lower
Baseline | C-36-ST-140 | Form Prestressed Elevated Slab @ 36th Pool Lvl | yes | Structure | 36 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-02-04 | 2027-02-05 | 2 | 14 | Building Structure | Structure at Lower
Baseline | C-36-ST-150 | Rebar & PT Tendons for Elevated Slab @ 36th Pool Lvl | yes | Structure | 36 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-09 | 3 | 14 | Building Structure | Structure at Lower
Baseline | C-36-ST-170 | Pour Elevated Slab @ 36th Pool Lvl | yes | Structure | 36 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-02-10 | 2027-02-10 | 1 | 14 | Building Structure | Structure at Lower
Baseline | C-36-ST-180 | F/R/P Columns & Shear Walls @ 36th Pool Lvl | yes | Structure | 36 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-12 | 2 | 14 | Building Structure | Structure at Lower
Baseline | C-36-ST-190 | Stress PT @ 36th Pool Lvl | yes | Structure | 36 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-02-12 | 2027-02-12 | 1 | 21 | Building Structure | Structure at Lower
Baseline | C-37-ST-100 | Form Prestressed Elevated Slab @ Roof Lvl | yes | Structure | 37 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Roof Lvl | TT_Task | TK_NotStart | 2027-02-18 | 2027-02-19 | 2 | 14 | Building Structure | Structure at Roof Lvl
Baseline | C-37-ST-110 | Rebar & PT Tendons for Elevated Slab @ Roof Lvl | yes | Structure | 37 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Roof Lvl | TT_Task | TK_NotStart | 2027-02-19 | 2027-02-23 | 3 | 14 | Building Structure | Structure at Roof Lvl
Baseline | C-37-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ Roof Lvl | yes | Structure | 37 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Roof Lvl | TT_Task | TK_NotStart | 2027-02-22 | 2027-02-22 | 1 | 15 | Building Structure | Structure at Roof Lvl
Baseline | C-37-ST-130 | Pour Elevated Slab @ Roof Lvl | yes | Structure | 37 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Roof Lvl | TT_Task | TK_NotStart | 2027-02-24 | 2027-02-24 | 1 | 14 | Building Structure | Structure at Roof Lvl
Baseline | C-37-ST-140 | F/R/P Columns & Shear Wall @ Roof Lvl | yes | Structure | 37 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Roof Lvl | TT_Task | TK_NotStart | 2027-02-26 | 2027-03-01 | 2 | 24 | Building Structure | Structure at Roof Lvl
Baseline | C-37-ST-150 | Stress PT @ Roof Lvl | yes | Structure | 37 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Roof Lvl | TT_Task | TK_NotStart | 2027-02-26 | 2027-02-26 | 1 | 24 | Building Structure | Structure at Roof Lvl
Baseline | C-37-ST-190 | Lay Parapet Walls @ High Roof Level | yes | Structure | 37 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at High Roof Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-22 | 4 | 24 | Building Structure | Structure at High Roof Lvl
Baseline | C-38-ST-100 | Form Prestressed Elevated Slab @ High Roof Lvl | yes | Structure | 38 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at High Roof Lvl | TT_Task | TK_NotStart | 2027-03-02 | 2027-03-03 | 2 | 24 | Building Structure | Structure at High Roof Lvl
Baseline | C-38-ST-110 | Rebar & PT Tendons for Elevated Slab @ High Roof Lvl | yes | Structure | 38 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at High Roof Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-04 | 2 | 24 | Building Structure | Structure at High Roof Lvl
Baseline | C-38-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ High Roof Lvl | yes | Structure | 38 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at High Roof Lvl | TT_Task | TK_NotStart | 2027-03-04 | 2027-03-04 | 1 | 24 | Building Structure | Structure at High Roof Lvl
Baseline | C-38-ST-130 | Pour Elevated Slab @ High Roof Lvl | yes | Structure | 38 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at High Roof Lvl | TT_Task | TK_NotStart | 2027-03-05 | 2027-03-05 | 1 | 24 | Building Structure | Structure at High Roof Lvl
Baseline | C-01-ST-400 | Lay Exterior & Interior CMU Walls @ L1 | yes | Envelope | 1 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-04-14 | 2027-04-27 | 10 | 14 | Building Structure | Exterior & Interior Masonry
Baseline | C-01-EX-100 | Install Exterior Storefronts & Doors @ L1 | yes | Envelope | 1 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-06-21 | 2027-07-19 | 20 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-02-ST-400 | Lay Exterior & Interior CMU Walls & Balcony Edges @ L2 | yes | Envelope | 2 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-05-28 | 2026-06-10 | 10 | 0 | Building Structure | Exterior & Interior Masonry
Baseline | C-02-EX-100 | Install Exterior Glazing @ L2 | yes | Envelope | 2 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-07-10 | 2026-07-17 | 6 | 29 | Exterior Envelope | Exterior Glazing
Baseline | C-03-ST-400 | Lay Exterior & Interior CMU Walls & Balcony Edges @ L3 | yes | Envelope | 3 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-06-11 | 2026-06-24 | 10 | 0 | Building Structure | Exterior & Interior Masonry
Baseline | C-03-EX-100 | Install Exterior Glazing @ L3 | yes | Envelope | 3 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-07-24 | 2026-07-31 | 6 | 25 | Exterior Envelope | Exterior Glazing
Baseline | C-04-ST-400 | Lay Exterior & Interior CMU Walls & Balcony Edges @ L4 | yes | Envelope | 4 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-06-25 | 2026-07-09 | 10 | 0 | Building Structure | Exterior & Interior Masonry
Baseline | C-04-EX-100 | Install Exterior Glazing @ L4 | yes | Envelope | 4 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-08-07 | 2026-08-14 | 6 | 21 | Exterior Envelope | Exterior Glazing
Baseline | C-05-ST-400 | Lay Exterior & Interior CMU Walls & Balcony Edges @ L5 | yes | Envelope | 5 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-07-10 | 2026-07-23 | 10 | 0 | Building Structure | Exterior & Interior Masonry
Baseline | C-05-EX-100 | Install Exterior Glazing @ L5 | yes | Envelope | 5 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-08-21 | 2026-08-28 | 6 | 17 | Exterior Envelope | Exterior Glazing
Baseline | C-06-ST-400 | Lay Exterior & Interior CMU Walls & Balcony Edges @ L6 | yes | Envelope | 6 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-07-24 | 2026-08-06 | 10 | 0 | Building Structure | Exterior & Interior Masonry
Baseline | C-06-EX-100 | Install Exterior Glazing @ L6 | yes | Envelope | 6 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-09-01 | 2026-09-09 | 6 | 16 | Exterior Envelope | Exterior Glazing
Baseline | C-07-ST-400 | Lay Exterior & Interior CMU Walls & Balcony Edges @ L7 | yes | Envelope | 7 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-08-07 | 2026-08-20 | 10 | 0 | Building Structure | Exterior & Interior Masonry
Baseline | C-07-EX-100 | Install Exterior Glazing @ L7 | yes | Envelope | 7 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-09-11 | 2026-09-21 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-08-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L8 | yes | Envelope | 8 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-08-21 | 2026-08-31 | 7 | 3 | Building Structure | Exterior & Interior Masonry
Baseline | C-08-EX-100 | Install Exterior Glazing @ L8 | yes | Envelope | 8 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-09-22 | 2026-09-30 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-09-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L9 | yes | Envelope | 9 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-09-01 | 2026-09-10 | 7 | 3 | Building Structure | Exterior & Interior Masonry
Baseline | C-09-EX-100 | Install Exterior Glazing @ L9 | yes | Envelope | 9 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-09 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-10-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L10 | yes | Envelope | 10 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-09-11 | 2026-09-21 | 7 | 3 | Building Structure | Exterior & Interior Masonry
Baseline | C-10-EX-100 | Install Exterior Glazing @ L10 | yes | Envelope | 10 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-10-12 | 2026-10-20 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-11-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L11 | yes | Envelope | 11 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-09-22 | 2026-09-30 | 7 | 3 | Building Structure | Exterior & Interior Masonry
Baseline | C-11-EX-100 | Install Exterior Glazing @ L11 | yes | Envelope | 11 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-10-21 | 2026-10-29 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-12-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L12 | yes | Envelope | 12 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-09 | 7 | 3 | Building Structure | Exterior & Interior Masonry
Baseline | C-12-EX-100 | Install Exterior Glazing @ L12 | yes | Envelope | 12 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-09 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-14-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L14 | yes | Envelope | 14 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-10-12 | 2026-10-20 | 7 | 3 | Building Structure | Exterior & Interior Masonry
Baseline | C-14-EX-100 | Install Exterior Glazing @ L14 | yes | Envelope | 14 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-11-10 | 2026-11-18 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-15-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L15 | yes | Envelope | 15 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-10-21 | 2026-10-29 | 7 | 3 | Building Structure | Exterior & Interior Masonry
Baseline | C-15-EX-100 | Install Exterior Glazing @ L15 | yes | Envelope | 15 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-11-19 | 2026-12-01 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-16-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L16 | yes | Envelope | 16 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-09 | 7 | 4 | Building Structure | Exterior & Interior Masonry
Baseline | C-16-EX-100 | Install Exterior Glazing @ L16 | yes | Envelope | 16 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-12-02 | 2026-12-10 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-17-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L17 | yes | Envelope | 17 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-11-10 | 2026-11-18 | 7 | 5 | Building Structure | Exterior & Interior Masonry
Baseline | C-17-EX-100 | Install Exterior Glazing @ L17 | yes | Envelope | 17 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-12-11 | 2026-12-21 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-18-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L18 | yes | Envelope | 18 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-11-19 | 2026-12-01 | 7 | 6 | Building Structure | Exterior & Interior Masonry
Baseline | C-18-EX-100 | Install Exterior Glazing @ L18 | yes | Envelope | 18 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-12-22 | 2026-12-31 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-19-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L19 | yes | Envelope | 19 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-12-02 | 2026-12-10 | 7 | 7 | Building Structure | Exterior & Interior Masonry
Baseline | C-19-EX-100 | Install Exterior Glazing @ L19 | yes | Envelope | 19 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-12 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-20-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L20 | yes | Envelope | 20 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-12-11 | 2026-12-21 | 7 | 8 | Building Structure | Exterior & Interior Masonry
Baseline | C-20-EX-100 | Install Exterior Glazing @ L20 | yes | Envelope | 20 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-01-13 | 2027-01-21 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-21-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L21 | yes | Envelope | 21 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-12-22 | 2026-12-31 | 7 | 9 | Building Structure | Exterior & Interior Masonry
Baseline | C-21-EX-100 | Install Exterior Glazing @ L21 | yes | Envelope | 21 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-01-22 | 2027-02-01 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-22-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L22 | yes | Envelope | 22 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-12 | 7 | 10 | Building Structure | Exterior & Interior Masonry
Baseline | C-22-EX-100 | Install Exterior Glazing @ L22 | yes | Envelope | 22 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-10 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-23-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L23 | yes | Envelope | 23 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-01-13 | 2027-01-21 | 7 | 11 | Building Structure | Exterior & Interior Masonry
Baseline | C-23-EX-100 | Install Exterior Glazing @ L23 | yes | Envelope | 23 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-19 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-24-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L24 | yes | Envelope | 24 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-01-22 | 2027-02-01 | 7 | 12 | Building Structure | Exterior & Interior Masonry
Baseline | C-24-EX-100 | Install Exterior Glazing @ L24 | yes | Envelope | 24 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-02-22 | 2027-03-02 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-25-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L25 | yes | Envelope | 25 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-10 | 7 | 13 | Building Structure | Exterior & Interior Masonry
Baseline | C-25-EX-100 | Install Exterior Glazing @ L25 | yes | Envelope | 25 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-11 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-26-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L26 | yes | Envelope | 26 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-19 | 7 | 13 | Building Structure | Exterior & Interior Masonry
Baseline | C-26-EX-100 | Install Exterior Glazing @ L26 | yes | Envelope | 26 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-03-12 | 2027-03-22 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-27-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L27 | yes | Envelope | 27 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-02-22 | 2027-03-02 | 7 | 13 | Building Structure | Exterior & Interior Masonry
Baseline | C-27-EX-100 | Install Exterior Glazing @ L27 | yes | Envelope | 27 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-03-23 | 2027-03-31 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-28-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L28 | yes | Envelope | 28 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-11 | 7 | 13 | Building Structure | Exterior & Interior Masonry
Baseline | C-28-EX-100 | Install Exterior Glazing @ L28 | yes | Envelope | 28 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-09 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-29-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L29 | yes | Envelope | 29 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-03-12 | 2027-03-22 | 7 | 13 | Building Structure | Exterior & Interior Masonry
Baseline | C-29-EX-100 | Install Exterior Glazing @ L29 | yes | Envelope | 29 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-04-12 | 2027-04-20 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-30-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L30 | yes | Envelope | 30 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-03-23 | 2027-03-31 | 7 | 13 | Building Structure | Exterior & Interior Masonry
Baseline | C-30-EX-100 | Install Exterior Glazing @ L30 | yes | Envelope | 30 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-04-21 | 2027-04-29 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-31-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L31 | yes | Envelope | 31 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-09 | 7 | 13 | Building Structure | Exterior & Interior Masonry
Baseline | C-31-EX-100 | Install Exterior Glazing @ L31 | yes | Envelope | 31 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-04-30 | 2027-05-10 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-32-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L32 | yes | Envelope | 32 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-04-12 | 2027-04-20 | 7 | 13 | Building Structure | Exterior & Interior Masonry
Baseline | C-32-EX-100 | Install Exterior Glazing @ L32 | yes | Envelope | 32 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-05-11 | 2027-05-19 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-33-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L33 | yes | Envelope | 33 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-04-21 | 2027-04-29 | 7 | 13 | Building Structure | Exterior & Interior Masonry
Baseline | C-33-EX-100 | Install Exterior Glazing @ L33 | yes | Envelope | 33 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-05-20 | 2027-05-28 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-34-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L34 | yes | Envelope | 34 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-04-30 | 2027-05-10 | 7 | 13 | Building Structure | Exterior & Interior Masonry
Baseline | C-34-EX-100 | Install Exterior Glazing @ L34 | yes | Envelope | 34 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-06-01 | 2027-06-09 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-35-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L35 | yes | Envelope | 35 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-05-11 | 2027-05-19 | 7 | 13 | Building Structure | Exterior & Interior Masonry
Baseline | C-35-EX-100 | Install Exterior Glazing @ L35 | yes | Envelope | 35 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-06-10 | 2027-06-18 | 7 | 15 | Exterior Envelope | Exterior Glazing
Baseline | C-36-ST-400 | Lay Exterior CMU Walls @ 36th Pool Lvl | yes | Envelope | 36 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-03-18 | 2027-03-24 | 5 | 90 | Building Structure | Exterior & Interior Masonry
Baseline | C-01-UC-FN-100 | Layout & Install Top Tracks @ Whole L1 | yes | Framing and MEP rough-in | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior Wall Framing & MEP Rough at Whole 1st Lvl > Wall Layout & Framing at Whole 1st Lvl | TT_Task | TK_NotStart | 2027-04-28 | 2027-04-29 | 2 | 14 | Interior MEPs & Finishes | Wall Layout & Framing
Baseline | C-01-UC-FN-120 | Install Drywall Framing & Furring @ Whole L1 | yes | Framing and MEP rough-in | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior Wall Framing & MEP Rough at Whole 1st Lvl > Wall Layout & Framing at Whole 1st Lvl | TT_Task | TK_NotStart | 2027-04-29 | 2027-05-19 | 15 | 14 | Interior MEPs & Finishes | Wall Layout & Framing
Baseline | C-01-UC-MP-140 | Install Plumbing Rough @ Whole L1 | yes | Framing and MEP rough-in | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior Wall Framing & MEP Rough at Whole 1st Lvl > MEP Rough at Whole 1st Lvl | TT_Task | TK_NotStart | 2027-05-06 | 2027-06-01 | 18 | 14 | Interior MEPs & Finishes | MEP Rough
Baseline | C-01-UC-MP-150 | Install FP Rough @ Whole L1 | yes | Framing and MEP rough-in | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior Wall Framing & MEP Rough at Whole 1st Lvl > MEP Rough at Whole 1st Lvl | TT_Task | TK_NotStart | 2027-05-18 | 2027-06-03 | 12 | 14 | Interior MEPs & Finishes | MEP Rough
Baseline | C-01-UC-FN-130 | Install Interior Door Frames @ Whole L1 | yes | Framing and MEP rough-in | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior Wall Framing & MEP Rough at Whole 1st Lvl > Wall Layout & Framing at Whole 1st Lvl | TT_Task | TK_NotStart | 2027-05-20 | 2027-05-24 | 3 | 53 | Interior MEPs & Finishes | Wall Layout & Framing
Baseline | C-01-UC-MP-160 | Install HVAC Ductwork @ Whole L1 | yes | Framing and MEP rough-in | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior Wall Framing & MEP Rough at Whole 1st Lvl > MEP Rough at Whole 1st Lvl | TT_Task | TK_NotStart | 2027-05-28 | 2027-06-25 | 20 | 14 | Interior MEPs & Finishes | MEP Rough
Baseline | C-01-UC-MP-170 | Install Electrical Rough @ Whole L1 | yes | Framing and MEP rough-in | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior Wall Framing & MEP Rough at Whole 1st Lvl > MEP Rough at Whole 1st Lvl | TT_Task | TK_NotStart | 2027-06-10 | 2027-06-30 | 15 | 14 | Interior MEPs & Finishes | MEP Rough
Baseline | C-01-UC-MP-180 | Install FA & Low Voltage Rough @ Whole L1 | yes | Framing and MEP rough-in | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior Wall Framing & MEP Rough at Whole 1st Lvl > MEP Rough at Whole 1st Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-07-09 | 8 | 14 | Interior MEPs & Finishes | MEP Rough
Baseline | C-01-UC-MP-190 | Inspect MEP Rough @ Whole L1 | yes | Framing and MEP rough-in | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior Wall Framing & MEP Rough at Whole 1st Lvl > MEP Rough at Whole 1st Lvl | TT_Task | TK_NotStart | 2027-07-12 | 2027-07-14 | 3 | 14 | Interior MEPs & Finishes | MEP Rough
Baseline | C-02-UC-FN-100 | Layout Interior Walls @ Units & Common Areas - L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > Wall Layout & Framing at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-06-11 | 2026-06-11 | 1 | 30 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Common Areas
Baseline | C-02-UC-FN-110 | Install Top Tracks @ Units & Common Areas - L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > Wall Layout & Framing at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-06-11 | 2026-06-12 | 2 | 30 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Common Areas
Baseline | C-02-UC-MP-100 | Install Plumbing Risers @ L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > MEP Rough at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-06-11 | 2026-06-15 | 3 | 30 | Interior MEPs & Finishes | MEP Rough at Units & Common Areas
Baseline | C-02-UC-FN-120 | Install Drywall Framing @ Units & Common Areas - L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > Wall Layout & Framing at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-06-15 | 2026-06-26 | 10 | 30 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Common Areas
Baseline | C-02-UC-MP-120 | Install FP Risers @ L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > MEP Rough at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-06-16 | 2026-06-17 | 2 | 31 | Interior MEPs & Finishes | MEP Rough at Units & Common Areas
Baseline | C-02-UC-MP-130 | Install Mech Risers @ L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > MEP Rough at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-06-18 | 2026-06-22 | 3 | 31 | Interior MEPs & Finishes | MEP Rough at Units & Common Areas
Baseline | C-02-UC-MP-140 | Install Plumbing Rough @ Units & Common Areas - L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > MEP Rough at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-06-22 | 2026-07-01 | 8 | 30 | Interior MEPs & Finishes | MEP Rough at Units & Common Areas
Baseline | C-02-UC-MP-150 | Install FP Rough @ Units & Common Areas - L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > MEP Rough at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-06-25 | 2026-07-09 | 10 | 30 | Interior MEPs & Finishes | MEP Rough at Units & Common Areas
Baseline | C-02-UC-FN-130 | Install Interior Door Frames @ Units & Common Areas - L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > Wall Layout & Framing at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-06-29 | 2026-07-01 | 3 | 48 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Common Areas
Baseline | C-02-UC-MP-160 | Install HVAC Ductwork @ Units & Common Areas - L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > MEP Rough at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-06-30 | 2026-07-16 | 12 | 30 | Interior MEPs & Finishes | MEP Rough at Units & Common Areas
Baseline | C-02-UC-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > MEP Rough at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-07-09 | 2026-07-14 | 4 | 19 | Interior MEPs & Finishes | MEP Rough at Units & Common Areas
Baseline | C-02-UC-MP-170 | Install Electrical Rough @ Units & Common Areas - L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > MEP Rough at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-07-15 | 2026-07-28 | 10 | 24 | Interior MEPs & Finishes | MEP Rough at Units & Common Areas
Baseline | C-02-UC-MP-180 | Install FA & Low Voltage Rough @ Units & Common Areas - L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > MEP Rough at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-07-23 | 2026-08-03 | 8 | 24 | Interior MEPs & Finishes | MEP Rough at Units & Common Areas
Baseline | C-02-UC-MP-190 | Inspect MEP Rough @ Units & Common Areas - L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > MEP Rough at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-04 | 2026-08-05 | 2 | 24 | Interior MEPs & Finishes | MEP Rough at Units & Common Areas
Baseline | C-03-U-FN-100 | Layout Interior Walls @ Units & Corridors - L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 3rd Lvl > Wall Layout & Framing at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-06-25 | 2026-06-26 | 2 | 8 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-03-U-MP-100 | Install Plumbing Risers @ L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 3rd Lvl > MEP Rough at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-06-25 | 2026-06-29 | 3 | 23 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-03-U-FN-110 | Install Top Tracks @ Units & Corridors - L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 3rd Lvl > Wall Layout & Framing at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-06-26 | 2026-06-29 | 2 | 8 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-03-U-FN-120 | Install Drywall Framing @ Units & Corridors - L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 3rd Lvl > Wall Layout & Framing at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-06-30 | 2026-07-14 | 10 | 8 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-03-U-MP-120 | Install FP Risers @ L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 3rd Lvl > MEP Rough at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-06-30 | 2026-07-01 | 2 | 24 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-03-U-MP-130 | Install Mech Risers @ L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 3rd Lvl > MEP Rough at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-07-02 | 2026-07-07 | 3 | 24 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-03-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 3rd Lvl > MEP Rough at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-07-08 | 2026-07-17 | 8 | 18 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-03-U-MP-150 | Install FP Rough @ Units & Corridors - L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 3rd Lvl > MEP Rough at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-07-13 | 2026-07-28 | 12 | 18 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-03-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 3rd Lvl > Wall Layout & Framing at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-07-15 | 2026-07-20 | 4 | 37 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-03-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 3rd Lvl > MEP Rough at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-07-15 | 2026-07-20 | 4 | 19 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-03-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 3rd Lvl > MEP Rough at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-07-16 | 2026-08-04 | 14 | 18 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-03-U-MP-170 | Install Electrical Rough @ Units & Corridors - L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 3rd Lvl > MEP Rough at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-07-22 | 2026-08-06 | 12 | 18 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-03-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 3rd Lvl > MEP Rough at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-03 | 2026-08-12 | 8 | 18 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-03-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 3rd Lvl > MEP Rough at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-13 | 2026-08-14 | 2 | 18 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-04-U-FN-100 | Layout Interior Walls @ Units & Corridors - L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > Wall Layout & Framing at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-07-10 | 2026-07-13 | 2 | 6 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-04-U-MP-100 | Install Plumbing Risers @ L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > MEP Rough at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-07-10 | 2026-07-14 | 3 | 26 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-04-U-FN-110 | Install Top Tracks @ Units & Corridors - L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > Wall Layout & Framing at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-07-13 | 2026-07-14 | 2 | 6 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-04-U-FN-120 | Install Drywall Framing @ Units & Corridors - L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > Wall Layout & Framing at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-07-15 | 2026-07-28 | 10 | 6 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-04-U-MP-120 | Install FP Risers @ L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > MEP Rough at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-07-15 | 2026-07-16 | 2 | 27 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-04-U-MP-130 | Install Mech Risers @ L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > MEP Rough at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-07-17 | 2026-07-21 | 3 | 27 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-04-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > MEP Rough at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-07-21 | 2026-07-24 | 4 | 25 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-04-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > MEP Rough at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-07-22 | 2026-07-31 | 8 | 21 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-04-U-MP-150 | Install FP Rough @ Units & Corridors - L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > MEP Rough at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-07-27 | 2026-08-11 | 12 | 21 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-04-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > Wall Layout & Framing at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-07-29 | 2026-08-03 | 4 | 40 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-04-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > MEP Rough at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-07-30 | 2026-08-18 | 14 | 21 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-04-U-MP-170 | Install Electrical Rough @ Units & Corridors - L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > MEP Rough at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-08-05 | 2026-08-20 | 12 | 21 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-04-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > MEP Rough at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-08-17 | 2026-08-26 | 8 | 21 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-04-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > MEP Rough at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-08-27 | 2026-08-28 | 2 | 21 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-05-U-FN-100 | Layout Interior Walls @ Units & Corridors - L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > Wall Layout & Framing at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-07-24 | 2026-07-27 | 2 | 4 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-05-U-MP-100 | Install Plumbing Risers @ L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > MEP Rough at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-07-24 | 2026-07-28 | 3 | 19 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-05-U-FN-110 | Install Top Tracks @ Units & Corridors - L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > Wall Layout & Framing at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-07-27 | 2026-07-28 | 2 | 4 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-05-U-FN-120 | Install Drywall Framing @ Units & Corridors - L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > Wall Layout & Framing at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-07-29 | 2026-08-11 | 10 | 4 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-05-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > MEP Rough at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-07-29 | 2026-08-03 | 4 | 23 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-05-U-MP-120 | Install FP Risers @ L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > MEP Rough at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-07-29 | 2026-07-30 | 2 | 20 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-05-U-MP-130 | Install Mech Risers @ L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > MEP Rough at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-07-31 | 2026-08-04 | 3 | 20 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-05-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > MEP Rough at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-08-05 | 2026-08-14 | 8 | 19 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-05-U-MP-150 | Install FP Rough @ Units & Corridors - L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > MEP Rough at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-08-10 | 2026-08-25 | 12 | 19 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-05-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > Wall Layout & Framing at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-08-12 | 2026-08-17 | 4 | 38 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-05-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > MEP Rough at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-08-13 | 2026-09-01 | 14 | 19 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-05-U-MP-170 | Install Electrical Rough @ Units & Corridors - L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > MEP Rough at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-08-19 | 2026-09-03 | 12 | 19 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-05-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > MEP Rough at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-08-31 | 2026-09-10 | 8 | 19 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-05-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > MEP Rough at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-09-11 | 2026-09-14 | 2 | 19 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-06-U-FN-100 | Layout Interior Walls @ Units & Corridors - L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > Wall Layout & Framing at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-08-07 | 2026-08-10 | 2 | 2 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-06-U-MP-100 | Install Plumbing Risers @ L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > MEP Rough at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-08-07 | 2026-08-11 | 3 | 12 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-06-U-FN-110 | Install Top Tracks @ Units & Corridors - L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > Wall Layout & Framing at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-08-10 | 2026-08-11 | 2 | 2 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-06-U-FN-120 | Install Drywall Framing @ Units & Corridors - L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > Wall Layout & Framing at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-08-12 | 2026-08-25 | 10 | 2 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-06-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > MEP Rough at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-08-12 | 2026-08-17 | 4 | 17 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-06-U-MP-120 | Install FP Risers @ L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > MEP Rough at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-08-12 | 2026-08-13 | 2 | 13 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-06-U-MP-130 | Install Mech Risers @ L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > MEP Rough at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-08-14 | 2026-08-18 | 3 | 13 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-06-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > MEP Rough at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-08-19 | 2026-08-28 | 8 | 17 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-06-U-MP-150 | Install FP Rough @ Units & Corridors - L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > MEP Rough at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-08-24 | 2026-09-09 | 12 | 17 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-06-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > Wall Layout & Framing at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-08-26 | 2026-08-31 | 4 | 36 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-06-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > MEP Rough at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-08-27 | 2026-09-16 | 14 | 17 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-06-U-MP-170 | Install Electrical Rough @ Units & Corridors - L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > MEP Rough at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-09-02 | 2026-09-18 | 12 | 17 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-06-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > MEP Rough at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-24 | 8 | 17 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-06-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > MEP Rough at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-09-25 | 2026-09-28 | 2 | 17 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-07-U-FN-100 | Layout Interior Walls @ Units & Corridors - L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > Wall Layout & Framing at Units & Corridors at 7th Lvl | TT_Task | TK_NotStart | 2026-08-21 | 2026-08-24 | 2 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-07-U-MP-100 | Install Plumbing Risers @ L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > MEP Rough at Units & Corridors at 7th Lvl | TT_Task | TK_NotStart | 2026-08-21 | 2026-08-25 | 3 | 5 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-07-U-FN-110 | Install Top Tracks @ Units & Corridors - L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > Wall Layout & Framing at Units & Corridors at 7th Lvl | TT_Task | TK_NotStart | 2026-08-24 | 2026-08-25 | 2 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-07-U-FN-120 | Install Drywall Framing @ Units & Corridors - L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > Wall Layout & Framing at Units & Corridors at 7th Lvl | TT_Task | TK_NotStart | 2026-08-26 | 2026-09-16 | 15 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-07-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > MEP Rough at Units & Corridors at 7th Lvl | TT_Task | TK_NotStart | 2026-08-26 | 2026-08-31 | 4 | 11 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-07-U-MP-120 | Install FP Risers @ L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > MEP Rough at Units & Corridors at 7th Lvl | TT_Task | TK_NotStart | 2026-08-26 | 2026-08-27 | 2 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-07-U-MP-130 | Install Mech Risers @ L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > MEP Rough at Units & Corridors at 7th Lvl | TT_Task | TK_NotStart | 2026-08-28 | 2026-09-01 | 3 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-07-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > MEP Rough at Units & Corridors at 7th Lvl | TT_Task | TK_NotStart | 2026-09-02 | 2026-09-14 | 8 | 0 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-07-U-MP-150 | Install FP Rough @ Units & Corridors - L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > MEP Rough at Units & Corridors at 7th Lvl | TT_Task | TK_NotStart | 2026-09-08 | 2026-09-23 | 12 | 0 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-07-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > MEP Rough at Units & Corridors at 7th Lvl | TT_Task | TK_NotStart | 2026-09-11 | 2026-09-30 | 14 | 0 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-07-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > Wall Layout & Framing at Units & Corridors at 7th Lvl | TT_Task | TK_NotStart | 2026-09-17 | 2026-09-23 | 5 | 13 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-07-U-MP-170 | Install Electrical Rough @ Units & Corridors - L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > MEP Rough at Units & Corridors at 7th Lvl | TT_Task | TK_NotStart | 2026-09-17 | 2026-10-02 | 12 | 0 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-07-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > MEP Rough at Units & Corridors at 7th Lvl | TT_Task | TK_NotStart | 2026-09-29 | 2026-10-08 | 8 | 0 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-07-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > MEP Rough at Units & Corridors at 7th Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-12 | 2 | 0 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-08-U-FN-100 | Layout Interior Walls @ Units & Corridors - L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > Wall Layout & Framing at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-09-01 | 2026-09-02 | 2 | 3 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-08-U-MP-100 | Install Plumbing Risers @ L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > MEP Rough at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-09-01 | 2026-09-03 | 3 | 8 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-08-U-FN-110 | Install Top Tracks @ Units & Corridors - L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > Wall Layout & Framing at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-09-02 | 2026-09-03 | 2 | 3 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-08-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > MEP Rough at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-09-04 | 2026-09-10 | 4 | 14 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-08-U-MP-120 | Install FP Risers @ L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > MEP Rough at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-09-04 | 2026-09-08 | 2 | 9 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-08-U-MP-130 | Install Mech Risers @ L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > MEP Rough at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-09-09 | 2026-09-11 | 3 | 9 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-08-U-FN-120 | Install Drywall Framing @ Units & Corridors - L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > Wall Layout & Framing at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-09-10 | 2026-09-25 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-08-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > MEP Rough at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-09-17 | 2026-09-28 | 8 | 0 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-08-U-MP-150 | Install FP Rough @ Units & Corridors - L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > MEP Rough at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-09-22 | 2026-10-07 | 12 | 0 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-08-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > MEP Rough at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-09-25 | 2026-10-14 | 14 | 0 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-08-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > Wall Layout & Framing at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-09-28 | 2026-10-02 | 5 | 16 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-08-U-MP-170 | Install Electrical Rough @ Units & Corridors - L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > MEP Rough at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-16 | 12 | 0 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-08-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > MEP Rough at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-10-13 | 2026-10-22 | 8 | 0 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-08-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > MEP Rough at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-10-23 | 2026-10-26 | 2 | 0 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-09-U-FN-100 | Layout Interior Walls @ Units & Corridors - L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > Wall Layout & Framing at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-09-11 | 2026-09-14 | 2 | 3 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-09-U-MP-100 | Install Plumbing Risers @ L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > MEP Rough at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-09-11 | 2026-09-15 | 3 | 9 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-09-U-FN-110 | Install Top Tracks @ Units & Corridors - L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > Wall Layout & Framing at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-09-14 | 2026-09-15 | 2 | 3 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-09-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > MEP Rough at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-09-16 | 2026-09-21 | 4 | 15 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-09-U-MP-120 | Install FP Risers @ L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > MEP Rough at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-09-16 | 2026-09-17 | 2 | 10 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-09-U-MP-130 | Install Mech Risers @ L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > MEP Rough at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-09-18 | 2026-09-22 | 3 | 10 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-09-U-FN-120 | Install Drywall Framing @ Units & Corridors - L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > Wall Layout & Framing at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-09-21 | 2026-10-06 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-09-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > MEP Rough at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-09-28 | 2026-10-07 | 8 | 1 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-09-U-MP-150 | Install FP Rough @ Units & Corridors - L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > MEP Rough at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-16 | 12 | 1 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-09-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > MEP Rough at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-23 | 14 | 1 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-09-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > Wall Layout & Framing at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-10-07 | 2026-10-13 | 5 | 17 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-09-U-MP-170 | Install Electrical Rough @ Units & Corridors - L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > MEP Rough at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-10-12 | 2026-10-27 | 12 | 1 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-09-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > MEP Rough at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-10-22 | 2026-11-02 | 8 | 1 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-09-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > MEP Rough at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-11-03 | 2026-11-04 | 2 | 1 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-10-U-FN-100 | Layout Interior Walls @ Units & Corridors - L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > Wall Layout & Framing at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-09-22 | 2026-09-23 | 2 | 3 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-10-U-MP-100 | Install Plumbing Risers @ L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > MEP Rough at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-09-22 | 2026-09-24 | 3 | 10 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-10-U-FN-110 | Install Top Tracks @ Units & Corridors - L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > Wall Layout & Framing at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-09-23 | 2026-09-24 | 2 | 3 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-10-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > MEP Rough at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-09-25 | 2026-09-30 | 4 | 16 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-10-U-MP-120 | Install FP Risers @ L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > MEP Rough at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-09-25 | 2026-09-28 | 2 | 11 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-10-U-MP-130 | Install Mech Risers @ L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > MEP Rough at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-09-29 | 2026-10-01 | 3 | 11 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-10-U-FN-120 | Install Drywall Framing @ Units & Corridors - L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > Wall Layout & Framing at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-09-30 | 2026-10-15 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-10-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > MEP Rough at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-10-07 | 2026-10-16 | 8 | 2 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-10-U-MP-150 | Install FP Rough @ Units & Corridors - L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > MEP Rough at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-10-12 | 2026-10-27 | 12 | 2 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-10-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > MEP Rough at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-11-03 | 14 | 2 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-10-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > Wall Layout & Framing at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-10-16 | 2026-10-22 | 5 | 18 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-10-U-MP-170 | Install Electrical Rough @ Units & Corridors - L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > MEP Rough at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-10-21 | 2026-11-05 | 12 | 2 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-10-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > MEP Rough at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-11-02 | 2026-11-11 | 8 | 2 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-10-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > MEP Rough at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-11-12 | 2026-11-13 | 2 | 2 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-11-U-FN-100 | Layout Interior Walls @ Units & Corridors - L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > Wall Layout & Framing at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-02 | 2 | 3 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-11-U-MP-100 | Install Plumbing Risers @ L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > MEP Rough at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-05 | 3 | 11 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-11-U-FN-110 | Install Top Tracks @ Units & Corridors - L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > Wall Layout & Framing at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-10-02 | 2026-10-05 | 2 | 3 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-11-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > MEP Rough at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-09 | 4 | 17 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-11-U-MP-120 | Install FP Risers @ L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > MEP Rough at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-07 | 2 | 12 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-11-U-MP-130 | Install Mech Risers @ L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > MEP Rough at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-10-08 | 2026-10-12 | 3 | 12 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-11-U-FN-120 | Install Drywall Framing @ Units & Corridors - L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > Wall Layout & Framing at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-26 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-11-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > MEP Rough at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-10-16 | 2026-10-27 | 8 | 3 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-11-U-MP-150 | Install FP Rough @ Units & Corridors - L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > MEP Rough at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-10-21 | 2026-11-05 | 12 | 3 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-11-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > MEP Rough at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-10-26 | 2026-11-12 | 14 | 3 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-11-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > Wall Layout & Framing at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-10-27 | 2026-11-02 | 5 | 19 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-11-U-MP-170 | Install Electrical Rough @ Units & Corridors - L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > MEP Rough at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-16 | 12 | 3 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-11-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > MEP Rough at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-11-11 | 2026-11-20 | 8 | 3 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-11-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > MEP Rough at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-11-23 | 2026-11-24 | 2 | 3 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-12-U-FN-100 | Layout Interior Walls @ Units & Corridors - L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > Wall Layout & Framing at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-10-12 | 2026-10-13 | 2 | 3 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-12-U-MP-100 | Install Plumbing Risers @ L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > MEP Rough at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-10-12 | 2026-10-14 | 3 | 12 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-12-U-FN-110 | Install Top Tracks @ Units & Corridors - L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > Wall Layout & Framing at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-10-13 | 2026-10-14 | 2 | 3 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-12-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > MEP Rough at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-20 | 4 | 18 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-12-U-MP-120 | Install FP Risers @ L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > MEP Rough at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-16 | 2 | 13 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-12-U-MP-130 | Install Mech Risers @ L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > MEP Rough at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-10-19 | 2026-10-21 | 3 | 13 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-12-U-FN-120 | Install Drywall Framing @ Units & Corridors - L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > Wall Layout & Framing at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-10-20 | 2026-11-04 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-12-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > MEP Rough at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-10-27 | 2026-11-05 | 8 | 4 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-12-U-MP-150 | Install FP Rough @ Units & Corridors - L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > MEP Rough at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-16 | 12 | 4 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-12-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > MEP Rough at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-23 | 14 | 4 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-12-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > Wall Layout & Framing at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-11-05 | 2026-11-11 | 5 | 20 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-12-U-MP-170 | Install Electrical Rough @ Units & Corridors - L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > MEP Rough at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-11-10 | 2026-11-25 | 12 | 4 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-12-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > MEP Rough at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-12-03 | 8 | 4 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-12-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > MEP Rough at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-12-04 | 2026-12-07 | 2 | 4 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-14-U-FN-100 | Layout Interior Walls @ Units & Corridors - L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > Wall Layout & Framing at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-10-21 | 2026-10-22 | 2 | 3 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-14-U-MP-100 | Install Plumbing Risers @ L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > MEP Rough at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-10-21 | 2026-10-23 | 3 | 13 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-14-U-FN-110 | Install Top Tracks @ Units & Corridors - L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > Wall Layout & Framing at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-10-22 | 2026-10-23 | 2 | 3 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-14-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > MEP Rough at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-10-26 | 2026-10-29 | 4 | 19 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-14-U-MP-120 | Install FP Risers @ L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > MEP Rough at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-10-26 | 2026-10-27 | 2 | 14 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-14-U-MP-130 | Install Mech Risers @ L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > MEP Rough at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-10-28 | 2026-10-30 | 3 | 14 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-14-U-FN-120 | Install Drywall Framing @ Units & Corridors - L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > Wall Layout & Framing at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-10-29 | 2026-11-13 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-14-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > MEP Rough at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-11-05 | 2026-11-16 | 8 | 5 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-14-U-MP-150 | Install FP Rough @ Units & Corridors - L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > MEP Rough at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-11-10 | 2026-11-25 | 12 | 5 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-14-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > MEP Rough at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-12-04 | 14 | 5 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-14-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > Wall Layout & Framing at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-11-16 | 2026-11-20 | 5 | 21 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-14-U-MP-170 | Install Electrical Rough @ Units & Corridors - L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > MEP Rough at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-11-19 | 2026-12-08 | 12 | 5 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-14-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > MEP Rough at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-14 | 8 | 5 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-14-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > MEP Rough at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-12-15 | 2026-12-16 | 2 | 5 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-15-U-FN-100 | Layout Interior Walls @ Units & Corridors - L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > Wall Layout & Framing at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-02 | 2 | 3 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-15-U-MP-100 | Install Plumbing Risers @ L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > MEP Rough at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-03 | 3 | 14 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-15-U-FN-110 | Install Top Tracks @ Units & Corridors - L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > Wall Layout & Framing at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-11-02 | 2026-11-03 | 2 | 3 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-15-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > MEP Rough at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-09 | 4 | 20 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-15-U-MP-120 | Install FP Risers @ L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > MEP Rough at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-05 | 2 | 15 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-15-U-MP-130 | Install Mech Risers @ L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > MEP Rough at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-11-06 | 2026-11-10 | 3 | 15 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-15-U-FN-120 | Install Drywall Framing @ Units & Corridors - L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > Wall Layout & Framing at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-24 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-15-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > MEP Rough at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-11-16 | 2026-11-25 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-15-U-MP-150 | Install FP Rough @ Units & Corridors - L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > MEP Rough at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-11-19 | 2026-12-08 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-15-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > MEP Rough at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-12-15 | 14 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-15-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > Wall Layout & Framing at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-11-25 | 2026-12-03 | 5 | 22 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-15-U-MP-170 | Install Electrical Rough @ Units & Corridors - L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > MEP Rough at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-12-02 | 2026-12-17 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-15-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > MEP Rough at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-12-14 | 2026-12-23 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-15-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > MEP Rough at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-12-24 | 2026-12-28 | 2 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-16-U-FN-100 | Layout Interior Walls @ Units & Corridors - L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > Wall Layout & Framing at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2026-11-10 | 2026-11-11 | 2 | 4 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-16-U-MP-100 | Install Plumbing Risers @ L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > MEP Rough at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2026-11-10 | 2026-11-12 | 3 | 15 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-16-U-FN-110 | Install Top Tracks @ Units & Corridors - L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > Wall Layout & Framing at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2026-11-11 | 2026-11-12 | 2 | 4 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-16-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > MEP Rough at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-18 | 4 | 21 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-16-U-MP-120 | Install FP Risers @ L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > MEP Rough at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-16 | 2 | 16 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-16-U-MP-130 | Install Mech Risers @ L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > MEP Rough at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2026-11-17 | 2026-11-19 | 3 | 16 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-16-U-FN-120 | Install Drywall Framing @ Units & Corridors - L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > Wall Layout & Framing at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2026-11-19 | 2026-12-08 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-16-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > MEP Rough at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2026-11-30 | 2026-12-09 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-16-U-MP-150 | Install FP Rough @ Units & Corridors - L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > MEP Rough at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-18 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-16-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > MEP Rough at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2026-12-08 | 2026-12-28 | 14 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-16-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > Wall Layout & Framing at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2026-12-09 | 2026-12-15 | 5 | 22 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-16-U-MP-170 | Install Electrical Rough @ Units & Corridors - L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > MEP Rough at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2026-12-14 | 2026-12-30 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-16-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > MEP Rough at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2026-12-24 | 2027-01-06 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-16-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > MEP Rough at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-08 | 2 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-17-U-FN-100 | Layout Interior Walls @ Units & Corridors - L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > Wall Layout & Framing at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2026-11-19 | 2026-11-20 | 2 | 5 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-17-U-MP-100 | Install Plumbing Risers @ L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > MEP Rough at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2026-11-19 | 2026-11-23 | 3 | 16 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-17-U-FN-110 | Install Top Tracks @ Units & Corridors - L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > Wall Layout & Framing at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-11-23 | 2 | 5 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-17-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > MEP Rough at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-12-01 | 4 | 22 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-17-U-MP-120 | Install FP Risers @ L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > MEP Rough at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-11-25 | 2 | 17 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-17-U-MP-130 | Install Mech Risers @ L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > MEP Rough at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2026-11-30 | 2026-12-02 | 3 | 17 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-17-U-FN-120 | Install Drywall Framing @ Units & Corridors - L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > Wall Layout & Framing at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-18 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-17-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > MEP Rough at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-21 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-17-U-MP-150 | Install FP Rough @ Units & Corridors - L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > MEP Rough at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2026-12-15 | 2026-12-31 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-17-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > MEP Rough at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2026-12-18 | 2027-01-08 | 14 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-17-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > Wall Layout & Framing at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2026-12-21 | 2026-12-28 | 5 | 22 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-17-U-MP-170 | Install Electrical Rough @ Units & Corridors - L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > MEP Rough at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2026-12-24 | 2027-01-12 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-17-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > MEP Rough at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-18 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-17-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > MEP Rough at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2027-01-19 | 2027-01-20 | 2 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-18-U-FN-100 | Layout Interior Walls @ Units & Corridors - L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > Wall Layout & Framing at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2026-12-02 | 2026-12-03 | 2 | 6 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-18-U-MP-100 | Install Plumbing Risers @ L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > MEP Rough at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2026-12-02 | 2026-12-04 | 3 | 17 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-18-U-FN-110 | Install Top Tracks @ Units & Corridors - L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > Wall Layout & Framing at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-04 | 2 | 6 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-18-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > MEP Rough at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-10 | 4 | 23 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-18-U-MP-120 | Install FP Risers @ L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > MEP Rough at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-08 | 2 | 18 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-18-U-MP-130 | Install Mech Risers @ L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > MEP Rough at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2026-12-09 | 2026-12-11 | 3 | 18 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-18-U-FN-120 | Install Drywall Framing @ Units & Corridors - L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > Wall Layout & Framing at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2026-12-15 | 2026-12-31 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-18-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > MEP Rough at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2026-12-22 | 2027-01-04 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-18-U-MP-150 | Install FP Rough @ Units & Corridors - L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > MEP Rough at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2027-01-13 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-18-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > MEP Rough at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2026-12-31 | 2027-01-20 | 14 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-18-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > Wall Layout & Framing at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-08 | 5 | 22 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-18-U-MP-170 | Install Electrical Rough @ Units & Corridors - L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > MEP Rough at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-22 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-18-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > MEP Rough at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2027-01-19 | 2027-01-28 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-18-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > MEP Rough at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2027-01-29 | 2027-02-01 | 2 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-19-U-FN-100 | Layout Interior Walls @ Units & Corridors - L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > Wall Layout & Framing at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2026-12-11 | 2026-12-14 | 2 | 7 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-19-U-MP-100 | Install Plumbing Risers @ L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > MEP Rough at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2026-12-11 | 2026-12-15 | 3 | 18 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-19-U-FN-110 | Install Top Tracks @ Units & Corridors - L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > Wall Layout & Framing at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2026-12-14 | 2026-12-15 | 2 | 7 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-19-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > MEP Rough at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2026-12-16 | 2026-12-21 | 4 | 24 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-19-U-MP-120 | Install FP Risers @ L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > MEP Rough at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2026-12-16 | 2026-12-17 | 2 | 19 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-19-U-MP-130 | Install Mech Risers @ L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > MEP Rough at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2026-12-18 | 2026-12-22 | 3 | 19 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-19-U-FN-120 | Install Drywall Framing @ Units & Corridors - L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > Wall Layout & Framing at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2027-01-13 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-19-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > MEP Rough at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2027-01-05 | 2027-01-14 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-19-U-MP-150 | Install FP Rough @ Units & Corridors - L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > MEP Rough at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2027-01-08 | 2027-01-25 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-19-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > MEP Rough at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2027-01-13 | 2027-02-01 | 14 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-19-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > Wall Layout & Framing at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2027-01-14 | 2027-01-20 | 5 | 22 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-19-U-MP-170 | Install Electrical Rough @ Units & Corridors - L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > MEP Rough at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2027-01-19 | 2027-02-03 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-19-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > MEP Rough at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2027-01-29 | 2027-02-09 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-19-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > MEP Rough at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2027-02-10 | 2027-02-11 | 2 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-20-U-FN-100 | Layout Interior Walls @ Units & Corridors - L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > Wall Layout & Framing at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2026-12-22 | 2026-12-23 | 2 | 8 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-20-U-MP-100 | Install Plumbing Risers @ L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > MEP Rough at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2026-12-22 | 2026-12-24 | 3 | 19 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-20-U-FN-110 | Install Top Tracks @ Units & Corridors - L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > Wall Layout & Framing at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2026-12-23 | 2026-12-24 | 2 | 8 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-20-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > MEP Rough at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2026-12-31 | 4 | 25 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-20-U-MP-120 | Install FP Risers @ L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > MEP Rough at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2026-12-29 | 2 | 20 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-20-U-MP-130 | Install Mech Risers @ L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > MEP Rough at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2026-12-30 | 2027-01-04 | 3 | 20 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-20-U-FN-120 | Install Drywall Framing @ Units & Corridors - L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > Wall Layout & Framing at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2027-01-08 | 2027-01-25 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-20-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > MEP Rough at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2027-01-15 | 2027-01-26 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-20-U-MP-150 | Install FP Rough @ Units & Corridors - L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > MEP Rough at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-02-04 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-20-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > MEP Rough at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2027-01-25 | 2027-02-11 | 14 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-20-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > Wall Layout & Framing at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2027-01-26 | 2027-02-01 | 5 | 22 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-20-U-MP-170 | Install Electrical Rough @ Units & Corridors - L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > MEP Rough at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2027-01-29 | 2027-02-15 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-20-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > MEP Rough at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2027-02-10 | 2027-02-19 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-20-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > MEP Rough at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2027-02-22 | 2027-02-23 | 2 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-21-U-FN-100 | Layout Interior Walls @ Units & Corridors - L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > Wall Layout & Framing at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-05 | 2 | 9 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-21-U-MP-100 | Install Plumbing Risers @ L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > MEP Rough at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-06 | 3 | 20 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-21-U-FN-110 | Install Top Tracks @ Units & Corridors - L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > Wall Layout & Framing at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2027-01-05 | 2027-01-06 | 2 | 9 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-21-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > MEP Rough at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-12 | 4 | 26 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-21-U-MP-120 | Install FP Risers @ L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > MEP Rough at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-08 | 2 | 21 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-21-U-MP-130 | Install Mech Risers @ L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > MEP Rough at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2027-01-11 | 2027-01-13 | 3 | 21 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-21-U-FN-120 | Install Drywall Framing @ Units & Corridors - L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > Wall Layout & Framing at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-02-04 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-21-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > MEP Rough at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-02-05 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-21-U-MP-150 | Install FP Rough @ Units & Corridors - L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > MEP Rough at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2027-02-01 | 2027-02-16 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-21-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > MEP Rough at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2027-02-04 | 2027-02-23 | 14 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-21-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > Wall Layout & Framing at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-11 | 5 | 22 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-21-U-MP-170 | Install Electrical Rough @ Units & Corridors - L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > MEP Rough at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2027-02-10 | 2027-02-25 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-21-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > MEP Rough at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2027-02-22 | 2027-03-03 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-21-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > MEP Rough at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2027-03-04 | 2027-03-05 | 2 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-22-U-FN-100 | Layout Interior Walls @ Units & Corridors - L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > Wall Layout & Framing at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2027-01-13 | 2027-01-14 | 2 | 10 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-22-U-MP-100 | Install Plumbing Risers @ L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > MEP Rough at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2027-01-13 | 2027-01-15 | 3 | 21 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-22-U-FN-110 | Install Top Tracks @ Units & Corridors - L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > Wall Layout & Framing at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2027-01-14 | 2027-01-15 | 2 | 10 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-22-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > MEP Rough at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-21 | 4 | 27 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-22-U-MP-120 | Install FP Risers @ L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > MEP Rough at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-19 | 2 | 22 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-22-U-MP-130 | Install Mech Risers @ L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > MEP Rough at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-01-22 | 3 | 22 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-22-U-FN-120 | Install Drywall Framing @ Units & Corridors - L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > Wall Layout & Framing at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2027-02-01 | 2027-02-16 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-22-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > MEP Rough at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2027-02-08 | 2027-02-17 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-22-U-MP-150 | Install FP Rough @ Units & Corridors - L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > MEP Rough at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-26 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-22-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > MEP Rough at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-03-05 | 14 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-22-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > Wall Layout & Framing at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2027-02-17 | 2027-02-23 | 5 | 22 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-22-U-MP-170 | Install Electrical Rough @ Units & Corridors - L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > MEP Rough at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2027-02-22 | 2027-03-09 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-22-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > MEP Rough at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-04 | 2027-03-15 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-22-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > MEP Rough at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-16 | 2027-03-17 | 2 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-23-U-FN-100 | Layout Interior Walls @ Units & Corridors - L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > Wall Layout & Framing at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2027-01-22 | 2027-01-25 | 2 | 11 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-23-U-MP-100 | Install Plumbing Risers @ L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > MEP Rough at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2027-01-22 | 2027-01-26 | 3 | 22 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-23-U-FN-110 | Install Top Tracks @ Units & Corridors - L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > Wall Layout & Framing at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2027-01-25 | 2027-01-26 | 2 | 11 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-23-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > MEP Rough at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-02-01 | 4 | 28 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-23-U-MP-120 | Install FP Risers @ L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > MEP Rough at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-01-28 | 2 | 23 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-23-U-MP-130 | Install Mech Risers @ L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > MEP Rough at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2027-01-29 | 2027-02-02 | 3 | 23 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-23-U-FN-120 | Install Drywall Framing @ Units & Corridors - L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > Wall Layout & Framing at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-26 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-23-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > MEP Rough at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2027-02-18 | 2027-03-01 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-23-U-MP-150 | Install FP Rough @ Units & Corridors - L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > MEP Rough at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-03-10 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-23-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > MEP Rough at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2027-02-26 | 2027-03-17 | 14 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-23-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > Wall Layout & Framing at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-01 | 2027-03-05 | 5 | 22 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-23-U-MP-170 | Install Electrical Rough @ Units & Corridors - L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > MEP Rough at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-04 | 2027-03-19 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-23-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > MEP Rough at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-16 | 2027-03-25 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-23-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > MEP Rough at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-03-29 | 2 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-24-U-FN-100 | Layout Interior Walls @ Units & Corridors - L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > Wall Layout & Framing at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-03 | 2 | 12 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-24-U-MP-100 | Install Plumbing Risers @ L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > MEP Rough at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-04 | 3 | 23 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-24-U-FN-110 | Install Top Tracks @ Units & Corridors - L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > Wall Layout & Framing at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2027-02-03 | 2027-02-04 | 2 | 12 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-24-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > MEP Rough at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-10 | 4 | 29 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-24-U-MP-120 | Install FP Risers @ L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > MEP Rough at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-08 | 2 | 24 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-24-U-MP-130 | Install Mech Risers @ L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > MEP Rough at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-11 | 3 | 24 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-24-U-FN-120 | Install Drywall Framing @ Units & Corridors - L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > Wall Layout & Framing at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-03-10 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-24-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > MEP Rough at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2027-03-02 | 2027-03-11 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-24-U-MP-150 | Install FP Rough @ Units & Corridors - L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > MEP Rough at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2027-03-05 | 2027-03-22 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-24-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > MEP Rough at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2027-03-10 | 2027-03-29 | 14 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-24-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > Wall Layout & Framing at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-17 | 5 | 22 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-24-U-MP-170 | Install Electrical Rough @ Units & Corridors - L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > MEP Rough at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2027-03-16 | 2027-03-31 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-24-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > MEP Rough at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-04-06 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-24-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > MEP Rough at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2027-04-07 | 2027-04-08 | 2 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-25-U-FN-100 | Layout Interior Walls @ Units & Corridors - L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > Wall Layout & Framing at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-12 | 2 | 13 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-25-U-MP-100 | Install Plumbing Risers @ L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > MEP Rough at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-15 | 3 | 24 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-25-U-FN-110 | Install Top Tracks @ Units & Corridors - L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > Wall Layout & Framing at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2027-02-12 | 2027-02-15 | 2 | 13 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-25-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > MEP Rough at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-19 | 4 | 30 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-25-U-MP-120 | Install FP Risers @ L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > MEP Rough at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-17 | 2 | 25 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-25-U-MP-130 | Install Mech Risers @ L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > MEP Rough at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2027-02-18 | 2027-02-22 | 3 | 25 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-25-U-FN-120 | Install Drywall Framing @ Units & Corridors - L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > Wall Layout & Framing at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2027-03-05 | 2027-03-22 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-25-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > MEP Rough at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2027-03-12 | 2027-03-23 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-25-U-MP-150 | Install FP Rough @ Units & Corridors - L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > MEP Rough at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-04-01 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-25-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > MEP Rough at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2027-03-22 | 2027-04-08 | 14 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-25-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > Wall Layout & Framing at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2027-03-23 | 2027-03-29 | 5 | 22 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-25-U-MP-170 | Install Electrical Rough @ Units & Corridors - L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > MEP Rough at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-04-12 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-25-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > MEP Rough at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2027-04-07 | 2027-04-16 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-25-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > MEP Rough at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2027-04-19 | 2027-04-20 | 2 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-26-U-FN-100 | Layout Interior Walls @ Units & Corridors - L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > Wall Layout & Framing at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2027-02-22 | 2027-02-23 | 2 | 13 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-26-U-MP-100 | Install Plumbing Risers @ L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > MEP Rough at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2027-02-22 | 2027-02-24 | 3 | 25 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-26-U-FN-110 | Install Top Tracks @ Units & Corridors - L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > Wall Layout & Framing at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-02-24 | 2 | 13 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-26-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > MEP Rough at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-03-02 | 4 | 31 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-26-U-MP-120 | Install FP Risers @ L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > MEP Rough at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-02-26 | 2 | 26 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-26-U-MP-130 | Install Mech Risers @ L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > MEP Rough at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2027-03-01 | 2027-03-03 | 3 | 26 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-26-U-FN-120 | Install Drywall Framing @ Units & Corridors - L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > Wall Layout & Framing at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2027-03-16 | 2027-03-31 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-26-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > MEP Rough at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2027-03-23 | 2027-04-01 | 8 | 7 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-26-U-MP-150 | Install FP Rough @ Units & Corridors - L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > MEP Rough at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-04-12 | 12 | 7 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-26-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > MEP Rough at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2027-03-31 | 2027-04-19 | 14 | 7 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-26-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > Wall Layout & Framing at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-07 | 5 | 23 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-26-U-MP-170 | Install Electrical Rough @ Units & Corridors - L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > MEP Rough at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-21 | 12 | 7 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-26-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > MEP Rough at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2027-04-16 | 2027-04-27 | 8 | 7 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-26-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > MEP Rough at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2027-04-28 | 2027-04-29 | 2 | 7 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-27-U-FN-100 | Layout Interior Walls @ Units & Corridors - L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > Wall Layout & Framing at Units & Corridors at 27th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-04 | 2 | 13 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-27-U-MP-100 | Install Plumbing Risers @ L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > MEP Rough at Units & Corridors at 27th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-05 | 3 | 26 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-27-U-FN-110 | Install Top Tracks @ Units & Corridors - L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > Wall Layout & Framing at Units & Corridors at 27th Lvl | TT_Task | TK_NotStart | 2027-03-04 | 2027-03-05 | 2 | 13 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-27-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > MEP Rough at Units & Corridors at 27th Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-11 | 4 | 32 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-27-U-MP-120 | Install FP Risers @ L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > MEP Rough at Units & Corridors at 27th Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-09 | 2 | 27 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-27-U-MP-130 | Install Mech Risers @ L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > MEP Rough at Units & Corridors at 27th Lvl | TT_Task | TK_NotStart | 2027-03-10 | 2027-03-12 | 3 | 27 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-27-U-FN-120 | Install Drywall Framing @ Units & Corridors - L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > Wall Layout & Framing at Units & Corridors at 27th Lvl | TT_Task | TK_NotStart | 2027-03-25 | 2027-04-09 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-27-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > MEP Rough at Units & Corridors at 27th Lvl | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-12 | 8 | 8 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-27-U-MP-150 | Install FP Rough @ Units & Corridors - L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > MEP Rough at Units & Corridors at 27th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-21 | 12 | 8 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-27-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > MEP Rough at Units & Corridors at 27th Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-28 | 14 | 8 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-27-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > Wall Layout & Framing at Units & Corridors at 27th Lvl | TT_Task | TK_NotStart | 2027-04-12 | 2027-04-16 | 5 | 24 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-27-U-MP-170 | Install Electrical Rough @ Units & Corridors - L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > MEP Rough at Units & Corridors at 27th Lvl | TT_Task | TK_NotStart | 2027-04-15 | 2027-04-30 | 12 | 8 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-27-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > MEP Rough at Units & Corridors at 27th Lvl | TT_Task | TK_NotStart | 2027-04-27 | 2027-05-06 | 8 | 8 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-27-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > MEP Rough at Units & Corridors at 27th Lvl | TT_Task | TK_NotStart | 2027-05-07 | 2027-05-10 | 2 | 8 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-28-U-FN-100 | Layout Interior Walls @ Units & Corridors - L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > Wall Layout & Framing at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2027-03-12 | 2027-03-15 | 2 | 13 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-28-U-MP-100 | Install Plumbing Risers @ L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > MEP Rough at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2027-03-12 | 2027-03-16 | 3 | 27 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-28-U-FN-110 | Install Top Tracks @ Units & Corridors - L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > Wall Layout & Framing at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2027-03-15 | 2027-03-16 | 2 | 13 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-28-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > MEP Rough at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-22 | 4 | 33 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-28-U-MP-120 | Install FP Risers @ L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > MEP Rough at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-18 | 2 | 28 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-28-U-MP-130 | Install Mech Risers @ L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > MEP Rough at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2027-03-19 | 2027-03-23 | 3 | 28 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-28-U-FN-120 | Install Drywall Framing @ Units & Corridors - L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > Wall Layout & Framing at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2027-04-05 | 2027-04-20 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-28-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > MEP Rough at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2027-04-12 | 2027-04-21 | 8 | 9 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-28-U-MP-150 | Install FP Rough @ Units & Corridors - L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > MEP Rough at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2027-04-15 | 2027-04-30 | 12 | 9 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-28-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > MEP Rough at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2027-04-20 | 2027-05-07 | 14 | 9 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-28-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > Wall Layout & Framing at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2027-04-21 | 2027-04-27 | 5 | 25 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-28-U-MP-170 | Install Electrical Rough @ Units & Corridors - L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > MEP Rough at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-05-11 | 12 | 9 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-28-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > MEP Rough at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2027-05-06 | 2027-05-17 | 8 | 9 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-28-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > MEP Rough at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2027-05-18 | 2027-05-19 | 2 | 9 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-29-U-FN-100 | Layout Interior Walls @ Units & Corridors - L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > Wall Layout & Framing at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2027-03-23 | 2027-03-24 | 2 | 13 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-29-U-MP-100 | Install Plumbing Risers @ L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > MEP Rough at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2027-03-23 | 2027-03-25 | 3 | 28 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-29-U-FN-110 | Install Top Tracks @ Units & Corridors - L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > Wall Layout & Framing at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-25 | 2 | 13 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-29-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > MEP Rough at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-03-31 | 4 | 34 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-29-U-MP-120 | Install FP Risers @ L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > MEP Rough at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-03-29 | 2 | 29 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-29-U-MP-130 | Install Mech Risers @ L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > MEP Rough at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2027-03-30 | 2027-04-01 | 3 | 29 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-29-U-FN-120 | Install Drywall Framing @ Units & Corridors - L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > Wall Layout & Framing at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2027-04-14 | 2027-04-29 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-29-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > MEP Rough at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2027-04-21 | 2027-04-30 | 8 | 10 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-29-U-MP-150 | Install FP Rough @ Units & Corridors - L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > MEP Rough at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-05-11 | 12 | 10 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-29-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > MEP Rough at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2027-04-29 | 2027-05-18 | 14 | 10 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-29-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > Wall Layout & Framing at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2027-04-30 | 2027-05-06 | 5 | 26 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-29-U-MP-170 | Install Electrical Rough @ Units & Corridors - L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > MEP Rough at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-20 | 12 | 10 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-29-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > MEP Rough at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2027-05-17 | 2027-05-26 | 8 | 10 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-29-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > MEP Rough at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2027-05-27 | 2027-05-28 | 2 | 10 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-30-U-FN-100 | Layout Interior Walls @ Units & Corridors - L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > Wall Layout & Framing at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-02 | 2 | 13 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-30-U-MP-100 | Install Plumbing Risers @ L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > MEP Rough at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-05 | 3 | 29 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-30-U-FN-110 | Install Top Tracks @ Units & Corridors - L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > Wall Layout & Framing at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2027-04-02 | 2027-04-05 | 2 | 13 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-30-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > MEP Rough at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-09 | 4 | 35 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-30-U-MP-120 | Install FP Risers @ L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > MEP Rough at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-07 | 2 | 30 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-30-U-MP-130 | Install Mech Risers @ L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > MEP Rough at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2027-04-08 | 2027-04-12 | 3 | 30 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-30-U-FN-120 | Install Drywall Framing @ Units & Corridors - L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > Wall Layout & Framing at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2027-04-23 | 2027-05-10 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-30-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > MEP Rough at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2027-04-30 | 2027-05-11 | 8 | 11 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-30-U-MP-150 | Install FP Rough @ Units & Corridors - L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > MEP Rough at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-20 | 12 | 11 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-30-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > MEP Rough at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-27 | 14 | 11 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-30-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > Wall Layout & Framing at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2027-05-11 | 2027-05-17 | 5 | 27 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-30-U-MP-170 | Install Electrical Rough @ Units & Corridors - L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > MEP Rough at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2027-05-14 | 2027-06-01 | 12 | 11 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-30-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > MEP Rough at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2027-05-26 | 2027-06-07 | 8 | 11 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-30-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > MEP Rough at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2027-06-08 | 2027-06-09 | 2 | 11 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-31-U-FN-100 | Layout Interior Walls @ Units & Corridors - L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > Wall Layout & Framing at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-04-12 | 2027-04-13 | 2 | 13 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-31-U-MP-100 | Install Plumbing Risers @ L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > MEP Rough at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-04-12 | 2027-04-14 | 3 | 30 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-31-U-FN-110 | Install Top Tracks @ Units & Corridors - L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > Wall Layout & Framing at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-04-13 | 2027-04-14 | 2 | 13 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-31-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > MEP Rough at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-04-15 | 2027-04-20 | 4 | 36 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-31-U-MP-120 | Install FP Risers @ L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > MEP Rough at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-04-15 | 2027-04-16 | 2 | 31 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-31-U-MP-130 | Install Mech Risers @ L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > MEP Rough at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-04-19 | 2027-04-21 | 3 | 31 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-31-U-FN-120 | Install Drywall Framing @ Units & Corridors - L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > Wall Layout & Framing at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-05-04 | 2027-05-19 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-31-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > MEP Rough at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-05-11 | 2027-05-20 | 8 | 12 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-31-U-MP-150 | Install FP Rough @ Units & Corridors - L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > MEP Rough at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-05-14 | 2027-06-01 | 12 | 12 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-31-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > MEP Rough at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-06-08 | 14 | 12 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-31-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > Wall Layout & Framing at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-05-20 | 2027-05-26 | 5 | 28 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-31-U-MP-170 | Install Electrical Rough @ Units & Corridors - L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > MEP Rough at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-06-10 | 12 | 12 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-31-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > MEP Rough at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-06-07 | 2027-06-16 | 8 | 12 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-31-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > MEP Rough at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-06-17 | 2027-06-18 | 2 | 12 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-32-U-FN-100 | Layout Interior Walls @ Units & Corridors - L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > Wall Layout & Framing at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-04-21 | 2027-04-22 | 2 | 13 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-32-U-MP-100 | Install Plumbing Risers @ L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > MEP Rough at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-04-21 | 2027-04-23 | 3 | 28 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-32-U-FN-110 | Install Top Tracks @ Units & Corridors - L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > Wall Layout & Framing at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-04-22 | 2027-04-23 | 2 | 13 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-32-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > MEP Rough at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-04-29 | 4 | 33 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-32-U-MP-120 | Install FP Risers @ L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > MEP Rough at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-04-27 | 2 | 29 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-32-U-MP-130 | Install Mech Risers @ L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > MEP Rough at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-04-28 | 2027-04-30 | 3 | 29 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-32-U-FN-120 | Install Drywall Framing @ Units & Corridors - L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > Wall Layout & Framing at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-05-13 | 2027-05-28 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-32-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > MEP Rough at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-05-20 | 2027-06-01 | 8 | 10 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-32-U-MP-150 | Install FP Rough @ Units & Corridors - L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > MEP Rough at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-06-10 | 12 | 10 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-32-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > MEP Rough at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-05-28 | 2027-06-17 | 14 | 10 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-32-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > Wall Layout & Framing at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-01 | 2027-06-07 | 5 | 26 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-32-U-MP-170 | Install Electrical Rough @ Units & Corridors - L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > MEP Rough at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-04 | 2027-06-21 | 12 | 10 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-32-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > MEP Rough at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-16 | 2027-06-25 | 8 | 10 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-32-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > MEP Rough at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-28 | 2027-06-29 | 2 | 10 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-33-U-FN-100 | Layout Interior Walls @ Units & Corridors - L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > Wall Layout & Framing at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-04-30 | 2027-05-03 | 2 | 13 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-33-U-MP-100 | Install Plumbing Risers @ L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > MEP Rough at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-04-30 | 2027-05-04 | 3 | 26 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-33-U-FN-110 | Install Top Tracks @ Units & Corridors - L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > Wall Layout & Framing at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-05-03 | 2027-05-04 | 2 | 13 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-33-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > MEP Rough at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-10 | 4 | 30 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-33-U-MP-120 | Install FP Risers @ L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > MEP Rough at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-06 | 2 | 27 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-33-U-MP-130 | Install Mech Risers @ L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > MEP Rough at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-05-07 | 2027-05-11 | 3 | 27 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-33-U-FN-120 | Install Drywall Framing @ Units & Corridors - L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > Wall Layout & Framing at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-05-24 | 2027-06-09 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-33-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > MEP Rough at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-06-01 | 2027-06-10 | 8 | 8 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-33-U-MP-150 | Install FP Rough @ Units & Corridors - L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > MEP Rough at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-06-04 | 2027-06-21 | 12 | 8 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-33-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > MEP Rough at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-06-09 | 2027-06-28 | 14 | 8 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-33-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > Wall Layout & Framing at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-06-10 | 2027-06-16 | 5 | 24 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-33-U-MP-170 | Install Electrical Rough @ Units & Corridors - L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > MEP Rough at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-06-15 | 2027-06-30 | 12 | 8 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-33-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > MEP Rough at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-06-25 | 2027-07-07 | 8 | 8 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-33-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > MEP Rough at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-08 | 2027-07-09 | 2 | 8 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-34-U-FN-100 | Layout Interior Walls @ Units & Corridors - L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > Wall Layout & Framing at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-05-11 | 2027-05-12 | 2 | 13 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-34-U-MP-100 | Install Plumbing Risers @ L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > MEP Rough at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-05-11 | 2027-05-13 | 3 | 22 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-34-U-FN-110 | Install Top Tracks @ Units & Corridors - L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > Wall Layout & Framing at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-05-12 | 2027-05-13 | 2 | 13 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-34-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > MEP Rough at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-05-14 | 2027-05-19 | 4 | 27 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-34-U-MP-120 | Install FP Risers @ L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > MEP Rough at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-05-14 | 2027-05-17 | 2 | 23 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-34-U-MP-130 | Install Mech Risers @ L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > MEP Rough at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-05-18 | 2027-05-20 | 3 | 23 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-34-U-FN-120 | Install Drywall Framing @ Units & Corridors - L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > Wall Layout & Framing at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-06-03 | 2027-06-18 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-34-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > MEP Rough at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-06-10 | 2027-06-21 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-34-U-MP-150 | Install FP Rough @ Units & Corridors - L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > MEP Rough at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-06-15 | 2027-06-30 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-34-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > MEP Rough at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-06-18 | 2027-07-08 | 14 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-34-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > Wall Layout & Framing at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-06-21 | 2027-06-25 | 5 | 22 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-34-U-MP-170 | Install Electrical Rough @ Units & Corridors - L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > MEP Rough at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-07-12 | 12 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-34-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > MEP Rough at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-07-07 | 2027-07-16 | 8 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-34-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > MEP Rough at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-07-19 | 2027-07-20 | 2 | 6 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-35-U-FN-100 | Layout Interior Walls @ Units & Corridors - L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > Wall Layout & Framing at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-05-20 | 2027-05-21 | 2 | 13 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-35-U-MP-100 | Install Plumbing Risers @ L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > MEP Rough at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-05-20 | 2027-05-24 | 3 | 18 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-35-U-FN-110 | Install Top Tracks @ Units & Corridors - L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > Wall Layout & Framing at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-05-21 | 2027-05-24 | 2 | 13 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-35-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > MEP Rough at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-05-28 | 4 | 24 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-35-U-MP-120 | Install FP Risers @ L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > MEP Rough at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-05-26 | 2 | 19 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-35-U-MP-130 | Install Mech Risers @ L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > MEP Rough at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-05-27 | 2027-06-01 | 3 | 19 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-35-U-FN-120 | Install Drywall Framing @ Units & Corridors - L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > Wall Layout & Framing at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-06-14 | 2027-06-29 | 12 | 0 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-35-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > MEP Rough at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-06-21 | 2027-06-30 | 8 | 0 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-35-U-MP-150 | Install FP Rough @ Units & Corridors - L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > MEP Rough at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-07-12 | 12 | 0 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-35-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > MEP Rough at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-07-19 | 14 | 0 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-35-U-FN-130 | Install Interior Door Frames @ Units & Corridors - L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > Wall Layout & Framing at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-06-30 | 2027-07-07 | 5 | 16 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Baseline | C-35-U-MP-170 | Install Electrical Rough @ Units & Corridors - L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > MEP Rough at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-07-06 | 2027-07-21 | 12 | 0 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-35-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > MEP Rough at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-07-16 | 2027-07-27 | 8 | 0 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-35-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > MEP Rough at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-07-28 | 2027-07-29 | 2 | 0 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Baseline | C-36-IN-MP-100 | Install Plumbing Risers @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > MEP Rough at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-03-25 | 2027-03-29 | 3 | 93 | Interior MEPs & Finishes | MEP Rough at Indoor
Baseline | C-36-IN-MP-110 | Install Electrical & Low Voltage & BDA Risers @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > MEP Rough at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-03-30 | 2027-04-02 | 4 | 99 | Interior MEPs & Finishes | MEP Rough at Indoor
Baseline | C-36-IN-MP-120 | Install FP Risers @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > MEP Rough at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-03-30 | 2027-03-31 | 2 | 94 | Interior MEPs & Finishes | MEP Rough at Indoor
Baseline | C-36-IN-MP-130 | Install Mech Risers @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > MEP Rough at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-05 | 3 | 94 | Interior MEPs & Finishes | MEP Rough at Indoor
Baseline | C-36-IN-FN-100 | Layout Interior Walls @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > Wall Layout & Framing at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-02 | 2027-06-02 | 1 | 42 | Interior MEPs & Finishes | Wall Layout & Framing at Indoor
Baseline | C-36-IN-FN-110 | Install Top Tracks @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > Wall Layout & Framing at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-02 | 2027-06-02 | 1 | 42 | Interior MEPs & Finishes | Wall Layout & Framing at Indoor
Baseline | C-36-IN-FN-120 | Install Drywall Framing @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > Wall Layout & Framing at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-03 | 2027-06-14 | 8 | 42 | Interior MEPs & Finishes | Wall Layout & Framing at Indoor
Baseline | C-36-IN-FN-130 | Install Interior Door Frames @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > Wall Layout & Framing at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-15 | 2027-06-16 | 2 | 59 | Interior MEPs & Finishes | Wall Layout & Framing at Indoor
Baseline | C-36-IN-MP-140 | Install Plumbing Rough @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > MEP Rough at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-23 | 2027-07-02 | 8 | 33 | Interior MEPs & Finishes | MEP Rough at Indoor
Baseline | C-36-IN-MP-150 | Install FP Rough @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > MEP Rough at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-28 | 2027-07-06 | 6 | 33 | Interior MEPs & Finishes | MEP Rough at Indoor
Baseline | C-36-IN-MP-160 | Install HVAC Ductwork @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > MEP Rough at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-13 | 8 | 33 | Interior MEPs & Finishes | MEP Rough at Indoor
Baseline | C-36-IN-MP-170 | Install Electrical Rough @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > MEP Rough at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-07-08 | 2027-07-19 | 8 | 33 | Interior MEPs & Finishes | MEP Rough at Indoor
Baseline | C-36-IN-MP-180 | Install FA & Low Voltage Rough @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > MEP Rough at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-07-14 | 2027-07-21 | 6 | 33 | Interior MEPs & Finishes | MEP Rough at Indoor
Baseline | C-01-UC-FN-200 | Install Drywall One Side & Insulation @ L1 | yes | Drywall and prime paint | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Interior Finishes at 1st Lvl | TT_Task | TK_NotStart | 2027-07-20 | 2027-07-26 | 5 | 15 | Interior MEPs & Finishes | Interior Finishes
Baseline | C-01-UC-FN-210 | Hang Drywall @ L1 | yes | Drywall and prime paint | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Interior Finishes at 1st Lvl | TT_Task | TK_NotStart | 2027-07-27 | 2027-08-05 | 8 | 15 | Interior MEPs & Finishes | Interior Finishes
Baseline | C-01-UC-FN-230 | Tape & Finish Drywall @ L1 | yes | Drywall and prime paint | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Interior Finishes at 1st Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-09 | 6 | 15 | Interior MEPs & Finishes | Interior Finishes
Baseline | C-01-UC-FN-270 | Paint Drywall - 1st Coat @ L1 | yes | Drywall and prime paint | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Interior Finishes at 1st Lvl | TT_Task | TK_NotStart | 2027-08-05 | 2027-08-11 | 5 | 18 | Interior MEPs & Finishes | Interior Finishes
Baseline | C-01-UC-FN-260 | Hang Interior Doors @ L1 | yes | Drywall and prime paint | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Interior Finishes at 1st Lvl | TT_Task | TK_NotStart | 2027-08-12 | 2027-08-13 | 2 | 31 | Interior MEPs & Finishes | Interior Finishes
Baseline | C-02-UC-FN-200 | Install Drywall One Side & Insulation @ Units & Common Areas - L2 | yes | Drywall and prime paint | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-06 | 2026-08-12 | 5 | 24 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Baseline | C-02-UC-FN-210 | Hang Drywall @ Units & Common Areas - L2 | yes | Drywall and prime paint | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-13 | 2026-08-24 | 8 | 24 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Baseline | C-02-UC-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units & Common Areas - L2 | yes | Drywall and prime paint | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-19 | 2026-08-28 | 8 | 24 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Baseline | C-02-UC-FN-230 | Tape & Finish Drywall @ Units & Common Areas - L2 | yes | Drywall and prime paint | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-19 | 2026-08-26 | 6 | 34 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Baseline | C-02-UC-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units & Common Areas - L2 | yes | Drywall and prime paint | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-27 | 2026-09-08 | 8 | 24 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Baseline | C-02-UC-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units & Common Areas - L2 | yes | Drywall and prime paint | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-04 | 2026-09-14 | 6 | 24 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Baseline | C-02-UC-FN-260 | Hang Interior Doors @ Units & Common Areas - L2 | yes | Drywall and prime paint | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-11 | 2026-09-15 | 3 | 24 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Baseline | C-02-UC-FN-270 | Paint Drywall - 1st Coat @ Units & Common Areas - L2 | yes | Drywall and prime paint | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-18 | 4 | 24 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Baseline | C-03-U-FN-200 | Install Drywall One Side & Insulation @ Units - L3 | yes | Drywall and prime paint | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-17 | 2026-08-21 | 5 | 18 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-03-U-FN-210 | Hang Drywall @ Units - L3 | yes | Drywall and prime paint | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-24 | 2026-09-02 | 8 | 18 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-03-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L3 | yes | Drywall and prime paint | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-28 | 2026-09-09 | 8 | 18 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-03-U-FN-230 | Tape & Finish Drywall @ Units - L3 | yes | Drywall and prime paint | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-28 | 2026-09-04 | 6 | 28 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-03-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L3 | yes | Drywall and prime paint | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-08 | 2026-09-17 | 8 | 18 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-03-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L3 | yes | Drywall and prime paint | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-16 | 2026-09-23 | 6 | 18 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-03-U-FN-260 | Hang Interior Doors @ Units - L3 | yes | Drywall and prime paint | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-22 | 2026-09-24 | 3 | 18 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-03-U-FN-270 | Paint Drywall - 1st Coat @ Units - L3 | yes | Drywall and prime paint | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-24 | 2026-09-29 | 4 | 18 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-04-U-FN-200 | Install Drywall One Side & Insulation @ Units - L4 | yes | Drywall and prime paint | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-08-31 | 2026-09-04 | 5 | 21 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-04-U-FN-210 | Hang Drywall @ Units - L4 | yes | Drywall and prime paint | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-09-08 | 2026-09-17 | 8 | 21 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-04-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L4 | yes | Drywall and prime paint | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-09-14 | 2026-09-23 | 8 | 21 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-04-U-FN-230 | Tape & Finish Drywall @ Units - L4 | yes | Drywall and prime paint | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-09-14 | 2026-09-21 | 6 | 31 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-04-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L4 | yes | Drywall and prime paint | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-09-22 | 2026-10-01 | 8 | 21 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-04-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L4 | yes | Drywall and prime paint | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-09-30 | 2026-10-07 | 6 | 21 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-04-U-FN-260 | Hang Interior Doors @ Units - L4 | yes | Drywall and prime paint | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-08 | 3 | 21 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-04-U-FN-270 | Paint Drywall - 1st Coat @ Units - L4 | yes | Drywall and prime paint | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-10-08 | 2026-10-13 | 4 | 21 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-05-U-FN-200 | Install Drywall One Side & Insulation @ Units - L5 | yes | Drywall and prime paint | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-21 | 5 | 19 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-05-U-FN-210 | Hang Drywall @ Units - L5 | yes | Drywall and prime paint | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-09-22 | 2026-10-01 | 8 | 19 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-05-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L5 | yes | Drywall and prime paint | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-09-28 | 2026-10-07 | 8 | 19 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-05-U-FN-230 | Tape & Finish Drywall @ Units - L5 | yes | Drywall and prime paint | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-09-28 | 2026-10-05 | 6 | 29 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-05-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L5 | yes | Drywall and prime paint | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-15 | 8 | 19 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-05-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L5 | yes | Drywall and prime paint | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-10-14 | 2026-10-21 | 6 | 19 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-05-U-FN-260 | Hang Interior Doors @ Units - L5 | yes | Drywall and prime paint | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-10-20 | 2026-10-22 | 3 | 19 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-05-U-FN-270 | Paint Drywall - 1st Coat @ Units - L5 | yes | Drywall and prime paint | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-10-22 | 2026-10-27 | 4 | 19 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-06-U-FN-200 | Install Drywall One Side & Insulation @ Units - L6 | yes | Drywall and prime paint | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-09-29 | 2026-10-05 | 5 | 17 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-06-U-FN-210 | Hang Drywall @ Units - L6 | yes | Drywall and prime paint | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-15 | 8 | 17 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-06-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L6 | yes | Drywall and prime paint | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-10-12 | 2026-10-21 | 8 | 17 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-06-U-FN-230 | Tape & Finish Drywall @ Units - L6 | yes | Drywall and prime paint | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-10-12 | 2026-10-19 | 6 | 27 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-06-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L6 | yes | Drywall and prime paint | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-10-20 | 2026-10-29 | 8 | 17 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-06-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L6 | yes | Drywall and prime paint | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-10-28 | 2026-11-04 | 6 | 17 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-06-U-FN-260 | Hang Interior Doors @ Units - L6 | yes | Drywall and prime paint | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-11-03 | 2026-11-05 | 3 | 17 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-06-U-FN-270 | Paint Drywall - 1st Coat @ Units - L6 | yes | Drywall and prime paint | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-11-05 | 2026-11-10 | 4 | 17 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-07-U-FN-200 | Install Drywall One Side & Insulation @ Units - L7 | yes | Drywall and prime paint | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-10-13 | 2026-10-21 | 7 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-07-U-FN-210 | Hang Drywall @ Units - L7 | yes | Drywall and prime paint | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-10-22 | 2026-11-04 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-07-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L7 | yes | Drywall and prime paint | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-12 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-07-U-FN-230 | Tape & Finish Drywall @ Units - L7 | yes | Drywall and prime paint | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-10 | 8 | 14 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-07-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L7 | yes | Drywall and prime paint | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-11-11 | 2026-11-24 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-07-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L7 | yes | Drywall and prime paint | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-11-23 | 2026-12-04 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-07-U-FN-260 | Hang Interior Doors @ Units - L7 | yes | Drywall and prime paint | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-08 | 4 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-07-U-FN-270 | Paint Drywall - 1st Coat @ Units - L7 | yes | Drywall and prime paint | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-12-08 | 2026-12-14 | 5 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-08-U-FN-200 | Install Drywall One Side & Insulation @ Units - L8 | yes | Drywall and prime paint | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-10-27 | 2026-11-04 | 7 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-08-U-FN-210 | Hang Drywall @ Units - L8 | yes | Drywall and prime paint | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-11-05 | 2026-11-18 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-08-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L8 | yes | Drywall and prime paint | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-30 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-08-U-FN-230 | Tape & Finish Drywall @ Units - L8 | yes | Drywall and prime paint | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-24 | 8 | 14 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-08-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L8 | yes | Drywall and prime paint | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-11-25 | 2026-12-10 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-08-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L8 | yes | Drywall and prime paint | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-12-09 | 2026-12-18 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-08-U-FN-260 | Hang Interior Doors @ Units - L8 | yes | Drywall and prime paint | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-12-17 | 2026-12-22 | 4 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-08-U-FN-270 | Paint Drywall - 1st Coat @ Units - L8 | yes | Drywall and prime paint | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-12-22 | 2026-12-29 | 5 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-09-U-FN-200 | Install Drywall One Side & Insulation @ Units - L9 | yes | Drywall and prime paint | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-11-05 | 2026-11-13 | 7 | 1 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-09-U-FN-210 | Hang Drywall @ Units - L9 | yes | Drywall and prime paint | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-11-16 | 2026-12-01 | 10 | 1 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-09-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L9 | yes | Drywall and prime paint | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-12-09 | 10 | 1 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-09-U-FN-230 | Tape & Finish Drywall @ Units - L9 | yes | Drywall and prime paint | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-12-07 | 8 | 15 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-09-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L9 | yes | Drywall and prime paint | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-12-08 | 2026-12-21 | 10 | 1 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-09-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L9 | yes | Drywall and prime paint | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-12-18 | 2026-12-30 | 8 | 1 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-09-U-FN-260 | Hang Interior Doors @ Units - L9 | yes | Drywall and prime paint | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-12-29 | 2027-01-04 | 4 | 1 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-09-U-FN-270 | Paint Drywall - 1st Coat @ Units - L9 | yes | Drywall and prime paint | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-08 | 5 | 1 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-10-U-FN-200 | Install Drywall One Side & Insulation @ Units - L10 | yes | Drywall and prime paint | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-11-16 | 2026-11-24 | 7 | 2 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-10-U-FN-210 | Hang Drywall @ Units - L10 | yes | Drywall and prime paint | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-11-25 | 2026-12-10 | 10 | 2 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-10-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L10 | yes | Drywall and prime paint | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-18 | 10 | 2 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-10-U-FN-230 | Tape & Finish Drywall @ Units - L10 | yes | Drywall and prime paint | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-16 | 8 | 16 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-10-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L10 | yes | Drywall and prime paint | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-12-17 | 2026-12-31 | 10 | 2 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-10-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L10 | yes | Drywall and prime paint | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-12-30 | 2027-01-11 | 8 | 2 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-10-U-FN-260 | Hang Interior Doors @ Units - L10 | yes | Drywall and prime paint | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2027-01-08 | 2027-01-13 | 4 | 2 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-10-U-FN-270 | Paint Drywall - 1st Coat @ Units - L10 | yes | Drywall and prime paint | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2027-01-13 | 2027-01-19 | 5 | 2 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-11-U-FN-200 | Install Drywall One Side & Insulation @ Units - L11 | yes | Drywall and prime paint | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-11-25 | 2026-12-07 | 7 | 3 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-11-U-FN-210 | Hang Drywall @ Units - L11 | yes | Drywall and prime paint | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-12-08 | 2026-12-21 | 10 | 3 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-11-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L11 | yes | Drywall and prime paint | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-12-16 | 2026-12-30 | 10 | 3 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-11-U-FN-230 | Tape & Finish Drywall @ Units - L11 | yes | Drywall and prime paint | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-12-16 | 2026-12-28 | 8 | 17 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-11-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L11 | yes | Drywall and prime paint | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-12-29 | 2027-01-12 | 10 | 3 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-11-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L11 | yes | Drywall and prime paint | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2027-01-11 | 2027-01-20 | 8 | 3 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-11-U-FN-260 | Hang Interior Doors @ Units - L11 | yes | Drywall and prime paint | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2027-01-19 | 2027-01-22 | 4 | 3 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-11-U-FN-270 | Paint Drywall - 1st Coat @ Units - L11 | yes | Drywall and prime paint | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2027-01-22 | 2027-01-28 | 5 | 3 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-12-U-FN-200 | Install Drywall One Side & Insulation @ Units - L12 | yes | Drywall and prime paint | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-12-08 | 2026-12-16 | 7 | 4 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-12-U-FN-210 | Hang Drywall @ Units - L12 | yes | Drywall and prime paint | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-12-17 | 2026-12-31 | 10 | 4 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-12-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L12 | yes | Drywall and prime paint | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2027-01-11 | 10 | 4 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-12-U-FN-230 | Tape & Finish Drywall @ Units - L12 | yes | Drywall and prime paint | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2027-01-07 | 8 | 18 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-12-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L12 | yes | Drywall and prime paint | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2027-01-08 | 2027-01-21 | 10 | 4 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-12-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L12 | yes | Drywall and prime paint | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-01-29 | 8 | 4 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-12-U-FN-260 | Hang Interior Doors @ Units - L12 | yes | Drywall and prime paint | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2027-01-28 | 2027-02-02 | 4 | 4 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-12-U-FN-270 | Paint Drywall - 1st Coat @ Units - L12 | yes | Drywall and prime paint | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-08 | 5 | 4 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-14-U-FN-200 | Install Drywall One Side & Insulation @ Units - L14 | yes | Drywall and prime paint | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2026-12-17 | 2026-12-28 | 7 | 5 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-14-U-FN-210 | Hang Drywall @ Units - L14 | yes | Drywall and prime paint | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2026-12-29 | 2027-01-12 | 10 | 5 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-14-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L14 | yes | Drywall and prime paint | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-20 | 10 | 5 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-14-U-FN-230 | Tape & Finish Drywall @ Units - L14 | yes | Drywall and prime paint | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-18 | 8 | 19 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-14-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L14 | yes | Drywall and prime paint | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-01-19 | 2027-02-01 | 10 | 5 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-14-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L14 | yes | Drywall and prime paint | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-01-29 | 2027-02-09 | 8 | 5 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-14-U-FN-260 | Hang Interior Doors @ Units - L14 | yes | Drywall and prime paint | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-02-08 | 2027-02-11 | 4 | 5 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-14-U-FN-270 | Paint Drywall - 1st Coat @ Units - L14 | yes | Drywall and prime paint | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-17 | 5 | 5 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-15-U-FN-200 | Install Drywall One Side & Insulation @ Units - L15 | yes | Drywall and prime paint | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2026-12-29 | 2027-01-07 | 7 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-15-U-FN-210 | Hang Drywall @ Units - L15 | yes | Drywall and prime paint | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-01-08 | 2027-01-21 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-15-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L15 | yes | Drywall and prime paint | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-29 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-15-U-FN-230 | Tape & Finish Drywall @ Units - L15 | yes | Drywall and prime paint | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-27 | 8 | 20 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-15-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L15 | yes | Drywall and prime paint | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-01-28 | 2027-02-10 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-15-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L15 | yes | Drywall and prime paint | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-18 | 8 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-15-U-FN-260 | Hang Interior Doors @ Units - L15 | yes | Drywall and prime paint | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-02-17 | 2027-02-22 | 4 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-15-U-FN-270 | Paint Drywall - 1st Coat @ Units - L15 | yes | Drywall and prime paint | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-02-22 | 2027-02-26 | 5 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-16-U-FN-200 | Install Drywall One Side & Insulation @ Units - L16 | yes | Drywall and prime paint | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-01-11 | 2027-01-19 | 7 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-16-U-FN-210 | Hang Drywall @ Units - L16 | yes | Drywall and prime paint | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-02-02 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-16-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L16 | yes | Drywall and prime paint | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-01-28 | 2027-02-10 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-16-U-FN-230 | Tape & Finish Drywall @ Units - L16 | yes | Drywall and prime paint | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-01-28 | 2027-02-08 | 8 | 20 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-16-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L16 | yes | Drywall and prime paint | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-22 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-16-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L16 | yes | Drywall and prime paint | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-02-19 | 2027-03-02 | 8 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-16-U-FN-260 | Hang Interior Doors @ Units - L16 | yes | Drywall and prime paint | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-03-01 | 2027-03-04 | 4 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-16-U-FN-270 | Paint Drywall - 1st Coat @ Units - L16 | yes | Drywall and prime paint | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-03-04 | 2027-03-10 | 5 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-17-U-FN-200 | Install Drywall One Side & Insulation @ Units - L17 | yes | Drywall and prime paint | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-01-21 | 2027-01-29 | 7 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-17-U-FN-210 | Hang Drywall @ Units - L17 | yes | Drywall and prime paint | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-02-01 | 2027-02-12 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-17-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L17 | yes | Drywall and prime paint | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-22 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-17-U-FN-230 | Tape & Finish Drywall @ Units - L17 | yes | Drywall and prime paint | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-18 | 8 | 20 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-17-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L17 | yes | Drywall and prime paint | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-02-19 | 2027-03-04 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-17-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L17 | yes | Drywall and prime paint | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-12 | 8 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-17-U-FN-260 | Hang Interior Doors @ Units - L17 | yes | Drywall and prime paint | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-16 | 4 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-17-U-FN-270 | Paint Drywall - 1st Coat @ Units - L17 | yes | Drywall and prime paint | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-03-16 | 2027-03-22 | 5 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-18-U-FN-200 | Install Drywall One Side & Insulation @ Units - L18 | yes | Drywall and prime paint | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-10 | 7 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-18-U-FN-210 | Hang Drywall @ Units - L18 | yes | Drywall and prime paint | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-24 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-18-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L18 | yes | Drywall and prime paint | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-02-19 | 2027-03-04 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-18-U-FN-230 | Tape & Finish Drywall @ Units - L18 | yes | Drywall and prime paint | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-02-19 | 2027-03-02 | 8 | 20 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-18-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L18 | yes | Drywall and prime paint | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-16 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-18-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L18 | yes | Drywall and prime paint | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-03-15 | 2027-03-24 | 8 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-18-U-FN-260 | Hang Interior Doors @ Units - L18 | yes | Drywall and prime paint | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-03-23 | 2027-03-26 | 4 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-18-U-FN-270 | Paint Drywall - 1st Coat @ Units - L18 | yes | Drywall and prime paint | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-04-01 | 5 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-19-U-FN-200 | Install Drywall One Side & Insulation @ Units - L19 | yes | Drywall and prime paint | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-02-12 | 2027-02-22 | 7 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-19-U-FN-210 | Hang Drywall @ Units - L19 | yes | Drywall and prime paint | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-03-08 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-19-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L19 | yes | Drywall and prime paint | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-16 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-19-U-FN-230 | Tape & Finish Drywall @ Units - L19 | yes | Drywall and prime paint | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-12 | 8 | 20 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-19-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L19 | yes | Drywall and prime paint | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-03-15 | 2027-03-26 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-19-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L19 | yes | Drywall and prime paint | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-03-25 | 2027-04-05 | 8 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-19-U-FN-260 | Hang Interior Doors @ Units - L19 | yes | Drywall and prime paint | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-04-02 | 2027-04-07 | 4 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-19-U-FN-270 | Paint Drywall - 1st Coat @ Units - L19 | yes | Drywall and prime paint | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-04-07 | 2027-04-13 | 5 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-20-U-FN-200 | Install Drywall One Side & Insulation @ Units - L20 | yes | Drywall and prime paint | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-02-24 | 2027-03-04 | 7 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-20-U-FN-210 | Hang Drywall @ Units - L20 | yes | Drywall and prime paint | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-03-05 | 2027-03-18 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-20-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L20 | yes | Drywall and prime paint | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-03-15 | 2027-03-26 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-20-U-FN-230 | Tape & Finish Drywall @ Units - L20 | yes | Drywall and prime paint | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-03-15 | 2027-03-24 | 8 | 20 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-20-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L20 | yes | Drywall and prime paint | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-03-25 | 2027-04-07 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-20-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L20 | yes | Drywall and prime paint | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-15 | 8 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-20-U-FN-260 | Hang Interior Doors @ Units - L20 | yes | Drywall and prime paint | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-04-14 | 2027-04-19 | 4 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-20-U-FN-270 | Paint Drywall - 1st Coat @ Units - L20 | yes | Drywall and prime paint | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-04-19 | 2027-04-23 | 5 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-21-U-FN-200 | Install Drywall One Side & Insulation @ Units - L21 | yes | Drywall and prime paint | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-16 | 7 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-21-U-FN-210 | Hang Drywall @ Units - L21 | yes | Drywall and prime paint | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-30 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-21-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L21 | yes | Drywall and prime paint | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-03-25 | 2027-04-07 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-21-U-FN-230 | Tape & Finish Drywall @ Units - L21 | yes | Drywall and prime paint | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-03-25 | 2027-04-05 | 8 | 20 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-21-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L21 | yes | Drywall and prime paint | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-19 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-21-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L21 | yes | Drywall and prime paint | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-04-16 | 2027-04-27 | 8 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-21-U-FN-260 | Hang Interior Doors @ Units - L21 | yes | Drywall and prime paint | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-04-29 | 4 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-21-U-FN-270 | Paint Drywall - 1st Coat @ Units - L21 | yes | Drywall and prime paint | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-04-29 | 2027-05-05 | 5 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-22-U-FN-200 | Install Drywall One Side & Insulation @ Units - L22 | yes | Drywall and prime paint | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-18 | 2027-03-26 | 7 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-22-U-FN-210 | Hang Drywall @ Units - L22 | yes | Drywall and prime paint | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-29 | 2027-04-09 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-22-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L22 | yes | Drywall and prime paint | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-19 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-22-U-FN-230 | Tape & Finish Drywall @ Units - L22 | yes | Drywall and prime paint | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-15 | 8 | 20 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-22-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L22 | yes | Drywall and prime paint | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-04-16 | 2027-04-29 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-22-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L22 | yes | Drywall and prime paint | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-04-28 | 2027-05-07 | 8 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-22-U-FN-260 | Hang Interior Doors @ Units - L22 | yes | Drywall and prime paint | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-05-06 | 2027-05-11 | 4 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-22-U-FN-270 | Paint Drywall - 1st Coat @ Units - L22 | yes | Drywall and prime paint | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-05-11 | 2027-05-17 | 5 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-23-U-FN-200 | Install Drywall One Side & Insulation @ Units - L23 | yes | Drywall and prime paint | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-30 | 2027-04-07 | 7 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-23-U-FN-210 | Hang Drywall @ Units - L23 | yes | Drywall and prime paint | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-04-08 | 2027-04-21 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-23-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L23 | yes | Drywall and prime paint | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-04-16 | 2027-04-29 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-23-U-FN-230 | Tape & Finish Drywall @ Units - L23 | yes | Drywall and prime paint | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-04-16 | 2027-04-27 | 8 | 20 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-23-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L23 | yes | Drywall and prime paint | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-04-28 | 2027-05-11 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-23-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L23 | yes | Drywall and prime paint | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-19 | 8 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-23-U-FN-260 | Hang Interior Doors @ Units - L23 | yes | Drywall and prime paint | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-05-18 | 2027-05-21 | 4 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-23-U-FN-270 | Paint Drywall - 1st Coat @ Units - L23 | yes | Drywall and prime paint | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-05-21 | 2027-05-27 | 5 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-24-U-FN-200 | Install Drywall One Side & Insulation @ Units - L24 | yes | Drywall and prime paint | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-19 | 7 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-24-U-FN-210 | Hang Drywall @ Units - L24 | yes | Drywall and prime paint | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-04-20 | 2027-05-03 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-24-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L24 | yes | Drywall and prime paint | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-04-28 | 2027-05-11 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-24-U-FN-230 | Tape & Finish Drywall @ Units - L24 | yes | Drywall and prime paint | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-04-28 | 2027-05-07 | 8 | 20 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-24-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L24 | yes | Drywall and prime paint | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-21 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-24-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L24 | yes | Drywall and prime paint | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-05-20 | 2027-06-01 | 8 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-24-U-FN-260 | Hang Interior Doors @ Units - L24 | yes | Drywall and prime paint | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-05-28 | 2027-06-03 | 4 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-24-U-FN-270 | Paint Drywall - 1st Coat @ Units - L24 | yes | Drywall and prime paint | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-06-03 | 2027-06-09 | 5 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-25-U-FN-200 | Install Drywall One Side & Insulation @ Units - L25 | yes | Drywall and prime paint | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-04-21 | 2027-04-29 | 7 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-25-U-FN-210 | Hang Drywall @ Units - L25 | yes | Drywall and prime paint | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-04-30 | 2027-05-13 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-25-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L25 | yes | Drywall and prime paint | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-21 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-25-U-FN-230 | Tape & Finish Drywall @ Units - L25 | yes | Drywall and prime paint | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-19 | 8 | 20 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-25-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L25 | yes | Drywall and prime paint | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-05-20 | 2027-06-03 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-25-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L25 | yes | Drywall and prime paint | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-06-02 | 2027-06-11 | 8 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-25-U-FN-260 | Hang Interior Doors @ Units - L25 | yes | Drywall and prime paint | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-06-10 | 2027-06-15 | 4 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-25-U-FN-270 | Paint Drywall - 1st Coat @ Units - L25 | yes | Drywall and prime paint | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-06-15 | 2027-06-21 | 5 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-26-U-FN-200 | Install Drywall One Side & Insulation @ Units - L26 | yes | Drywall and prime paint | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-04-30 | 2027-05-10 | 7 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-26-U-FN-210 | Hang Drywall @ Units - L26 | yes | Drywall and prime paint | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-05-11 | 2027-05-24 | 10 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-26-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L26 | yes | Drywall and prime paint | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-06-02 | 10 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-26-U-FN-230 | Tape & Finish Drywall @ Units - L26 | yes | Drywall and prime paint | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-05-28 | 8 | 21 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-26-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L26 | yes | Drywall and prime paint | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-06-01 | 2027-06-14 | 10 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-26-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L26 | yes | Drywall and prime paint | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-06-11 | 2027-06-22 | 8 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-26-U-FN-260 | Hang Interior Doors @ Units - L26 | yes | Drywall and prime paint | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-06-21 | 2027-06-24 | 4 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-26-U-FN-270 | Paint Drywall - 1st Coat @ Units - L26 | yes | Drywall and prime paint | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-30 | 5 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-27-U-FN-200 | Install Drywall One Side & Insulation @ Units - L27 | yes | Drywall and prime paint | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-05-11 | 2027-05-19 | 7 | 8 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-27-U-FN-210 | Hang Drywall @ Units - L27 | yes | Drywall and prime paint | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-05-20 | 2027-06-03 | 10 | 8 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-27-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L27 | yes | Drywall and prime paint | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-05-28 | 2027-06-11 | 10 | 8 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-27-U-FN-230 | Tape & Finish Drywall @ Units - L27 | yes | Drywall and prime paint | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-05-28 | 2027-06-09 | 8 | 22 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-27-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L27 | yes | Drywall and prime paint | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-06-10 | 2027-06-23 | 10 | 8 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-27-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L27 | yes | Drywall and prime paint | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-06-22 | 2027-07-01 | 8 | 8 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-27-U-FN-260 | Hang Interior Doors @ Units - L27 | yes | Drywall and prime paint | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-06-30 | 2027-07-06 | 4 | 8 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-27-U-FN-270 | Paint Drywall - 1st Coat @ Units - L27 | yes | Drywall and prime paint | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-07-06 | 2027-07-12 | 5 | 8 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-28-U-FN-200 | Install Drywall One Side & Insulation @ Units - L28 | yes | Drywall and prime paint | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-05-20 | 2027-05-28 | 7 | 9 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-28-U-FN-210 | Hang Drywall @ Units - L28 | yes | Drywall and prime paint | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-06-01 | 2027-06-14 | 10 | 9 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-28-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L28 | yes | Drywall and prime paint | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-06-09 | 2027-06-22 | 10 | 9 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-28-U-FN-230 | Tape & Finish Drywall @ Units - L28 | yes | Drywall and prime paint | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-06-09 | 2027-06-18 | 8 | 23 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-28-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L28 | yes | Drywall and prime paint | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-06-21 | 2027-07-02 | 10 | 9 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-28-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L28 | yes | Drywall and prime paint | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-13 | 8 | 9 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-28-U-FN-260 | Hang Interior Doors @ Units - L28 | yes | Drywall and prime paint | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-07-12 | 2027-07-15 | 4 | 9 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-28-U-FN-270 | Paint Drywall - 1st Coat @ Units - L28 | yes | Drywall and prime paint | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-21 | 5 | 9 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-29-U-FN-200 | Install Drywall One Side & Insulation @ Units - L29 | yes | Drywall and prime paint | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-06-01 | 2027-06-09 | 7 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-29-U-FN-210 | Hang Drywall @ Units - L29 | yes | Drywall and prime paint | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-06-10 | 2027-06-23 | 10 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-29-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L29 | yes | Drywall and prime paint | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-06-18 | 2027-07-01 | 10 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-29-U-FN-230 | Tape & Finish Drywall @ Units - L29 | yes | Drywall and prime paint | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-06-18 | 2027-06-29 | 8 | 24 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-29-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L29 | yes | Drywall and prime paint | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-06-30 | 2027-07-14 | 10 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-29-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L29 | yes | Drywall and prime paint | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-07-13 | 2027-07-22 | 8 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-29-U-FN-260 | Hang Interior Doors @ Units - L29 | yes | Drywall and prime paint | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-07-21 | 2027-07-26 | 4 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-29-U-FN-270 | Paint Drywall - 1st Coat @ Units - L29 | yes | Drywall and prime paint | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-07-26 | 2027-07-30 | 5 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-30-U-FN-200 | Install Drywall One Side & Insulation @ Units - L30 | yes | Drywall and prime paint | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-06-10 | 2027-06-18 | 7 | 11 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-30-U-FN-210 | Hang Drywall @ Units - L30 | yes | Drywall and prime paint | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-06-21 | 2027-07-02 | 10 | 11 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-30-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L30 | yes | Drywall and prime paint | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-07-13 | 10 | 11 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-30-U-FN-230 | Tape & Finish Drywall @ Units - L30 | yes | Drywall and prime paint | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-07-09 | 8 | 25 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-30-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L30 | yes | Drywall and prime paint | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-07-12 | 2027-07-23 | 10 | 11 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-30-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L30 | yes | Drywall and prime paint | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-08-02 | 8 | 11 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-30-U-FN-260 | Hang Interior Doors @ Units - L30 | yes | Drywall and prime paint | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-07-30 | 2027-08-04 | 4 | 11 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-30-U-FN-270 | Paint Drywall - 1st Coat @ Units - L30 | yes | Drywall and prime paint | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-08-04 | 2027-08-10 | 5 | 11 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-31-U-FN-200 | Install Drywall One Side & Insulation @ Units - L31 | yes | Drywall and prime paint | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-06-21 | 2027-06-29 | 7 | 12 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-31-U-FN-210 | Hang Drywall @ Units - L31 | yes | Drywall and prime paint | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-06-30 | 2027-07-14 | 10 | 12 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-31-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L31 | yes | Drywall and prime paint | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-22 | 10 | 12 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-31-U-FN-230 | Tape & Finish Drywall @ Units - L31 | yes | Drywall and prime paint | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-20 | 8 | 26 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-31-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L31 | yes | Drywall and prime paint | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-07-21 | 2027-08-03 | 10 | 12 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-31-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L31 | yes | Drywall and prime paint | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-11 | 8 | 12 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-31-U-FN-260 | Hang Interior Doors @ Units - L31 | yes | Drywall and prime paint | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-08-10 | 2027-08-13 | 4 | 12 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-31-U-FN-270 | Paint Drywall - 1st Coat @ Units - L31 | yes | Drywall and prime paint | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-08-13 | 2027-08-19 | 5 | 12 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-32-U-FN-200 | Install Drywall One Side & Insulation @ Units - L32 | yes | Drywall and prime paint | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-30 | 2027-07-09 | 7 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-32-U-FN-210 | Hang Drywall @ Units - L32 | yes | Drywall and prime paint | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-07-12 | 2027-07-23 | 10 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-32-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L32 | yes | Drywall and prime paint | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-07-20 | 2027-08-02 | 10 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-32-U-FN-230 | Tape & Finish Drywall @ Units - L32 | yes | Drywall and prime paint | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-07-20 | 2027-07-29 | 8 | 24 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-32-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L32 | yes | Drywall and prime paint | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-07-30 | 2027-08-12 | 10 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-32-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L32 | yes | Drywall and prime paint | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-08-11 | 2027-08-20 | 8 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-32-U-FN-260 | Hang Interior Doors @ Units - L32 | yes | Drywall and prime paint | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-08-19 | 2027-08-24 | 4 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-32-U-FN-270 | Paint Drywall - 1st Coat @ Units - L32 | yes | Drywall and prime paint | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-08-24 | 2027-08-30 | 5 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-33-U-FN-200 | Install Drywall One Side & Insulation @ Units - L33 | yes | Drywall and prime paint | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-12 | 2027-07-20 | 7 | 8 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-33-U-FN-210 | Hang Drywall @ Units - L33 | yes | Drywall and prime paint | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-21 | 2027-08-03 | 10 | 8 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-33-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L33 | yes | Drywall and prime paint | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-29 | 2027-08-11 | 10 | 8 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-33-U-FN-230 | Tape & Finish Drywall @ Units - L33 | yes | Drywall and prime paint | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-29 | 2027-08-09 | 8 | 22 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-33-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L33 | yes | Drywall and prime paint | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-08-10 | 2027-08-23 | 10 | 8 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-33-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L33 | yes | Drywall and prime paint | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-08-20 | 2027-08-31 | 8 | 8 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-33-U-FN-260 | Hang Interior Doors @ Units - L33 | yes | Drywall and prime paint | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-08-30 | 2027-09-02 | 4 | 8 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-33-U-FN-270 | Paint Drywall - 1st Coat @ Units - L33 | yes | Drywall and prime paint | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-09-02 | 2027-09-09 | 5 | 8 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-34-U-FN-200 | Install Drywall One Side & Insulation @ Units - L34 | yes | Drywall and prime paint | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-07-21 | 2027-07-29 | 7 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-34-U-FN-210 | Hang Drywall @ Units - L34 | yes | Drywall and prime paint | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-07-30 | 2027-08-12 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-34-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L34 | yes | Drywall and prime paint | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-08-09 | 2027-08-20 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-34-U-FN-230 | Tape & Finish Drywall @ Units - L34 | yes | Drywall and prime paint | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-08-09 | 2027-08-18 | 8 | 20 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-34-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L34 | yes | Drywall and prime paint | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-08-19 | 2027-09-01 | 10 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-34-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L34 | yes | Drywall and prime paint | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-08-31 | 2027-09-10 | 8 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-34-U-FN-260 | Hang Interior Doors @ Units - L34 | yes | Drywall and prime paint | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-09-09 | 2027-09-14 | 4 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-34-U-FN-270 | Paint Drywall - 1st Coat @ Units - L34 | yes | Drywall and prime paint | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-09-14 | 2027-09-20 | 5 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-35-U-FN-200 | Install Drywall One Side & Insulation @ Units - L35 | yes | Drywall and prime paint | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-07-30 | 2027-08-09 | 7 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-35-U-FN-210 | Hang Drywall @ Units - L35 | yes | Drywall and prime paint | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-08-10 | 2027-08-23 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-35-U-FN-230 | Tape & Finish Drywall @ Units - L35 | yes | Drywall and prime paint | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-27 | 8 | 17 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-35-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L35 | yes | Drywall and prime paint | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-08-20 | 2027-09-02 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-35-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L35 | yes | Drywall and prime paint | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-09-01 | 2027-09-15 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-35-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L35 | yes | Drywall and prime paint | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-09-14 | 2027-09-23 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-35-U-FN-260 | Hang Interior Doors @ Units - L35 | yes | Drywall and prime paint | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-09-23 | 2027-09-28 | 4 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-35-U-FN-270 | Paint Drywall - 1st Coat @ Units - L35 | yes | Drywall and prime paint | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-09-29 | 2027-10-05 | 5 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-36-IN-FN-200 | Install Drywall One Side & Insulation @ Indoor - L36 | yes | Drywall and prime paint | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-07-26 | 2027-07-28 | 3 | 33 | Interior MEPs & Finishes | Interior Finishes at Indoor
Baseline | C-36-IN-FN-210 | Hang Drywall @ Indoor - L36 | yes | Drywall and prime paint | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-07-29 | 2027-08-04 | 5 | 33 | Interior MEPs & Finishes | Interior Finishes at Indoor
Baseline | C-36-IN-FN-220 | Frame GWB Ceilings @ Indoor - L36 | yes | Drywall and prime paint | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-04 | 2027-08-09 | 4 | 33 | Interior MEPs & Finishes | Interior Finishes at Indoor
Baseline | C-36-IN-FN-230 | Tape & Finish Drywall @ Indoor - L36 | yes | Drywall and prime paint | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-04 | 2027-08-09 | 4 | 39 | Interior MEPs & Finishes | Interior Finishes at Indoor
Baseline | C-36-IN-FN-240 | Hang GWB Ceilings @ Indoor - L36 | yes | Drywall and prime paint | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-12 | 2027-08-16 | 3 | 33 | Interior MEPs & Finishes | Interior Finishes at Indoor
Baseline | C-36-IN-FN-250 | Tape & Finish GWB Ceilings @ Indoor - L36 | yes | Drywall and prime paint | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-17 | 2027-08-19 | 3 | 33 | Interior MEPs & Finishes | Interior Finishes at Indoor
Baseline | C-36-IN-FN-260 | Hang Interior Doors @ Indoor - L36 | yes | Drywall and prime paint | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-19 | 2 | 33 | Interior MEPs & Finishes | Interior Finishes at Indoor
Baseline | C-36-IN-FN-270 | Paint Drywall - 1st Coat @ Indoor - L36 | yes | Drywall and prime paint | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-20 | 2027-08-24 | 3 | 33 | Interior MEPs & Finishes | Interior Finishes at Indoor
Baseline | C-01-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > Interior Finishes at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-08-12 | 2027-08-19 | 6 | 18 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridors
Baseline | C-01-UC-MP-200 | Install Mech Heat Pump & Eqp @ Future Tenant - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > MEP Eqp & Trim at 1st Lvl | TT_Task | TK_NotStart | 2027-08-12 | 2027-08-18 | 5 | 42 | Interior MEPs & Finishes | MEP Eqp & Trim
Baseline | C-01-UC-FN-310 | Paint Final Coat @ L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Interior Finishes at 1st Lvl | TT_Task | TK_NotStart | 2027-08-16 | 2027-08-20 | 5 | 31 | Interior MEPs & Finishes | Interior Finishes
Baseline | C-01-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > Interior Finishes at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-08-20 | 2027-08-26 | 5 | 18 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridors
Baseline | C-01-UC-FN-320 | Install Lockers & Shelving @ Packages Rm #119 - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Interior Finishes at 1st Lvl | TT_Task | TK_NotStart | 2027-08-23 | 2027-08-27 | 5 | 35 | Interior MEPs & Finishes | Interior Finishes
Baseline | C-01-UC-FN-330 | Install Door Hardware @ L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Interior Finishes at 1st Lvl | TT_Task | TK_NotStart | 2027-08-23 | 2027-08-24 | 2 | 38 | Interior MEPs & Finishes | Interior Finishes
Baseline | C-01-UC-FN-370 | Install Flooring & Base @ L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Interior Finishes at 1st Lvl | TT_Task | TK_NotStart | 2027-08-23 | 2027-09-01 | 8 | 32 | Interior MEPs & Finishes | Interior Finishes
Baseline | C-01-UC-MP-400 | Install HVAC Trim & Control @ L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > MEP Eqp & Trim at 1st Lvl | TT_Task | TK_NotStart | 2027-08-23 | 2027-08-27 | 5 | 35 | Interior MEPs & Finishes | MEP Eqp & Trim
Baseline | C-01-UC-MP-410 | Install Electrical Power Trim @ L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > MEP Eqp & Trim at 1st Lvl | TT_Task | TK_NotStart | 2027-08-23 | 2027-08-26 | 4 | 31 | Interior MEPs & Finishes | MEP Eqp & Trim
Baseline | C-01-UC-MP-420 | Install Light Fixtures @ L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > MEP Eqp & Trim at 1st Lvl | TT_Task | TK_NotStart | 2027-08-25 | 2027-09-02 | 7 | 31 | Interior MEPs & Finishes | MEP Eqp & Trim
Baseline | C-01-C-FN-120 | Frame GWB Ceiling @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > Interior Finishes at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-08-27 | 2027-09-02 | 5 | 18 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridors
Baseline | C-01-UC-MP-430 | Install FA & Low Voltage Devices @ L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > MEP Eqp & Trim at 1st Lvl | TT_Task | TK_NotStart | 2027-08-27 | 2027-08-31 | 3 | 33 | Interior MEPs & Finishes | MEP Eqp & Trim
Baseline | C-01-UC-MP-440 | Install FP Sprinkler Heads @ L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > MEP Eqp & Trim at 1st Lvl | TT_Task | TK_NotStart | 2027-08-27 | 2027-08-30 | 2 | 34 | Interior MEPs & Finishes | MEP Eqp & Trim
Baseline | C-01-C-FN-140 | Hang/Tape/Finish GWB Ceiling @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > Interior Finishes at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-09-01 | 2027-09-08 | 5 | 18 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridors
Baseline | C-01-UC-FN-400 | Rough Cleanup @ L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Interior Finishes at 1st Lvl | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-07 | 2 | 31 | Interior MEPs & Finishes | Interior Finishes
Baseline | C-01-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > Interior Finishes at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-09-09 | 2027-09-14 | 4 | 18 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridors
Baseline | C-01-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > Interior Finishes at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-09-15 | 2027-09-15 | 1 | 23 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridors
Baseline | C-01-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > Interior Finishes at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-09-15 | 2027-09-20 | 4 | 20 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridors
Baseline | C-01-C-MP-120 | Install HVAC EFs & Trim @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > MEP Eqp & Trim at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-09-15 | 2027-09-20 | 4 | 18 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridors
Baseline | C-01-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > MEP Eqp & Trim at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-09-15 | 2027-09-16 | 2 | 19 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridors
Baseline | C-01-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > MEP Eqp & Trim at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-09-17 | 2027-09-20 | 2 | 19 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridors
Baseline | C-01-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > MEP Eqp & Trim at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-09-20 | 2027-09-21 | 2 | 19 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridors
Baseline | C-01-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > MEP Eqp & Trim at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-09-21 | 2027-09-22 | 2 | 18 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridors
Baseline | C-01-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > Interior Finishes at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-09-23 | 2027-09-24 | 2 | 18 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridors
Baseline | C-02-UC-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-17 | 2026-09-24 | 6 | 24 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Baseline | C-02-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > Interior Finishes at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-21 | 2026-09-24 | 4 | 110 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-02-UC-MP-200 | Install Mech Heat Pumps & Eqp @ Units & Common Areas - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > MEP Eqp at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-21 | 2026-10-09 | 15 | 32 | Interior MEPs & Finishes | MEP Eqp at Units & Common Areas
Baseline | C-02-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > Interior Finishes at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-25 | 2026-09-29 | 3 | 125 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-02-UC-FN-290 | Install Vanities & Mirrors @ B/Rs - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-25 | 2026-09-28 | 2 | 24 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Baseline | C-02-UC-FN-300 | Install Shower Enclosures @ B/Rs L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-29 | 2026-10-01 | 3 | 24 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Baseline | C-02-UC-MP-210 | Install Plumbing Fixtures @ B/Rs - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > MEP Eqp at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-29 | 2026-09-30 | 2 | 120 | Interior MEPs & Finishes | MEP Eqp at Units & Common Areas
Baseline | C-02-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > Interior Finishes at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-30 | 2026-10-05 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-02-C-FN-130 | Install Trash Chute @ Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > Interior Finishes at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-30 | 2026-09-30 | 1 | 130 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-02-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > Interior Finishes at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-02 | 2026-10-07 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-02-C-MP-100 | Install Elect & Low Voltage Panels & Eqp @ Telecomm/Elect Rm #221- L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-02 | 2026-10-22 | 15 | 159 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-02-UC-FN-310 | Paint Final Coat @ Units & Common Areas - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-02 | 2026-10-08 | 5 | 24 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Baseline | C-02-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > Interior Finishes at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-08 | 2026-10-12 | 3 | 125 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-02-UC-FN-320 | Install Storage Lockers @ Storage Locker Rm #229 - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-26 | 12 | 105 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Baseline | C-02-UC-FN-330 | Install Door Hardware @ Units & Common Areas - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-12 | 2 | 115 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Baseline | C-02-UC-FN-340 | Install Toilet Partitions & Accessories @ B/Rs - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-13 | 3 | 114 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Baseline | C-02-UC-FN-350 | Install Kitchen Cabinets & & Countertops & Millwork @ Units & Common Areas - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-19 | 7 | 24 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Baseline | C-02-UC-FN-360 | Install Laundry Eqp @ Laundry Rm #224 - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-13 | 3 | 111 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Baseline | C-02-UC-MP-400 | Install HVAC Trim & Control @ Units & Common Areas - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > MEP Trim at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-14 | 4 | 113 | Interior MEPs & Finishes | MEP Trim at Units & Common Areas
Baseline | C-02-UC-MP-410 | Install Electrical Power Trim @ Units & Common Areas - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > MEP Trim at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-14 | 4 | 108 | Interior MEPs & Finishes | MEP Trim at Units & Common Areas
Baseline | C-02-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > Interior Finishes at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-13 | 2026-10-13 | 1 | 171 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-02-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > Interior Finishes at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-13 | 2026-10-16 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-02-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-13 | 2026-10-13 | 1 | 168 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-02-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-13 | 2026-10-14 | 2 | 168 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-02-UC-MP-420 | Install Light Fixtures @ Units & Common Areas - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > MEP Trim at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-13 | 2026-10-21 | 7 | 108 | Interior MEPs & Finishes | MEP Trim at Units & Common Areas
Baseline | C-02-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-16 | 2 | 168 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-02-UC-MP-430 | Install FA & Low Voltage Devices @ Units & Common Areas - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > MEP Trim at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-19 | 3 | 110 | Interior MEPs & Finishes | MEP Trim at Units & Common Areas
Baseline | C-02-UC-MP-440 | Install FP Sprinkler Heads @ Units & Common Areas - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > MEP Trim at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-16 | 2 | 111 | Interior MEPs & Finishes | MEP Trim at Units & Common Areas
Baseline | C-02-UC-FN-370 | Install Flooring & Base @ Units & Common Areas - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-20 | 2026-10-29 | 8 | 26 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Baseline | C-02-UC-FN-390 | Install Kitchen Appliances @ Units - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-20 | 2026-10-22 | 3 | 107 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Baseline | C-02-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-23 | 2026-10-26 | 2 | 159 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-02-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-27 | 2026-10-28 | 2 | 159 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-02-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-28 | 2026-10-29 | 2 | 159 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-02-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > Interior Finishes at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-02 | 2 | 159 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-02-UC-FN-450 | Install Laundry Eqp @ Laundry Rm #224 - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-02 | 2 | 102 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Baseline | C-02-UC-FN-400 | Touch-up Paint @ L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-11-03 | 2026-11-04 | 2 | 157 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Baseline | C-03-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-28 | 2026-10-05 | 6 | 24 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-03-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > Interior Finishes at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-30 | 2026-10-05 | 4 | 107 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-03-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > MEP Eqp at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-30 | 2026-10-20 | 15 | 18 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-03-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > Interior Finishes at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-08 | 3 | 122 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-03-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-07 | 2 | 24 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-03-U-FN-300 | Install Shower Enclosures @ B/Rs L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-10-08 | 2026-10-12 | 3 | 24 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-03-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > MEP Eqp at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-10-08 | 2026-10-09 | 2 | 121 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-03-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > Interior Finishes at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-14 | 4 | 122 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-03-C-FN-130 | Install Trash Chute @ Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > Interior Finishes at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-09 | 1 | 127 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-03-C-MP-100 | Install Elect Panels & Stack Meters @ Stack Vault #321- L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-29 | 15 | 159 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-03-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > Interior Finishes at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-10-13 | 2026-10-16 | 4 | 122 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-03-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > Interior Finishes at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-10-19 | 2026-10-21 | 3 | 122 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-03-U-FN-310 | Paint Final Coat @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-10-21 | 2026-10-27 | 5 | 18 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-03-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > Interior Finishes at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-10-22 | 2026-10-22 | 1 | 169 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-03-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > Interior Finishes at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-10-22 | 2026-10-27 | 4 | 122 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-03-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-10-22 | 2026-10-22 | 1 | 166 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-03-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-10-22 | 2026-10-23 | 2 | 166 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-03-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-10-26 | 2026-10-27 | 2 | 166 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-03-U-FN-330 | Install Door Hardware @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-10-28 | 2026-10-29 | 2 | 109 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-03-U-FN-340 | Install Toilet Accessories @ B/Rs - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-10-28 | 2026-10-29 | 2 | 109 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-03-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-10-28 | 2026-11-06 | 8 | 18 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-03-U-MP-400 | Install HVAC Trim & Control @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > MEP Trim at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-10-28 | 2026-11-02 | 4 | 107 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-03-U-MP-410 | Install Electrical Power Trim @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > MEP Trim at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-10-28 | 2026-11-02 | 4 | 102 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-03-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-02 | 2 | 159 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-03-U-MP-420 | Install Light Fixtures @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > MEP Trim at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-09 | 7 | 102 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-03-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-11-03 | 2026-11-04 | 2 | 159 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-03-U-MP-430 | Install FA & Low Voltage Devices @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > MEP Trim at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-11-03 | 2026-11-05 | 3 | 104 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-03-U-MP-440 | Install FP Sprinkler Heads @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > MEP Trim at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-11-03 | 2026-11-04 | 2 | 105 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-03-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-05 | 2 | 159 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-03-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > Interior Finishes at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-11-06 | 2026-11-09 | 2 | 159 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-03-U-FN-370 | Install Flooring & Base @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-18 | 8 | 20 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-03-U-FN-390 | Install Kitchen Appliances @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-11 | 3 | 100 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-03-U-FN-400 | Rough Cleanup @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-11-19 | 2026-11-20 | 2 | 95 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-03-U-FN-410 | Touch-up Paint @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-11-23 | 2026-11-24 | 2 | 148 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-04-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-10-12 | 2026-10-19 | 6 | 22 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-04-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > Interior Finishes at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-10-14 | 2026-10-19 | 4 | 101 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-04-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > MEP Eqp at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-10-14 | 2026-10-27 | 10 | 21 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-04-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > Interior Finishes at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-10-20 | 2026-10-22 | 3 | 116 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-04-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-10-20 | 2026-10-21 | 2 | 22 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-04-U-FN-300 | Install Shower Enclosures @ B/Rs L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-10-22 | 2026-10-26 | 3 | 22 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-04-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > MEP Eqp at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-10-22 | 2026-10-23 | 2 | 118 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-04-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > Interior Finishes at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-10-23 | 2026-10-28 | 4 | 116 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-04-C-FN-130 | Install Trash Chute @ Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > Interior Finishes at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-10-23 | 2026-10-23 | 1 | 121 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-04-C-MP-100 | Install Elect Panels & Eqp @ Elect. Rm #421- L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-10-23 | 2026-11-12 | 15 | 154 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-04-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > Interior Finishes at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-10-27 | 2026-10-30 | 4 | 116 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-04-U-FN-310 | Paint Final Coat @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-10-28 | 2026-11-03 | 5 | 21 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-04-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > Interior Finishes at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-11-02 | 2026-11-04 | 3 | 116 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-04-U-FN-330 | Install Door Hardware @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-05 | 2 | 111 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-04-U-FN-340 | Install Toilet Accessories @ B/Rs - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-05 | 2 | 111 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-04-U-MP-400 | Install HVAC Trim & Control @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > MEP Trim at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-09 | 4 | 109 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-04-U-MP-410 | Install Electrical Power Trim @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > MEP Trim at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-09 | 4 | 104 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-04-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > Interior Finishes at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-11-05 | 2026-11-05 | 1 | 164 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-04-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > Interior Finishes at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-11-05 | 2026-11-10 | 4 | 116 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-04-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-11-05 | 2026-11-05 | 1 | 161 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-04-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-11-05 | 2026-11-06 | 2 | 161 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-04-U-MP-420 | Install Light Fixtures @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > MEP Trim at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-11-06 | 2026-11-16 | 7 | 104 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-04-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-10 | 2 | 161 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-04-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-18 | 8 | 18 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-04-U-MP-430 | Install FA & Low Voltage Devices @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > MEP Trim at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-11-10 | 2026-11-12 | 3 | 106 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-04-U-MP-440 | Install FP Sprinkler Heads @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > MEP Trim at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-11-10 | 2026-11-11 | 2 | 107 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-04-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-16 | 2 | 154 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-04-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-11-17 | 2026-11-18 | 2 | 154 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-04-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-11-18 | 2026-11-19 | 2 | 154 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-04-U-FN-370 | Install Flooring & Base @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-11-19 | 2026-12-02 | 8 | 20 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-04-U-FN-390 | Install Kitchen Appliances @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-11-19 | 2026-11-23 | 3 | 99 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-04-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > Interior Finishes at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-11-23 | 2 | 154 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-04-U-FN-400 | Rough Cleanup @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-04 | 2 | 94 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-04-U-FN-410 | Touch-up Paint @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-08 | 2 | 145 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-05-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-10-26 | 2026-11-02 | 6 | 20 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-05-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > Interior Finishes at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-10-28 | 2026-11-02 | 4 | 95 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-05-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > MEP Eqp at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-10-28 | 2026-11-10 | 10 | 19 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-05-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > Interior Finishes at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-11-03 | 2026-11-05 | 3 | 110 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-05-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-11-03 | 2026-11-04 | 2 | 20 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-05-U-FN-300 | Install Shower Enclosures @ B/Rs L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-11-05 | 2026-11-09 | 3 | 20 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-05-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > MEP Eqp at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-11-05 | 2026-11-06 | 2 | 115 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-05-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > Interior Finishes at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-11-06 | 2026-11-11 | 4 | 110 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-05-C-FN-130 | Install Trash Chute @ Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > Interior Finishes at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-11-06 | 2026-11-06 | 1 | 115 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-05-C-MP-100 | Install Elect & Low Voltage Panels & Eqp @ Telecom/Elect Rm #521- L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-11-06 | 2026-11-30 | 15 | 149 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-05-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > Interior Finishes at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-11-10 | 2026-11-13 | 4 | 110 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-05-U-FN-310 | Paint Final Coat @ Units - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-11-11 | 2026-11-17 | 5 | 19 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-05-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > Interior Finishes at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-11-16 | 2026-11-18 | 3 | 110 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-05-U-FN-330 | Install Door Hardware @ Units - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-11-18 | 2026-11-19 | 2 | 108 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-05-U-FN-340 | Install Toilet Accessories @ B/Rs - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-11-18 | 2026-11-19 | 2 | 108 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-05-U-MP-400 | Install HVAC Trim & Control @ Units - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > MEP Trim at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-11-18 | 2026-11-23 | 4 | 106 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-05-U-MP-410 | Install Electrical Power Trim @ Units - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > MEP Trim at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-11-18 | 2026-11-23 | 4 | 101 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-05-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > Interior Finishes at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-11-19 | 2026-11-19 | 1 | 159 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-05-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > Interior Finishes at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-11-19 | 2026-11-24 | 4 | 110 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-05-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-11-19 | 2026-11-19 | 1 | 156 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-05-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-11-19 | 2026-11-20 | 2 | 156 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-05-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-11-19 | 2026-12-02 | 8 | 18 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-05-U-MP-420 | Install Light Fixtures @ Units - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > MEP Trim at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-12-02 | 7 | 101 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-05-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-11-23 | 2026-11-24 | 2 | 156 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-05-U-MP-430 | Install FA & Low Voltage Devices @ Units - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > MEP Trim at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-11-30 | 3 | 103 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-05-U-MP-440 | Install FP Sprinkler Heads @ Units - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > MEP Trim at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-11-25 | 2 | 104 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-05-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-12-01 | 2026-12-02 | 2 | 149 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-05-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-04 | 2 | 149 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-05-U-FN-370 | Install Flooring & Base @ Units - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-14 | 8 | 20 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-05-U-FN-390 | Install Kitchen Appliances @ Units - L6 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-07 | 3 | 98 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-05-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-12-04 | 2026-12-07 | 2 | 149 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-05-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > Interior Finishes at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-12-08 | 2026-12-09 | 2 | 149 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-05-U-FN-400 | Rough Cleanup @ Units - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-12-15 | 2026-12-16 | 2 | 93 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-05-U-FN-410 | Touch-up Paint @ Units - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-12-17 | 2026-12-18 | 2 | 142 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-06-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-16 | 6 | 18 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-06-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > Interior Finishes at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-11-11 | 2026-11-16 | 4 | 89 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-06-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > MEP Eqp at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-11-11 | 2026-11-24 | 10 | 17 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-06-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > Interior Finishes at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-11-17 | 2026-11-19 | 3 | 104 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-06-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-11-17 | 2026-11-18 | 2 | 18 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-06-U-FN-300 | Install Shower Enclosures @ B/Rs L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-11-19 | 2026-11-23 | 3 | 18 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-06-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > MEP Eqp at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-11-19 | 2026-11-20 | 2 | 112 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-06-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > Interior Finishes at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-11-25 | 4 | 104 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-06-C-FN-130 | Install Trash Chute @ Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > Interior Finishes at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-11-20 | 1 | 109 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-06-C-MP-100 | Install Elect Panels & Stack Meters @ Stack Vault #621- L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-12-14 | 15 | 144 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-06-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > Interior Finishes at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-12-01 | 4 | 104 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-06-U-FN-310 | Paint Final Coat @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-11-25 | 2026-12-03 | 5 | 17 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-06-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > Interior Finishes at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-12-02 | 2026-12-04 | 3 | 104 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-06-U-FN-330 | Install Door Hardware @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-12-04 | 2026-12-07 | 2 | 105 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-06-U-FN-340 | Install Toilet Accessories @ B/Rs - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-12-04 | 2026-12-07 | 2 | 105 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-06-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-12-04 | 2026-12-15 | 8 | 17 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-06-U-MP-400 | Install HVAC Trim & Control @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > MEP Trim at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-12-04 | 2026-12-09 | 4 | 103 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-06-U-MP-410 | Install Electrical Power Trim @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > MEP Trim at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-12-04 | 2026-12-09 | 4 | 98 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-06-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > Interior Finishes at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-07 | 1 | 154 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-06-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > Interior Finishes at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-10 | 4 | 104 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-06-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-07 | 1 | 151 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-06-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-08 | 2 | 151 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-06-U-MP-420 | Install Light Fixtures @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > MEP Trim at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-12-08 | 2026-12-16 | 7 | 98 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-06-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-12-09 | 2026-12-10 | 2 | 151 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-06-U-MP-430 | Install FA & Low Voltage Devices @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > MEP Trim at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-14 | 3 | 100 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-06-U-MP-440 | Install FP Sprinkler Heads @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > MEP Trim at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-11 | 2 | 101 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-06-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-12-15 | 2026-12-16 | 2 | 144 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-06-U-FN-370 | Install Flooring & Base @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-12-16 | 2026-12-28 | 8 | 19 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-06-U-FN-390 | Install Kitchen Appliances @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-12-16 | 2026-12-18 | 3 | 96 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-06-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-12-17 | 2026-12-18 | 2 | 144 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-06-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-12-18 | 2026-12-21 | 2 | 144 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-06-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > Interior Finishes at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-12-22 | 2026-12-23 | 2 | 144 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-06-U-FN-400 | Rough Cleanup @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-12-29 | 2026-12-30 | 2 | 91 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-06-U-FN-410 | Touch-up Paint @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-12-31 | 2027-01-04 | 2 | 138 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-07-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-12-11 | 2026-12-21 | 7 | 1 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-07-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > Interior Finishes at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2026-12-15 | 2026-12-21 | 5 | 71 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-07-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > MEP Eqp at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-12-15 | 2026-12-31 | 12 | 0 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-07-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > Interior Finishes at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2026-12-22 | 2026-12-28 | 4 | 81 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-07-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-12-22 | 2026-12-23 | 2 | 1 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-07-U-FN-300 | Install Shower Enclosures @ B/Rs L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-12-24 | 2026-12-30 | 4 | 1 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-07-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > MEP Eqp at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-12-24 | 2026-12-30 | 4 | 93 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-07-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > Interior Finishes at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2026-12-29 | 2027-01-05 | 5 | 81 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-07-C-FN-130 | Install Trash Chute @ Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > Interior Finishes at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2026-12-29 | 2026-12-29 | 1 | 88 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-07-C-MP-100 | Install Elect Panels @ Elect Rm #721- L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2026-12-29 | 2027-01-19 | 15 | 123 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-07-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > Interior Finishes at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-08 | 5 | 81 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-07-U-FN-310 | Paint Final Coat @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-11 | 6 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-07-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > Interior Finishes at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2027-01-11 | 2027-01-14 | 4 | 81 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-07-U-FN-320 | Install Flooring @ Gym - 7th FL | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-13 | 2 | 79 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-07-U-FN-330 | Install Door Hardware @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-14 | 3 | 86 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-07-U-FN-340 | Install Toilet Accessories @ B/Rs - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-14 | 3 | 86 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-07-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-25 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-07-U-MP-400 | Install HVAC Trim & Control @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > MEP Trim at Units at 7th Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-18 | 5 | 84 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-07-U-MP-410 | Install Electrical Power Trim @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > MEP Trim at Units at 7th Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-18 | 5 | 78 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-07-U-FN-360 | Install Gym Millwork & Eqp @ Gym - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2027-01-14 | 2027-01-25 | 8 | 79 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-07-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > Interior Finishes at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2027-01-15 | 2027-01-15 | 1 | 131 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-07-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > Interior Finishes at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2027-01-15 | 2027-01-21 | 5 | 81 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-07-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2027-01-15 | 2027-01-15 | 1 | 127 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-07-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2027-01-15 | 2027-01-20 | 4 | 126 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-07-U-MP-420 | Install Light Fixtures @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > MEP Trim at Units at 7th Lvl | TT_Task | TK_NotStart | 2027-01-15 | 2027-01-26 | 8 | 78 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-07-U-MP-430 | Install FA & Low Voltage Devices @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > MEP Trim at Units at 7th Lvl | TT_Task | TK_NotStart | 2027-01-19 | 2027-01-22 | 4 | 80 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-07-U-MP-440 | Install FP Sprinkler Heads @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > MEP Trim at Units at 7th Lvl | TT_Task | TK_NotStart | 2027-01-19 | 2027-01-20 | 2 | 82 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-07-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-01-21 | 2 | 123 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-07-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2027-01-21 | 2027-01-22 | 2 | 126 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-07-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2027-01-22 | 2027-01-25 | 2 | 123 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-07-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2027-01-25 | 2027-01-27 | 3 | 123 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-07-U-FN-370 | Install Flooring & Base @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2027-01-26 | 2027-02-08 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-07-U-FN-390 | Install Kitchen Appliances @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2027-01-26 | 2027-01-28 | 3 | 76 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-07-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > Interior Finishes at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2027-01-28 | 2027-01-29 | 2 | 123 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-07-U-FN-400 | Rough Cleanup @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-10 | 2 | 69 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-07-U-FN-410 | Touch-up Paint @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-12 | 2 | 113 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-08-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2027-01-06 | 7 | 1 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-08-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > Interior Finishes at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2026-12-30 | 2027-01-06 | 5 | 66 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-08-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > MEP Eqp at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-12-30 | 2027-01-15 | 12 | 0 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-08-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > Interior Finishes at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-12 | 4 | 76 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-08-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-08 | 2 | 1 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-08-U-FN-300 | Install Shower Enclosures @ B/Rs L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2027-01-11 | 2027-01-14 | 4 | 1 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-08-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > MEP Eqp at Units at 8th Lvl | TT_Task | TK_NotStart | 2027-01-11 | 2027-01-14 | 4 | 90 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-08-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > Interior Finishes at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2027-01-13 | 2027-01-19 | 5 | 76 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-08-C-FN-130 | Install Trash Chute @ Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > Interior Finishes at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2027-01-13 | 2027-01-13 | 1 | 83 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-08-C-MP-100 | Install Low Voltage Panels @ Telecom Rm #821- L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2027-01-13 | 2027-02-02 | 15 | 113 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-08-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > Interior Finishes at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-22 | 5 | 76 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-08-U-FN-310 | Paint Final Coat @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-25 | 6 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-08-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > Interior Finishes at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2027-01-25 | 2027-01-28 | 4 | 76 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-08-U-FN-330 | Install Door Hardware @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2027-01-26 | 2027-01-28 | 3 | 83 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-08-U-FN-340 | Install Toilet Accessories @ B/Rs - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2027-01-26 | 2027-01-28 | 3 | 83 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-08-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2027-01-26 | 2027-02-04 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-08-U-MP-400 | Install HVAC Trim & Control @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > MEP Trim at Units at 8th Lvl | TT_Task | TK_NotStart | 2027-01-26 | 2027-02-01 | 5 | 81 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-08-U-MP-410 | Install Electrical Power Trim @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > MEP Trim at Units at 8th Lvl | TT_Task | TK_NotStart | 2027-01-26 | 2027-02-01 | 5 | 75 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-08-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > Interior Finishes at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2027-01-29 | 2027-01-29 | 1 | 121 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-08-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > Interior Finishes at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2027-01-29 | 2027-02-04 | 5 | 76 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-08-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2027-01-29 | 2027-01-29 | 1 | 117 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-08-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2027-01-29 | 2027-02-03 | 4 | 116 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-08-U-MP-420 | Install Light Fixtures @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > MEP Trim at Units at 8th Lvl | TT_Task | TK_NotStart | 2027-01-29 | 2027-02-09 | 8 | 75 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-08-U-MP-430 | Install FA & Low Voltage Devices @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > MEP Trim at Units at 8th Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-05 | 4 | 77 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-08-U-MP-440 | Install FP Sprinkler Heads @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > MEP Trim at Units at 8th Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-03 | 2 | 79 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-08-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2027-02-03 | 2027-02-04 | 2 | 113 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-08-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2027-02-04 | 2027-02-05 | 2 | 116 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-08-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-08 | 2 | 113 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-08-U-FN-390 | Install Kitchen Appliances @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-09 | 3 | 75 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-08-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2027-02-08 | 2027-02-10 | 3 | 113 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-08-U-FN-370 | Install Flooring & Base @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-22 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-08-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > Interior Finishes at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-12 | 2 | 113 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-08-U-FN-400 | Rough Cleanup @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-02-24 | 2 | 66 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-08-U-FN-410 | Touch-up Paint @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-02-26 | 2 | 103 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-09-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-15 | 7 | 2 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-09-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > Interior Finishes at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2027-01-11 | 2027-01-15 | 5 | 64 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-09-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > MEP Eqp at Units at 9th Lvl | TT_Task | TK_NotStart | 2027-01-11 | 2027-01-26 | 12 | 1 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-09-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > Interior Finishes at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-21 | 4 | 74 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-09-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-19 | 2 | 2 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-09-U-FN-300 | Install Shower Enclosures @ B/Rs L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-01-25 | 4 | 2 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-09-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > MEP Eqp at Units at 9th Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-01-25 | 4 | 90 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-09-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > Interior Finishes at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2027-01-22 | 2027-01-28 | 5 | 74 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-09-C-FN-130 | Install Trash Chute @ Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > Interior Finishes at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2027-01-22 | 2027-01-22 | 1 | 81 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-09-C-MP-100 | Install Elect Panels & Stack Meters @ Stack Vault #921- L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2027-01-22 | 2027-02-11 | 15 | 106 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-09-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > Interior Finishes at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-02-02 | 5 | 74 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-09-U-FN-310 | Paint Final Coat @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-02-03 | 6 | 1 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-09-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > Interior Finishes at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2027-02-03 | 2027-02-08 | 4 | 74 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-09-U-FN-330 | Install Door Hardware @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2027-02-04 | 2027-02-08 | 3 | 83 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-09-U-FN-340 | Install Toilet Accessories @ B/Rs - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2027-02-04 | 2027-02-08 | 3 | 83 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-09-U-MP-400 | Install HVAC Trim & Control @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > MEP Trim at Units at 9th Lvl | TT_Task | TK_NotStart | 2027-02-04 | 2027-02-10 | 5 | 81 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-09-U-MP-410 | Install Electrical Power Trim @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > MEP Trim at Units at 9th Lvl | TT_Task | TK_NotStart | 2027-02-04 | 2027-02-10 | 5 | 75 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-09-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-16 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-09-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > Interior Finishes at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-09 | 1 | 114 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-09-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > Interior Finishes at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-15 | 5 | 74 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-09-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-09 | 1 | 110 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-09-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-12 | 4 | 109 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-09-U-MP-420 | Install Light Fixtures @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > MEP Trim at Units at 9th Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-18 | 8 | 75 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-09-U-MP-430 | Install FA & Low Voltage Devices @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > MEP Trim at Units at 9th Lvl | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-16 | 4 | 77 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-09-U-MP-440 | Install FP Sprinkler Heads @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > MEP Trim at Units at 9th Lvl | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-12 | 2 | 79 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-09-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2027-02-12 | 2027-02-15 | 2 | 106 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-09-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2027-02-15 | 2027-02-16 | 2 | 109 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-09-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-17 | 2 | 106 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-09-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2027-02-17 | 2027-02-19 | 3 | 106 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-09-U-FN-390 | Install Kitchen Appliances @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2027-02-17 | 2027-02-19 | 3 | 74 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-09-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > Interior Finishes at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2027-02-22 | 2027-02-23 | 2 | 106 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-09-U-FN-370 | Install Flooring & Base @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-03-08 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-09-U-FN-400 | Rough Cleanup @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2027-03-09 | 2027-03-10 | 2 | 63 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-09-U-FN-410 | Touch-up Paint @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-12 | 2 | 93 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-10-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-26 | 7 | 3 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-10-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > Interior Finishes at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-01-26 | 5 | 62 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-10-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > MEP Eqp at Units at 10th Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-02-04 | 12 | 2 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-10-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > Interior Finishes at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-02-01 | 4 | 72 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-10-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-01-28 | 2 | 3 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-10-U-FN-300 | Install Shower Enclosures @ B/Rs L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2027-01-29 | 2027-02-03 | 4 | 3 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-10-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > MEP Eqp at Units at 10th Lvl | TT_Task | TK_NotStart | 2027-01-29 | 2027-02-03 | 4 | 90 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-10-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > Interior Finishes at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-08 | 5 | 72 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-10-C-FN-130 | Install Trash Chute @ Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > Interior Finishes at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-02 | 1 | 79 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-10-C-MP-100 | Install Mech Eqp @ Mech Eqp Rm #1021- L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-22 | 15 | 75 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-10-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > Interior Finishes at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-11 | 5 | 72 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-10-U-FN-310 | Paint Final Coat @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-12 | 6 | 2 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-10-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > Interior Finishes at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2027-02-12 | 2027-02-17 | 4 | 72 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-10-U-FN-330 | Install Door Hardware @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2027-02-15 | 2027-02-17 | 3 | 83 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-10-U-FN-340 | Install Toilet Accessories @ B/Rs - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2027-02-15 | 2027-02-17 | 3 | 83 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-10-U-MP-410 | Install Electrical Power Trim @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > MEP Trim at Units at 10th Lvl | TT_Task | TK_NotStart | 2027-02-15 | 2027-02-19 | 5 | 75 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-10-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2027-02-17 | 2027-02-26 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-10-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > Interior Finishes at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2027-02-18 | 2027-02-18 | 1 | 112 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-10-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > Interior Finishes at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2027-02-18 | 2027-02-24 | 5 | 72 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-10-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2027-02-18 | 2027-02-18 | 1 | 108 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-10-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2027-02-18 | 2027-02-19 | 2 | 107 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-10-U-MP-420 | Install Light Fixtures @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > MEP Trim at Units at 10th Lvl | TT_Task | TK_NotStart | 2027-02-18 | 2027-03-01 | 8 | 75 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-10-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2027-02-22 | 2027-02-23 | 2 | 107 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-10-U-MP-430 | Install FA & Low Voltage Devices @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > MEP Trim at Units at 10th Lvl | TT_Task | TK_NotStart | 2027-02-22 | 2027-02-25 | 4 | 77 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-10-U-MP-440 | Install FP Sprinkler Heads @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > MEP Trim at Units at 10th Lvl | TT_Task | TK_NotStart | 2027-02-22 | 2027-02-23 | 2 | 79 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-10-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-02-26 | 4 | 104 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-10-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-02-25 | 3 | 107 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-10-U-MP-400 | Install HVAC Trim & Control @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > MEP Trim at Units at 10th Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-03-01 | 5 | 75 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-10-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2027-03-01 | 2027-03-02 | 2 | 104 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-10-U-FN-390 | Install Kitchen Appliances @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2027-03-01 | 2027-03-03 | 3 | 73 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-10-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > Interior Finishes at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-04 | 2 | 104 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-10-U-FN-370 | Install Flooring & Base @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2027-03-09 | 2027-03-22 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-10-U-FN-400 | Rough Cleanup @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2027-03-23 | 2027-03-24 | 2 | 60 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-10-U-FN-410 | Touch-up Paint @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2027-03-25 | 2027-03-26 | 2 | 88 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-11-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-02-04 | 7 | 4 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-11-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > Interior Finishes at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2027-01-29 | 2027-02-04 | 5 | 60 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-11-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > MEP Eqp at Units at 11th Lvl | TT_Task | TK_NotStart | 2027-01-29 | 2027-02-15 | 12 | 3 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-11-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > Interior Finishes at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-10 | 4 | 70 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-11-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-08 | 2 | 4 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-11-U-FN-300 | Install Shower Enclosures @ B/Rs L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-12 | 4 | 4 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-11-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > MEP Eqp at Units at 11th Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-12 | 4 | 90 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-11-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > Interior Finishes at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-17 | 5 | 70 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-11-C-FN-130 | Install Trash Chute @ Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > Interior Finishes at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-11 | 1 | 77 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-11-C-MP-100 | Install Elect & Low Voltage Panels @ Telecom/Elect Rm #1121- L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2027-02-11 | 2027-03-03 | 15 | 97 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-11-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > Interior Finishes at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-22 | 5 | 70 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-11-U-FN-310 | Paint Final Coat @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-23 | 6 | 3 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-11-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > Interior Finishes at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-02-26 | 4 | 70 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-11-U-FN-330 | Install Door Hardware @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2027-02-24 | 2027-02-26 | 3 | 83 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-11-U-FN-340 | Install Toilet Accessories @ B/Rs - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2027-02-24 | 2027-02-26 | 3 | 83 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-11-U-MP-400 | Install HVAC Trim & Control @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > MEP Trim at Units at 11th Lvl | TT_Task | TK_NotStart | 2027-02-24 | 2027-03-02 | 5 | 81 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-11-U-MP-410 | Install Electrical Power Trim @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > MEP Trim at Units at 11th Lvl | TT_Task | TK_NotStart | 2027-02-24 | 2027-03-02 | 5 | 75 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-11-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > Interior Finishes at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2027-03-01 | 2027-03-01 | 1 | 105 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-11-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > Interior Finishes at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2027-03-01 | 2027-03-05 | 5 | 70 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-11-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2027-03-01 | 2027-03-01 | 1 | 101 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-11-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2027-03-01 | 2027-03-04 | 4 | 100 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-11-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2027-03-01 | 2027-03-10 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-11-U-MP-420 | Install Light Fixtures @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > MEP Trim at Units at 11th Lvl | TT_Task | TK_NotStart | 2027-03-01 | 2027-03-10 | 8 | 75 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-11-U-MP-430 | Install FA & Low Voltage Devices @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > MEP Trim at Units at 11th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-08 | 4 | 77 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-11-U-MP-440 | Install FP Sprinkler Heads @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > MEP Trim at Units at 11th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-04 | 2 | 79 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-11-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2027-03-04 | 2027-03-05 | 2 | 97 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-11-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2027-03-05 | 2027-03-08 | 2 | 100 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-11-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-09 | 2 | 97 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-11-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2027-03-09 | 2027-03-11 | 3 | 97 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-11-U-FN-390 | Install Kitchen Appliances @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-15 | 3 | 72 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-11-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > Interior Finishes at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2027-03-12 | 2027-03-15 | 2 | 97 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-11-U-FN-370 | Install Flooring & Base @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2027-03-23 | 2027-04-05 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-11-U-FN-400 | Rough Cleanup @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-07 | 2 | 57 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-11-U-FN-410 | Touch-up Paint @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2027-04-08 | 2027-04-09 | 2 | 78 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-12-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-15 | 7 | 5 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-12-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > Interior Finishes at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-15 | 5 | 58 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-12-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > MEP Eqp at Units at 12th Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-24 | 12 | 4 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-12-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > Interior Finishes at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-19 | 4 | 68 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-12-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-17 | 2 | 5 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-12-U-FN-300 | Install Shower Enclosures @ B/Rs L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2027-02-18 | 2027-02-23 | 4 | 5 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-12-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > MEP Eqp at Units at 12th Lvl | TT_Task | TK_NotStart | 2027-02-18 | 2027-02-23 | 4 | 90 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-12-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > Interior Finishes at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2027-02-22 | 2027-02-26 | 5 | 68 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-12-C-FN-130 | Install Trash Chute @ Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > Interior Finishes at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2027-02-22 | 2027-02-22 | 1 | 75 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-12-C-MP-100 | Install Elect & Low Voltage Panels @ Telecom/Elect Rm #1221- L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2027-02-22 | 2027-03-12 | 15 | 90 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-12-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > Interior Finishes at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-03-03 | 5 | 68 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-12-U-FN-310 | Paint Final Coat @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-03-04 | 6 | 4 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-12-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > Interior Finishes at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2027-03-04 | 2027-03-09 | 4 | 68 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-12-U-FN-330 | Install Door Hardware @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2027-03-05 | 2027-03-09 | 3 | 83 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-12-U-FN-340 | Install Toilet Accessories @ B/Rs - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2027-03-05 | 2027-03-09 | 3 | 83 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-12-U-MP-400 | Install HVAC Trim & Control @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > MEP Trim at Units at 12th Lvl | TT_Task | TK_NotStart | 2027-03-05 | 2027-03-11 | 5 | 81 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-12-U-MP-410 | Install Electrical Power Trim @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > MEP Trim at Units at 12th Lvl | TT_Task | TK_NotStart | 2027-03-05 | 2027-03-11 | 5 | 75 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-12-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > Interior Finishes at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2027-03-10 | 2027-03-10 | 1 | 98 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-12-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > Interior Finishes at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2027-03-10 | 2027-03-16 | 5 | 68 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-12-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2027-03-10 | 2027-03-10 | 1 | 94 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-12-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2027-03-10 | 2027-03-15 | 4 | 93 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-12-U-MP-420 | Install Light Fixtures @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > MEP Trim at Units at 12th Lvl | TT_Task | TK_NotStart | 2027-03-10 | 2027-03-19 | 8 | 75 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-12-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-22 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-12-U-MP-430 | Install FA & Low Voltage Devices @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > MEP Trim at Units at 12th Lvl | TT_Task | TK_NotStart | 2027-03-12 | 2027-03-17 | 4 | 77 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-12-U-MP-440 | Install FP Sprinkler Heads @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > MEP Trim at Units at 12th Lvl | TT_Task | TK_NotStart | 2027-03-12 | 2027-03-15 | 2 | 79 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-12-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2027-03-15 | 2027-03-16 | 2 | 90 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-12-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2027-03-16 | 2027-03-17 | 2 | 93 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-12-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-18 | 2 | 90 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-12-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2027-03-18 | 2027-03-22 | 3 | 90 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-12-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > Interior Finishes at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2027-03-23 | 2027-03-24 | 2 | 90 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-12-U-FN-390 | Install Kitchen Appliances @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2027-03-23 | 2027-03-25 | 3 | 71 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-12-U-FN-370 | Install Flooring & Base @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-19 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-12-U-FN-400 | Rough Cleanup @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2027-04-20 | 2027-04-21 | 2 | 54 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-12-U-FN-410 | Touch-up Paint @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2027-04-22 | 2027-04-23 | 2 | 68 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-14-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-24 | 7 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-14-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > Interior Finishes at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2027-02-18 | 2027-02-24 | 5 | 56 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-14-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > MEP Eqp at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-02-18 | 2027-03-05 | 12 | 5 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-14-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > Interior Finishes at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-03-02 | 4 | 66 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-14-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-02-26 | 2 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-14-U-FN-300 | Install Shower Enclosures @ B/Rs L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-03-01 | 2027-03-04 | 4 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-14-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > MEP Eqp at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-03-01 | 2027-03-04 | 4 | 90 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-14-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > Interior Finishes at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-09 | 5 | 66 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-14-C-FN-130 | Install Trash Chute @ Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > Interior Finishes at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-03 | 1 | 73 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-14-C-MP-100 | Install Mech Eqp @ Mech Eqp Rm #1421 - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-23 | 15 | 75 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-14-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > Interior Finishes at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-12 | 5 | 66 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-14-U-FN-310 | Paint Final Coat @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-15 | 6 | 5 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-14-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > Interior Finishes at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2027-03-15 | 2027-03-18 | 4 | 66 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-14-U-FN-330 | Install Door Hardware @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-03-16 | 2027-03-18 | 3 | 83 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-14-U-FN-340 | Install Toilet Accessories @ B/Rs - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-03-16 | 2027-03-18 | 3 | 83 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-14-U-MP-410 | Install Electrical Power Trim @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > MEP Trim at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-03-16 | 2027-03-22 | 5 | 75 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-14-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > Interior Finishes at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2027-03-19 | 2027-03-19 | 1 | 91 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-14-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > Interior Finishes at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2027-03-19 | 2027-03-25 | 5 | 66 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-14-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2027-03-19 | 2027-03-19 | 1 | 87 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-14-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2027-03-19 | 2027-03-22 | 2 | 86 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-14-U-MP-420 | Install Light Fixtures @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > MEP Trim at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-03-19 | 2027-03-30 | 8 | 75 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-14-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2027-03-23 | 2027-03-24 | 2 | 86 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-14-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-03-23 | 2027-04-01 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-14-U-MP-430 | Install FA & Low Voltage Devices @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > MEP Trim at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-03-23 | 2027-03-26 | 4 | 77 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-14-U-MP-440 | Install FP Sprinkler Heads @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > MEP Trim at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-03-23 | 2027-03-24 | 2 | 79 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-14-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-29 | 4 | 83 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-14-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-26 | 3 | 86 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-14-U-MP-400 | Install HVAC Trim & Control @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > MEP Trim at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-30 | 5 | 75 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-14-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - 14h Lvl | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2027-03-30 | 2027-03-31 | 2 | 83 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-14-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > Interior Finishes at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-02 | 2 | 83 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-14-U-FN-390 | Install Kitchen Appliances @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-04-02 | 2027-04-06 | 3 | 70 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-14-U-FN-370 | Install Flooring & Base @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-04-20 | 2027-05-03 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-14-U-FN-400 | Rough Cleanup @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-05-04 | 2027-05-05 | 2 | 51 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-14-U-FN-410 | Touch-up Paint @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-05-06 | 2027-05-07 | 2 | 58 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-15-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-03-05 | 7 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-15-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > Interior Finishes at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-03-01 | 2027-03-05 | 5 | 54 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-15-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > MEP Eqp at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-03-01 | 2027-03-16 | 12 | 6 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-15-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > Interior Finishes at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-11 | 4 | 64 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-15-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-09 | 2 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-15-U-FN-300 | Install Shower Enclosures @ B/Rs L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-03-10 | 2027-03-15 | 4 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-15-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > MEP Eqp at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-03-10 | 2027-03-15 | 4 | 87 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-15-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > Interior Finishes at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-03-12 | 2027-03-18 | 5 | 64 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-15-C-FN-130 | Install Trash Chute @ Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > Interior Finishes at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-03-12 | 2027-03-12 | 1 | 71 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-15-C-MP-100 | Install Low Voltage Panels @ Telecom Rm #1521- L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-03-12 | 2027-04-01 | 15 | 78 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-15-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > Interior Finishes at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-23 | 5 | 64 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-15-U-FN-310 | Paint Final Coat @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-24 | 6 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-15-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > Interior Finishes at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-29 | 4 | 64 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-15-U-FN-330 | Install Door Hardware @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-03-25 | 2027-03-29 | 3 | 80 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-15-U-FN-340 | Install Toilet Accessories @ B/Rs - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-03-25 | 2027-03-29 | 3 | 80 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-15-U-MP-400 | Install HVAC Trim & Control @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > MEP Trim at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-03-25 | 2027-03-31 | 5 | 78 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-15-U-MP-410 | Install Electrical Power Trim @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > MEP Trim at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-03-25 | 2027-03-31 | 5 | 72 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-15-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > Interior Finishes at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-03-30 | 2027-03-30 | 1 | 86 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-15-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > Interior Finishes at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-03-30 | 2027-04-05 | 5 | 64 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-15-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-03-30 | 2027-03-30 | 1 | 82 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-15-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-03-30 | 2027-04-02 | 4 | 81 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-15-U-MP-420 | Install Light Fixtures @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > MEP Trim at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-03-30 | 2027-04-08 | 8 | 72 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-15-U-MP-430 | Install FA & Low Voltage Devices @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > MEP Trim at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-06 | 4 | 74 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-15-U-MP-440 | Install FP Sprinkler Heads @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > MEP Trim at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-02 | 2 | 76 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-15-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-04-02 | 2027-04-05 | 2 | 78 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-15-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-04-02 | 2027-04-13 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-15-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-04-05 | 2027-04-06 | 2 | 81 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-15-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-07 | 2 | 78 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-15-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-04-07 | 2027-04-09 | 3 | 78 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-15-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > Interior Finishes at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-04-12 | 2027-04-13 | 2 | 78 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-15-U-FN-390 | Install Kitchen Appliances @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-04-14 | 2027-04-16 | 3 | 66 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-15-U-FN-370 | Install Flooring & Base @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-05-04 | 2027-05-17 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-15-U-FN-400 | Rough Cleanup @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-05-18 | 2027-05-19 | 2 | 45 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-15-U-FN-410 | Touch-up Paint @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-05-20 | 2027-05-21 | 2 | 50 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-16-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-03-09 | 2027-03-17 | 7 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-16-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > Interior Finishes at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-17 | 5 | 51 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-16-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > MEP Eqp at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-26 | 12 | 6 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-16-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > Interior Finishes at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-03-18 | 2027-03-23 | 4 | 61 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-16-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-03-18 | 2027-03-19 | 2 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-16-U-FN-300 | Install Shower Enclosures @ B/Rs L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-03-22 | 2027-03-25 | 4 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-16-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > MEP Eqp at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-03-22 | 2027-03-25 | 4 | 89 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-16-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > Interior Finishes at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-30 | 5 | 61 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-16-C-FN-130 | Install Trash Chute @ Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > Interior Finishes at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-24 | 1 | 68 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-16-C-MP-100 | Install Elect Panels & Stack Meters @ Stack Vault #1621- L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-04-13 | 15 | 109 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-16-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > Interior Finishes at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-03-29 | 2027-04-02 | 5 | 61 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-16-U-FN-310 | Paint Final Coat @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-03-29 | 2027-04-05 | 6 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-16-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > Interior Finishes at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-04-05 | 2027-04-08 | 4 | 61 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-16-U-FN-330 | Install Door Hardware @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-08 | 3 | 82 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-16-U-FN-340 | Install Toilet Accessories @ B/Rs - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-08 | 3 | 82 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-16-U-MP-400 | Install HVAC Trim & Control @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > MEP Trim at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-12 | 5 | 80 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-16-U-MP-410 | Install Electrical Power Trim @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > MEP Trim at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-12 | 5 | 74 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-16-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > Interior Finishes at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-09 | 1 | 117 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-16-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > Interior Finishes at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-15 | 5 | 61 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-16-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-09 | 1 | 113 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-16-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-14 | 4 | 112 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-16-U-MP-420 | Install Light Fixtures @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > MEP Trim at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-20 | 8 | 74 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-16-U-MP-430 | Install FA & Low Voltage Devices @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > MEP Trim at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-04-13 | 2027-04-16 | 4 | 76 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-16-U-MP-440 | Install FP Sprinkler Heads @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > MEP Trim at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-04-13 | 2027-04-14 | 2 | 78 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-16-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-04-14 | 2027-04-15 | 2 | 109 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-16-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-04-14 | 2027-04-23 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-16-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-04-15 | 2027-04-16 | 2 | 112 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-16-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-04-16 | 2027-04-19 | 2 | 109 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-16-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-04-19 | 2027-04-21 | 3 | 109 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-16-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > Interior Finishes at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-04-22 | 2027-04-23 | 2 | 109 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-16-U-FN-390 | Install Kitchen Appliances @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-04-28 | 3 | 68 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-16-U-FN-370 | Install Flooring & Base @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-05-18 | 2027-06-01 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-16-U-FN-400 | Rough Cleanup @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-06-02 | 2027-06-03 | 2 | 45 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-16-U-FN-410 | Touch-up Paint @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-06-04 | 2027-06-07 | 2 | 79 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-17-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-03-19 | 2027-03-29 | 7 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-17-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > Interior Finishes at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-03-23 | 2027-03-29 | 5 | 48 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-17-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > MEP Eqp at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-03-23 | 2027-04-07 | 12 | 6 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-17-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > Interior Finishes at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-03-30 | 2027-04-02 | 4 | 58 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-17-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-03-30 | 2027-03-31 | 2 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-17-U-FN-300 | Install Shower Enclosures @ B/Rs L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-06 | 4 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-17-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > MEP Eqp at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-06 | 4 | 85 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-17-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > Interior Finishes at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-04-05 | 2027-04-09 | 5 | 58 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-17-C-FN-130 | Install Trash Chute @ Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > Interior Finishes at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-04-05 | 2027-04-05 | 1 | 65 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-17-C-MP-100 | Install Mech Eqp @ Mech Eqp Rm #1721 - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-04-05 | 2027-04-23 | 15 | 70 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-17-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > Interior Finishes at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-04-08 | 2027-04-14 | 5 | 58 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-17-U-FN-310 | Paint Final Coat @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-04-08 | 2027-04-15 | 6 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-17-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > Interior Finishes at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-04-15 | 2027-04-20 | 4 | 58 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-17-U-FN-330 | Install Door Hardware @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-04-16 | 2027-04-20 | 3 | 78 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-17-U-FN-340 | Install Toilet Accessories @ B/Rs - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-04-16 | 2027-04-20 | 3 | 78 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-17-U-MP-410 | Install Electrical Power Trim @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > MEP Trim at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-04-16 | 2027-04-22 | 5 | 70 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-17-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > Interior Finishes at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-04-21 | 2027-04-21 | 1 | 111 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-17-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > Interior Finishes at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-04-21 | 2027-04-27 | 5 | 58 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-17-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-04-21 | 2027-04-21 | 1 | 107 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-17-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-04-21 | 2027-04-22 | 2 | 106 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-17-U-MP-420 | Install Light Fixtures @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > MEP Trim at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-04-21 | 2027-04-30 | 8 | 70 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-17-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-04-23 | 2027-04-26 | 2 | 106 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-17-U-MP-430 | Install FA & Low Voltage Devices @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > MEP Trim at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-04-23 | 2027-04-28 | 4 | 72 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-17-U-MP-440 | Install FP Sprinkler Heads @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > MEP Trim at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-04-23 | 2027-04-26 | 2 | 74 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-17-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-04-29 | 4 | 103 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-17-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-04-28 | 3 | 106 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-17-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-05-05 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-17-U-MP-400 | Install HVAC Trim & Control @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > MEP Trim at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-04-30 | 5 | 70 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-17-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-04-30 | 2027-05-03 | 2 | 103 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-17-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > Interior Finishes at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-05-04 | 2027-05-05 | 2 | 103 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-17-U-FN-390 | Install Kitchen Appliances @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-05-06 | 2027-05-10 | 3 | 64 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-17-U-FN-370 | Install Flooring & Base @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-06-01 | 2027-06-14 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-17-U-FN-400 | Rough Cleanup @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-06-15 | 2027-06-16 | 2 | 40 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-17-U-FN-410 | Touch-up Paint @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-06-17 | 2027-06-18 | 2 | 72 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-18-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-03-31 | 2027-04-08 | 7 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-18-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > Interior Finishes at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-04-02 | 2027-04-08 | 5 | 45 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-18-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > MEP Eqp at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-04-02 | 2027-04-19 | 12 | 6 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-18-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > Interior Finishes at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-14 | 4 | 55 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-18-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-12 | 2 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-18-U-FN-300 | Install Shower Enclosures @ B/Rs L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-04-13 | 2027-04-16 | 4 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-18-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > MEP Eqp at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-04-13 | 2027-04-16 | 4 | 81 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-18-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > Interior Finishes at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-04-15 | 2027-04-21 | 5 | 55 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-18-C-FN-130 | Install Trash Chute @ Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > Interior Finishes at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-04-15 | 2027-04-15 | 1 | 62 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-18-C-MP-100 | Install Elect & Low Voltage Panels @ Telecom/Elect Rm #1821- L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-04-15 | 2027-05-05 | 15 | 95 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-18-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > Interior Finishes at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-04-20 | 2027-04-26 | 5 | 55 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-18-U-FN-310 | Paint Final Coat @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-04-20 | 2027-04-27 | 6 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-18-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > Interior Finishes at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-04-27 | 2027-04-30 | 4 | 55 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-18-U-FN-330 | Install Door Hardware @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-04-28 | 2027-04-30 | 3 | 74 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-18-U-FN-340 | Install Toilet Accessories @ B/Rs - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-04-28 | 2027-04-30 | 3 | 74 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-18-U-MP-400 | Install HVAC Trim & Control @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > MEP Trim at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-04-28 | 2027-05-04 | 5 | 72 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-18-U-MP-410 | Install Electrical Power Trim @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > MEP Trim at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-04-28 | 2027-05-04 | 5 | 66 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-18-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > Interior Finishes at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-05-03 | 2027-05-03 | 1 | 103 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-18-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > Interior Finishes at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-05-03 | 2027-05-07 | 5 | 55 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-18-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-05-03 | 2027-05-03 | 1 | 99 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-18-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-05-03 | 2027-05-06 | 4 | 98 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-18-U-MP-420 | Install Light Fixtures @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > MEP Trim at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-05-03 | 2027-05-12 | 8 | 66 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-18-U-MP-430 | Install FA & Low Voltage Devices @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > MEP Trim at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-10 | 4 | 68 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-18-U-MP-440 | Install FP Sprinkler Heads @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > MEP Trim at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-06 | 2 | 70 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-18-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-05-06 | 2027-05-07 | 2 | 95 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-18-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-05-06 | 2027-05-17 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-18-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-05-07 | 2027-05-10 | 2 | 98 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-18-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-11 | 2 | 95 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-18-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-05-11 | 2027-05-13 | 3 | 95 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-18-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > Interior Finishes at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-05-14 | 2027-05-17 | 2 | 95 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-18-U-FN-390 | Install Kitchen Appliances @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-05-18 | 2027-05-20 | 3 | 60 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-18-U-FN-370 | Install Flooring & Base @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-06-14 | 2027-06-25 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-18-U-FN-400 | Rough Cleanup @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-06-28 | 2027-06-29 | 2 | 35 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-18-U-FN-410 | Touch-up Paint @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-06-30 | 2027-07-01 | 2 | 63 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-19-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-04-12 | 2027-04-20 | 7 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-19-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > Interior Finishes at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-04-14 | 2027-04-20 | 5 | 42 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-19-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > MEP Eqp at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-04-14 | 2027-04-29 | 12 | 6 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-19-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > Interior Finishes at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-04-21 | 2027-04-26 | 4 | 52 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-19-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-04-21 | 2027-04-22 | 2 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-19-U-FN-300 | Install Shower Enclosures @ B/Rs L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-04-23 | 2027-04-28 | 4 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-19-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > MEP Eqp at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-04-23 | 2027-04-28 | 4 | 77 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-19-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > Interior Finishes at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-04-27 | 2027-05-03 | 5 | 52 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-19-C-FN-130 | Install Trash Chute @ Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > Interior Finishes at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-04-27 | 2027-04-27 | 1 | 59 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-19-C-MP-100 | Install Elect & Low Voltage Panels @ Telecom/Elect Rm #1921- L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-04-27 | 2027-05-17 | 15 | 87 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-19-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > Interior Finishes at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-04-30 | 2027-05-06 | 5 | 52 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-19-U-FN-310 | Paint Final Coat @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-04-30 | 2027-05-07 | 6 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-19-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > Interior Finishes at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-05-07 | 2027-05-12 | 4 | 52 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-19-U-FN-330 | Install Door Hardware @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-12 | 3 | 70 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-19-U-FN-340 | Install Toilet Accessories @ B/Rs - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-12 | 3 | 70 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-19-U-MP-400 | Install HVAC Trim & Control @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > MEP Trim at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-14 | 5 | 68 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-19-U-MP-410 | Install Electrical Power Trim @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > MEP Trim at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-14 | 5 | 62 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-19-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > Interior Finishes at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-05-13 | 2027-05-13 | 1 | 95 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-19-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > Interior Finishes at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-05-13 | 2027-05-19 | 5 | 52 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-19-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-05-13 | 2027-05-13 | 1 | 91 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-19-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-05-13 | 2027-05-18 | 4 | 90 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-19-U-MP-420 | Install Light Fixtures @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > MEP Trim at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-05-13 | 2027-05-24 | 8 | 62 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-19-U-MP-430 | Install FA & Low Voltage Devices @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > MEP Trim at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-05-17 | 2027-05-20 | 4 | 64 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-19-U-MP-440 | Install FP Sprinkler Heads @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > MEP Trim at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-05-17 | 2027-05-18 | 2 | 66 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-19-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-05-18 | 2027-05-19 | 2 | 87 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-19-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-05-18 | 2027-05-27 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-19-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-05-20 | 2 | 90 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-19-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-05-20 | 2027-05-21 | 2 | 87 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-19-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-05-21 | 2027-05-25 | 3 | 87 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-19-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > Interior Finishes at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-05-26 | 2027-05-27 | 2 | 87 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-19-U-FN-390 | Install Kitchen Appliances @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-05-28 | 2027-06-02 | 3 | 56 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-19-U-FN-370 | Install Flooring & Base @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-06-25 | 2027-07-09 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-19-U-FN-400 | Rough Cleanup @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-07-12 | 2027-07-13 | 2 | 30 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-19-U-FN-410 | Touch-up Paint @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-07-14 | 2027-07-15 | 2 | 54 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-20-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-04-22 | 2027-04-30 | 7 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-20-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > Interior Finishes at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-04-30 | 5 | 39 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-20-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > MEP Eqp at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-05-11 | 12 | 6 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-20-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > Interior Finishes at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-05-03 | 2027-05-06 | 4 | 49 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-20-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-05-03 | 2027-05-04 | 2 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-20-U-FN-300 | Install Shower Enclosures @ B/Rs L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-10 | 4 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-20-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > MEP Eqp at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-10 | 4 | 73 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-20-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > Interior Finishes at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-05-07 | 2027-05-13 | 5 | 49 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-20-C-FN-130 | Install Trash Chute @ Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > Interior Finishes at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-05-07 | 2027-05-07 | 1 | 56 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-20-C-MP-100 | Install Mech Eqp @ Mech Eqp Rm #2021 - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-05-07 | 2027-05-27 | 15 | 58 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-20-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > Interior Finishes at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-05-12 | 2027-05-18 | 5 | 49 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-20-U-FN-310 | Paint Final Coat @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-05-12 | 2027-05-19 | 6 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-20-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > Interior Finishes at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-05-24 | 4 | 49 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-20-U-FN-330 | Install Door Hardware @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-05-20 | 2027-05-24 | 3 | 66 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-20-U-FN-340 | Install Toilet Accessories @ B/Rs - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-05-20 | 2027-05-24 | 3 | 66 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-20-U-MP-410 | Install Electrical Power Trim @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > MEP Trim at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-05-20 | 2027-05-26 | 5 | 58 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-20-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > Interior Finishes at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-05-25 | 1 | 87 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-20-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > Interior Finishes at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-06-01 | 5 | 49 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-20-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-05-25 | 1 | 83 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-20-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-05-26 | 2 | 82 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-20-U-MP-420 | Install Light Fixtures @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > MEP Trim at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-06-04 | 8 | 58 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-20-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-05-27 | 2027-05-28 | 2 | 82 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-20-U-MP-430 | Install FA & Low Voltage Devices @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > MEP Trim at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-05-27 | 2027-06-02 | 4 | 60 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-20-U-MP-440 | Install FP Sprinkler Heads @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > MEP Trim at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-05-27 | 2027-05-28 | 2 | 62 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-20-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-05-28 | 2027-06-03 | 4 | 79 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-20-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-05-28 | 2027-06-02 | 3 | 82 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-20-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-05-28 | 2027-06-09 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-20-U-MP-400 | Install HVAC Trim & Control @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > MEP Trim at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-05-28 | 2027-06-04 | 5 | 58 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-20-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-06-04 | 2027-06-07 | 2 | 79 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-20-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > Interior Finishes at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-06-08 | 2027-06-09 | 2 | 79 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-20-U-FN-390 | Install Kitchen Appliances @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-06-10 | 2027-06-14 | 3 | 52 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-20-U-FN-370 | Install Flooring & Base @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-22 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-20-U-FN-400 | Rough Cleanup @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-07-23 | 2027-07-26 | 2 | 25 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-20-U-FN-410 | Touch-up Paint @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-07-27 | 2027-07-28 | 2 | 45 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-21-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-05-04 | 2027-05-12 | 7 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-21-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > Interior Finishes at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-05-06 | 2027-05-12 | 5 | 36 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-21-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > MEP Eqp at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-05-06 | 2027-05-21 | 12 | 6 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-21-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > Interior Finishes at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-05-13 | 2027-05-18 | 4 | 46 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-21-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-05-13 | 2027-05-14 | 2 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-21-U-FN-300 | Install Shower Enclosures @ B/Rs L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-05-17 | 2027-05-20 | 4 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-21-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > MEP Eqp at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-05-17 | 2027-05-20 | 4 | 69 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-21-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > Interior Finishes at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-05-25 | 5 | 46 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-21-C-FN-130 | Install Trash Chute @ Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > Interior Finishes at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-05-19 | 1 | 53 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-21-C-MP-100 | Install Low Voltage Panels @ Telecom Rm #2121- L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-06-09 | 15 | 71 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-21-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > Interior Finishes at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-05-24 | 2027-05-28 | 5 | 46 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-21-U-FN-310 | Paint Final Coat @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-05-24 | 2027-06-01 | 6 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-21-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > Interior Finishes at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-06-01 | 2027-06-04 | 4 | 46 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-21-U-FN-330 | Install Door Hardware @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-06-02 | 2027-06-04 | 3 | 62 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-21-U-FN-340 | Install Toilet Accessories @ B/Rs - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-06-02 | 2027-06-04 | 3 | 62 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-21-U-MP-400 | Install HVAC Trim & Control @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > MEP Trim at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-06-02 | 2027-06-08 | 5 | 60 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-21-U-MP-410 | Install Electrical Power Trim @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > MEP Trim at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-06-02 | 2027-06-08 | 5 | 54 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-21-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > Interior Finishes at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-06-07 | 2027-06-07 | 1 | 79 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-21-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > Interior Finishes at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-06-07 | 2027-06-11 | 5 | 46 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-21-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-06-07 | 2027-06-07 | 1 | 75 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-21-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-06-07 | 2027-06-10 | 4 | 74 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-21-U-MP-420 | Install Light Fixtures @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > MEP Trim at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-06-07 | 2027-06-16 | 8 | 54 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-21-U-MP-430 | Install FA & Low Voltage Devices @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > MEP Trim at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-06-09 | 2027-06-14 | 4 | 56 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-21-U-MP-440 | Install FP Sprinkler Heads @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > MEP Trim at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-06-09 | 2027-06-10 | 2 | 58 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-21-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-06-10 | 2027-06-11 | 2 | 71 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-21-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-06-10 | 2027-06-21 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-21-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-06-11 | 2027-06-14 | 2 | 74 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-21-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-06-14 | 2027-06-15 | 2 | 71 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-21-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-06-15 | 2027-06-17 | 3 | 71 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-21-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > Interior Finishes at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-06-18 | 2027-06-21 | 2 | 71 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-21-U-FN-390 | Install Kitchen Appliances @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-06-22 | 2027-06-24 | 3 | 48 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-21-U-FN-370 | Install Flooring & Base @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-08-04 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-21-U-FN-400 | Rough Cleanup @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-08-05 | 2027-08-06 | 2 | 20 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-21-U-FN-410 | Touch-up Paint @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-08-09 | 2027-08-10 | 2 | 36 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-22-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-05-14 | 2027-05-24 | 7 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-22-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > Interior Finishes at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-05-18 | 2027-05-24 | 5 | 33 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-22-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > MEP Eqp at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-05-18 | 2027-06-03 | 12 | 6 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-22-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > Interior Finishes at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-05-28 | 4 | 43 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-22-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-05-26 | 2 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-22-U-FN-300 | Install Shower Enclosures @ B/Rs L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-05-27 | 2027-06-02 | 4 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-22-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > MEP Eqp at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-05-27 | 2027-06-02 | 4 | 65 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-22-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > Interior Finishes at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-06-01 | 2027-06-07 | 5 | 43 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-22-C-FN-130 | Install Trash Chute @ Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > Interior Finishes at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-06-01 | 2027-06-01 | 1 | 50 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-22-C-MP-100 | Install Elect & Panels & Stack Meters @ Stack Vault #2221 - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-06-01 | 2027-06-21 | 15 | 63 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-22-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > Interior Finishes at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-06-04 | 2027-06-10 | 5 | 43 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-22-U-FN-310 | Paint Final Coat @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-06-04 | 2027-06-11 | 6 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-22-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > Interior Finishes at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-06-11 | 2027-06-16 | 4 | 43 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-22-U-FN-330 | Install Door Hardware @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-06-14 | 2027-06-16 | 3 | 58 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-22-U-FN-340 | Install Toilet Accessories @ B/Rs - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-06-14 | 2027-06-16 | 3 | 58 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-22-U-MP-400 | Install HVAC Trim & Control @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > MEP Trim at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-06-14 | 2027-06-18 | 5 | 56 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-22-U-MP-410 | Install Electrical Power Trim @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > MEP Trim at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-06-14 | 2027-06-18 | 5 | 50 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-22-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > Interior Finishes at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-06-17 | 2027-06-17 | 1 | 71 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-22-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > Interior Finishes at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-06-17 | 2027-06-23 | 5 | 43 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-22-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-06-17 | 2027-06-17 | 1 | 67 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-22-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-06-17 | 2027-06-22 | 4 | 66 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-22-U-MP-420 | Install Light Fixtures @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > MEP Trim at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-06-17 | 2027-06-28 | 8 | 50 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-22-U-MP-430 | Install FA & Low Voltage Devices @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > MEP Trim at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-06-21 | 2027-06-24 | 4 | 52 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-22-U-MP-440 | Install FP Sprinkler Heads @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > MEP Trim at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-06-21 | 2027-06-22 | 2 | 54 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-22-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-06-22 | 2027-06-23 | 2 | 63 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-22-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-06-22 | 2027-07-01 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-22-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-06-23 | 2027-06-24 | 2 | 66 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-22-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-25 | 2 | 63 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-22-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-06-25 | 2027-06-29 | 3 | 63 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-22-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > Interior Finishes at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-06-30 | 2027-07-01 | 2 | 63 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-22-U-FN-390 | Install Kitchen Appliances @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-07-02 | 2027-07-07 | 3 | 44 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-22-U-FN-370 | Install Flooring & Base @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-08-04 | 2027-08-17 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-22-U-FN-400 | Rough Cleanup @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-19 | 2 | 15 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-22-U-FN-410 | Touch-up Paint @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-08-20 | 2027-08-23 | 2 | 27 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-23-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-05-26 | 2027-06-04 | 7 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-23-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > Interior Finishes at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-05-28 | 2027-06-04 | 5 | 30 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-23-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > MEP Eqp at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-05-28 | 2027-06-15 | 12 | 6 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-23-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > Interior Finishes at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-06-07 | 2027-06-10 | 4 | 40 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-23-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-06-07 | 2027-06-08 | 2 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-23-U-FN-300 | Install Shower Enclosures @ B/Rs L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-06-09 | 2027-06-14 | 4 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-23-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > MEP Eqp at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-06-09 | 2027-06-14 | 4 | 61 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-23-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > Interior Finishes at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-06-11 | 2027-06-17 | 5 | 40 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-23-C-FN-130 | Install Trash Chute @ Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > Interior Finishes at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-06-11 | 2027-06-11 | 1 | 47 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-23-C-MP-100 | Install Mech Eqp @ Mech Eqp Rm #2321 - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-06-11 | 2027-07-01 | 15 | 46 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-23-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > Interior Finishes at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-06-16 | 2027-06-22 | 5 | 40 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-23-U-FN-310 | Paint Final Coat @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-06-16 | 2027-06-23 | 6 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-23-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > Interior Finishes at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-06-23 | 2027-06-28 | 4 | 40 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-23-U-FN-330 | Install Door Hardware @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-28 | 3 | 54 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-23-U-FN-340 | Install Toilet Accessories @ B/Rs - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-28 | 3 | 54 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-23-U-MP-410 | Install Electrical Power Trim @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > MEP Trim at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-30 | 5 | 46 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-23-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > Interior Finishes at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-06-29 | 1 | 63 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-23-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > Interior Finishes at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-07-06 | 5 | 40 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-23-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-06-29 | 1 | 59 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-23-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-06-30 | 2 | 58 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-23-U-MP-420 | Install Light Fixtures @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > MEP Trim at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-07-09 | 8 | 46 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-23-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-02 | 2 | 58 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-23-U-MP-430 | Install FA & Low Voltage Devices @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > MEP Trim at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-07 | 4 | 48 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-23-U-MP-440 | Install FP Sprinkler Heads @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > MEP Trim at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-02 | 2 | 50 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-23-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-07-02 | 2027-07-08 | 4 | 55 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-23-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-07-02 | 2027-07-07 | 3 | 58 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-23-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-07-02 | 2027-07-14 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-23-U-MP-400 | Install HVAC Trim & Control @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > MEP Trim at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-07-02 | 2027-07-09 | 5 | 46 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-23-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-12 | 2 | 55 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-23-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > Interior Finishes at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-07-13 | 2027-07-14 | 2 | 55 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-23-U-FN-390 | Install Kitchen Appliances @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-19 | 3 | 40 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-23-U-FN-370 | Install Flooring & Base @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-08-17 | 2027-08-30 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-23-U-FN-400 | Rough Cleanup @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-08-31 | 2027-09-01 | 2 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-23-U-FN-410 | Touch-up Paint @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-09-02 | 2027-09-03 | 2 | 18 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-24-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-06-08 | 2027-06-16 | 7 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-24-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > Interior Finishes at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-06-10 | 2027-06-16 | 5 | 27 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-24-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > MEP Eqp at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-06-10 | 2027-06-25 | 12 | 6 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-24-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > Interior Finishes at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-06-17 | 2027-06-22 | 4 | 37 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-24-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-06-17 | 2027-06-18 | 2 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-24-U-FN-300 | Install Shower Enclosures @ B/Rs L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-06-21 | 2027-06-24 | 4 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-24-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > MEP Eqp at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-06-21 | 2027-06-24 | 4 | 57 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-24-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > Interior Finishes at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-06-23 | 2027-06-29 | 5 | 37 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-24-C-FN-130 | Install Trash Chute @ Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > Interior Finishes at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-06-23 | 2027-06-23 | 1 | 44 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-24-C-MP-100 | Install Elect & Low Voltage Panels @ Telecom/Elect Rm #2421- L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-06-23 | 2027-07-14 | 15 | 47 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-24-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > Interior Finishes at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-06-28 | 2027-07-02 | 5 | 37 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-24-U-FN-310 | Paint Final Coat @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-06-28 | 2027-07-06 | 6 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-24-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > Interior Finishes at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-07-06 | 2027-07-09 | 4 | 37 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-24-U-FN-330 | Install Door Hardware @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-07-07 | 2027-07-09 | 3 | 50 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-24-U-FN-340 | Install Toilet Accessories @ B/Rs - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-07-07 | 2027-07-09 | 3 | 50 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-24-U-MP-400 | Install HVAC Trim & Control @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > MEP Trim at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-07-07 | 2027-07-13 | 5 | 48 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-24-U-MP-410 | Install Electrical Power Trim @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > MEP Trim at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-07-07 | 2027-07-13 | 5 | 42 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-24-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > Interior Finishes at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-07-12 | 2027-07-12 | 1 | 55 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-24-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > Interior Finishes at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-07-12 | 2027-07-16 | 5 | 37 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-24-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-07-12 | 2027-07-12 | 1 | 51 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-24-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-07-12 | 2027-07-15 | 4 | 50 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-24-U-MP-420 | Install Light Fixtures @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > MEP Trim at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-07-12 | 2027-07-21 | 8 | 42 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-24-U-MP-430 | Install FA & Low Voltage Devices @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > MEP Trim at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-07-14 | 2027-07-19 | 4 | 44 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-24-U-MP-440 | Install FP Sprinkler Heads @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > MEP Trim at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-07-14 | 2027-07-15 | 2 | 46 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-24-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-16 | 2 | 47 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-24-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-26 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-24-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-07-16 | 2027-07-19 | 2 | 50 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-24-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-07-19 | 2027-07-20 | 2 | 47 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-24-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-07-20 | 2027-07-22 | 3 | 47 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-24-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > Interior Finishes at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-07-23 | 2027-07-26 | 2 | 47 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-24-U-FN-390 | Install Kitchen Appliances @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-07-27 | 2027-07-29 | 3 | 36 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-24-U-FN-370 | Install Flooring & Base @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-08-30 | 2027-09-13 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-24-U-FN-400 | Rough Cleanup @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-09-14 | 2027-09-15 | 2 | 5 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-24-U-FN-410 | Touch-up Paint @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-09-16 | 2027-09-17 | 2 | 9 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-25-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-06-18 | 2027-06-28 | 7 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-25-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > Interior Finishes at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-06-22 | 2027-06-28 | 5 | 24 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-25-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > MEP Eqp at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-06-22 | 2027-07-08 | 12 | 6 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-25-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > Interior Finishes at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-07-02 | 4 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-25-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-06-30 | 2 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-25-U-FN-300 | Install Shower Enclosures @ B/Rs L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-07 | 4 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-25-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > MEP Eqp at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-07 | 4 | 52 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-25-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > Interior Finishes at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-07-06 | 2027-07-12 | 5 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-25-C-FN-130 | Install Trash Chute @ Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > Interior Finishes at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-07-06 | 2027-07-06 | 1 | 41 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-25-C-MP-100 | Install Elect & Panels & Stack Meters @ Stack Vault #2521 - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-07-06 | 2027-07-26 | 15 | 39 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-25-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > Interior Finishes at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-15 | 5 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-25-U-FN-310 | Paint Final Coat @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-16 | 6 | 6 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-25-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > Interior Finishes at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-07-16 | 2027-07-21 | 4 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-25-U-FN-330 | Install Door Hardware @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-07-19 | 2027-07-21 | 3 | 45 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-25-U-FN-340 | Install Toilet Accessories @ B/Rs - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-07-19 | 2027-07-21 | 3 | 45 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-25-U-MP-400 | Install HVAC Trim & Control @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > MEP Trim at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-07-19 | 2027-07-23 | 5 | 43 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-25-U-MP-410 | Install Electrical Power Trim @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > MEP Trim at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-07-19 | 2027-07-23 | 5 | 37 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-25-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > Interior Finishes at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-07-22 | 1 | 47 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-25-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > Interior Finishes at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-07-28 | 5 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-25-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-07-22 | 1 | 43 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-25-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-07-27 | 4 | 42 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-25-U-MP-420 | Install Light Fixtures @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > MEP Trim at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-08-02 | 8 | 37 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-25-U-MP-430 | Install FA & Low Voltage Devices @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > MEP Trim at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-07-26 | 2027-07-29 | 4 | 39 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-25-U-MP-440 | Install FP Sprinkler Heads @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > MEP Trim at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-07-26 | 2027-07-27 | 2 | 41 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-25-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-07-27 | 2027-07-28 | 2 | 39 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-25-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-07-27 | 2027-08-05 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-25-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-07-28 | 2027-07-29 | 2 | 42 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-25-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-07-29 | 2027-07-30 | 2 | 39 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-25-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-07-30 | 2027-08-03 | 3 | 39 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-25-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > Interior Finishes at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-08-04 | 2027-08-05 | 2 | 39 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-25-U-FN-390 | Install Kitchen Appliances @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-08-06 | 2027-08-10 | 3 | 31 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-25-U-FN-370 | Install Flooring & Base @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-09-10 | 2027-09-23 | 10 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-25-U-FN-400 | Rough Cleanup @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-09-24 | 2027-09-27 | 2 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-25-U-FN-410 | Touch-up Paint @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-09-28 | 2027-09-29 | 2 | 1 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-26-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-07-08 | 7 | 8 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-26-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > Interior Finishes at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-08 | 5 | 22 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-26-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > MEP Eqp at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-19 | 12 | 7 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-26-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > Interior Finishes at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-14 | 4 | 32 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-26-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-12 | 2 | 8 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-26-U-FN-300 | Install Shower Enclosures @ B/Rs L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-07-13 | 2027-07-16 | 4 | 8 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-26-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > MEP Eqp at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-07-13 | 2027-07-16 | 4 | 57 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-26-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > Interior Finishes at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-21 | 5 | 32 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-26-C-FN-130 | Install Trash Chute @ Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > Interior Finishes at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-15 | 1 | 39 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-26-C-MP-100 | Install Mech Eqp @ Mech Eqp Rm #2621- L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-08-04 | 15 | 42 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-26-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > Interior Finishes at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-07-20 | 2027-07-26 | 5 | 32 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-26-U-FN-310 | Paint Final Coat @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-07-20 | 2027-07-27 | 6 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-26-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > Interior Finishes at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-07-27 | 2027-07-30 | 4 | 32 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-26-U-FN-330 | Install Door Hardware @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-07-28 | 2027-07-30 | 3 | 50 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-26-U-FN-340 | Install Toilet Accessories @ B/Rs - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-07-28 | 2027-07-30 | 3 | 50 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-26-U-MP-410 | Install Electrical Power Trim @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > MEP Trim at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-07-28 | 2027-08-03 | 5 | 42 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-26-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > Interior Finishes at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-02 | 1 | 81 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-26-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > Interior Finishes at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-06 | 5 | 32 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-26-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-02 | 1 | 77 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-26-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-03 | 2 | 76 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-26-U-MP-420 | Install Light Fixtures @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > MEP Trim at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-11 | 8 | 42 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-26-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-08-04 | 2027-08-05 | 2 | 76 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-26-U-MP-430 | Install FA & Low Voltage Devices @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > MEP Trim at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-08-04 | 2027-08-09 | 4 | 44 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-26-U-MP-440 | Install FP Sprinkler Heads @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > MEP Trim at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-08-04 | 2027-08-05 | 2 | 46 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-26-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-08-05 | 2027-08-10 | 4 | 73 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-26-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-08-05 | 2027-08-09 | 3 | 76 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-26-U-MP-400 | Install HVAC Trim & Control @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > MEP Trim at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-08-05 | 2027-08-11 | 5 | 42 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-26-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-08-06 | 2027-08-17 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-26-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-08-11 | 2027-08-12 | 2 | 73 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-26-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > Interior Finishes at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-08-13 | 2027-08-16 | 2 | 73 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-26-U-FN-370 | Install Flooring & Base @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-31 | 10 | 28 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-26-U-FN-390 | Install Kitchen Appliances @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-20 | 3 | 35 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-26-U-FN-400 | Rough Cleanup @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-09-01 | 2027-09-02 | 2 | 28 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-26-U-FN-410 | Touch-up Paint @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-07 | 2 | 58 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-27-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-19 | 7 | 9 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-27-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > Interior Finishes at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-07-13 | 2027-07-19 | 5 | 20 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-27-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > MEP Eqp at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-07-13 | 2027-07-28 | 12 | 8 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-27-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > Interior Finishes at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-07-20 | 2027-07-23 | 4 | 30 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-27-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-07-20 | 2027-07-21 | 2 | 9 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-27-U-FN-300 | Install Shower Enclosures @ B/Rs L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-07-27 | 4 | 9 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-27-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > MEP Eqp at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-07-27 | 4 | 52 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-27-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > Interior Finishes at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-07-26 | 2027-07-30 | 5 | 30 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-27-C-FN-130 | Install Trash Chute @ Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > Interior Finishes at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-07-26 | 2027-07-26 | 1 | 37 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-27-C-MP-100 | Install Low Voltage Panels @ Telecom Rm #2721- L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-07-26 | 2027-08-13 | 15 | 66 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-27-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > Interior Finishes at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-07-29 | 2027-08-04 | 5 | 30 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-27-U-FN-310 | Paint Final Coat @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-07-29 | 2027-08-05 | 6 | 8 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-27-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > Interior Finishes at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-08-05 | 2027-08-10 | 4 | 30 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-27-U-FN-330 | Install Door Hardware @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-08-06 | 2027-08-10 | 3 | 45 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-27-U-FN-340 | Install Toilet Accessories @ B/Rs - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-08-06 | 2027-08-10 | 3 | 45 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-27-U-MP-400 | Install HVAC Trim & Control @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > MEP Trim at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-08-06 | 2027-08-12 | 5 | 43 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-27-U-MP-410 | Install Electrical Power Trim @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > MEP Trim at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-08-06 | 2027-08-12 | 5 | 37 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-27-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > Interior Finishes at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-08-11 | 2027-08-11 | 1 | 74 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-27-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > Interior Finishes at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-08-11 | 2027-08-17 | 5 | 30 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-27-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-08-11 | 2027-08-11 | 1 | 70 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-27-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-08-11 | 2027-08-16 | 4 | 69 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-27-U-MP-420 | Install Light Fixtures @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > MEP Trim at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-08-11 | 2027-08-20 | 8 | 37 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-27-U-MP-430 | Install FA & Low Voltage Devices @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > MEP Trim at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-08-13 | 2027-08-18 | 4 | 39 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-27-U-MP-440 | Install FP Sprinkler Heads @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > MEP Trim at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-08-13 | 2027-08-16 | 2 | 41 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-27-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-08-16 | 2027-08-17 | 2 | 66 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-27-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-08-17 | 2027-08-18 | 2 | 69 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-27-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-19 | 2 | 66 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-27-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-27 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-27-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-08-19 | 2027-08-23 | 3 | 66 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-27-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > Interior Finishes at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-08-24 | 2027-08-25 | 2 | 66 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-27-U-FN-370 | Install Flooring & Base @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-08-30 | 2027-09-13 | 10 | 22 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-27-U-FN-390 | Install Kitchen Appliances @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-08-30 | 2027-09-01 | 3 | 29 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-27-U-FN-400 | Rough Cleanup @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-09-14 | 2027-09-15 | 2 | 22 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-27-U-FN-410 | Touch-up Paint @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-09-16 | 2027-09-17 | 2 | 50 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-28-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-07-20 | 2027-07-28 | 7 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-28-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > Interior Finishes at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-07-28 | 5 | 18 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-28-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > MEP Eqp at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-08-06 | 12 | 9 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-28-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > Interior Finishes at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-07-29 | 2027-08-03 | 4 | 28 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-28-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-07-29 | 2027-07-30 | 2 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-28-U-FN-300 | Install Shower Enclosures @ B/Rs L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-05 | 4 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-28-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > MEP Eqp at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-05 | 4 | 47 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-28-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > Interior Finishes at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-08-04 | 2027-08-10 | 5 | 28 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-28-C-FN-130 | Install Trash Chute @ Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > Interior Finishes at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-08-04 | 2027-08-04 | 1 | 35 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-28-C-MP-100 | Install Elect Panels & Stack Meters @ Stack Vault #2821- L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-08-04 | 2027-08-24 | 15 | 59 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-28-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > Interior Finishes at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-08-09 | 2027-08-13 | 5 | 28 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-28-U-FN-310 | Paint Final Coat @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-08-09 | 2027-08-16 | 6 | 9 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-28-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > Interior Finishes at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-08-16 | 2027-08-19 | 4 | 28 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-28-U-FN-330 | Install Door Hardware @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-08-17 | 2027-08-19 | 3 | 40 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-28-U-FN-340 | Install Toilet Accessories @ B/Rs - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-08-17 | 2027-08-19 | 3 | 40 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-28-U-MP-400 | Install HVAC Trim & Control @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > MEP Trim at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-08-17 | 2027-08-23 | 5 | 38 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-28-U-MP-410 | Install Electrical Power Trim @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > MEP Trim at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-08-17 | 2027-08-23 | 5 | 32 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-28-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > Interior Finishes at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-08-20 | 2027-08-20 | 1 | 67 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-28-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > Interior Finishes at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-08-20 | 2027-08-26 | 5 | 28 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-28-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-08-20 | 2027-08-20 | 1 | 63 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-28-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-08-20 | 2027-08-25 | 4 | 62 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-28-U-MP-420 | Install Light Fixtures @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > MEP Trim at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-08-20 | 2027-08-31 | 8 | 32 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-28-U-MP-430 | Install FA & Low Voltage Devices @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > MEP Trim at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-08-24 | 2027-08-27 | 4 | 34 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-28-U-MP-440 | Install FP Sprinkler Heads @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > MEP Trim at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-08-24 | 2027-08-25 | 2 | 36 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-28-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-08-25 | 2027-08-26 | 2 | 59 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-28-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-08-26 | 2027-08-27 | 2 | 62 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-28-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-08-27 | 2027-08-30 | 2 | 59 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-28-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-08-30 | 2027-09-01 | 3 | 59 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-28-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-08-30 | 2027-09-09 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-28-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > Interior Finishes at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-09-02 | 2027-09-03 | 2 | 59 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-28-U-FN-370 | Install Flooring & Base @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-09-10 | 2027-09-23 | 10 | 16 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-28-U-FN-390 | Install Kitchen Appliances @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-09-10 | 2027-09-14 | 3 | 23 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-28-U-FN-400 | Rough Cleanup @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-09-24 | 2027-09-27 | 2 | 16 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-28-U-FN-410 | Touch-up Paint @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-09-28 | 2027-09-29 | 2 | 42 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-29-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-07-29 | 2027-08-06 | 7 | 11 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-29-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > Interior Finishes at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-06 | 5 | 16 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-29-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > MEP Eqp at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-17 | 12 | 10 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-29-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > Interior Finishes at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-08-09 | 2027-08-12 | 4 | 26 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-29-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-08-09 | 2027-08-10 | 2 | 11 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-29-U-FN-300 | Install Shower Enclosures @ B/Rs L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-08-11 | 2027-08-16 | 4 | 11 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-29-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > MEP Eqp at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-08-11 | 2027-08-16 | 4 | 42 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-29-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > Interior Finishes at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-08-13 | 2027-08-19 | 5 | 26 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-29-C-FN-130 | Install Trash Chute @ Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > Interior Finishes at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-08-13 | 2027-08-13 | 1 | 33 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-29-C-MP-100 | Install Mech Eqp @ Mech Eqp Rm #2921 - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-08-13 | 2027-09-02 | 15 | 27 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-29-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > Interior Finishes at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-24 | 5 | 26 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-29-U-FN-310 | Paint Final Coat @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-25 | 6 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-29-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > Interior Finishes at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-08-25 | 2027-08-30 | 4 | 26 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-29-U-FN-330 | Install Door Hardware @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-08-26 | 2027-08-30 | 3 | 35 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-29-U-FN-340 | Install Toilet Accessories @ B/Rs - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-08-26 | 2027-08-30 | 3 | 35 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-29-U-MP-410 | Install Electrical Power Trim @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > MEP Trim at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-08-26 | 2027-09-01 | 5 | 27 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-29-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > Interior Finishes at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-08-31 | 2027-08-31 | 1 | 60 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-29-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > Interior Finishes at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-08-31 | 2027-09-07 | 5 | 26 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-29-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-08-31 | 2027-08-31 | 1 | 56 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-29-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-08-31 | 2027-09-01 | 2 | 55 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-29-U-MP-420 | Install Light Fixtures @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > MEP Trim at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-08-31 | 2027-09-10 | 8 | 27 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-29-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-09-02 | 2027-09-03 | 2 | 55 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-29-U-MP-430 | Install FA & Low Voltage Devices @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > MEP Trim at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-09-02 | 2027-09-08 | 4 | 29 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-29-U-MP-440 | Install FP Sprinkler Heads @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > MEP Trim at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-09-02 | 2027-09-03 | 2 | 31 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-29-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-09 | 4 | 52 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-29-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-08 | 3 | 55 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-29-U-MP-400 | Install HVAC Trim & Control @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > MEP Trim at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-10 | 5 | 27 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-29-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-09-10 | 2027-09-13 | 2 | 52 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-29-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-09-10 | 2027-09-21 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-29-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > Interior Finishes at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-09-14 | 2027-09-15 | 2 | 52 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-29-U-FN-370 | Install Flooring & Base @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-09-22 | 2027-10-05 | 10 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-29-U-FN-390 | Install Kitchen Appliances @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-09-22 | 2027-09-24 | 3 | 17 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-29-U-FN-400 | Rough Cleanup @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-10-06 | 2027-10-07 | 2 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-29-U-FN-410 | Touch-up Paint @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-10-08 | 2027-10-11 | 2 | 34 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-30-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-08-09 | 2027-08-17 | 7 | 12 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-30-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > Interior Finishes at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-08-11 | 2027-08-17 | 5 | 14 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-30-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > MEP Eqp at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-08-11 | 2027-08-26 | 12 | 11 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-30-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > Interior Finishes at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-23 | 4 | 24 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-30-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-19 | 2 | 12 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-30-U-FN-300 | Install Shower Enclosures @ B/Rs L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-08-20 | 2027-08-25 | 4 | 12 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-30-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > MEP Eqp at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-08-20 | 2027-08-25 | 4 | 40 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-30-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > Interior Finishes at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-08-24 | 2027-08-30 | 5 | 24 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-30-C-FN-130 | Install Trash Chute @ Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > Interior Finishes at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-08-24 | 2027-08-24 | 1 | 31 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-30-C-MP-100 | Install Elect & Low Voltage Panels @ Telecom/Elect Rm #3021- L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-08-24 | 2027-09-14 | 15 | 45 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-30-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > Interior Finishes at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-08-27 | 2027-09-02 | 5 | 24 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-30-U-FN-310 | Paint Final Coat @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-08-27 | 2027-09-03 | 6 | 11 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-30-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > Interior Finishes at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-09 | 4 | 24 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-30-U-FN-330 | Install Door Hardware @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-09-07 | 2027-09-09 | 3 | 33 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-30-U-FN-340 | Install Toilet Accessories @ B/Rs - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-09-07 | 2027-09-09 | 3 | 33 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-30-U-MP-400 | Install HVAC Trim & Control @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > MEP Trim at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-09-07 | 2027-09-13 | 5 | 31 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-30-U-MP-410 | Install Electrical Power Trim @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > MEP Trim at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-09-07 | 2027-09-13 | 5 | 25 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-30-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > Interior Finishes at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-09-10 | 2027-09-10 | 1 | 53 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-30-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > Interior Finishes at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-09-10 | 2027-09-16 | 5 | 24 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-30-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-09-10 | 2027-09-10 | 1 | 49 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-30-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-09-10 | 2027-09-15 | 4 | 48 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-30-U-MP-420 | Install Light Fixtures @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > MEP Trim at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-09-10 | 2027-09-21 | 8 | 25 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-30-U-MP-430 | Install FA & Low Voltage Devices @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > MEP Trim at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-09-14 | 2027-09-17 | 4 | 27 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-30-U-MP-440 | Install FP Sprinkler Heads @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > MEP Trim at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-09-14 | 2027-09-15 | 2 | 29 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-30-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-09-15 | 2027-09-16 | 2 | 45 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-30-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-09-16 | 2027-09-17 | 2 | 48 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-30-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-09-17 | 2027-09-20 | 2 | 45 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-30-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-09-20 | 2027-09-22 | 3 | 45 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-30-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-09-22 | 2027-10-01 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-30-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > Interior Finishes at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-09-23 | 2027-09-24 | 2 | 45 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-30-U-FN-370 | Install Flooring & Base @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-10-04 | 2027-10-15 | 10 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-30-U-FN-390 | Install Kitchen Appliances @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-10-04 | 2027-10-06 | 3 | 14 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-30-U-FN-400 | Rough Cleanup @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-10-18 | 2027-10-19 | 2 | 7 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-30-U-FN-410 | Touch-up Paint @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-10-20 | 2027-10-21 | 2 | 26 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-31-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-26 | 7 | 13 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-31-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > Interior Finishes at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-08-20 | 2027-08-26 | 5 | 12 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-31-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > MEP Eqp at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-08-20 | 2027-09-07 | 12 | 12 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-31-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > Interior Finishes at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-08-27 | 2027-09-01 | 4 | 22 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-31-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-08-27 | 2027-08-30 | 2 | 13 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-31-U-FN-300 | Install Shower Enclosures @ B/Rs L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-08-31 | 2027-09-03 | 4 | 13 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-31-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > MEP Eqp at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-08-31 | 2027-09-03 | 4 | 38 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-31-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > Interior Finishes at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-09-02 | 2027-09-09 | 5 | 22 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-31-C-FN-130 | Install Trash Chute @ Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > Interior Finishes at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-09-02 | 2027-09-02 | 1 | 29 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-31-C-MP-100 | Install Elect & Low Voltage Panels @ Telecom/Elect Rm #3121- L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-09-02 | 2027-09-23 | 15 | 38 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-31-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > Interior Finishes at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-09-08 | 2027-09-14 | 5 | 22 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-31-U-FN-310 | Paint Final Coat @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-09-08 | 2027-09-15 | 6 | 12 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-31-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > Interior Finishes at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-09-15 | 2027-09-20 | 4 | 22 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-31-U-FN-330 | Install Door Hardware @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-09-16 | 2027-09-20 | 3 | 31 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-31-U-FN-340 | Install Toilet Accessories @ B/Rs - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-09-16 | 2027-09-20 | 3 | 31 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-31-U-MP-400 | Install HVAC Trim & Control @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > MEP Trim at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-09-16 | 2027-09-22 | 5 | 29 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-31-U-MP-410 | Install Electrical Power Trim @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > MEP Trim at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-09-16 | 2027-09-22 | 5 | 23 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-31-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > Interior Finishes at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-09-21 | 2027-09-21 | 1 | 46 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-31-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > Interior Finishes at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-09-21 | 2027-09-27 | 5 | 22 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-31-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-09-21 | 2027-09-21 | 1 | 42 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-31-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-09-21 | 2027-09-24 | 4 | 41 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-31-U-MP-420 | Install Light Fixtures @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > MEP Trim at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-09-21 | 2027-09-30 | 8 | 23 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-31-U-MP-430 | Install FA & Low Voltage Devices @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > MEP Trim at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-09-23 | 2027-09-28 | 4 | 25 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-31-U-MP-440 | Install FP Sprinkler Heads @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > MEP Trim at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-09-23 | 2027-09-24 | 2 | 27 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-31-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-09-24 | 2027-09-27 | 2 | 38 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-31-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-09-27 | 2027-09-28 | 2 | 41 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-31-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-09-28 | 2027-09-29 | 2 | 38 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-31-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-09-29 | 2027-10-01 | 3 | 38 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-31-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > Interior Finishes at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-10-04 | 2027-10-05 | 2 | 38 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-31-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-10-04 | 2027-10-13 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-31-U-FN-370 | Install Flooring & Base @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-10-14 | 2027-10-27 | 10 | 4 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-31-U-FN-390 | Install Kitchen Appliances @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-10-14 | 2027-10-18 | 3 | 11 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-31-U-FN-400 | Rough Cleanup @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-10-28 | 2027-10-29 | 2 | 4 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-31-U-FN-410 | Touch-up Paint @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-11-01 | 2027-11-02 | 2 | 18 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-32-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-08-27 | 2027-09-07 | 7 | 14 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-32-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > Interior Finishes at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-08-31 | 2027-09-07 | 5 | 10 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-32-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > MEP Eqp at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-08-31 | 2027-09-16 | 12 | 13 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-32-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > Interior Finishes at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-09-08 | 2027-09-13 | 4 | 20 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-32-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-09-08 | 2027-09-09 | 2 | 14 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-32-U-FN-300 | Install Shower Enclosures @ B/Rs L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-09-10 | 2027-09-15 | 4 | 14 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-32-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > MEP Eqp at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-09-10 | 2027-09-15 | 4 | 36 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-32-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > Interior Finishes at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-09-14 | 2027-09-20 | 5 | 20 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-32-C-FN-130 | Install Trash Chute @ Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > Interior Finishes at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-09-14 | 2027-09-14 | 1 | 27 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-32-C-MP-100 | Install Mech Eqp @ Mech Eqp Rm #3221 - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-09-14 | 2027-10-04 | 15 | 21 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-32-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > Interior Finishes at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-09-17 | 2027-09-23 | 5 | 20 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-32-U-FN-310 | Paint Final Coat @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-09-17 | 2027-09-24 | 6 | 13 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-32-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > Interior Finishes at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-09-24 | 2027-09-29 | 4 | 20 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-32-U-FN-330 | Install Door Hardware @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-09-27 | 2027-09-29 | 3 | 29 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-32-U-FN-340 | Install Toilet Accessories @ B/Rs - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-09-27 | 2027-09-29 | 3 | 29 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-32-U-MP-410 | Install Electrical Power Trim @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > MEP Trim at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-09-27 | 2027-10-01 | 5 | 21 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-32-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > Interior Finishes at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-09-30 | 2027-09-30 | 1 | 39 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-32-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > Interior Finishes at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-09-30 | 2027-10-06 | 5 | 20 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-32-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-09-30 | 2027-09-30 | 1 | 35 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-32-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-09-30 | 2027-10-01 | 2 | 34 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-32-U-MP-420 | Install Light Fixtures @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > MEP Trim at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-09-30 | 2027-10-11 | 8 | 21 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-32-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-10-04 | 2027-10-05 | 2 | 34 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-32-U-MP-430 | Install FA & Low Voltage Devices @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > MEP Trim at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-10-04 | 2027-10-07 | 4 | 23 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-32-U-MP-440 | Install FP Sprinkler Heads @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > MEP Trim at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-10-04 | 2027-10-05 | 2 | 25 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-32-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-10-05 | 2027-10-08 | 4 | 31 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-32-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-10-05 | 2027-10-07 | 3 | 34 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-32-U-MP-400 | Install HVAC Trim & Control @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > MEP Trim at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-10-05 | 2027-10-11 | 5 | 21 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-32-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-10-11 | 2027-10-12 | 2 | 31 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-32-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > Interior Finishes at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-10-13 | 2027-10-14 | 2 | 31 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-32-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-10-14 | 2027-10-25 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-32-U-FN-370 | Install Flooring & Base @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-10-26 | 2027-11-08 | 10 | 66 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-32-U-FN-390 | Install Kitchen Appliances @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-10-26 | 2027-10-28 | 3 | 8 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-32-U-FN-400 | Rough Cleanup @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-10-29 | 2027-11-01 | 2 | 8 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-32-U-FN-410 | Touch-up Paint @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-11-02 | 2027-11-03 | 2 | 17 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-33-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-09-08 | 2027-09-16 | 7 | 14 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-33-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > Interior Finishes at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-09-10 | 2027-09-16 | 5 | 8 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-33-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > MEP Eqp at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-09-10 | 2027-09-27 | 12 | 13 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-33-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > Interior Finishes at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-09-17 | 2027-09-22 | 4 | 18 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-33-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-09-17 | 2027-09-20 | 2 | 14 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-33-U-FN-300 | Install Shower Enclosures @ B/Rs L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-09-21 | 2027-09-24 | 4 | 14 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-33-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > MEP Eqp at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-09-21 | 2027-09-24 | 4 | 32 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-33-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > Interior Finishes at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-09-23 | 2027-09-29 | 5 | 18 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-33-C-FN-130 | Install Trash Chute @ Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > Interior Finishes at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-09-23 | 2027-09-23 | 1 | 25 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-33-C-MP-100 | Install Low Voltage Panels @ Telecom Rm #3321- L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-09-23 | 2027-10-13 | 15 | 24 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-33-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > Interior Finishes at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-09-28 | 2027-10-04 | 5 | 18 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-33-U-FN-310 | Paint Final Coat @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-09-28 | 2027-10-05 | 6 | 13 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-33-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > Interior Finishes at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-10-05 | 2027-10-08 | 4 | 18 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-33-U-FN-330 | Install Door Hardware @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-10-06 | 2027-10-08 | 3 | 25 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-33-U-FN-340 | Install Toilet Accessories @ B/Rs - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-10-06 | 2027-10-08 | 3 | 25 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-33-U-MP-400 | Install HVAC Trim & Control @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > MEP Trim at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-10-06 | 2027-10-12 | 5 | 23 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-33-U-MP-410 | Install Electrical Power Trim @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > MEP Trim at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-10-06 | 2027-10-12 | 5 | 17 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-33-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > Interior Finishes at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-10-11 | 2027-10-11 | 1 | 32 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-33-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > Interior Finishes at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-10-11 | 2027-10-15 | 5 | 18 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-33-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-10-11 | 2027-10-11 | 1 | 28 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-33-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-10-11 | 2027-10-14 | 4 | 27 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-33-U-MP-420 | Install Light Fixtures @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > MEP Trim at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-10-11 | 2027-10-20 | 8 | 17 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-33-U-MP-430 | Install FA & Low Voltage Devices @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > MEP Trim at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-10-13 | 2027-10-18 | 4 | 19 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-33-U-MP-440 | Install FP Sprinkler Heads @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > MEP Trim at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-10-13 | 2027-10-14 | 2 | 21 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-33-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-10-14 | 2027-10-15 | 2 | 24 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-33-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-10-15 | 2027-10-18 | 2 | 27 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-33-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-10-18 | 2027-10-19 | 2 | 24 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-33-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-10-19 | 2027-10-21 | 3 | 24 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-33-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > Interior Finishes at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-10-22 | 2027-10-25 | 2 | 24 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-33-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-10-25 | 2027-11-03 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-33-U-FN-370 | Install Flooring & Base @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-11-04 | 2027-11-17 | 10 | 64 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-33-U-FN-390 | Install Kitchen Appliances @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-11-04 | 2027-11-08 | 3 | 4 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-33-U-FN-400 | Rough Cleanup @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-11-09 | 2027-11-10 | 2 | 4 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-33-U-FN-410 | Touch-up Paint @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-11-11 | 2027-11-12 | 2 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-34-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-09-17 | 2027-09-27 | 7 | 16 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-34-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > Interior Finishes at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-09-21 | 2027-09-27 | 5 | 6 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-34-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > MEP Eqp at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-09-21 | 2027-10-06 | 12 | 15 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-34-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > Interior Finishes at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-09-28 | 2027-10-01 | 4 | 16 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-34-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-09-28 | 2027-09-29 | 2 | 16 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-34-U-FN-300 | Install Shower Enclosures @ B/Rs L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-09-30 | 2027-10-05 | 4 | 16 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-34-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > MEP Eqp at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-09-30 | 2027-10-05 | 4 | 28 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-34-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > Interior Finishes at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-10-04 | 2027-10-08 | 5 | 16 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-34-C-FN-130 | Install Trash Chute @ Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > Interior Finishes at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-10-04 | 2027-10-04 | 1 | 23 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-34-C-MP-100 | Install Elect Panels & Stack Meters @ Stack Vault #3421- L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-10-04 | 2027-10-22 | 15 | 17 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-34-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > Interior Finishes at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-10-07 | 2027-10-13 | 5 | 16 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-34-U-FN-310 | Paint Final Coat @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-10-07 | 2027-10-14 | 6 | 15 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-34-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > Interior Finishes at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-10-14 | 2027-10-19 | 4 | 16 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-34-U-FN-330 | Install Door Hardware @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-10-15 | 2027-10-19 | 3 | 21 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-34-U-FN-340 | Install Toilet Accessories @ B/Rs - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-10-15 | 2027-10-19 | 3 | 21 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-34-U-MP-400 | Install HVAC Trim & Control @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > MEP Trim at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-10-15 | 2027-10-21 | 5 | 19 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-34-U-MP-410 | Install Electrical Power Trim @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > MEP Trim at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-10-15 | 2027-10-21 | 5 | 15 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-34-U-MP-420 | Install Light Fixtures @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > MEP Trim at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-10-18 | 2027-10-27 | 8 | 15 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-34-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > Interior Finishes at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-10-20 | 2027-10-20 | 1 | 25 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-34-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > Interior Finishes at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-10-20 | 2027-10-26 | 5 | 16 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-34-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-10-20 | 2027-10-20 | 1 | 21 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-34-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-10-20 | 2027-10-25 | 4 | 20 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-34-U-MP-430 | Install FA & Low Voltage Devices @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > MEP Trim at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-10-22 | 2027-10-27 | 4 | 15 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-34-U-MP-440 | Install FP Sprinkler Heads @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > MEP Trim at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-10-22 | 2027-10-25 | 2 | 17 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-34-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-10-25 | 2027-10-26 | 2 | 17 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-34-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-10-26 | 2027-10-27 | 2 | 20 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-34-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-10-27 | 2027-10-28 | 2 | 17 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-34-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-10-28 | 2027-11-01 | 3 | 17 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-34-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > Interior Finishes at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-11-02 | 2027-11-03 | 2 | 17 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-34-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-11-03 | 2027-11-12 | 8 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-34-U-FN-370 | Install Flooring & Base @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-11-15 | 2027-11-30 | 10 | 62 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-34-U-FN-390 | Install Kitchen Appliances @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-11-15 | 2027-11-17 | 3 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-34-U-FN-400 | Rough Cleanup @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-11-18 | 2027-11-19 | 2 | 0 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-34-U-FN-410 | Touch-up Paint @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-11-22 | 2027-11-23 | 2 | 3 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-35-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > Interior Finishes at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-10-06 | 2027-10-12 | 5 | 0 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-35-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-10-06 | 2027-10-14 | 7 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-35-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > MEP Eqp at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-10-06 | 2027-10-21 | 12 | 11 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-35-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > Interior Finishes at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-10-13 | 2027-10-18 | 4 | 0 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-35-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-10-15 | 2027-10-18 | 2 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-35-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > Interior Finishes at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-10-19 | 2027-10-25 | 5 | 3 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-35-C-FN-130 | Install Trash Chute @ Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > Interior Finishes at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-10-19 | 2027-10-19 | 1 | 10 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-35-C-MP-100 | Install Elect Panels @ Elect Rm #3521- L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-10-19 | 2027-11-08 | 15 | 0 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-35-U-FN-300 | Install Shower Enclosures @ B/Rs L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-10-19 | 2027-10-22 | 4 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-35-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > MEP Eqp at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-10-19 | 2027-10-22 | 4 | 20 | Interior MEPs & Finishes | MEP Eqp at Units
Baseline | C-35-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > Interior Finishes at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-10-22 | 2027-10-28 | 5 | 3 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-35-U-FN-310 | Paint Final Coat @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-10-25 | 2027-11-01 | 6 | 10 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-35-U-MP-400 | Install HVAC Trim & Control @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > MEP Trim at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-10-28 | 2027-11-03 | 5 | 10 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-35-U-MP-410 | Install Electrical Power Trim @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > MEP Trim at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-10-28 | 2027-11-03 | 5 | 10 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-35-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > Interior Finishes at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-10-29 | 2027-11-03 | 4 | 3 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-35-U-MP-420 | Install Light Fixtures @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > MEP Trim at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-10-29 | 2027-11-09 | 8 | 10 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-35-U-FN-330 | Install Door Hardware @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-11-01 | 2027-11-02 | 2 | 15 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-35-U-FN-340 | Install Toilet Accessories @ B/Rs - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-11-01 | 2027-11-02 | 2 | 15 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-35-U-MP-430 | Install FA & Low Voltage Devices @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > MEP Trim at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-11-01 | 2027-11-04 | 4 | 13 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-35-U-MP-440 | Install FP Sprinkler Heads @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > MEP Trim at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-11-01 | 2027-11-02 | 2 | 15 | Interior MEPs & Finishes | MEP Trim at Units
Baseline | C-35-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > Interior Finishes at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-11-04 | 2027-11-04 | 1 | 14 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-35-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > Interior Finishes at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-11-04 | 2027-11-10 | 5 | 10 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-35-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-11-04 | 2027-11-04 | 1 | 10 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-35-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-11-04 | 2027-11-09 | 4 | 9 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-35-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-11-09 | 2027-11-10 | 2 | 0 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-35-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-11-10 | 2027-11-11 | 2 | 9 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-35-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-11-11 | 2027-11-12 | 2 | 6 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-35-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L23 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-11-11 | 2027-11-19 | 7 | 2 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-35-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-11-12 | 2027-11-16 | 3 | 6 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Baseline | C-35-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > Interior Finishes at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-11-17 | 2027-11-18 | 2 | 6 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-35-U-FN-390 | Install Kitchen Appliances @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-11-18 | 2027-11-19 | 2 | 2 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-35-U-FN-370 | Install Flooring & Base @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-11-22 | 2027-12-07 | 10 | 62 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-35-U-FN-400 | Rough Cleanup @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-11-22 | 2027-11-22 | 1 | 2 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-35-U-FN-410 | Touch-up Paint @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-11-23 | 2027-11-24 | 2 | 2 | Interior MEPs & Finishes | Interior Finishes at Units
Baseline | C-36-IN-MP-200 | Inspect MEP Rough @ Indoor - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > MEP Rough at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-07-23 | 2 | 33 | Interior MEPs & Finishes | MEP Rough at Indoor
Baseline | C-36-IN-MP-400 | Install Mech EFs @ Indoor - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > MEP Eqp & Trim at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-10 | 2027-08-11 | 2 | 33 | Interior MEPs & Finishes | MEP Eqp & Trim at Indoor
Baseline | C-36-IN-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-25 | 2027-08-27 | 3 | 41 | Interior MEPs & Finishes | Interior Finishes at Indoor
Baseline | C-36-IN-FN-290 | Install Vanities & Mirrors @ B/Rs - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-30 | 2027-08-30 | 1 | 41 | Interior MEPs & Finishes | Interior Finishes at Indoor
Baseline | C-36-IN-FN-310 | Paint Final Coat @ Indoor - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-31 | 2027-09-02 | 3 | 41 | Interior MEPs & Finishes | Interior Finishes at Indoor
Baseline | C-36-IN-MP-410 | Install Plumbing Fixtures @ B/Rs - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > MEP Eqp & Trim at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-31 | 2027-09-01 | 2 | 51 | Interior MEPs & Finishes | MEP Eqp & Trim at Indoor
Baseline | C-36-IN-FN-330 | Install Door Hardware @ Indoor - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-07 | 2 | 49 | Interior MEPs & Finishes | Interior Finishes at Indoor
Baseline | C-36-IN-FN-340 | Install Toilet Accessories @ B/Rs - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-03 | 1 | 50 | Interior MEPs & Finishes | Interior Finishes at Indoor
Baseline | C-36-IN-FN-350 | Install Kitchen Cabinets & Countertops @ Indoor - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-15 | 8 | 43 | Interior MEPs & Finishes | Interior Finishes at Indoor
Baseline | C-36-IN-MP-420 | Install HVAC Trim & Control @ Indoor - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > MEP Eqp & Trim at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-08 | 3 | 48 | Interior MEPs & Finishes | MEP Eqp & Trim at Indoor
Baseline | C-36-IN-MP-430 | Install Electrical Power Trim @ Indoor - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > MEP Eqp & Trim at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-07 | 2 | 46 | Interior MEPs & Finishes | MEP Eqp & Trim at Indoor
Baseline | C-36-IN-MP-440 | Install Light Fixtures @ Indoor - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > MEP Eqp & Trim at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-09 | 4 | 47 | Interior MEPs & Finishes | MEP Eqp & Trim at Indoor
Baseline | C-36-IN-MP-450 | Install FA & Low Voltage Devices @ Indoor - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > MEP Eqp & Trim at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-08 | 2027-09-10 | 3 | 46 | Interior MEPs & Finishes | MEP Eqp & Trim at Indoor
Baseline | C-36-IN-MP-460 | Install FP Sprinkler Heads @ Indoor - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > MEP Eqp & Trim at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-08 | 2027-09-09 | 2 | 47 | Interior MEPs & Finishes | MEP Eqp & Trim at Indoor
Baseline | C-36-IN-MP-470 | Install Steam Eqp @ Steam Rms #3608 & #3609 - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > MEP Eqp & Trim at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-16 | 2027-09-29 | 10 | 33 | Interior MEPs & Finishes | MEP Eqp & Trim at Indoor
Baseline | C-36-IN-FN-400 | Rough Cleanup @ Indoor - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-30 | 2027-10-01 | 2 | 33 | Interior MEPs & Finishes | Interior Finishes at Indoor
Baseline | C-01-U-PC-900 | Partial MEP Systems Inspections @ L1 | yes | Inspection and contractor punch | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Units Partial Inspections & Punchout & Key Delivery at 1st Lvl | TT_Task | TK_NotStart | 2027-09-27 | 2027-10-15 | 15 | 18 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-01-U-PC-910 | Subcontractor Punch List & Punch Paint @ L1 | yes | Inspection and contractor punch | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Units Partial Inspections & Punchout & Key Delivery at 1st Lvl | TT_Task | TK_NotStart | 2027-10-18 | 2027-11-05 | 15 | 76 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-01-U-PC-920 | GC Punchlist @ L1 | yes | Inspection and contractor punch | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Units Partial Inspections & Punchout & Key Delivery at 1st Lvl | TT_Task | TK_NotStart | 2027-11-08 | 2027-11-12 | 5 | 76 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-02-U-PC-900 | Partial MEP Systems Inspections @ L2 | yes | Inspection and contractor punch | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 2nd Lvl | TT_Task | TK_NotStart | 2027-03-30 | 2027-04-07 | 7 | 1 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-02-U-PC-910 | Subcontractor Punch List & Punch Paint @ L2 | yes | Inspection and contractor punch | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 2nd Lvl | TT_Task | TK_NotStart | 2027-04-08 | 2027-04-28 | 15 | 51 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-02-U-PC-920 | GC Punchlist @ L2 | yes | Inspection and contractor punch | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 2nd Lvl | TT_Task | TK_NotStart | 2027-04-29 | 2027-05-05 | 5 | 51 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-03-U-PC-900 | Partial MEP Systems Inspections @ Units - L3 | yes | Inspection and contractor punch | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 3rd Lvl | TT_Task | TK_NotStart | 2027-04-08 | 2027-04-16 | 7 | 1 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-03-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L3 | yes | Inspection and contractor punch | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 3rd Lvl | TT_Task | TK_NotStart | 2027-04-19 | 2027-05-07 | 15 | 49 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-03-U-PC-920 | GC Punchlist @ Units - L3 | yes | Inspection and contractor punch | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 3rd Lvl | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-14 | 5 | 49 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-04-U-PC-900 | Partial MEP Systems Inspections @ Units - L4 | yes | Inspection and contractor punch | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Units Partial Inspections & Punchout & Key Delivery at 4th Lvl | TT_Task | TK_NotStart | 2027-04-19 | 2027-04-27 | 7 | 1 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-04-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L4 | yes | Inspection and contractor punch | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Units Partial Inspections & Punchout & Key Delivery at 4th Lvl | TT_Task | TK_NotStart | 2027-04-28 | 2027-05-18 | 15 | 47 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-04-U-PC-920 | GC Punchlist @ Units - L4 | yes | Inspection and contractor punch | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Units Partial Inspections & Punchout & Key Delivery at 4th Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-05-25 | 5 | 47 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-05-U-PC-900 | Partial MEP Systems Inspections @ Units - L5 | yes | Inspection and contractor punch | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Units Partial Inspections & Punchout & Key Delivery at 5th Lvl | TT_Task | TK_NotStart | 2027-04-28 | 2027-05-06 | 7 | 1 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-05-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L5 | yes | Inspection and contractor punch | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Units Partial Inspections & Punchout & Key Delivery at 5th Lvl | TT_Task | TK_NotStart | 2027-05-07 | 2027-05-27 | 15 | 45 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-05-U-PC-920 | GC Punchlist @ Units - L5 | yes | Inspection and contractor punch | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Units Partial Inspections & Punchout & Key Delivery at 5th Lvl | TT_Task | TK_NotStart | 2027-05-28 | 2027-06-04 | 5 | 45 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-06-U-PC-900 | Partial MEP Systems Inspections @ Units - L6 | yes | Inspection and contractor punch | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Units Partial Inspections & Punchout & Key Delivery at 6th Lvl | TT_Task | TK_NotStart | 2027-05-07 | 2027-05-17 | 7 | 1 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-06-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L6 | yes | Inspection and contractor punch | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Units Partial Inspections & Punchout & Key Delivery at 6th Lvl | TT_Task | TK_NotStart | 2027-05-18 | 2027-06-08 | 15 | 43 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-06-U-PC-920 | GC Punchlist @ Units - L6 | yes | Inspection and contractor punch | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Units Partial Inspections & Punchout & Key Delivery at 6th Lvl | TT_Task | TK_NotStart | 2027-06-09 | 2027-06-15 | 5 | 43 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-07-U-PC-900 | Partial MEP Systems Inspections @ Units - L7 | yes | Inspection and contractor punch | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Units Partial Inspections & Punchout & Key Delivery at 7th Lvl | TT_Task | TK_NotStart | 2027-05-18 | 2027-05-26 | 7 | 1 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-07-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L7 | yes | Inspection and contractor punch | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Units Partial Inspections & Punchout & Key Delivery at 7th Lvl | TT_Task | TK_NotStart | 2027-05-27 | 2027-06-17 | 15 | 40 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-07-U-PC-920 | GC Punchlist @ Units - L7 | yes | Inspection and contractor punch | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Units Partial Inspections & Punchout & Key Delivery at 7th Lvl | TT_Task | TK_NotStart | 2027-06-18 | 2027-06-24 | 5 | 40 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-08-U-PC-900 | Partial MEP Systems Inspections @ Units - L8 | yes | Inspection and contractor punch | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Units Partial Inspections & Punchout & Key Delivery at 8th Lvl | TT_Task | TK_NotStart | 2027-05-27 | 2027-06-07 | 7 | 1 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-08-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L8 | yes | Inspection and contractor punch | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Units Partial Inspections & Punchout & Key Delivery at 8th Lvl | TT_Task | TK_NotStart | 2027-06-08 | 2027-06-28 | 15 | 33 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-08-U-PC-920 | GC Punchlist @ Units - L8 | yes | Inspection and contractor punch | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Units Partial Inspections & Punchout & Key Delivery at 8th Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-07-06 | 5 | 33 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-09-U-PC-900 | Partial MEP Systems Inspections @ Units - L9 | yes | Inspection and contractor punch | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Units Partial Inspections & Punchout & Key Delivery at 9th Lvl | TT_Task | TK_NotStart | 2027-06-08 | 2027-06-16 | 7 | 1 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-09-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L9 | yes | Inspection and contractor punch | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Units Partial Inspections & Punchout & Key Delivery at 9th Lvl | TT_Task | TK_NotStart | 2027-06-17 | 2027-07-08 | 15 | 26 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-09-U-PC-920 | GC Punchlist @ Units - L9 | yes | Inspection and contractor punch | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Units Partial Inspections & Punchout & Key Delivery at 9th Lvl | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-15 | 5 | 26 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-10-U-PC-900 | Partial MEP Systems Inspections @ Units - L10 | yes | Inspection and contractor punch | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Units Partial Inspections & Punchout & Key Delivery at 10th Lvl | TT_Task | TK_NotStart | 2027-06-17 | 2027-06-25 | 7 | 1 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-10-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L10 | yes | Inspection and contractor punch | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Units Partial Inspections & Punchout & Key Delivery at 10th Lvl | TT_Task | TK_NotStart | 2027-06-28 | 2027-07-12 | 10 | 24 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-10-U-PC-920 | GC Punchlist @ Units - L10 | yes | Inspection and contractor punch | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Units Partial Inspections & Punchout & Key Delivery at 10th Lvl | TT_Task | TK_NotStart | 2027-07-13 | 2027-07-19 | 5 | 24 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-11-U-PC-900 | Partial MEP Systems Inspections @ Units - L11 | yes | Inspection and contractor punch | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Units Partial Inspections & Punchout & Key Delivery at 11th Lvl | TT_Task | TK_NotStart | 2027-06-28 | 2027-07-07 | 7 | 1 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-11-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L11 | yes | Inspection and contractor punch | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Units Partial Inspections & Punchout & Key Delivery at 11th Lvl | TT_Task | TK_NotStart | 2027-07-08 | 2027-07-21 | 10 | 17 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-11-U-PC-920 | GC Punchlist @ Units - L11 | yes | Inspection and contractor punch | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Units Partial Inspections & Punchout & Key Delivery at 11th Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-07-28 | 5 | 17 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-12-U-PC-900 | Partial MEP Systems Inspections @ Units - L12 | yes | Inspection and contractor punch | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Units Partial Inspections & Punchout & Key Delivery at 12th Lvl | TT_Task | TK_NotStart | 2027-07-08 | 2027-07-16 | 7 | 1 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-12-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L12 | yes | Inspection and contractor punch | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Units Partial Inspections & Punchout & Key Delivery at 12th Lvl | TT_Task | TK_NotStart | 2027-07-19 | 2027-07-30 | 10 | 10 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-12-U-PC-920 | GC Punchlist @ Units - L12 | yes | Inspection and contractor punch | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Units Partial Inspections & Punchout & Key Delivery at 12th Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-06 | 5 | 10 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-14-U-PC-900 | Partial MEP Systems Inspections @ Units - L14 | yes | Inspection and contractor punch | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Units Partial Inspections & Punchout & Key Delivery at 14th Lvl | TT_Task | TK_NotStart | 2027-07-19 | 2027-07-27 | 7 | 1 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-14-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L14 | yes | Inspection and contractor punch | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Units Partial Inspections & Punchout & Key Delivery at 14th Lvl | TT_Task | TK_NotStart | 2027-07-28 | 2027-08-10 | 10 | 3 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-14-U-PC-920 | GC Punchlist @ Units - L14 | yes | Inspection and contractor punch | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Units Partial Inspections & Punchout & Key Delivery at 14th Lvl | TT_Task | TK_NotStart | 2027-08-11 | 2027-08-17 | 5 | 3 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-15-U-PC-900 | Partial MEP Systems Inspections @ Units - L15 | yes | Inspection and contractor punch | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Units Partial Inspections & Punchout & Key Delivery at 15th Lvl | TT_Task | TK_NotStart | 2027-07-23 | 2027-08-02 | 7 | 1 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-15-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L15 | yes | Inspection and contractor punch | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Units Partial Inspections & Punchout & Key Delivery at 15th Lvl | TT_Task | TK_NotStart | 2027-08-03 | 2027-08-16 | 10 | 1 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-15-U-PC-920 | GC Punchlist @ Units - L15 | yes | Inspection and contractor punch | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Units Partial Inspections & Punchout & Key Delivery at 15th Lvl | TT_Task | TK_NotStart | 2027-08-13 | 2027-08-19 | 5 | 1 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-16-U-PC-900 | Partial MEP Systems Inspections @ Units - L16 | yes | Inspection and contractor punch | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Units Partial Inspections & Punchout & Key Delivery at 16th Lvl | TT_Task | TK_NotStart | 2027-08-03 | 2027-08-09 | 5 | 4 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-16-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L16 | yes | Inspection and contractor punch | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Units Partial Inspections & Punchout & Key Delivery at 16th Lvl | TT_Task | TK_NotStart | 2027-08-10 | 2027-08-23 | 10 | 35 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-16-U-PC-920 | GC Punchlist @ Units - L16 | yes | Inspection and contractor punch | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Units Partial Inspections & Punchout & Key Delivery at 16th Lvl | TT_Task | TK_NotStart | 2027-08-24 | 2027-08-30 | 5 | 35 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-17-U-PC-900 | Partial MEP Systems Inspections @ Units - L17 | yes | Inspection and contractor punch | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Units Partial Inspections & Punchout & Key Delivery at 17th Lvl | TT_Task | TK_NotStart | 2027-08-09 | 2027-08-13 | 5 | 4 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-17-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L17 | yes | Inspection and contractor punch | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Units Partial Inspections & Punchout & Key Delivery at 17th Lvl | TT_Task | TK_NotStart | 2027-08-16 | 2027-08-27 | 10 | 33 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-17-U-PC-920 | GC Punchlist @ Units - L17 | yes | Inspection and contractor punch | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Units Partial Inspections & Punchout & Key Delivery at 17th Lvl | TT_Task | TK_NotStart | 2027-08-30 | 2027-09-03 | 5 | 33 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-18-U-PC-900 | Partial MEP Systems Inspections @ Units - L18 | yes | Inspection and contractor punch | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Units Partial Inspections & Punchout & Key Delivery at 18th Lvl | TT_Task | TK_NotStart | 2027-08-13 | 2027-08-19 | 5 | 4 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-18-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L18 | yes | Inspection and contractor punch | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Units Partial Inspections & Punchout & Key Delivery at 18th Lvl | TT_Task | TK_NotStart | 2027-08-20 | 2027-09-02 | 10 | 29 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-18-U-PC-920 | GC Punchlist @ Units - L18 | yes | Inspection and contractor punch | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Units Partial Inspections & Punchout & Key Delivery at 18th Lvl | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-10 | 5 | 29 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-19-U-PC-900 | Partial MEP Systems Inspections @ Units - L19 | yes | Inspection and contractor punch | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Units Partial Inspections & Punchout & Key Delivery at 19th Lvl | TT_Task | TK_NotStart | 2027-08-19 | 2027-08-25 | 5 | 4 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-19-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L19 | yes | Inspection and contractor punch | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Units Partial Inspections & Punchout & Key Delivery at 19th Lvl | TT_Task | TK_NotStart | 2027-08-26 | 2027-09-09 | 10 | 25 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-19-U-PC-920 | GC Punchlist @ Units - L19 | yes | Inspection and contractor punch | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Units Partial Inspections & Punchout & Key Delivery at 19th Lvl | TT_Task | TK_NotStart | 2027-09-10 | 2027-09-16 | 5 | 25 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-20-U-PC-900 | Partial MEP Systems Inspections @ Units - L20 | yes | Inspection and contractor punch | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Units Partial Inspections & Punchout & Key Delivery at 20th Lvl | TT_Task | TK_NotStart | 2027-08-25 | 2027-08-31 | 5 | 4 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-20-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L20 | yes | Inspection and contractor punch | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Units Partial Inspections & Punchout & Key Delivery at 20th Lvl | TT_Task | TK_NotStart | 2027-09-01 | 2027-09-15 | 10 | 21 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-20-U-PC-920 | GC Punchlist @ Units - L20 | yes | Inspection and contractor punch | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Units Partial Inspections & Punchout & Key Delivery at 20th Lvl | TT_Task | TK_NotStart | 2027-09-16 | 2027-09-22 | 5 | 21 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-21-U-PC-900 | Partial MEP Systems Inspections @ Units - L21 | yes | Inspection and contractor punch | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Units Partial Inspections & Punchout & Key Delivery at 21st Lvl | TT_Task | TK_NotStart | 2027-08-31 | 2027-09-07 | 5 | 4 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-21-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L21 | yes | Inspection and contractor punch | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Units Partial Inspections & Punchout & Key Delivery at 21st Lvl | TT_Task | TK_NotStart | 2027-09-08 | 2027-09-21 | 10 | 17 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-21-U-PC-920 | GC Punchlist @ Units - L21 | yes | Inspection and contractor punch | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Units Partial Inspections & Punchout & Key Delivery at 21st Lvl | TT_Task | TK_NotStart | 2027-09-22 | 2027-09-28 | 5 | 17 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-22-U-PC-900 | Partial MEP Systems Inspections @ Units - L22 | yes | Inspection and contractor punch | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 22nd Lvl | TT_Task | TK_NotStart | 2027-09-07 | 2027-09-13 | 5 | 4 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-22-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L22 | yes | Inspection and contractor punch | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 22nd Lvl | TT_Task | TK_NotStart | 2027-09-14 | 2027-09-27 | 10 | 13 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-22-U-PC-920 | GC Punchlist @ Units - L22 | yes | Inspection and contractor punch | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 22nd Lvl | TT_Task | TK_NotStart | 2027-09-28 | 2027-10-04 | 5 | 13 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-23-U-PC-900 | Partial MEP Systems Inspections @ Units - L23 | yes | Inspection and contractor punch | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 23rd Lvl | TT_Task | TK_NotStart | 2027-09-13 | 2027-09-17 | 5 | 4 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-23-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L23 | yes | Inspection and contractor punch | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 23rd Lvl | TT_Task | TK_NotStart | 2027-09-20 | 2027-10-01 | 10 | 9 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-23-U-PC-920 | GC Punchlist @ Units - L23 | yes | Inspection and contractor punch | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 23rd Lvl | TT_Task | TK_NotStart | 2027-10-04 | 2027-10-08 | 5 | 9 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-24-U-PC-900 | Partial MEP Systems Inspections @ Units - L24 | yes | Inspection and contractor punch | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Units Partial Inspections & Punchout & Key Delivery at 24th Lvl | TT_Task | TK_NotStart | 2027-09-17 | 2027-09-23 | 5 | 4 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-24-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L24 | yes | Inspection and contractor punch | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Units Partial Inspections & Punchout & Key Delivery at 24th Lvl | TT_Task | TK_NotStart | 2027-09-24 | 2027-10-07 | 10 | 5 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-24-U-PC-920 | GC Punchlist @ Units - L24 | yes | Inspection and contractor punch | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Units Partial Inspections & Punchout & Key Delivery at 24th Lvl | TT_Task | TK_NotStart | 2027-10-08 | 2027-10-14 | 5 | 5 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-25-U-PC-900 | Partial MEP Systems Inspections @ Units - L25 | yes | Inspection and contractor punch | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Units Partial Inspections & Punchout & Key Delivery at 25th Lvl | TT_Task | TK_NotStart | 2027-09-28 | 2027-10-04 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-25-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L25 | yes | Inspection and contractor punch | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Units Partial Inspections & Punchout & Key Delivery at 25th Lvl | TT_Task | TK_NotStart | 2027-10-01 | 2027-10-14 | 10 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-25-U-PC-920 | GC Punchlist @ Units - L25 | yes | Inspection and contractor punch | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Units Partial Inspections & Punchout & Key Delivery at 25th Lvl | TT_Task | TK_NotStart | 2027-10-15 | 2027-10-21 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-26-U-PC-900 | Partial MEP Systems Inspections @ Units - L26 | yes | Inspection and contractor punch | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Units Partial Inspections & Punchout & Key Delivery at 26th Lvl | TT_Task | TK_NotStart | 2027-10-05 | 2027-10-11 | 5 | 7 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-26-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L26 | yes | Inspection and contractor punch | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Units Partial Inspections & Punchout & Key Delivery at 26th Lvl | TT_Task | TK_NotStart | 2027-10-12 | 2027-10-25 | 10 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-26-U-PC-920 | GC Punchlist @ Units - L26 | yes | Inspection and contractor punch | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Units Partial Inspections & Punchout & Key Delivery at 26th Lvl | TT_Task | TK_NotStart | 2027-10-26 | 2027-11-01 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-27-U-PC-900 | Partial MEP Systems Inspections @ Units - L27 | yes | Inspection and contractor punch | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Units Partial Inspections & Punchout & Key Delivery at 27th Lvl | TT_Task | TK_NotStart | 2027-10-07 | 2027-10-13 | 5 | 7 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-27-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L27 | yes | Inspection and contractor punch | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Units Partial Inspections & Punchout & Key Delivery at 27th Lvl | TT_Task | TK_NotStart | 2027-10-14 | 2027-10-27 | 10 | 32 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-27-U-PC-920 | GC Punchlist @ Units - L27 | yes | Inspection and contractor punch | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Units Partial Inspections & Punchout & Key Delivery at 27th Lvl | TT_Task | TK_NotStart | 2027-10-28 | 2027-11-03 | 5 | 32 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-28-U-PC-900 | Partial MEP Systems Inspections @ Units - L28 | yes | Inspection and contractor punch | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Units Partial Inspections & Punchout & Key Delivery at 28th Lvl | TT_Task | TK_NotStart | 2027-10-11 | 2027-10-15 | 5 | 7 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-28-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L28 | yes | Inspection and contractor punch | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Units Partial Inspections & Punchout & Key Delivery at 28th Lvl | TT_Task | TK_NotStart | 2027-10-18 | 2027-10-29 | 10 | 30 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-28-U-PC-920 | GC Punchlist @ Units - L28 | yes | Inspection and contractor punch | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Units Partial Inspections & Punchout & Key Delivery at 28th Lvl | TT_Task | TK_NotStart | 2027-11-01 | 2027-11-05 | 5 | 30 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-29-U-PC-900 | Partial MEP Systems Inspections @ Units - L29 | yes | Inspection and contractor punch | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Units Partial Inspections & Punchout & Key Delivery at 29th Lvl | TT_Task | TK_NotStart | 2027-10-13 | 2027-10-19 | 5 | 7 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-29-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L29 | yes | Inspection and contractor punch | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Units Partial Inspections & Punchout & Key Delivery at 29th Lvl | TT_Task | TK_NotStart | 2027-10-20 | 2027-11-02 | 10 | 28 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-29-U-PC-920 | GC Punchlist @ Units - L29 | yes | Inspection and contractor punch | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Units Partial Inspections & Punchout & Key Delivery at 29th Lvl | TT_Task | TK_NotStart | 2027-11-03 | 2027-11-09 | 5 | 28 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-30-U-PC-900 | Partial MEP Systems Inspections @ Units - L30 | yes | Inspection and contractor punch | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Units Partial Inspections & Punchout & Key Delivery at 30th Lvl | TT_Task | TK_NotStart | 2027-10-20 | 2027-10-26 | 5 | 7 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-30-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L30 | yes | Inspection and contractor punch | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Units Partial Inspections & Punchout & Key Delivery at 30th Lvl | TT_Task | TK_NotStart | 2027-10-27 | 2027-11-09 | 10 | 23 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-30-U-PC-920 | GC Punchlist @ Units - L30 | yes | Inspection and contractor punch | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Units Partial Inspections & Punchout & Key Delivery at 30th Lvl | TT_Task | TK_NotStart | 2027-11-10 | 2027-11-16 | 5 | 23 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-31-U-PC-900 | Partial MEP Systems Inspections @ Units - L31 | yes | Inspection and contractor punch | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Units Partial Inspections & Punchout & Key Delivery at 31st Lvl | TT_Task | TK_NotStart | 2027-11-01 | 2027-11-05 | 5 | 4 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-31-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L31 | yes | Inspection and contractor punch | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Units Partial Inspections & Punchout & Key Delivery at 31st Lvl | TT_Task | TK_NotStart | 2027-11-08 | 2027-11-19 | 10 | 15 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-31-U-PC-920 | GC Punchlist @ Units - L31 | yes | Inspection and contractor punch | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Units Partial Inspections & Punchout & Key Delivery at 31st Lvl | TT_Task | TK_NotStart | 2027-11-22 | 2027-11-30 | 5 | 15 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-32-U-PC-900 | Partial MEP Systems Inspections @ Units - L32 | yes | Inspection and contractor punch | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 32nd Lvl | TT_Task | TK_NotStart | 2027-11-08 | 2027-11-12 | 5 | 4 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-32-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L32 | yes | Inspection and contractor punch | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 32nd Lvl | TT_Task | TK_NotStart | 2027-11-15 | 2027-11-30 | 10 | 10 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-32-U-PC-920 | GC Punchlist @ Units - L32 | yes | Inspection and contractor punch | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 32nd Lvl | TT_Task | TK_NotStart | 2027-12-01 | 2027-12-07 | 5 | 10 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-33-U-PC-900 | Partial MEP Systems Inspections @ Units - L33 | yes | Inspection and contractor punch | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 33rd Lvl | TT_Task | TK_NotStart | 2027-11-11 | 2027-11-17 | 5 | 4 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-33-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L33 | yes | Inspection and contractor punch | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 33rd Lvl | TT_Task | TK_NotStart | 2027-11-18 | 2027-12-03 | 10 | 7 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-33-U-PC-920 | GC Punchlist @ Units - L33 | yes | Inspection and contractor punch | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 33rd Lvl | TT_Task | TK_NotStart | 2027-12-06 | 2027-12-10 | 5 | 7 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-34-U-PC-900 | Partial MEP Systems Inspections @ Units - L34 | yes | Inspection and contractor punch | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Units Partial Inspections & Punchout & Key Delivery at 34th Lvl | TT_Task | TK_NotStart | 2027-11-22 | 2027-11-30 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-34-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L34 | yes | Inspection and contractor punch | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Units Partial Inspections & Punchout & Key Delivery at 34th Lvl | TT_Task | TK_NotStart | 2027-12-01 | 2027-12-14 | 10 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-34-U-PC-920 | GC Punchlist @ Units - L34 | yes | Inspection and contractor punch | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Units Partial Inspections & Punchout & Key Delivery at 34th Lvl | TT_Task | TK_NotStart | 2027-12-15 | 2027-12-21 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-35-U-PC-900 | Partial MEP Systems Inspections @ Units - L35 | yes | Inspection and contractor punch | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Units Partial Inspections & Punchout & Key Delivery at 35th Lvl | TT_Task | TK_NotStart | 2027-11-29 | 2027-12-03 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-35-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L35 | yes | Inspection and contractor punch | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Units Partial Inspections & Punchout & Key Delivery at 35th Lvl | TT_Task | TK_NotStart | 2027-12-01 | 2027-12-14 | 10 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-35-U-PC-920 | GC Punchlist @ Units - L35 | yes | Inspection and contractor punch | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Units Partial Inspections & Punchout & Key Delivery at 35th Lvl | TT_Task | TK_NotStart | 2027-12-15 | 2027-12-21 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-36-IN-PC-900 | Partial MEP Systems Inspections @ Indoor - L36 | yes | Inspection and contractor punch | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Units Partial Inspections & Punchout & Key Delivery at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-10-04 | 2027-10-08 | 5 | 33 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery at Indoor
Baseline | C-36-IN-PC-910 | Subcontractor Punch List & Punch Paint @ Indoor - L36 | yes | Inspection and contractor punch | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Units Partial Inspections & Punchout & Key Delivery at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-10-11 | 2027-10-29 | 15 | 81 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery at Indoor
Baseline | C-36-IN-PC-920 | GC Punchlist @ Indoor - L36 | yes | Inspection and contractor punch | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Units Partial Inspections & Punchout & Key Delivery at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-11-01 | 2027-11-05 | 5 | 81 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery at Indoor
Baseline | C-01-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L1 | yes | Final clean and Owner punch | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > Interior Finishes at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-09-27 | 2027-09-27 | 1 | 117 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridors
Baseline | C-01-U-PC-930 | Final Cleanup @ L1 | yes | Final clean and Owner punch | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Units Partial Inspections & Punchout & Key Delivery at 1st Lvl | TT_Task | TK_NotStart | 2027-11-15 | 2027-11-19 | 5 | 76 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-01-U-PC-940 | Touch-up Paint @ L1 | yes | Final clean and Owner punch | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Units Partial Inspections & Punchout & Key Delivery at 1st Lvl | TT_Task | TK_NotStart | 2027-11-22 | 2027-11-23 | 2 | 76 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-01-U-PC-950 | Owner/Arch Punch List @ L1 | yes | Final clean and Owner punch | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Units Partial Inspections & Punchout & Key Delivery at 1st Lvl | TT_Task | TK_NotStart | 2027-11-24 | 2027-12-02 | 5 | 76 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-02-U-PC-930 | Final Cleanup @ L2 | yes | Final clean and Owner punch | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 2nd Lvl | TT_Task | TK_NotStart | 2027-05-06 | 2027-05-12 | 5 | 51 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-02-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L2 | yes | Final clean and Owner punch | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > Interior Finishes at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2027-05-13 | 2027-05-13 | 1 | 51 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-02-U-PC-950 | Owner/Arch Punch List @ L2 | yes | Final clean and Owner punch | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 2nd Lvl | TT_Task | TK_NotStart | 2027-05-14 | 2027-05-20 | 5 | 51 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-03-U-PC-930 | Final Cleanup @ Units - L3 | yes | Final clean and Owner punch | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 3rd Lvl | TT_Task | TK_NotStart | 2027-05-17 | 2027-05-21 | 5 | 49 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-03-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L3 | yes | Final clean and Owner punch | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > Interior Finishes at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2027-05-24 | 2027-05-24 | 1 | 49 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-03-U-PC-950 | Owner/Arch Punch List @ L3 | yes | Final clean and Owner punch | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units 3rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 3rd Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-06-01 | 5 | 49 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-04-U-PC-930 | Final Cleanup @ Units - L4 | yes | Final clean and Owner punch | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Units Partial Inspections & Punchout & Key Delivery at 4th Lvl | TT_Task | TK_NotStart | 2027-05-26 | 2027-06-02 | 5 | 47 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-04-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L4 | yes | Final clean and Owner punch | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > Interior Finishes at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2027-06-03 | 2027-06-03 | 1 | 47 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-04-U-PC-950 | Owner/Arch Punch List @ L4 | yes | Final clean and Owner punch | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units 4th Lvl > Units Partial Inspections & Punchout & Key Delivery at 4th Lvl | TT_Task | TK_NotStart | 2027-06-04 | 2027-06-10 | 5 | 47 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-05-U-PC-930 | Final Cleanup @ Units - L5 | yes | Final clean and Owner punch | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Units Partial Inspections & Punchout & Key Delivery at 5th Lvl | TT_Task | TK_NotStart | 2027-06-07 | 2027-06-11 | 5 | 45 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-05-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L5 | yes | Final clean and Owner punch | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > Interior Finishes at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2027-06-14 | 2027-06-14 | 1 | 45 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-05-U-PC-950 | Owner/Arch Punch List @ L5 | yes | Final clean and Owner punch | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units 5th Lvl > Units Partial Inspections & Punchout & Key Delivery at 5th Lvl | TT_Task | TK_NotStart | 2027-06-15 | 2027-06-21 | 5 | 45 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-06-U-PC-930 | Final Cleanup @ Units - L6 | yes | Final clean and Owner punch | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Units Partial Inspections & Punchout & Key Delivery at 6th Lvl | TT_Task | TK_NotStart | 2027-06-16 | 2027-06-22 | 5 | 43 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-06-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L6 | yes | Final clean and Owner punch | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > Interior Finishes at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2027-06-23 | 2027-06-23 | 1 | 43 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-06-U-PC-950 | Owner/Arch Punch List @ L6 | yes | Final clean and Owner punch | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units 6th Lvl > Units Partial Inspections & Punchout & Key Delivery at 6th Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-30 | 5 | 43 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-07-U-PC-930 | Final Cleanup @ Units - L7 | yes | Final clean and Owner punch | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Units Partial Inspections & Punchout & Key Delivery at 7th Lvl | TT_Task | TK_NotStart | 2027-06-25 | 2027-07-01 | 5 | 41 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-07-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L7 | yes | Final clean and Owner punch | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > Interior Finishes at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2027-07-02 | 2027-07-02 | 1 | 41 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-07-U-PC-950 | Owner/Arch Punch List @ L7 | yes | Final clean and Owner punch | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Units Partial Inspections & Punchout & Key Delivery at 7th Lvl | TT_Task | TK_NotStart | 2027-07-06 | 2027-07-12 | 5 | 41 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-08-U-PC-930 | Final Cleanup @ Units - L8 | yes | Final clean and Owner punch | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Units Partial Inspections & Punchout & Key Delivery at 8th Lvl | TT_Task | TK_NotStart | 2027-07-07 | 2027-07-13 | 5 | 39 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-08-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L8 | yes | Final clean and Owner punch | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > Interior Finishes at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2027-07-14 | 2027-07-14 | 1 | 39 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-08-U-PC-950 | Owner/Arch Punch List @ L8 | yes | Final clean and Owner punch | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Units Partial Inspections & Punchout & Key Delivery at 8th Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-21 | 5 | 39 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-09-U-PC-930 | Final Cleanup @ Units - L9 | yes | Final clean and Owner punch | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Units Partial Inspections & Punchout & Key Delivery at 9th Lvl | TT_Task | TK_NotStart | 2027-07-16 | 2027-07-22 | 5 | 37 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-09-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L9 | yes | Final clean and Owner punch | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > Interior Finishes at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2027-07-23 | 2027-07-23 | 1 | 37 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-09-U-PC-950 | Owner/Arch Punch List @ L9 | yes | Final clean and Owner punch | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Units Partial Inspections & Punchout & Key Delivery at 9th Lvl | TT_Task | TK_NotStart | 2027-07-26 | 2027-07-30 | 5 | 37 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-10-U-PC-930 | Final Cleanup @ Units - L10 | yes | Final clean and Owner punch | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Units Partial Inspections & Punchout & Key Delivery at 10th Lvl | TT_Task | TK_NotStart | 2027-07-23 | 2027-07-29 | 5 | 37 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-10-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L10 | yes | Final clean and Owner punch | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > Interior Finishes at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2027-07-30 | 2027-07-30 | 1 | 37 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-10-U-PC-950 | Owner/Arch Punch List @ L10 | yes | Final clean and Owner punch | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Units Partial Inspections & Punchout & Key Delivery at 10th Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-06 | 5 | 37 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-11-U-PC-930 | Final Cleanup @ Units - L11 | yes | Final clean and Owner punch | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Units Partial Inspections & Punchout & Key Delivery at 11th Lvl | TT_Task | TK_NotStart | 2027-07-30 | 2027-08-05 | 5 | 37 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-11-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L11 | yes | Final clean and Owner punch | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > Interior Finishes at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2027-08-06 | 2027-08-06 | 1 | 37 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-11-U-PC-950 | Owner/Arch Punch List @ L11 | yes | Final clean and Owner punch | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Units Partial Inspections & Punchout & Key Delivery at 11th Lvl | TT_Task | TK_NotStart | 2027-08-09 | 2027-08-13 | 5 | 37 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-12-U-PC-930 | Final Cleanup @ Units - L12 | yes | Final clean and Owner punch | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Units Partial Inspections & Punchout & Key Delivery at 12th Lvl | TT_Task | TK_NotStart | 2027-08-09 | 2027-08-13 | 5 | 36 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-12-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L12 | yes | Final clean and Owner punch | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > Interior Finishes at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2027-08-16 | 2027-08-16 | 1 | 36 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-12-U-PC-950 | Owner/Arch Punch List @ L12 | yes | Final clean and Owner punch | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Units Partial Inspections & Punchout & Key Delivery at 12th Lvl | TT_Task | TK_NotStart | 2027-08-17 | 2027-08-23 | 5 | 36 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-14-U-PC-930 | Final Cleanup @ Units - L14 | yes | Final clean and Owner punch | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Units Partial Inspections & Punchout & Key Delivery at 14th Lvl | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-24 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-14-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L14 | yes | Final clean and Owner punch | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > Interior Finishes at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2027-08-25 | 2027-08-25 | 1 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-14-U-PC-950 | Owner/Arch Punch List @ L14 | yes | Final clean and Owner punch | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Units Partial Inspections & Punchout & Key Delivery at 14th Lvl | TT_Task | TK_NotStart | 2027-08-26 | 2027-09-01 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-15-U-PC-930 | Final Cleanup @ Units - L15 | yes | Final clean and Owner punch | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Units Partial Inspections & Punchout & Key Delivery at 15th Lvl | TT_Task | TK_NotStart | 2027-08-25 | 2027-08-31 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-15-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L15 | yes | Final clean and Owner punch | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > Interior Finishes at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-09-01 | 2027-09-01 | 1 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-15-U-PC-950 | Owner/Arch Punch List @ L15 | yes | Final clean and Owner punch | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Units Partial Inspections & Punchout & Key Delivery at 15th Lvl | TT_Task | TK_NotStart | 2027-09-02 | 2027-09-09 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-16-U-PC-930 | Final Cleanup @ Units - L16 | yes | Final clean and Owner punch | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Units Partial Inspections & Punchout & Key Delivery at 16th Lvl | TT_Task | TK_NotStart | 2027-09-01 | 2027-09-08 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-16-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L16 | yes | Final clean and Owner punch | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > Interior Finishes at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-09-09 | 2027-09-09 | 1 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-16-U-PC-950 | Owner/Arch Punch List @ L16 | yes | Final clean and Owner punch | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Units Partial Inspections & Punchout & Key Delivery at 16th Lvl | TT_Task | TK_NotStart | 2027-09-10 | 2027-09-16 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-17-U-PC-930 | Final Cleanup @ Units - L17 | yes | Final clean and Owner punch | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Units Partial Inspections & Punchout & Key Delivery at 17th Lvl | TT_Task | TK_NotStart | 2027-09-09 | 2027-09-15 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-17-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L17 | yes | Final clean and Owner punch | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > Interior Finishes at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-09-16 | 2027-09-16 | 1 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-17-U-PC-950 | Owner/Arch Punch List @ Units - L17 | yes | Final clean and Owner punch | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Units Partial Inspections & Punchout & Key Delivery at 17th Lvl | TT_Task | TK_NotStart | 2027-09-17 | 2027-09-23 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-18-U-PC-930 | Final Cleanup @ Units - L18 | yes | Final clean and Owner punch | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Units Partial Inspections & Punchout & Key Delivery at 18th Lvl | TT_Task | TK_NotStart | 2027-09-16 | 2027-09-22 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-18-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L18 | yes | Final clean and Owner punch | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > Interior Finishes at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-09-23 | 2027-09-23 | 1 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-18-U-PC-950 | Owner/Arch Punch List @ L18 | yes | Final clean and Owner punch | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Units Partial Inspections & Punchout & Key Delivery at 18th Lvl | TT_Task | TK_NotStart | 2027-09-24 | 2027-09-30 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-19-U-PC-930 | Final Cleanup @ Units - L19 | yes | Final clean and Owner punch | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Units Partial Inspections & Punchout & Key Delivery at 19th Lvl | TT_Task | TK_NotStart | 2027-09-23 | 2027-09-29 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-19-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L19 | yes | Final clean and Owner punch | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > Interior Finishes at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-09-30 | 2027-09-30 | 1 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-19-U-PC-950 | Owner/Arch Punch List @ L19 | yes | Final clean and Owner punch | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Units Partial Inspections & Punchout & Key Delivery at 19th Lvl | TT_Task | TK_NotStart | 2027-10-01 | 2027-10-07 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-20-U-PC-930 | Final Cleanup @ Units - L20 | yes | Final clean and Owner punch | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Units Partial Inspections & Punchout & Key Delivery at 20th Lvl | TT_Task | TK_NotStart | 2027-09-30 | 2027-10-06 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-20-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L20 | yes | Final clean and Owner punch | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > Interior Finishes at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-10-07 | 2027-10-07 | 1 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-20-U-PC-950 | Owner/Arch Punch List @ L20 | yes | Final clean and Owner punch | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Units Partial Inspections & Punchout & Key Delivery at 20th Lvl | TT_Task | TK_NotStart | 2027-10-08 | 2027-10-14 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-21-U-PC-930 | Final Cleanup @ Units - L21 | yes | Final clean and Owner punch | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Units Partial Inspections & Punchout & Key Delivery at 21st Lvl | TT_Task | TK_NotStart | 2027-10-07 | 2027-10-13 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-21-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L21 | yes | Final clean and Owner punch | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > Interior Finishes at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-10-14 | 2027-10-14 | 1 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-21-U-PC-950 | Owner/Arch Punch List @ L21 | yes | Final clean and Owner punch | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Units Partial Inspections & Punchout & Key Delivery at 21st Lvl | TT_Task | TK_NotStart | 2027-10-15 | 2027-10-21 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-22-U-PC-930 | Final Cleanup @ Units - L22 | yes | Final clean and Owner punch | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 22nd Lvl | TT_Task | TK_NotStart | 2027-10-14 | 2027-10-20 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-22-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L22 | yes | Final clean and Owner punch | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > Interior Finishes at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-10-21 | 2027-10-21 | 1 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-22-U-PC-950 | Owner/Arch Punch List @ L22 | yes | Final clean and Owner punch | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 22nd Lvl | TT_Task | TK_NotStart | 2027-10-22 | 2027-10-28 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-23-U-PC-930 | Final Cleanup @ Units - L23 | yes | Final clean and Owner punch | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 23rd Lvl | TT_Task | TK_NotStart | 2027-10-21 | 2027-10-27 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-23-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L23 | yes | Final clean and Owner punch | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > Interior Finishes at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-10-28 | 2027-10-28 | 1 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-23-U-PC-950 | Owner/Arch Punch List @ L23 | yes | Final clean and Owner punch | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 23rd Lvl | TT_Task | TK_NotStart | 2027-10-29 | 2027-11-04 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-24-U-PC-930 | Final Cleanup @ Units - L24 | yes | Final clean and Owner punch | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Units Partial Inspections & Punchout & Key Delivery at 24th Lvl | TT_Task | TK_NotStart | 2027-10-28 | 2027-11-03 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-24-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L24 | yes | Final clean and Owner punch | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > Interior Finishes at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-11-04 | 2027-11-04 | 1 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-24-U-PC-950 | Owner/Arch Punch List @ L24 | yes | Final clean and Owner punch | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Units Partial Inspections & Punchout & Key Delivery at 24th Lvl | TT_Task | TK_NotStart | 2027-11-05 | 2027-11-11 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-25-U-PC-930 | Final Cleanup @ Units - L25 | yes | Final clean and Owner punch | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Units Partial Inspections & Punchout & Key Delivery at 25th Lvl | TT_Task | TK_NotStart | 2027-11-04 | 2027-11-10 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-25-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L25 | yes | Final clean and Owner punch | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > Interior Finishes at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-11-11 | 2027-11-11 | 1 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-25-U-PC-950 | Owner/Arch Punch List @ L25 | yes | Final clean and Owner punch | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Units Partial Inspections & Punchout & Key Delivery at 25th Lvl | TT_Task | TK_NotStart | 2027-11-12 | 2027-11-18 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-26-U-PC-930 | Final Cleanup @ Units - L26 | yes | Final clean and Owner punch | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Units Partial Inspections & Punchout & Key Delivery at 26th Lvl | TT_Task | TK_NotStart | 2027-11-11 | 2027-11-17 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-26-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L26 | yes | Final clean and Owner punch | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > Interior Finishes at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-11-18 | 2027-11-18 | 1 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-26-U-PC-950 | Owner/Arch Punch List @ L26 | yes | Final clean and Owner punch | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Units Partial Inspections & Punchout & Key Delivery at 26th Lvl | TT_Task | TK_NotStart | 2027-11-19 | 2027-11-29 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-27-U-PC-930 | Final Cleanup @ Units - L27 | yes | Final clean and Owner punch | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Units Partial Inspections & Punchout & Key Delivery at 27th Lvl | TT_Task | TK_NotStart | 2027-11-18 | 2027-11-24 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-27-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L27 | yes | Final clean and Owner punch | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > Interior Finishes at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-11-29 | 2027-11-29 | 1 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-27-U-PC-950 | Owner/Arch Punch List @ L27 | yes | Final clean and Owner punch | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Units Partial Inspections & Punchout & Key Delivery at 27th Lvl | TT_Task | TK_NotStart | 2027-11-30 | 2027-12-06 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-28-U-PC-930 | Final Cleanup @ Units - L28 | yes | Final clean and Owner punch | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Units Partial Inspections & Punchout & Key Delivery at 28th Lvl | TT_Task | TK_NotStart | 2027-11-29 | 2027-12-03 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-28-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L28 | yes | Final clean and Owner punch | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > Interior Finishes at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-12-06 | 2027-12-06 | 1 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-28-U-PC-950 | Owner/Arch Punch List @ L28 | yes | Final clean and Owner punch | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Units Partial Inspections & Punchout & Key Delivery at 28th Lvl | TT_Task | TK_NotStart | 2027-12-07 | 2027-12-13 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-29-U-PC-930 | Final Cleanup @ Units - L29 | yes | Final clean and Owner punch | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Units Partial Inspections & Punchout & Key Delivery at 29th Lvl | TT_Task | TK_NotStart | 2027-12-06 | 2027-12-10 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-29-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L29 | yes | Final clean and Owner punch | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > Interior Finishes at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-12-13 | 2027-12-13 | 1 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-29-U-PC-950 | Owner/Arch Punch List @ L29 | yes | Final clean and Owner punch | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Units Partial Inspections & Punchout & Key Delivery at 29th Lvl | TT_Task | TK_NotStart | 2027-12-14 | 2027-12-20 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-30-U-PC-930 | Final Cleanup @ Units - L30 | yes | Final clean and Owner punch | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Units Partial Inspections & Punchout & Key Delivery at 30th Lvl | TT_Task | TK_NotStart | 2027-12-13 | 2027-12-17 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-30-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L30 | yes | Final clean and Owner punch | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > Interior Finishes at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-12-20 | 2027-12-20 | 1 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-30-U-PC-950 | Owner/Arch Punch List @ L30 | yes | Final clean and Owner punch | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Units Partial Inspections & Punchout & Key Delivery at 30th Lvl | TT_Task | TK_NotStart | 2027-12-21 | 2027-12-28 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-31-U-PC-930 | Final Cleanup @ Units - L31 | yes | Final clean and Owner punch | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Units Partial Inspections & Punchout & Key Delivery at 31st Lvl | TT_Task | TK_NotStart | 2027-12-20 | 2027-12-27 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-31-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L31 | yes | Final clean and Owner punch | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > Interior Finishes at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-12-28 | 2027-12-28 | 1 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-31-U-PC-950 | Owner/Arch Punch List @ L31 | yes | Final clean and Owner punch | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Units Partial Inspections & Punchout & Key Delivery at 31st Lvl | TT_Task | TK_NotStart | 2027-12-29 | 2028-01-05 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-32-U-PC-930 | Final Cleanup @ Units - L32 | yes | Final clean and Owner punch | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 32nd Lvl | TT_Task | TK_NotStart | 2027-12-28 | 2028-01-04 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-32-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L32 | yes | Final clean and Owner punch | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > Interior Finishes at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2028-01-05 | 2028-01-05 | 1 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-32-U-PC-950 | Owner/Arch Punch List @ L32 | yes | Final clean and Owner punch | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 32nd Lvl | TT_Task | TK_NotStart | 2028-01-06 | 2028-01-12 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-33-U-PC-930 | Final Cleanup @ Units - L33 | yes | Final clean and Owner punch | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 33rd Lvl | TT_Task | TK_NotStart | 2028-01-05 | 2028-01-11 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-33-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L33 | yes | Final clean and Owner punch | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > Interior Finishes at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2028-01-12 | 2028-01-12 | 1 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-33-U-PC-950 | Owner/Arch Punch List @ L33 | yes | Final clean and Owner punch | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 33rd Lvl | TT_Task | TK_NotStart | 2028-01-13 | 2028-01-19 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-34-U-PC-930 | Final Cleanup @ Units - L34 | yes | Final clean and Owner punch | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Units Partial Inspections & Punchout & Key Delivery at 34th Lvl | TT_Task | TK_NotStart | 2028-01-12 | 2028-01-18 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-34-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L34 | yes | Final clean and Owner punch | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > Interior Finishes at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2028-01-19 | 2028-01-19 | 1 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-34-U-PC-950 | Owner/Arch Punch List @ L34 | yes | Final clean and Owner punch | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Units Partial Inspections & Punchout & Key Delivery at 34th Lvl | TT_Task | TK_NotStart | 2028-01-20 | 2028-01-26 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-35-U-PC-930 | Final Cleanup @ Units - L35 | yes | Final clean and Owner punch | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Units Partial Inspections & Punchout & Key Delivery at 35th Lvl | TT_Task | TK_NotStart | 2028-01-19 | 2028-01-25 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-35-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L35 | yes | Final clean and Owner punch | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > Interior Finishes at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2028-01-26 | 2028-01-26 | 1 | 34 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Baseline | C-35-U-PC-950 | Owner/Arch Punch List @ L35 | yes | Final clean and Owner punch | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Units Partial Inspections & Punchout & Key Delivery at 35th Lvl | TT_Task | TK_NotStart | 2028-01-27 | 2028-02-02 | 5 | 34 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Baseline | C-36-IN-PC-930 | Final Cleanup @ Indoor - L36 | yes | Final clean and Owner punch | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Units Partial Inspections & Punchout & Key Delivery at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-11-08 | 2027-11-12 | 5 | 81 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery at Indoor
Baseline | C-36-IN-PC-940 | Touchup Paint @ Indoor - L36 | yes | Final clean and Owner punch | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Units Partial Inspections & Punchout & Key Delivery at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-11-15 | 2027-11-16 | 2 | 81 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery at Indoor
Baseline | C-36-IN-PC-950 | Owner/Arch Punch List @ Indoor - L36 | yes | Final clean and Owner punch | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Units Partial Inspections & Punchout & Key Delivery at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-11-17 | 2027-11-23 | 5 | 81 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery at Indoor
Baseline | C-00-PL-100 | Install & Report Test Piles @ Site | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Piling Work | TT_Task | TK_NotStart | 2025-11-11 | 2025-12-10 | 20 | 0 | Building Structure | Piling Work
Baseline | C-00-ST-100 | Excavate Entire Lot 3' ft @ Site | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2025-11-11 | 2025-12-03 | 15 | 22 | Building Structure | Foundation Work
Baseline | C-00-WL-100 | Install Perm Wells @ Site | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2025-12-04 | 2025-12-17 | 10 | 22 | Building Structure | Foundation Work
Baseline | C-00-PL-200 | Install Production Piles @ Bldg | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Piling Work | TT_Task | TK_NotStart | 2025-12-11 | 2026-01-16 | 25 | 0 | Building Structure | Piling Work
Baseline | C-00-PL-300 | Cut-off Piles @ Site | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Piling Work | TT_Task | TK_NotStart | 2026-01-19 | 2026-01-23 | 5 | 0 | Building Structure | Piling Work
Baseline | C-00-ST-200 | Form PIle Caps @ Foundations | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2026-01-21 | 2026-01-27 | 5 | 0 | Building Structure | Foundation Work
Baseline | C-00-ST-210 | Rebar Pile Caps @ Foundations | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2026-01-26 | 2026-02-06 | 10 | 0 | Building Structure | Foundation Work
Baseline | C-00-ST-220 | Pour Pile Caps @ Foundations | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2026-02-09 | 2026-02-10 | 2 | 0 | Building Structure | Foundation Work
Baseline | C-00-ST-300 | Rebar Shear Walls @ Foundations | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2026-02-11 | 2026-02-24 | 10 | 0 | Building Structure | Foundation Work
Baseline | C-00-ST-310 | Form Shear Walls @ Foundations | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2026-02-25 | 2026-02-27 | 3 | 0 | Building Structure | Foundation Work
Baseline | C-00-ST-320 | Pour Shear Walls @ Foundations | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2026-03-02 | 2026-03-03 | 2 | 0 | Building Structure | Foundation Work
Baseline | C-00-ST-400 | Form Grade Beams @ Foundations | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2026-03-04 | 2026-03-05 | 2 | 0 | Building Structure | Foundation Work
Baseline | C-00-ST-410 | Rebar Grade Beams @ Foundations | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2026-03-06 | 2026-03-12 | 5 | 0 | Building Structure | Foundation Work
Baseline | C-00-ST-420 | Pour Grade Beams @ Foundations | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2026-03-13 | 2026-03-13 | 1 | 0 | Building Structure | Foundation Work
Baseline | C-00-ST-500 | F/R/P 1st Lift Columns @ Foundations - L1 | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2026-03-16 | 2026-03-20 | 5 | 0 | Building Structure | Foundation Work
Baseline | C-00-ST-600 | Backfill & Compact @ Foundations | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2026-03-20 | 2026-03-23 | 2 | 0 | Building Structure | Foundation Work
Baseline | C-00-MP-300 | Install U/G Electrical @ FPL Vault Area | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Superstructure > U/G MEPs & SOG at 1st Lvl > FPL Vault SOG - Early Work | TT_Task | TK_NotStart | 2026-08-18 | 2026-09-08 | 15 | 6 | Building Structure | FPL Vault SOG - Early Work
Baseline | C-00-MP-100 | Install U/G Plumbing @ Subsurface | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Superstructure > U/G MEPs & SOG at 1st Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-03-17 | 15 | 14 | Building Structure | U/G MEPs & SOG
Baseline | C-00-MP-110 | Install U/G Electrical @ Subsurface | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Superstructure > U/G MEPs & SOG at 1st Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-31 | 15 | 14 | Building Structure | U/G MEPs & SOG
Baseline | C-01-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-05-08 | 2026-05-13 | 4 | 5 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-01-ST-310 | Apply Vapor Barrier Under S.O.G. @ FPL Vault #118 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Building Superstructure > U/G MEPs & SOG at 1st Lvl > FPL Vault SOG - Early Work | TT_Task | TK_NotStart | 2026-09-09 | 2026-09-09 | 1 | 6 | Building Structure | FPL Vault SOG - Early Work
Baseline | C-01-ST-320 | F/R/P S.O.G. @ FPL Vault #118 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Building Superstructure > U/G MEPs & SOG at 1st Lvl > FPL Vault SOG - Early Work | TT_Task | TK_NotStart | 2026-09-10 | 2026-09-14 | 3 | 6 | Building Structure | FPL Vault SOG - Early Work
Baseline | C-01-ST-330 | Lay CMU Walls @ FPL Vault #118 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Building Superstructure > U/G MEPs & SOG at 1st Lvl > FPL Vault SOG - Early Work | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-17 | 3 | 6 | Building Structure | FPL Vault SOG - Early Work
Baseline | C-01-MP-MP-100 | Prep Room to Receive FPL Work @ FPL Vault #118 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > FPL Vault #118 at 1st Lvl | TT_Task | TK_NotStart | 2026-09-18 | 2026-10-15 | 20 | 6 | Interior MEPs & Finishes | FPL Vault #118
Baseline | C-01-MP-MP-110 | Verify Vault by FPL Work @ FPL Vault #118 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > FPL Vault #118 at 1st Lvl | TT_Task | TK_NotStart | 2026-10-16 | 2026-11-05 | 15 | 6 | Interior MEPs & Finishes | FPL Vault #118
Baseline | C-01-MP-MP-120 | Coordinate & Schedule with FPL for Work @ FPL Vault #118 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > FPL Vault #118 at 1st Lvl | TT_Task | TK_NotStart | 2026-11-06 | 2027-01-06 | 40 | 6 | Interior MEPs & Finishes | FPL Vault #118
Baseline | C-01-MP-MP-130 | FPL Work @ FPL Vault #118 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > FPL Vault #118 at 1st Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-03-17 | 50 | 6 | Interior MEPs & Finishes | FPL Vault #118
Baseline | C-01-MP-130 | Install Grease (GI-1) & Solid (SI-1) Interceptors & Piping @ Subsurface | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Building Superstructure > U/G MEPs & SOG at 1st Lvl | TT_Task | TK_NotStart | 2027-03-18 | 2027-03-31 | 10 | 14 | Building Structure | U/G MEPs & SOG
Baseline | C-01-ST-200 | Apply Vapor Barrier Under S.O.G. @ L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Building Superstructure > U/G MEPs & SOG at 1st Lvl | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-05 | 3 | 14 | Building Structure | U/G MEPs & SOG
Baseline | C-01-ST-210 | F/R/P S.O.G. @ L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Building Superstructure > U/G MEPs & SOG at 1st Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-13 | 6 | 14 | Building Structure | U/G MEPs & SOG
Baseline | C-01-PG-MP-200 | Install Plumbing Floor Drains @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > MEP Eqp & Trim at Parking & Drop-Offat 1st Lvl | TT_Task | TK_NotStart | 2027-06-02 | 2027-06-04 | 3 | 107 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking & Drop-Offat
Baseline | C-01-PG-MP-210 | Install Mech GEFs @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > MEP Eqp & Trim at Parking & Drop-Offat 1st Lvl | TT_Task | TK_NotStart | 2027-06-28 | 2027-07-02 | 5 | 65 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking & Drop-Offat
Baseline | C-01-KT-100 | Kitchen Buildout (By Others) @ L1 (Place Holder) | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Work by Others Future Space (Work by Others) - Place Holders | TT_Task | TK_NotStart | 2027-07-15 | 2028-03-01 | 160 | 14 | Interior MEPs & Finishes | Work by Others Future Space (Work by Others) - Place Holders
Baseline | C-01-LB-100 | Lobby & Restaurant Buildout (By Others) @ L1 (Place Holder) | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Work by Others Future Space (Work by Others) - Place Holders | TT_Task | TK_NotStart | 2027-07-15 | 2028-02-16 | 150 | 24 | Interior MEPs & Finishes | Work by Others Future Space (Work by Others) - Place Holders
Baseline | C-01-MP-MP-200 | Prep Room to Receive FC Eqp @ Fire Command #112 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Command #112 at 1st Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-08-04 | 15 | 34 | Interior MEPs & Finishes | Fire Command #112
Baseline | C-01-MP-MP-300 | Prep Room to Receive Pump Eqp @ Fire Pump Rm #116 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Pump Rm #116 at 1st Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-08-04 | 15 | 38 | Interior MEPs & Finishes | Fire Pump Rm #116
Baseline | C-01-MP-MP-500 | Prep Room to Receive Trash Eqp @ Trash Rms #115 & #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Trash Rms #115 & #122 at 1st Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-08-04 | 15 | 33 | Interior MEPs & Finishes | Trash Rms #115 & #122
Baseline | C-01-PG-EV-100 | Install Car Elevators @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-11-04 | 80 | 80 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Baseline | C-01-MP-MP-210 | Install Mech A/C Eqp @ Fire Command #112 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Command #112 at 1st Lvl | TT_Task | TK_NotStart | 2027-08-05 | 2027-08-06 | 2 | 34 | Interior MEPs & Finishes | Fire Command #112
Baseline | C-01-MP-MP-310 | F/R/P Pump Pads @ Fire Pump Rm #116 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Pump Rm #116 at 1st Lvl | TT_Task | TK_NotStart | 2027-08-05 | 2027-08-06 | 2 | 38 | Interior MEPs & Finishes | Fire Pump Rm #116
Baseline | C-01-MP-MP-400 | Prep Room to Receive Pump Eqp @ Domestic Water #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Domestic Water Rm #121 at 1st Lvl | TT_Task | TK_NotStart | 2027-08-05 | 2027-08-25 | 15 | 88 | Interior MEPs & Finishes | Domestic Water Rm #121
Baseline | C-01-MP-MP-510 | Install Floor Drains (GDs) @ Trash Rms #115 & #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Trash Rms #115 & #122 at 1st Lvl | TT_Task | TK_NotStart | 2027-08-05 | 2027-08-06 | 2 | 33 | Interior MEPs & Finishes | Trash Rms #115 & #122
Baseline | C-01-MP-MP-220 | Install Electrical Panels @ Fire Command #112 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Command #112 at 1st Lvl | TT_Task | TK_NotStart | 2027-08-09 | 2027-08-13 | 5 | 34 | Interior MEPs & Finishes | Fire Command #112
Baseline | C-01-MP-MP-320 | Install Floor Drain (FD) @ Fire Pump Rm #116 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Pump Rm #116 at 1st Lvl | TT_Task | TK_NotStart | 2027-08-09 | 2027-08-09 | 1 | 38 | Interior MEPs & Finishes | Fire Pump Rm #116
Baseline | C-01-MP-MP-520 | Install Mech A/C Eqp @ Trash Rms #115 & #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Trash Rms #115 & #122 at 1st Lvl | TT_Task | TK_NotStart | 2027-08-09 | 2027-08-12 | 4 | 33 | Interior MEPs & Finishes | Trash Rms #115 & #122
Baseline | C-01-MP-MP-330 | Apply Waterproofing @ Fire Pump Rm #116 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Pump Rm #116 at 1st Lvl | TT_Task | TK_NotStart | 2027-08-10 | 2027-08-11 | 2 | 38 | Interior MEPs & Finishes | Fire Pump Rm #116
Baseline | C-01-PG-FN-110 | Frame GWB Ceilings @ Drop-Off - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-08-10 | 2027-08-17 | 6 | 15 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Baseline | C-01-MP-MP-340 | Install Mech A/C Eqp @ Fire Pump Rm #116 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Pump Rm #116 at 1st Lvl | TT_Task | TK_NotStart | 2027-08-12 | 2027-08-13 | 2 | 38 | Interior MEPs & Finishes | Fire Pump Rm #116
Baseline | C-01-MP-MP-530 | Install MEP Trim @ Trash Rms #115 & #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Trash Rms #115 & #122 at 1st Lvl | TT_Task | TK_NotStart | 2027-08-13 | 2027-08-23 | 7 | 33 | Interior MEPs & Finishes | Trash Rms #115 & #122
Baseline | C-01-MP-MP-230 | Install Fire Alarm FA/V-CP & FACP & FAPS Panels @ Fire Command #112 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Command #112 at 1st Lvl | TT_Task | TK_NotStart | 2027-08-16 | 2027-09-03 | 15 | 34 | Interior MEPs & Finishes | Fire Command #112
Baseline | C-01-MP-MP-240 | Install Generator Switch (SS) & Status Panel (GENAN) @ Fire Command #112 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Command #112 at 1st Lvl | TT_Task | TK_NotStart | 2027-08-16 | 2027-08-20 | 5 | 44 | Interior MEPs & Finishes | Fire Command #112
Baseline | C-01-MP-MP-350 | Install & Connect Fire Pumps @ Fire Pump Rm #116 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Pump Rm #116 at 1st Lvl | TT_Task | TK_NotStart | 2027-08-16 | 2027-09-03 | 15 | 38 | Interior MEPs & Finishes | Fire Pump Rm #116
Baseline | C-01-PG-FN-120 | Hang GWB Ceilings @ Drop-Off - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-08-16 | 2027-08-23 | 6 | 15 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Baseline | C-01-PG-FN-130 | Tape & Finish GWB Ceilings @ Drop-Off - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-08-20 | 2027-08-26 | 5 | 15 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Baseline | C-01-MP-MP-540 | Install Trash Eqp @ Trash Rms #115 & #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Trash Rms #115 & #122 at 1st Lvl | TT_Task | TK_NotStart | 2027-08-24 | 2027-09-02 | 8 | 33 | Interior MEPs & Finishes | Trash Rms #115 & #122
Baseline | C-01-MP-MP-410 | F/R/P Pump Pads @ Domestic Water #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Domestic Water Rm #121 at 1st Lvl | TT_Task | TK_NotStart | 2027-08-26 | 2027-08-27 | 2 | 88 | Interior MEPs & Finishes | Domestic Water Rm #121
Baseline | C-01-PG-FN-140 | Install Bollards @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-08-27 | 2027-08-31 | 3 | 27 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Baseline | C-01-PG-FN-150 | Install Metal Canopy @ Drop-Off - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-08-27 | 2027-09-08 | 8 | 114 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Baseline | C-01-PG-FN-160 | Stucco @ Drop-off & Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-08-27 | 2027-09-17 | 15 | 15 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Baseline | C-01-MP-MP-420 | Install Floor Drain (FD) @ Domestic Water #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Domestic Water Rm #121 at 1st Lvl | TT_Task | TK_NotStart | 2027-08-30 | 2027-08-30 | 1 | 88 | Interior MEPs & Finishes | Domestic Water Rm #121
Baseline | C-01-MP-MP-430 | Apply Waterproofing @ Domestic Water #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Domestic Water Rm #121 at 1st Lvl | TT_Task | TK_NotStart | 2027-08-31 | 2027-09-01 | 2 | 88 | Interior MEPs & Finishes | Domestic Water Rm #121
Baseline | C-01-ES-100 | Fine Grade @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-09-02 | 2027-09-13 | 7 | 26 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Baseline | C-01-MP-MP-440 | Install Mech A/C & GEF Eqp @ Dometic Water #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Domestic Water Rm #121 at 1st Lvl | TT_Task | TK_NotStart | 2027-09-02 | 2027-09-03 | 2 | 88 | Interior MEPs & Finishes | Domestic Water Rm #121
Baseline | C-01-MP-MP-250 | Install SCU & Head-End Control Panels @ Fire Command #112 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Command #112 at 1st Lvl | TT_Task | TK_NotStart | 2027-09-07 | 2027-09-13 | 5 | 34 | Interior MEPs & Finishes | Fire Command #112
Baseline | C-01-MP-MP-260 | Install MEP Trim @ Fire Command #112 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Command #112 at 1st Lvl | TT_Task | TK_NotStart | 2027-09-07 | 2027-09-15 | 7 | 37 | Interior MEPs & Finishes | Fire Command #112
Baseline | C-01-MP-MP-360 | Install MEP Trim @ Fire Pump Rm #116 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Pump Rm #116 at 1st Lvl | TT_Task | TK_NotStart | 2027-09-07 | 2027-09-13 | 5 | 38 | Interior MEPs & Finishes | Fire Pump Rm #116
Baseline | C-01-MP-MP-450 | Install & Connect Dometic Pumps @ Dometic Water #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Domestic Water Rm #121 at 1st Lvl | TT_Task | TK_NotStart | 2027-09-07 | 2027-09-27 | 15 | 88 | Interior MEPs & Finishes | Domestic Water Rm #121
Baseline | C-01-PG-FN-170 | Install Porcelain Tiles @ Drop-Off - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-09-09 | 2027-09-22 | 10 | 114 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Baseline | C-01-ES-110 | F/R/P Planters @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-09-14 | 2027-10-04 | 15 | 26 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Baseline | C-01-ES-120 | Install Electrical Rough @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-09-14 | 2027-09-20 | 5 | 43 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Baseline | C-01-MP-MP-270 | Install Elevator ANN Panel (ELAN) @ Fire Command #112 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Command #112 at 1st Lvl | TT_Task | TK_NotStart | 2027-09-14 | 2027-09-20 | 5 | 34 | Interior MEPs & Finishes | Fire Command #112
Baseline | C-01-MP-MP-370 | Install & Pump Controller & Gas Sub Meters @ Fire Pump Rm #116 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Pump Rm #116 at 1st Lvl | TT_Task | TK_NotStart | 2027-09-14 | 2027-09-17 | 4 | 38 | Interior MEPs & Finishes | Fire Pump Rm #116
Baseline | C-01-PG-FN-180 | Paint @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-09-20 | 2027-09-28 | 7 | 15 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Baseline | C-01-PG-FN-190 | Lightweight Concrete Cladding (DEKKO) @ Drop-off - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-09-20 | 2027-10-01 | 10 | 111 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Baseline | C-01-PG-MP-220 | Install Mech Condensing Units @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > MEP Eqp & Trim at Parking & Drop-Offat 1st Lvl | TT_Task | TK_NotStart | 2027-09-20 | 2027-09-22 | 3 | 19 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking & Drop-Offat
Baseline | C-01-MP-MP-280 | Install BDA Panel @ Fire Command #112 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Command #112 at 1st Lvl | TT_Task | TK_NotStart | 2027-09-21 | 2027-09-23 | 3 | 34 | Interior MEPs & Finishes | Fire Command #112
Baseline | C-01-MP-MP-460 | Install MEP Trim @ Domestic Water #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Domestic Water Rm #121 at 1st Lvl | TT_Task | TK_NotStart | 2027-09-22 | 2027-09-28 | 5 | 88 | Interior MEPs & Finishes | Domestic Water Rm #121
Baseline | C-01-ES-130 | Install Irrigation Mainlines & Laterals Rough @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-09-28 | 2027-10-13 | 12 | 26 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Baseline | C-01-MP-MP-470 | Install & Pump Controller @ Dometic Water #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Domestic Water Rm #121 at 1st Lvl | TT_Task | TK_NotStart | 2027-09-29 | 2027-10-01 | 3 | 88 | Interior MEPs & Finishes | Domestic Water Rm #121
Baseline | C-01-PG-FN-200 | Install Column Protection & Pipe Guards @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-09-29 | 2027-10-05 | 5 | 102 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Baseline | C-01-PG-FN-210 | Install Fire Extinguisher Cabinet (FEC) @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-09-29 | 2027-09-29 | 1 | 113 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Baseline | C-01-PG-MP-230 | Install Light Fixtures @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > MEP Eqp & Trim at Parking & Drop-Offat 1st Lvl | TT_Task | TK_NotStart | 2027-09-29 | 2027-10-05 | 5 | 15 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking & Drop-Offat
Baseline | C-01-ES-140 | Install Drainage @ Planters - E. & S. Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-10-05 | 2027-10-18 | 10 | 40 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Baseline | C-01-PG-MP-240 | Install Electrical Power Trim @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > MEP Eqp & Trim at Parking & Drop-Offat 1st Lvl | TT_Task | TK_NotStart | 2027-10-06 | 2027-10-11 | 4 | 15 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking & Drop-Offat
Baseline | C-01-PG-MP-250 | Install FP Sprinkler Heads @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > MEP Eqp & Trim at Parking & Drop-Offat 1st Lvl | TT_Task | TK_NotStart | 2027-10-12 | 2027-10-14 | 3 | 15 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking & Drop-Offat
Baseline | C-01-ES-150 | Form & Pour Conc Curbs & Gutters @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-10-14 | 2027-10-29 | 12 | 26 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Baseline | C-01-PG-MP-260 | Install FA & Low Voltage Devices (CCTV-Access Ctrl-PA) @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > MEP Eqp & Trim at Parking & Drop-Offat 1st Lvl | TT_Task | TK_NotStart | 2027-10-15 | 2027-10-20 | 4 | 15 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking & Drop-Offat
Baseline | C-01-ES-160 | Form & Pour Sidewalks @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-10-25 | 2027-11-05 | 10 | 26 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Baseline | C-01-PG-FN-220 | Apply Waterproofing & Seal Concrete @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-11-05 | 2027-11-09 | 3 | 80 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Baseline | C-01-ES-170 | Install Metal Bike Racks @ E. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-11-08 | 2027-11-08 | 1 | 72 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Baseline | C-01-ES-180 | Apply Stucco @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-11-08 | 2027-11-15 | 6 | 26 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Baseline | C-01-PG-FN-230 | Apply Pavement Markings @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-11-10 | 2027-11-11 | 2 | 80 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Baseline | C-01-PG-FN-240 | Install Signage @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-11-12 | 2027-11-15 | 2 | 80 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Baseline | C-01-ES-190 | Paint Stucco @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-11-16 | 2027-11-17 | 2 | 26 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Baseline | C-01-PG-FN-250 | Final Cleanup @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-11-16 | 2027-11-17 | 2 | 80 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Baseline | C-01-ES-200 | Lay Concrete & Stone Pavers & Tiles @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-11-18 | 2027-12-17 | 20 | 26 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Baseline | C-01-ES-210 | Building Signage @ Planter - S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-11-18 | 2027-11-24 | 5 | 56 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Baseline | C-01-ES-220 | Fill Soil Mix @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-11-18 | 2027-11-22 | 3 | 33 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Baseline | C-01-ES-230 | Sod & Plant Trees & Shrubs @ Planters - E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-11-23 | 2027-12-08 | 10 | 33 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Baseline | C-01-ES-240 | Install Signage @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-11-29 | 2027-12-02 | 4 | 56 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Baseline | C-01-ES-250 | Plant Trees & Landscaping @ SW 2nd Ave - West Site | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-12-20 | 2028-01-11 | 15 | 26 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Baseline | C-01-ES-260 | Asphalt Pavement @ SW 11th St & 2nd Ave | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2028-01-12 | 2028-01-14 | 3 | 30 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Baseline | C-01-ES-270 | Install Irrigation Spray Sprinkler & Controls @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2028-01-12 | 2028-01-14 | 3 | 26 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Baseline | C-01-ES-280 | Install Tree Grates @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2028-01-17 | 2028-01-18 | 2 | 26 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Baseline | C-01-ES-290 | Install Tree Up-Lighting @ SW 2nd Ave - West Site | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2028-01-19 | 2028-01-20 | 2 | 26 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Baseline | C-01-ES-300 | Apply Pavement Markings @ SW 11th St & 2nd Ave | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2028-01-21 | 2028-01-24 | 2 | 26 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Baseline | C-02-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-05-21 | 2026-05-27 | 4 | 0 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-02-MP-MP-100 | Prep Room (MEP Rough & Finishes) to Receive Elect Panels & Eqp @ Main Elect/MDF #235 - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > MEP Eqp at MEP Rooms at 2nd Lvl > Main Electrical & MDF Room #235 at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-16 | 2026-11-12 | 20 | 51 | Interior MEPs & Finishes | Main Electrical & MDF Room #235
Baseline | C-02-MP-MP-200 | Prep Room (MEP Rough & Finishes) to Receive Gen Eqp @ Generator #234 - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > MEP Eqp at MEP Rooms at 2nd Lvl > Generator Room #234 at 2nd Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-12-14 | 20 | 207 | Interior MEPs & Finishes | Generator Room #234
Baseline | C-02-MP-MP-210 | F/R/P Generator Pad @ Generator #234 - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > MEP Eqp at MEP Rooms at 2nd Lvl > Generator Room #234 at 2nd Lvl | TT_Task | TK_NotStart | 2026-12-15 | 2026-12-16 | 2 | 207 | Interior MEPs & Finishes | Generator Room #234
Baseline | C-02-MP-MP-220 | Setup Generator & Sub-Base Tank @ Generator #234 - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > MEP Eqp at MEP Rooms at 2nd Lvl > Generator Room #234 at 2nd Lvl | TT_Task | TK_NotStart | 2026-12-17 | 2026-12-23 | 5 | 207 | Interior MEPs & Finishes | Generator Room #234
Baseline | C-02-MP-MP-230 | Close CMU Wall Opening @ Generator #234 - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > MEP Eqp at MEP Rooms at 2nd Lvl > Generator Room #234 at 2nd Lvl | TT_Task | TK_NotStart | 2026-12-24 | 2026-12-29 | 3 | 207 | Interior MEPs & Finishes | Generator Room #234
Baseline | C-02-MP-MP-240 | Install Mech Exhaust Fan (GEF) @ Generator #234 - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > MEP Eqp at MEP Rooms at 2nd Lvl > Generator Room #234 at 2nd Lvl | TT_Task | TK_NotStart | 2026-12-30 | 2026-12-31 | 2 | 233 | Interior MEPs & Finishes | Generator Room #234
Baseline | C-02-PG-MP-100 | Install Plumbing Rough @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > MEP Rough at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2027-01-05 | 2027-01-18 | 10 | 49 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-02-PG-MP-110 | Install Fire Protection Rough @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > MEP Rough at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-25 | 10 | 76 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-02-PG-MP-120 | Install Plumbing Floor Drains @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > MEP Rough at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2027-01-15 | 2027-01-21 | 5 | 86 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-02-PG-MP-130 | Install Electrical Rough @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > MEP Rough at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2027-01-19 | 2027-02-01 | 10 | 76 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-02-MP-MP-110 | Install Electrical Switchgear & Boards & Panels @ Main Elect/MDF #235 - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > MEP Eqp at MEP Rooms at 2nd Lvl > Main Electrical & MDF Room #235 at 2nd Lvl | TT_Task | TK_NotStart | 2027-01-28 | 2027-03-24 | 40 | 1 | Interior MEPs & Finishes | Main Electrical & MDF Room #235
Baseline | C-02-PG-MP-140 | Install FA & Low Voltage Rough @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > MEP Rough at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2027-01-28 | 2027-02-04 | 6 | 76 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-02-PG-MP-200 | Install Mech Condensing Units @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > MEP Eqp & Trim at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-04 | 3 | 106 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-02-PG-MP-150 | Inspect MEP Rough @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > MEP Rough at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-08 | 2 | 76 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-02-PG-FN-110 | Paint @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > Interior Finishes at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-16 | 6 | 76 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-02-PG-FN-120 | Install Column Protection & Pipe Guards @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > Interior Finishes at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2027-02-17 | 2027-02-23 | 5 | 83 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-02-PG-FN-130 | Install Fire Extinguisher Cabinet (FEC) @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > Interior Finishes at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2027-02-17 | 2027-02-17 | 1 | 87 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-02-PG-FN-140 | Install Parking Stacker Lifts @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > Interior Finishes at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2027-02-17 | 2027-03-04 | 12 | 76 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-02-RF-100 | Install Roof Drain Base @ North Roof (CL 2-5/D-E) - L3 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at North Side at (CL 1-2/D-E) - 2nd Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-02-25 | 1 | 46 | Exterior Envelope | Roofing at North Side at (CL 1-2/D-E)
Baseline | C-02-RF-110 | Tapered Insulation @ North Roof (CL 1-2/D-E) - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at North Side at (CL 1-2/D-E) - 2nd Lvl | TT_Task | TK_NotStart | 2027-02-26 | 2027-02-26 | 1 | 46 | Exterior Envelope | Roofing at North Side at (CL 1-2/D-E)
Baseline | C-02-RF-120 | Apply Roofing Membrane & Flashing @ North Roof (CL 1-2/D-E) - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at North Side at (CL 1-2/D-E) - 2nd Lvl | TT_Task | TK_NotStart | 2027-03-01 | 2027-03-03 | 3 | 46 | Exterior Envelope | Roofing at North Side at (CL 1-2/D-E)
Baseline | C-02-RF-130 | Install Overflow Scupper @ North Roof (CL 1-2/D-E) - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at North Side at (CL 1-2/D-E) - 2nd Lvl | TT_Task | TK_NotStart | 2027-03-04 | 2027-03-04 | 1 | 46 | Exterior Envelope | Roofing at North Side at (CL 1-2/D-E)
Baseline | C-02-PG-FN-150 | Apply Waterproofing/ Seal Concrete @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > Interior Finishes at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2027-03-05 | 2027-03-09 | 3 | 76 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-02-RF-210 | Tapered Insulation @ North Roof (CL 7-8/F-G) - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at North Side at (CL 7-8/F-G) - 2nd Lvl | TT_Task | TK_NotStart | 2027-03-05 | 2027-03-05 | 1 | 46 | Exterior Envelope | Roofing at North Side at (CL 7-8/F-G)
Baseline | C-02-RF-220 | Apply Roofing Membrane & Flashing @ North Roof (CL 7-8/F-G) - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at North Side at (CL 7-8/F-G) - 2nd Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-10 | 3 | 46 | Exterior Envelope | Roofing at North Side at (CL 7-8/F-G)
Baseline | C-02-PG-FN-160 | Install Wheel Stops @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > Interior Finishes at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2027-03-10 | 2027-03-16 | 5 | 76 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-02-RF-230 | Install Overflow Scuppers @ North Roof (CL 7-8/F-G) - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at North Side at (CL 7-8/F-G) - 2nd Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-11 | 1 | 46 | Exterior Envelope | Roofing at North Side at (CL 7-8/F-G)
Baseline | C-02-PG-FN-170 | Apply Pavement Markings @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > Interior Finishes at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-18 | 2 | 76 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-02-PG-FN-180 | Install Signage @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > Interior Finishes at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2027-03-19 | 2027-03-22 | 2 | 98 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-02-PG-MP-210 | Install Light Fixtures @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > MEP Eqp & Trim at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2027-03-19 | 2027-03-25 | 5 | 76 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-02-MP-MP-250 | Install MEP Connections for Generator @ Generator #234 - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > MEP Eqp at MEP Rooms at 2nd Lvl > Generator Room #234 at 2nd Lvl | TT_Task | TK_NotStart | 2027-03-25 | 2027-05-05 | 30 | 147 | Interior MEPs & Finishes | Generator Room #234
Baseline | C-02-PG-MP-220 | Install Electrical Power Trim @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > MEP Eqp & Trim at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-03-31 | 4 | 76 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-02-PG-MP-230 | Install FP Sprinkler Heads @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > MEP Eqp & Trim at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-05 | 3 | 76 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-02-PG-MP-240 | Install FA & Low Voltage Devices (CCTV-Access Ctrl-PA) @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > MEP Eqp & Trim at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-09 | 4 | 76 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-02-PG-FN-190 | Final Cleanup @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > Interior Finishes at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2027-04-12 | 2027-04-13 | 2 | 84 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-03-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-06-04 | 2026-06-09 | 4 | 1 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-03-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-03 | 2026-08-14 | 10 | 106 | Exterior Envelope | Exterior Balconies
Baseline | C-03-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-17 | 2026-08-21 | 5 | 106 | Exterior Envelope | Exterior Balconies
Baseline | C-03-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-24 | 2026-08-27 | 4 | 106 | Exterior Envelope | Exterior Balconies
Baseline | C-03-EX-230 | Install Balcony Glass Railings @ Balconies - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-28 | 2026-09-04 | 6 | 106 | Exterior Envelope | Exterior Balconies
Baseline | C-03-PG-MP-100 | Install Plumbing Rough @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Rough at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2027-01-19 | 2027-02-01 | 10 | 49 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-03-PG-MP-110 | Install Fire Protection Rough @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Rough at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2027-01-26 | 2027-02-08 | 10 | 67 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-03-PG-MP-120 | Install Plumbing Floor Drains @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Rough at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2027-01-29 | 2027-02-04 | 5 | 77 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-03-PG-MP-130 | Install Electrical Rough @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Rough at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-15 | 10 | 67 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-03-PG-MP-140 | Install FA & Low Voltage Rough @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Rough at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-18 | 6 | 67 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-03-PG-MP-200 | Install Mech Condensing Units @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Eqp & Trim at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-18 | 3 | 95 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-03-PG-MP-150 | Inspect MEP Rough @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Rough at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2027-02-19 | 2027-02-22 | 2 | 67 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-03-PG-FN-110 | Paint @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > Interior Finishes at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-03-02 | 6 | 67 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-03-PG-FN-120 | Install Column Protection & Pipe Guards @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > Interior Finishes at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-09 | 5 | 77 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-03-PG-FN-130 | Install Fire Extinguisher Cabinet (FEC) @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > Interior Finishes at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-03 | 1 | 81 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-03-PG-FN-140 | Install Parking Stacker Lifts @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > Interior Finishes at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-23 | 15 | 67 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-03-PG-MP-250 | Install EV Chargers & Eqp @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Eqp & Trim at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-09 | 5 | 87 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-03-RF-100 | Install Roof Drain Bases @ North Roof (CL 2-5/D-E) - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at North Side at (CL 2-5/D-E) - 3rd Lvl | TT_Task | TK_NotStart | 2027-03-12 | 2027-03-15 | 2 | 46 | Exterior Envelope | Roofing at North Side at (CL 2-5/D-E)
Baseline | C-03-RF-110 | Tapered Insulation @ North Roof (CL 2-5/D-E) - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at North Side at (CL 2-5/D-E) - 3rd Lvl | TT_Task | TK_NotStart | 2027-03-16 | 2027-03-18 | 3 | 46 | Exterior Envelope | Roofing at North Side at (CL 2-5/D-E)
Baseline | C-03-RF-120 | Apply Roofing Membrane & Flashing @ North Roof (CL 2-5/D-E) - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at North Side at (CL 2-5/D-E) - 3rd Lvl | TT_Task | TK_NotStart | 2027-03-19 | 2027-03-29 | 7 | 46 | Exterior Envelope | Roofing at North Side at (CL 2-5/D-E)
Baseline | C-03-PG-FN-150 | Apply Waterproofing/ Seal Concrete @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > Interior Finishes at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-26 | 3 | 67 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-03-PG-FN-160 | Install Wheel Stops @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > Interior Finishes at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2027-03-29 | 2027-04-02 | 5 | 67 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-03-RF-130 | Install Overflow Scuppers @ North Roof (CL 2-5/D-E) - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at North Side at (CL 2-5/D-E) - 3rd Lvl | TT_Task | TK_NotStart | 2027-03-30 | 2027-03-31 | 2 | 46 | Exterior Envelope | Roofing at North Side at (CL 2-5/D-E)
Baseline | C-03-RF-200 | Install Roof Drain Base @ West Roof (CL 7-8/A-B) - L7 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at West Side at (CL 7-8/A-B) - 7th Lvl | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-01 | 1 | 46 | Exterior Envelope | Roofing at West Side at (CL 7-8/A-B)
Baseline | C-03-RF-210 | Tapered Insulation @ West Roof (CL 7-8/A-B) - L7 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at West Side at (CL 7-8/A-B) - 7th Lvl | TT_Task | TK_NotStart | 2027-04-02 | 2027-04-05 | 2 | 46 | Exterior Envelope | Roofing at West Side at (CL 7-8/A-B)
Baseline | C-03-PG-FN-170 | Apply Pavement Markings @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > Interior Finishes at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2027-04-05 | 2027-04-06 | 2 | 67 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-03-RF-220 | Apply Roofing Membrane & Flashing @ West Roof (CL 7-8/A-B) - L7 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at West Side at (CL 7-8/A-B) - 7th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-12 | 5 | 46 | Exterior Envelope | Roofing at West Side at (CL 7-8/A-B)
Baseline | C-03-PG-FN-180 | Install Signage @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > Interior Finishes at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2027-04-07 | 2027-04-08 | 2 | 87 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-03-PG-MP-210 | Install Light Fixtures @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Eqp & Trim at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2027-04-07 | 2027-04-13 | 5 | 67 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-03-RF-230 | Install Overflow Scuppers @ West Roof (CL 7-8/A-B) - L7 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at West Side at (CL 7-8/A-B) - 7th Lvl | TT_Task | TK_NotStart | 2027-04-13 | 2027-04-13 | 1 | 46 | Exterior Envelope | Roofing at West Side at (CL 7-8/A-B)
Baseline | C-03-PG-MP-220 | Install Electrical Power Trim @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Eqp & Trim at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2027-04-14 | 2027-04-19 | 4 | 67 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-03-PG-MP-230 | Install FP Sprinkler Heads @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Eqp & Trim at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2027-04-20 | 2027-04-22 | 3 | 67 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-03-PG-MP-240 | Install FA & Low Voltage Devices (CCTV-Access Ctrl-PA) @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Eqp & Trim at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2027-04-23 | 2027-04-28 | 4 | 67 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-03-PG-FN-190 | Final Cleanup @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > Interior Finishes at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2027-04-29 | 2027-04-30 | 2 | 73 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-04-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-06-17 | 2026-06-22 | 4 | 2 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-04-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 4th Lvl | TT_Task | TK_NotStart | 2026-08-17 | 2026-08-28 | 10 | 101 | Exterior Envelope | Exterior Balconies
Baseline | C-04-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 4th Lvl | TT_Task | TK_NotStart | 2026-08-31 | 2026-09-04 | 5 | 101 | Exterior Envelope | Exterior Balconies
Baseline | C-04-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 4th Lvl | TT_Task | TK_NotStart | 2026-09-08 | 2026-09-14 | 5 | 101 | Exterior Envelope | Exterior Balconies
Baseline | C-04-EX-230 | Install Balcony Glass Railings @ Balconies - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 4th Lvl | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-22 | 6 | 101 | Exterior Envelope | Exterior Balconies
Baseline | C-04-PG-MP-100 | Install Plumbing Rough @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > MEP Rough at Parking at 4th Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-15 | 10 | 49 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-04-PG-MP-110 | Install Fire Protection Rough @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > MEP Rough at Parking at 4th Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-22 | 10 | 61 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-04-PG-MP-120 | Install Plumbing Floor Drains @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > MEP Rough at Parking at 4th Lvl | TT_Task | TK_NotStart | 2027-02-12 | 2027-02-18 | 5 | 71 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-04-PG-MP-130 | Install Electrical Rough @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > MEP Rough at Parking at 4th Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-03-01 | 10 | 61 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-04-PG-MP-140 | Install FA & Low Voltage Rough @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > MEP Rough at Parking at 4th Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-03-04 | 6 | 61 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-04-PG-MP-200 | Install Mech Condensing Units @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > MEP Eqp & Trim at Parking at 4th Lvl | TT_Task | TK_NotStart | 2027-03-02 | 2027-03-04 | 3 | 114 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-04-PG-MP-150 | Inspect MEP Rough @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > MEP Rough at Parking at 4th Lvl | TT_Task | TK_NotStart | 2027-03-05 | 2027-03-08 | 2 | 61 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-04-PG-FN-110 | Paint @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > Interior Finishes at Parking at 4th Lvl | TT_Task | TK_NotStart | 2027-03-09 | 2027-03-16 | 6 | 61 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-04-PG-FN-120 | Install Column Protection & Pipe Guards @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > Interior Finishes at Parking at 4th Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-23 | 5 | 71 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-04-PG-FN-130 | Install Fire Extinguisher Cabinet (FEC) @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > Interior Finishes at Parking at 4th Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-17 | 1 | 75 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-04-PG-FN-140 | Install Parking Stacker Lifts @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > Interior Finishes at Parking at 4th Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-04-06 | 15 | 61 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-04-PG-FN-150 | Apply Waterproofing/ Seal Concrete @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > Interior Finishes at Parking at 4th Lvl | TT_Task | TK_NotStart | 2027-04-07 | 2027-04-09 | 3 | 61 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-04-PG-FN-160 | Install Wheel Stops @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > Interior Finishes at Parking at 4th Lvl | TT_Task | TK_NotStart | 2027-04-12 | 2027-04-16 | 5 | 61 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-04-PG-FN-170 | Apply Pavement Markings @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > Interior Finishes at Parking at 4th Lvl | TT_Task | TK_NotStart | 2027-04-19 | 2027-04-20 | 2 | 61 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-04-PG-FN-180 | Install Signage @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > Interior Finishes at Parking at 4th Lvl | TT_Task | TK_NotStart | 2027-04-21 | 2027-04-22 | 2 | 79 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-04-PG-MP-210 | Install Light Fixtures @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > MEP Eqp & Trim at Parking at 4th Lvl | TT_Task | TK_NotStart | 2027-04-21 | 2027-04-27 | 5 | 61 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-04-PG-MP-220 | Install Electrical Power Trim @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > MEP Eqp & Trim at Parking at 4th Lvl | TT_Task | TK_NotStart | 2027-04-28 | 2027-05-03 | 4 | 61 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-04-PG-MP-230 | Install FP Sprinkler Heads @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > MEP Eqp & Trim at Parking at 4th Lvl | TT_Task | TK_NotStart | 2027-05-04 | 2027-05-06 | 3 | 61 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-04-PG-FN-190 | Final Cleanup @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > Interior Finishes at Parking at 4th Lvl | TT_Task | TK_NotStart | 2027-05-13 | 2027-05-14 | 2 | 65 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-05-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-06-26 | 2026-07-01 | 4 | 5 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-05-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 5th Lvl | TT_Task | TK_NotStart | 2026-08-31 | 2026-09-14 | 10 | 98 | Exterior Envelope | Exterior Balconies
Baseline | C-05-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 5th Lvl | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-21 | 5 | 98 | Exterior Envelope | Exterior Balconies
Baseline | C-05-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 5th Lvl | TT_Task | TK_NotStart | 2026-09-22 | 2026-09-25 | 4 | 98 | Exterior Envelope | Exterior Balconies
Baseline | C-05-EX-230 | Install Balcony Glass Railings @ Balconies - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 5th Lvl | TT_Task | TK_NotStart | 2026-09-28 | 2026-10-05 | 6 | 98 | Exterior Envelope | Exterior Balconies
Baseline | C-05-PG-MP-100 | Install Plumbing Rough @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > MEP Rough at Parking at 5th Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-03-01 | 10 | 49 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-05-PG-MP-110 | Install Fire Protection Rough @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > MEP Rough at Parking at 5th Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-03-08 | 10 | 55 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-05-PG-MP-120 | Install Plumbing Floor Drains @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > MEP Rough at Parking at 5th Lvl | TT_Task | TK_NotStart | 2027-02-26 | 2027-03-04 | 5 | 65 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-05-PG-MP-130 | Install Electrical Rough @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > MEP Rough at Parking at 5th Lvl | TT_Task | TK_NotStart | 2027-03-02 | 2027-03-15 | 10 | 55 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-05-PG-MP-140 | Install FA & Low Voltage Rough @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > MEP Rough at Parking at 5th Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-18 | 6 | 55 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-05-PG-MP-200 | Install Mech Condensing Units @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > MEP Eqp & Trim at Parking at 5th Lvl | TT_Task | TK_NotStart | 2027-03-16 | 2027-03-18 | 3 | 88 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-05-PG-MP-150 | Inspect MEP Rough @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > MEP Rough at Parking at 5th Lvl | TT_Task | TK_NotStart | 2027-03-19 | 2027-03-22 | 2 | 55 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-05-PG-FN-110 | Paint @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > Interior Finishes at Parking at 5th Lvl | TT_Task | TK_NotStart | 2027-03-23 | 2027-03-30 | 6 | 55 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-05-PG-FN-120 | Install Column Protection & Pipe Guards @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > Interior Finishes at Parking at 5th Lvl | TT_Task | TK_NotStart | 2027-03-31 | 2027-04-06 | 5 | 65 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-05-PG-FN-130 | Install Fire Extinguisher Cabinet (FEC) @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > Interior Finishes at Parking at 5th Lvl | TT_Task | TK_NotStart | 2027-03-31 | 2027-03-31 | 1 | 69 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-05-PG-FN-140 | Install Parking Stacker Lifts @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > Interior Finishes at Parking at 5th Lvl | TT_Task | TK_NotStart | 2027-03-31 | 2027-04-20 | 15 | 55 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-05-PG-FN-150 | Apply Waterproofing/ Seal Concrete @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > Interior Finishes at Parking at 5th Lvl | TT_Task | TK_NotStart | 2027-04-21 | 2027-04-23 | 3 | 55 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-05-PG-FN-160 | Install Wheel Stops @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > Interior Finishes at Parking at 5th Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-04-30 | 5 | 55 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-05-PG-FN-170 | Apply Pavement Markings @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > Interior Finishes at Parking at 5th Lvl | TT_Task | TK_NotStart | 2027-05-03 | 2027-05-04 | 2 | 55 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-05-PG-FN-180 | Install Signage @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > Interior Finishes at Parking at 5th Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-06 | 2 | 71 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-05-PG-MP-210 | Install Light Fixtures @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > MEP Eqp & Trim at Parking at 5th Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-11 | 5 | 55 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-05-PG-MP-240 | Install FA & Low Voltage Devices (CCTV-Access Ctrl-PA) @ Parking - L4 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > MEP Eqp & Trim at Parking at 4th Lvl | TT_Task | TK_NotStart | 2027-05-07 | 2027-05-12 | 4 | 61 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-05-PG-MP-220 | Install Electrical Power Trim @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > MEP Eqp & Trim at Parking at 5th Lvl | TT_Task | TK_NotStart | 2027-05-12 | 2027-05-17 | 4 | 55 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-05-PG-MP-230 | Install FP Sprinkler Heads @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > MEP Eqp & Trim at Parking at 5th Lvl | TT_Task | TK_NotStart | 2027-05-18 | 2027-05-20 | 3 | 55 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-05-PG-MP-250 | Install FA & Low Voltage Devices (CCTV-Access Ctrl-PA) @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > MEP Eqp & Trim at Parking at 5th Lvl | TT_Task | TK_NotStart | 2027-05-21 | 2027-05-26 | 4 | 55 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-05-PG-FN-190 | Final Cleanup @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > Interior Finishes at Parking at 5th Lvl | TT_Task | TK_NotStart | 2027-05-27 | 2027-05-28 | 2 | 57 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-06-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-07-08 | 2026-07-13 | 4 | 8 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-06-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 6th Lvl | TT_Task | TK_NotStart | 2026-09-10 | 2026-09-23 | 10 | 97 | Exterior Envelope | Exterior Balconies
Baseline | C-06-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 6th Lvl | TT_Task | TK_NotStart | 2026-09-24 | 2026-09-30 | 5 | 97 | Exterior Envelope | Exterior Balconies
Baseline | C-06-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 6th Lvl | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-06 | 4 | 97 | Exterior Envelope | Exterior Balconies
Baseline | C-06-EX-230 | Install Balcony Glass Railings @ Balconies - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 6th Lvl | TT_Task | TK_NotStart | 2026-10-07 | 2026-10-14 | 6 | 97 | Exterior Envelope | Exterior Balconies
Baseline | C-06-PG-MP-100 | Install Plumbing Rough @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > MEP Rough at Parking at 6th Lvl | TT_Task | TK_NotStart | 2027-03-02 | 2027-03-15 | 10 | 49 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-06-PG-MP-110 | Install Fire Protection Rough @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > MEP Rough at Parking at 6th Lvl | TT_Task | TK_NotStart | 2027-03-09 | 2027-03-22 | 10 | 49 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-06-PG-MP-120 | Install Plumbing Floor Drains (FDs & SDs & GDs) @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > MEP Rough at Parking at 6th Lvl | TT_Task | TK_NotStart | 2027-03-12 | 2027-03-18 | 5 | 59 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-06-PG-MP-130 | Install Electrical Rough @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > MEP Rough at Parking at 6th Lvl | TT_Task | TK_NotStart | 2027-03-16 | 2027-03-29 | 10 | 49 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-06-PG-MP-140 | Install FA & Low Voltage Rough @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > MEP Rough at Parking at 6th Lvl | TT_Task | TK_NotStart | 2027-03-25 | 2027-04-01 | 6 | 49 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-06-PG-MP-200 | Install Mech Condensing Units @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > MEP Eqp & Trim at Parking at 6th Lvl | TT_Task | TK_NotStart | 2027-03-30 | 2027-04-01 | 3 | 62 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-06-PG-MP-150 | Inspect MEP Rough @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > MEP Rough at Parking at 6th Lvl | TT_Task | TK_NotStart | 2027-04-02 | 2027-04-05 | 2 | 49 | Interior MEPs & Finishes | MEP Rough at Parking
Baseline | C-06-PG-FN-110 | Paint @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > Interior Finishes at Parking at 6th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-13 | 6 | 49 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-06-PG-MP-190 | Install Fire Pump & Eqp @ Hi Zone Fire Pump Rm #625 - Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > MEP Eqp & Trim at Parking at 6th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-05-03 | 20 | 60 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-06-PG-FN-120 | Install Column Protection & Pipe Guards @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > Interior Finishes at Parking at 6th Lvl | TT_Task | TK_NotStart | 2027-04-14 | 2027-04-20 | 5 | 59 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-06-PG-FN-130 | Install Fire Extinguisher Cabinet (FEC) @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > Interior Finishes at Parking at 6th Lvl | TT_Task | TK_NotStart | 2027-04-14 | 2027-04-14 | 1 | 63 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-06-PG-FN-140 | Install Parking Stacker Lifts @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > Interior Finishes at Parking at 6th Lvl | TT_Task | TK_NotStart | 2027-04-14 | 2027-05-04 | 15 | 49 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-06-PG-FN-150 | Apply Waterproofing/ Seal Concrete @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > Interior Finishes at Parking at 6th Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-07 | 3 | 49 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-06-PG-FN-160 | Install Wheel Stops @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > Interior Finishes at Parking at 6th Lvl | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-14 | 5 | 49 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-06-PG-FN-170 | Apply Pavement Markings @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > Interior Finishes at Parking at 6th Lvl | TT_Task | TK_NotStart | 2027-05-17 | 2027-05-18 | 2 | 49 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-06-PG-FN-180 | Install Signage @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > Interior Finishes at Parking at 6th Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-05-20 | 2 | 63 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-06-PG-MP-210 | Install Light Fixtures @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > MEP Eqp & Trim at Parking at 6th Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-05-25 | 5 | 49 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-06-PG-MP-220 | Install Electrical Power Trim @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > MEP Eqp & Trim at Parking at 6th Lvl | TT_Task | TK_NotStart | 2027-05-26 | 2027-06-01 | 4 | 49 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-06-PG-MP-230 | Install FP Sprinkler Heads @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > MEP Eqp & Trim at Parking at 6th Lvl | TT_Task | TK_NotStart | 2027-06-02 | 2027-06-04 | 3 | 49 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-06-PG-MP-240 | Install FA & Low Voltage Devices (CCTV-Access Ctrl-PA) @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > MEP Eqp & Trim at Parking at 6th Lvl | TT_Task | TK_NotStart | 2027-06-07 | 2027-06-10 | 4 | 49 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Baseline | C-06-PG-FN-190 | Final Cleanup @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > Interior Finishes at Parking at 6th Lvl | TT_Task | TK_NotStart | 2027-06-11 | 2027-06-14 | 2 | 49 | Interior MEPs & Finishes | Interior Finishes at Parking
Baseline | C-07-ST-200 | F/R/P Planter Walls @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 7th Lvl | TT_Task | TK_NotStart | 2026-06-09 | 2026-07-07 | 20 | 299 | Building Structure | Structure
Baseline | C-07-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-07-17 | 2026-07-22 | 4 | 11 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-07-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 7th Lvl | TT_Task | TK_NotStart | 2026-09-22 | 2026-10-05 | 10 | 95 | Exterior Envelope | Exterior Balconies
Baseline | C-07-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 7th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-12 | 5 | 95 | Exterior Envelope | Exterior Balconies
Baseline | C-07-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 7th Lvl | TT_Task | TK_NotStart | 2026-10-13 | 2026-10-16 | 4 | 95 | Exterior Envelope | Exterior Balconies
Baseline | C-07-EX-230 | Install Balcony Glass Railings @ Balconies - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 7th Lvl | TT_Task | TK_NotStart | 2026-10-19 | 2026-10-26 | 6 | 95 | Exterior Envelope | Exterior Balconies
Baseline | C-07-RD-100 | Install Pluming Rough @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > MEP Rough at Outdoors at th Lvl | TT_Task | TK_NotStart | 2027-05-20 | 2027-05-28 | 7 | 62 | Exterior Envelope | MEP Rough at Outdoors at th Lvl
Baseline | C-07-RD-110 | Install Electrical & LV Rough @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > MEP Rough at Outdoors at th Lvl | TT_Task | TK_NotStart | 2027-06-01 | 2027-06-10 | 8 | 62 | Exterior Envelope | MEP Rough at Outdoors at th Lvl
Baseline | C-07-RD-200 | Install Exercise Unit Structural Base @ Fitness Area - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Roofing & Planter Walls at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-06-11 | 2027-06-11 | 1 | 62 | Exterior Envelope | Roofing & Planter Walls at Roof Deck
Baseline | C-07-RD-220 | Install Roof Drain Bases @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Roofing & Planter Walls at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-06-14 | 2027-06-18 | 5 | 62 | Exterior Envelope | Roofing & Planter Walls at Roof Deck
Baseline | C-07-RD-230 | F/R/P Topping Slabs @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Roofing & Planter Walls at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-06-21 | 2027-07-02 | 10 | 62 | Exterior Envelope | Roofing & Planter Walls at Roof Deck
Baseline | C-07-RD-240 | Apply Fluid Membrane @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Roofing & Planter Walls at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-07-06 | 2027-07-14 | 7 | 62 | Exterior Envelope | Roofing & Planter Walls at Roof Deck
Baseline | C-07-RD-250 | Install Drain Mats @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Roofing & Planter Walls at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-21 | 5 | 62 | Exterior Envelope | Roofing & Planter Walls at Roof Deck
Baseline | C-07-RD-300 | Install Stone Tile Flooring @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Finishes & Flooring at Roof Deck 7th Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-08-11 | 15 | 62 | Exterior Envelope | Finishes & Flooring at Roof Deck
Baseline | C-07-RD-400 | Install Drainage @ Planters - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Planters at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-08-12 | 2027-08-25 | 10 | 62 | Exterior Envelope | Planters at Roof Deck
Baseline | C-07-RD-410 | Apply Waterproofing Membrane @ Planters - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Planters at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-08-26 | 2027-09-03 | 7 | 62 | Exterior Envelope | Planters at Roof Deck
Baseline | C-07-RD-420 | Install Electrical Rough @ Planters - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Planters at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-09-07 | 2027-09-13 | 5 | 75 | Exterior Envelope | Planters at Roof Deck
Baseline | C-07-RD-430 | Install Irrigation & Prping & Valves @ Planters - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Planters at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-09-07 | 2027-09-16 | 8 | 62 | Exterior Envelope | Planters at Roof Deck
Baseline | C-07-RD-440 | Apply Stucco @ Planters - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Planters at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-09-17 | 2027-09-23 | 5 | 62 | Exterior Envelope | Planters at Roof Deck
Baseline | C-07-RD-450 | Paint Stucco @ Planters - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Planters at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-09-24 | 2027-09-30 | 5 | 62 | Exterior Envelope | Planters at Roof Deck
Baseline | C-07-RD-370 | Install Perimeter Railing @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Finishes & Flooring at Roof Deck 7th Lvl | TT_Task | TK_NotStart | 2027-10-01 | 2027-10-14 | 10 | 91 | Exterior Envelope | Finishes & Flooring at Roof Deck
Baseline | C-07-RD-460 | Fill Soil Mix @ Planters - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Planters at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-10-01 | 2027-10-07 | 5 | 62 | Exterior Envelope | Planters at Roof Deck
Baseline | C-07-RD-470 | Plant Trees & Shrubs @ Planters - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Planters at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-10-08 | 2027-10-28 | 15 | 62 | Exterior Envelope | Planters at Roof Deck
Baseline | C-07-RD-310 | Install Pergola with Angled Louvers @ Treatment Area - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Finishes & Flooring at Roof Deck 7th Lvl | TT_Task | TK_NotStart | 2027-10-29 | 2027-11-04 | 5 | 62 | Exterior Envelope | Finishes & Flooring at Roof Deck
Baseline | C-07-RD-480 | Install Irrigation Trim @ Planters - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Planters at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-10-29 | 2027-11-01 | 2 | 76 | Exterior Envelope | Planters at Roof Deck
Baseline | C-07-RD-490 | Install Lighting @ Planters - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Planters at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-11-02 | 2027-11-04 | 3 | 76 | Exterior Envelope | Planters at Roof Deck
Baseline | C-07-RD-320 | Install Wood Decking @ Yoga - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Finishes & Flooring at Roof Deck 7th Lvl | TT_Task | TK_NotStart | 2027-11-05 | 2027-11-16 | 8 | 62 | Exterior Envelope | Finishes & Flooring at Roof Deck
Baseline | C-07-RD-330 | Install Privacy Screen @ Treatment Area - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Finishes & Flooring at Roof Deck 7th Lvl | TT_Task | TK_NotStart | 2027-11-05 | 2027-11-08 | 2 | 74 | Exterior Envelope | Finishes & Flooring at Roof Deck
Baseline | C-07-RD-340 | Pour-in-Place Rubber Flooring @ Fitness Area - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Finishes & Flooring at Roof Deck 7th Lvl | TT_Task | TK_NotStart | 2027-11-17 | 2027-11-18 | 2 | 62 | Exterior Envelope | Finishes & Flooring at Roof Deck
Baseline | C-07-RD-350 | Install Exercise Unit @ Fitness Area - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Finishes & Flooring at Roof Deck 7th Lvl | TT_Task | TK_NotStart | 2027-11-19 | 2027-11-19 | 1 | 65 | Exterior Envelope | Finishes & Flooring at Roof Deck
Baseline | C-07-RD-360 | Install Synthetic Turf @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Finishes & Flooring at Roof Deck 7th Lvl | TT_Task | TK_NotStart | 2027-11-19 | 2027-11-23 | 3 | 62 | Exterior Envelope | Finishes & Flooring at Roof Deck
Baseline | C-07-RD-260 | Install Roof Drain Strainers @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Roofing & Planter Walls at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-11-24 | 2027-11-24 | 1 | 62 | Exterior Envelope | Roofing & Planter Walls at Roof Deck
Baseline | C-07-RD-380 | Install FF&Es @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Finishes & Flooring at Roof Deck 7th Lvl | TT_Task | TK_NotStart | 2027-11-29 | 2027-12-01 | 3 | 62 | Exterior Envelope | Finishes & Flooring at Roof Deck
Baseline | C-08-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L8 | no |  | 8 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-07-28 | 2026-07-30 | 3 | 18 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-08-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L8 | no |  | 8 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 8th Lvl | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-16 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-08-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L8 | no |  | 8 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 8th Lvl | TT_Task | TK_NotStart | 2026-10-19 | 2026-10-23 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-08-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L8 | no |  | 8 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 8th Lvl | TT_Task | TK_NotStart | 2026-10-26 | 2026-10-30 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-08-EX-230 | Install Balcony Glass Railings @ Balconies - L8 | no |  | 8 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 8th Lvl | TT_Task | TK_NotStart | 2026-11-02 | 2026-11-10 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-09-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L9 | no |  | 9 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-08-07 | 2026-08-11 | 3 | 17 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-09-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L9 | no |  | 9 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 9th Lvl | TT_Task | TK_NotStart | 2026-10-12 | 2026-10-27 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-09-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L9 | no |  | 9 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 9th Lvl | TT_Task | TK_NotStart | 2026-10-28 | 2026-11-03 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-09-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L9 | no |  | 9 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 9th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-10 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-09-EX-230 | Install Balcony Glass Railings @ Balconies - L9 | no |  | 9 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 9th Lvl | TT_Task | TK_NotStart | 2026-11-11 | 2026-11-19 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-10-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L10 | no |  | 10 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-08-18 | 2026-08-20 | 3 | 17 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-10-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L10 | no |  | 10 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 10th Lvl | TT_Task | TK_NotStart | 2026-10-21 | 2026-11-05 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-10-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L10 | no |  | 10 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 10th Lvl | TT_Task | TK_NotStart | 2026-11-06 | 2026-11-12 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-10-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L10 | no |  | 10 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 10th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-19 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-10-EX-230 | Install Balcony Glass Railings @ Balconies - L10 | no |  | 10 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 10th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-12-02 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-11-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L11 | no |  | 11 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-08-25 | 2026-08-27 | 3 | 19 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-11-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L11 | no |  | 11 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 11th Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-16 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-11-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L11 | no |  | 11 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 11th Lvl | TT_Task | TK_NotStart | 2026-11-17 | 2026-11-23 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-11-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L11 | no |  | 11 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 11th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-12-02 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-11-EX-230 | Install Balcony Glass Railings @ Balconies - L11 | no |  | 11 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 11th Lvl | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-11 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-12-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L12 | no |  | 12 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-09-01 | 2026-09-03 | 3 | 21 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-12-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L12 | no |  | 12 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 12th Lvl | TT_Task | TK_NotStart | 2026-11-10 | 2026-11-25 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-12-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L12 | no |  | 12 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 12th Lvl | TT_Task | TK_NotStart | 2026-11-30 | 2026-12-04 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-12-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L12 | no |  | 12 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 12th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-11 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-12-EX-230 | Install Balcony Glass Railings @ Balconies - L12 | no |  | 12 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 12th Lvl | TT_Task | TK_NotStart | 2026-12-14 | 2026-12-22 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-14-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L14 | no |  | 14 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-09-09 | 2026-09-11 | 3 | 23 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-14-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L14 | no |  | 14 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 14th Lvl | TT_Task | TK_NotStart | 2026-11-19 | 2026-12-08 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-14-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L14 | no |  | 14 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 14th Lvl | TT_Task | TK_NotStart | 2026-12-09 | 2026-12-15 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-14-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L14 | no |  | 14 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 14th Lvl | TT_Task | TK_NotStart | 2026-12-16 | 2026-12-22 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-14-EX-230 | Install Balcony Glass Railings @ Balconies - L14 | no |  | 14 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 14th Lvl | TT_Task | TK_NotStart | 2026-12-23 | 2027-01-04 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-15-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L15 | no |  | 15 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-09-16 | 2026-09-18 | 3 | 25 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-15-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L15 | no |  | 15 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 15th Lvl | TT_Task | TK_NotStart | 2026-12-02 | 2026-12-17 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-15-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L15 | no |  | 15 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 15th Lvl | TT_Task | TK_NotStart | 2026-12-18 | 2026-12-24 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-15-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L15 | no |  | 15 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 15th Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2027-01-04 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-15-EX-230 | Install Balcony Glass Railings @ Balconies - L15 | no |  | 15 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 15th Lvl | TT_Task | TK_NotStart | 2027-01-05 | 2027-01-13 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-16-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L16 | no |  | 16 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-09-23 | 2026-09-25 | 3 | 28 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-16-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L16 | no |  | 16 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 16th Lvl | TT_Task | TK_NotStart | 2026-12-11 | 2026-12-29 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-16-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L16 | no |  | 16 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 16th Lvl | TT_Task | TK_NotStart | 2026-12-30 | 2027-01-06 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-16-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L16 | no |  | 16 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 16th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-13 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-16-EX-230 | Install Balcony Glass Railings @ Balconies - L16 | no |  | 16 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 16th Lvl | TT_Task | TK_NotStart | 2027-01-14 | 2027-01-22 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-17-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L17 | no |  | 17 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-09-30 | 2026-10-02 | 3 | 31 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-17-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L17 | no |  | 17 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 17th Lvl | TT_Task | TK_NotStart | 2026-12-22 | 2027-01-08 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-17-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L17 | no |  | 17 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 17th Lvl | TT_Task | TK_NotStart | 2027-01-11 | 2027-01-15 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-17-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L17 | no |  | 17 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 17th Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-22 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-17-EX-230 | Install Balcony Glass Railings @ Balconies - L17 | no |  | 17 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 17th Lvl | TT_Task | TK_NotStart | 2027-01-25 | 2027-02-02 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-18-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L18 | no |  | 18 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-10-07 | 2026-10-09 | 3 | 34 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-18-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L18 | no |  | 18 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 18th Lvl | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-19 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-18-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L18 | no |  | 18 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 18th Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-01-26 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-18-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L18 | no |  | 18 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 18th Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-02-02 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-18-EX-230 | Install Balcony Glass Railings @ Balconies - L18 | no |  | 18 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 18th Lvl | TT_Task | TK_NotStart | 2027-02-03 | 2027-02-11 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-19-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L19 | no |  | 19 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-10-14 | 2026-10-16 | 3 | 37 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-19-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L19 | no |  | 19 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 19th Lvl | TT_Task | TK_NotStart | 2027-01-13 | 2027-01-28 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-19-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L19 | no |  | 19 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 19th Lvl | TT_Task | TK_NotStart | 2027-01-29 | 2027-02-04 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-19-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L19 | no |  | 19 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 19th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-11 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-19-EX-230 | Install Balcony Glass Railings @ Balconies - L19 | no |  | 19 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 19th Lvl | TT_Task | TK_NotStart | 2027-02-12 | 2027-02-22 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-20-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L20 | no |  | 20 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-10-21 | 2026-10-23 | 3 | 40 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-20-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L20 | no |  | 20 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 20th Lvl | TT_Task | TK_NotStart | 2027-01-22 | 2027-02-08 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-20-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L20 | no |  | 20 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 20th Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-15 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-20-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L20 | no |  | 20 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 20th Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-22 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-20-EX-230 | Install Balcony Glass Railings @ Balconies - L20 | no |  | 20 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 20th Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-03-03 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-21-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L21 | no |  | 21 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-10-28 | 2026-10-30 | 3 | 43 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-21-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L21 | no |  | 21 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 21st Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-17 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-21-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L21 | no |  | 21 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 21st Lvl | TT_Task | TK_NotStart | 2027-02-18 | 2027-02-24 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-21-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L21 | no |  | 21 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 21st Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-03-03 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-21-EX-230 | Install Balcony Glass Railings @ Balconies - L21 | no |  | 21 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 21st Lvl | TT_Task | TK_NotStart | 2027-03-04 | 2027-03-12 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-22-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L22 | no |  | 22 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-06 | 3 | 46 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-22-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L22 | no |  | 22 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 22nd Lvl | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-26 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-22-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L22 | no |  | 22 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-01 | 2027-03-05 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-22-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L22 | no |  | 22 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-12 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-22-EX-230 | Install Balcony Glass Railings @ Balconies - L22 | no |  | 22 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-15 | 2027-03-23 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-23-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L23 | no |  | 23 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-11-11 | 2026-11-13 | 3 | 49 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-23-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L23 | no |  | 23 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 23rd Lvl | TT_Task | TK_NotStart | 2027-02-22 | 2027-03-09 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-23-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L23 | no |  | 23 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-10 | 2027-03-16 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-23-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L23 | no |  | 23 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-23 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-23-EX-230 | Install Balcony Glass Railings @ Balconies - L23 | no |  | 23 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-04-01 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-24-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L24 | no |  | 24 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-11-18 | 2026-11-20 | 3 | 52 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-24-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L24 | no |  | 24 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 24th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-18 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-24-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L24 | no |  | 24 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 24th Lvl | TT_Task | TK_NotStart | 2027-03-19 | 2027-03-25 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-24-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L24 | no |  | 24 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 24th Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-04-01 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-24-EX-230 | Install Balcony Glass Railings @ Balconies - L24 | no |  | 24 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 24th Lvl | TT_Task | TK_NotStart | 2027-04-02 | 2027-04-12 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-25-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L25 | no |  | 25 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-11-25 | 2026-12-01 | 3 | 55 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-25-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L25 | no |  | 25 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 25th Lvl | TT_Task | TK_NotStart | 2027-03-12 | 2027-03-29 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-25-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L25 | no |  | 25 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 25th Lvl | TT_Task | TK_NotStart | 2027-03-30 | 2027-04-05 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-25-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L25 | no |  | 25 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 25th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-12 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-25-EX-230 | Install Balcony Glass Railings @ Balconies - L25 | no |  | 25 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 25th Lvl | TT_Task | TK_NotStart | 2027-04-13 | 2027-04-21 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-26-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L26 | no |  | 26 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-12-04 | 2026-12-08 | 3 | 57 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-26-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L26 | no |  | 26 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 26th Lvl | TT_Task | TK_NotStart | 2027-03-23 | 2027-04-07 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-26-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L26 | no |  | 26 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 26th Lvl | TT_Task | TK_NotStart | 2027-04-08 | 2027-04-14 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-26-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L26 | no |  | 26 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 26th Lvl | TT_Task | TK_NotStart | 2027-04-15 | 2027-04-21 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-26-EX-230 | Install Balcony Glass Railings @ Balconies - L26 | no |  | 26 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 26th Lvl | TT_Task | TK_NotStart | 2027-04-22 | 2027-04-30 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-27-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L27 | no |  | 27 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-12-11 | 2026-12-15 | 3 | 59 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-27-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L27 | no |  | 27 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 27th Lvl | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-16 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-27-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L27 | no |  | 27 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 27th Lvl | TT_Task | TK_NotStart | 2027-04-19 | 2027-04-23 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-27-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L27 | no |  | 27 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 27th Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-04-30 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-27-EX-230 | Install Balcony Glass Railings @ Balconies - L27 | no |  | 27 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 27th Lvl | TT_Task | TK_NotStart | 2027-05-03 | 2027-05-11 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-28-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L28 | no |  | 28 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-12-22 | 2026-12-24 | 3 | 59 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-28-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L28 | no |  | 28 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 28th Lvl | TT_Task | TK_NotStart | 2027-04-12 | 2027-04-27 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-28-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L28 | no |  | 28 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 28th Lvl | TT_Task | TK_NotStart | 2027-04-28 | 2027-05-04 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-28-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L28 | no |  | 28 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 28th Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-11 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-28-EX-230 | Install Balcony Glass Railings @ Balconies - L28 | no |  | 28 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 28th Lvl | TT_Task | TK_NotStart | 2027-05-12 | 2027-05-20 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-29-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L29 | no |  | 29 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2027-01-05 | 2027-01-07 | 3 | 58 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-29-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L29 | no |  | 29 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 29th Lvl | TT_Task | TK_NotStart | 2027-04-21 | 2027-05-06 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-29-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L29 | no |  | 29 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 29th Lvl | TT_Task | TK_NotStart | 2027-05-07 | 2027-05-13 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-29-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L29 | no |  | 29 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 29th Lvl | TT_Task | TK_NotStart | 2027-05-14 | 2027-05-20 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-29-EX-230 | Install Balcony Glass Railings @ Balconies - L29 | no |  | 29 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 29th Lvl | TT_Task | TK_NotStart | 2027-05-21 | 2027-06-01 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-30-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L30 | no |  | 30 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2027-01-14 | 2027-01-18 | 3 | 58 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-30-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L30 | no |  | 30 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 30th Lvl | TT_Task | TK_NotStart | 2027-04-30 | 2027-05-17 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-30-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L30 | no |  | 30 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 30th Lvl | TT_Task | TK_NotStart | 2027-05-18 | 2027-05-24 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-30-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L30 | no |  | 30 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 30th Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-06-01 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-30-EX-230 | Install Balcony Glass Railings @ Balconies - L30 | no |  | 30 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 30th Lvl | TT_Task | TK_NotStart | 2027-06-02 | 2027-06-10 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-31-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L31 | no |  | 31 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2027-01-26 | 2027-01-28 | 3 | 57 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-31-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L31 | no |  | 31 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 31st Lvl | TT_Task | TK_NotStart | 2027-05-11 | 2027-05-26 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-31-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L31 | no |  | 31 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 31st Lvl | TT_Task | TK_NotStart | 2027-05-27 | 2027-06-03 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-31-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L31 | no |  | 31 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 31st Lvl | TT_Task | TK_NotStart | 2027-06-04 | 2027-06-10 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-31-EX-230 | Install Balcony Glass Railings @ Balconies - L31 | no |  | 31 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 31st Lvl | TT_Task | TK_NotStart | 2027-06-11 | 2027-06-21 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-32-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L32 | no |  | 32 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2027-02-08 | 2027-02-10 | 3 | 55 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-32-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L32 | no |  | 32 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 32nd Lvl | TT_Task | TK_NotStart | 2027-05-20 | 2027-06-07 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-32-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L32 | no |  | 32 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-08 | 2027-06-14 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-32-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L32 | no |  | 32 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-15 | 2027-06-21 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-32-EX-230 | Install Balcony Glass Railings @ Balconies - L32 | no |  | 32 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-22 | 2027-06-30 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-33-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L33 | no |  | 33 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-15 | 3 | 59 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-33-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L33 | no |  | 33 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 33rd Lvl | TT_Task | TK_NotStart | 2027-06-01 | 2027-06-16 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-33-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L33 | no |  | 33 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 33rd Lvl | TT_Task | TK_NotStart | 2027-06-17 | 2027-06-23 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-33-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L33 | no |  | 33 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 33rd Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-30 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-33-EX-230 | Install Balcony Glass Railings @ Balconies - L33 | no |  | 33 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-12 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-34-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L34 | no |  | 34 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2027-02-23 | 2027-02-25 | 3 | 58 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-34-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L34 | no |  | 34 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 34th Lvl | TT_Task | TK_NotStart | 2027-06-10 | 2027-06-25 | 12 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-34-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L34 | no |  | 34 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 34th Lvl | TT_Task | TK_NotStart | 2027-06-28 | 2027-07-02 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-34-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L34 | no |  | 34 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 34th Lvl | TT_Task | TK_NotStart | 2027-07-06 | 2027-07-12 | 5 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-34-EX-230 | Install Balcony Glass Railings @ Balconies - L34 | no |  | 34 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 34th Lvl | TT_Task | TK_NotStart | 2027-07-13 | 2027-07-21 | 7 | 91 | Exterior Envelope | Exterior Balconies
Baseline | C-35-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L35 | no |  | 35 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2027-03-04 | 2027-03-08 | 3 | 58 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-35-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies - L35 | no |  | 35 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 35th Lvl | TT_Task | TK_NotStart | 2027-06-21 | 2027-07-07 | 12 | 84 | Exterior Envelope | Exterior Balconies
Baseline | C-35-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L35 | no |  | 35 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 35th Lvl | TT_Task | TK_NotStart | 2027-07-08 | 2027-07-14 | 5 | 84 | Exterior Envelope | Exterior Balconies
Baseline | C-35-EX-220 | Paint Stucco Walls & Ceilings @ Balconies - L35 | no |  | 35 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 35th Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-21 | 5 | 84 | Exterior Envelope | Exterior Balconies
Baseline | C-35-EX-230 | Install Balcony Glass Railings @ Balconies - L35 | no |  | 35 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies > Exterior Balconies at 35th Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-07-30 | 7 | 84 | Exterior Envelope | Exterior Balconies
Baseline | C-36-MP-160 | Install MEP Inserts & Sleeves at Elevated Slab @ 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-09 | 3 | 14 | Building Structure | Structure at Lower
Baseline | C-36-MP-500 | Prep Pad & Set Mech DOUA-1 Unit @ Mech Eqp Rm #3611 - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Mech Eqp Rm #3611 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-02-15 | 2027-02-17 | 3 | 14 | Exterior Envelope | MEP Work at Mech Eqp Rm #3611
Baseline | C-36-ST-200 | Lay Parapet Walls @ 36th Pool Level | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-03-02 | 2027-03-10 | 7 | 55 | Building Structure | Structure at Lower
Baseline | C-36-ST-210 | F/R/P Planter Walls @ 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-31 | 15 | 55 | Building Structure | Structure at Lower
Baseline | C-36-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2027-03-16 | 2027-03-17 | 2 | 90 | Building Structure | Shoring Removals & Slab Preparation
Baseline | C-36-MP-510 | Prep Room & Housekeeping Pads to Receive Eqp @ Mech Eqp Rm #3611 - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Mech Eqp Rm #3611 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-03-25 | 2027-04-07 | 10 | 90 | Exterior Envelope | MEP Work at Mech Eqp Rm #3611
Baseline | C-36-MP-520 | Install Stands/ & Supports for Mech Eqp & Piping @ Mech Eqp Rm #3611 - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Mech Eqp Rm #3611 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-04-08 | 2027-04-14 | 5 | 90 | Exterior Envelope | MEP Work at Mech Eqp Rm #3611
Baseline | C-36-MP-530 | Set Mech CWP-1 & CWP-2 & CTP-1 & CTP-2 & EFs Eqp @ Mech Eqp Rm #3611 - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Mech Eqp Rm #3611 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-04-15 | 2027-04-21 | 5 | 90 | Exterior Envelope | MEP Work at Mech Eqp Rm #3611
Baseline | C-36-MP-540 | Install Mech Heat Pump & VFDs @ Mech Eqp Rm #3611 - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Mech Eqp Rm #3611 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-04-22 | 2027-04-27 | 4 | 104 | Exterior Envelope | MEP Work at Mech Eqp Rm #3611
Baseline | C-36-MP-550 | Install Mech Eqp Refrig Piping & Ductwork @ Mech Eqp Rm #3611 - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Mech Eqp Rm #3611 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-04-22 | 2027-06-03 | 30 | 90 | Exterior Envelope | MEP Work at Mech Eqp Rm #3611
Baseline | C-36-RF-200 | Install AD Drain Bases @ Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Pool Deck at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-05-03 | 2027-05-05 | 3 | 33 | Exterior Envelope | Roofing at Pool Deck
Baseline | C-36-RF-210 | Install Alum Trellises Base Plates @ Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Pool Deck at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-05-06 | 2027-05-10 | 3 | 33 | Exterior Envelope | Roofing at Pool Deck
Baseline | C-36-RF-220 | Apply Waterproofing Membrane @ Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Pool Deck at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-05-11 | 2027-05-19 | 7 | 33 | Exterior Envelope | Roofing at Pool Deck
Baseline | C-36-MP-560 | Install Electrical for Mech Eqp @ Mech Eqp Rm #3611 - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Mech Eqp Rm #3611 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-05-18 | 2027-06-08 | 15 | 90 | Exterior Envelope | MEP Work at Mech Eqp Rm #3611
Baseline | C-36-RF-230 | Pour Light Weight Concrete Topping @ Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Pool Deck at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-05-20 | 2027-06-01 | 8 | 33 | Exterior Envelope | Roofing at Pool Deck
Baseline | C-36-PD-300 | Install Drainage @ Planters - Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Planters at Pool Deck - 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-02 | 2027-06-17 | 12 | 85 | Exterior Envelope | Planters at Pool Deck
Baseline | C-36-PD-800 | Install Plumbing Rough @ Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > MEP Work at Pool Deck at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-02 | 2027-06-22 | 15 | 33 | Exterior Envelope | MEP Work at Pool Deck
Baseline | C-36-RF-240 | Install Roof Drain Strainers @ Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Pool Deck at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-02 | 2027-06-03 | 2 | 95 | Exterior Envelope | Roofing at Pool Deck
Baseline | C-36-PD-310 | Apply Waterproofing Membrane @ Planters - Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Planters at Pool Deck - 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-18 | 2027-06-29 | 8 | 85 | Exterior Envelope | Planters at Pool Deck
Baseline | C-36-PL-200 | Install MEP Rough @ Swim Spa Eqp Rm #3610 - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-23 | 2027-07-21 | 20 | 53 | Exterior Envelope | Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602
Baseline | C-36-PD-320 | Install Electrical Rough @ Planters - Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Planters at Pool Deck - 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-30 | 2027-07-09 | 7 | 120 | Exterior Envelope | Planters at Pool Deck
Baseline | C-36-PD-330 | Install Irrigation Piping & Valves @ Planters - Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Planters at Pool Deck - 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-30 | 2027-07-14 | 10 | 85 | Exterior Envelope | Planters at Pool Deck
Baseline | C-36-PD-340 | Apply Stucco @ Planters - Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Planters at Pool Deck - 36th Pool Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-30 | 12 | 85 | Exterior Envelope | Planters at Pool Deck
Baseline | C-36-PL-210 | Apply Waterproofing Membrane @ Swim Spa Eqp Rm #3610 - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-07-27 | 4 | 53 | Exterior Envelope | Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602
Baseline | C-36-PL-220 | Install Pool Equipment Curbs & Housekeeping Pads @ Swim Spa Eqp Rm #3610 - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-07-28 | 2027-08-02 | 4 | 53 | Exterior Envelope | Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602
Baseline | C-36-PD-350 | Paint Stucco @ Planters - Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Planters at Pool Deck - 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-06 | 5 | 85 | Exterior Envelope | Planters at Pool Deck
Baseline | C-36-PL-230 | Setup Pool Equipment @ Swim Spa Eqp Rm #3610 - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-03 | 2027-08-30 | 20 | 53 | Exterior Envelope | Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602
Baseline | C-36-PD-360 | Fill Soil Mix @ Planters - Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Planters at Pool Deck - 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-09 | 2027-08-13 | 5 | 100 | Exterior Envelope | Planters at Pool Deck
Baseline | C-36-PD-370 | Plant Trees & Shrubs @ Planters - Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Planters at Pool Deck - 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-16 | 2027-09-13 | 20 | 100 | Exterior Envelope | Planters at Pool Deck
Baseline | C-36-PL-240 | Install Plumbing Piping & Connections @ Swim Spa Eqp Rm #3610 - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-17 | 2027-09-14 | 20 | 53 | Exterior Envelope | Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602
Baseline | C-36-LB-FN-100 | Hang Drywall @ Elev Lobby & Corr - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > Interior Finishes at Elev Lobby at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-25 | 2027-08-26 | 2 | 33 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby
Baseline | C-36-LB-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > Interior Finishes at Elev Lobby at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-27 | 2027-08-27 | 1 | 33 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby
Baseline | C-36-LB-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > Interior Finishes at Elev Lobby at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-30 | 2027-09-01 | 3 | 33 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby
Baseline | C-36-LB-FN-130 | Install Trash Chute @ Corr - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > Interior Finishes at Elev Lobby at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-30 | 2027-08-30 | 1 | 41 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby
Baseline | C-36-LB-MP-200 | Install Elect & Low Voltage Panels @ Telecom/Elect Rm #3601- L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > MEP Eqp & Trim at Elev Lobby & MEP Rooms at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-30 | 2027-09-20 | 15 | 114 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & MEP Rooms
Baseline | C-36-LB-MP-210 | Install Mech Heat Pump @ Elev Lobby - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > MEP Eqp & Trim at Elev Lobby & MEP Rooms at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-02 | 2027-09-07 | 3 | 33 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & MEP Rooms
Baseline | C-36-LB-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > Interior Finishes at Elev Lobby at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-08 | 2027-09-10 | 3 | 33 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby
Baseline | C-36-PL-260 | Electrical Connections @ Swim Spa Eqp Rm #3610 - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-09 | 2027-09-16 | 6 | 97 | Exterior Envelope | Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602
Baseline | C-36-LB-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > Interior Finishes at Elev Lobby at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-13 | 2027-09-15 | 3 | 33 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby
Baseline | C-36-PL-100 | Apply Waterproofing @ Pool - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Swim Spa Pool Work at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-13 | 2027-09-16 | 4 | 53 | Exterior Envelope | Swim Spa Pool Work
Baseline | C-36-PD-380 | Install Irrigation Trim @ Planters - Outdoor Rooftop - Roof Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Planters at Pool Deck - 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-14 | 2027-09-15 | 2 | 108 | Exterior Envelope | Planters at Pool Deck
Baseline | C-36-PL-250 | Install Gas Detection @ Swim Spa Eqp Rm #3610 - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-15 | 2027-09-21 | 5 | 94 | Exterior Envelope | Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602
Baseline | C-36-LB-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > Interior Finishes at Elev Lobby at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-16 | 2027-09-16 | 1 | 122 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby
Baseline | C-36-LB-MP-220 | Install HVAC Trim @ Elev Lobby - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > MEP Eqp & Trim at Elev Lobby & MEP Rooms at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-16 | 2027-09-21 | 4 | 117 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & MEP Rooms
Baseline | C-36-PD-390 | Install Lighting @ Planters - Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Planters at Pool Deck - 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-16 | 2027-09-22 | 5 | 108 | Exterior Envelope | Planters at Pool Deck
Baseline | C-36-JC-400 | Apply Waterproofing @ Jacuzzi - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Jacuzzi Work at 36th Pool Lvl > Jacuzzi at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-17 | 2027-09-20 | 2 | 93 | Exterior Envelope | Jacuzzi
Baseline | C-36-PL-110 | Install Trench Drains & Grated Gutters @ Pool - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Swim Spa Pool Work at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-17 | 2027-09-22 | 4 | 53 | Exterior Envelope | Swim Spa Pool Work
Baseline | C-36-JC-410 | Install Jacuzzi Surface Finish @ Jacuzzi - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Jacuzzi Work at 36th Pool Lvl > Jacuzzi at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-21 | 2027-09-27 | 5 | 93 | Exterior Envelope | Jacuzzi
Baseline | C-36-LB-MP-230 | Install FA & Low Voltage Devices @ Elev Lobby - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > MEP Eqp & Trim at Elev Lobby & MEP Rooms at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-21 | 2027-09-22 | 2 | 114 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & MEP Rooms
Baseline | C-36-PL-270 | Pool Equipment Installation Complete @ Swim Spa Eqp Rm #3610 - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602 at 36th Pool Lvl | TT_FinMile | TK_NotStart | 2027-09-21 | 2027-09-21 | 0 | 94 | Exterior Envelope | Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602
Baseline | C-36-LB-MP-240 | Install FP Sprinkler Heads @ Elev Lobby - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > MEP Eqp & Trim at Elev Lobby & MEP Rooms at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-22 | 2027-09-23 | 2 | 117 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & MEP Rooms
Baseline | C-36-PD-100 | Lay Tile Pavers @ Pool Deck - 36th pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Pool Deck Finishes at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-23 | 2027-10-13 | 15 | 53 | Exterior Envelope | Pool Deck Finishes
Baseline | C-36-PL-130 | Install Pool Surface Finish @ Pool - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Swim Spa Pool Work at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-23 | 2027-10-06 | 10 | 83 | Exterior Envelope | Swim Spa Pool Work
Baseline | C-36-JC-420 | Install Grab Rails & Accessories @ Jacuzzi - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Jacuzzi Work at 36th Pool Lvl > Jacuzzi at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-24 | 2027-09-27 | 2 | 93 | Exterior Envelope | Jacuzzi
Baseline | C-36-JC-430 | Install Light Fixtures @ Jacuzzi - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Jacuzzi Work at 36th Pool Lvl > Jacuzzi at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-24 | 2027-09-24 | 1 | 94 | Exterior Envelope | Jacuzzi
Baseline | C-36-LB-MP-250 | Install Electrical Power Trim @ Elev Lobby - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > MEP Eqp & Trim at Elev Lobby & MEP Rooms at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-30 | 2027-10-01 | 2 | 109 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & MEP Rooms
Baseline | C-36-LB-MP-260 | Install Light Fixtures @ Elev Lobby - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > MEP Eqp & Trim at Elev Lobby & MEP Rooms at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-10-01 | 2027-10-05 | 3 | 109 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & MEP Rooms
Baseline | C-36-PD-110 | Erect Pergola (Trellis) Structure & Finishes @ Pool Deck - 36th pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Pool Deck Finishes at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-10-14 | 2027-11-03 | 15 | 53 | Exterior Envelope | Pool Deck Finishes
Baseline | C-36-PD-120 | Install Plunge Bucket Shower & Pergola @ Pool Deck - 36th pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Pool Deck Finishes at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-10-14 | 2027-10-19 | 4 | 89 | Exterior Envelope | Pool Deck Finishes
Baseline | C-36-PD-810 | Install Electrical & Low Voltage Rough @ Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > MEP Work at Pool Deck at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-10-14 | 2027-10-27 | 10 | 66 | Exterior Envelope | MEP Work at Pool Deck
Baseline | C-36-PL-150 | Install Pool Handrails & Grab Rails & Accessories @ Pool - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Swim Spa Pool Work at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-10-14 | 2027-10-15 | 2 | 76 | Exterior Envelope | Swim Spa Pool Work
Baseline | C-36-PL-140 | Install Light Fixtures @ Pool - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Swim Spa Pool Work at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-10-28 | 2027-10-29 | 2 | 66 | Exterior Envelope | Swim Spa Pool Work
Baseline | C-36-LB-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > Interior Finishes at Elev Lobby at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-11-01 | 2027-11-03 | 3 | 88 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby
Baseline | C-36-LB-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > Interior Finishes at Elev Lobby at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-11-04 | 2027-11-04 | 1 | 88 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby
Baseline | C-36-PD-130 | Install Perimeter Glass Railings @ Pool Deck - 36th pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Pool Deck Finishes at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-11-04 | 2027-11-17 | 10 | 53 | Exterior Envelope | Pool Deck Finishes
Baseline | C-36-PD-140 | Install Signage @ Pool Deck - 36th pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Pool Deck Finishes at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-11-04 | 2027-11-08 | 3 | 75 | Exterior Envelope | Pool Deck Finishes
Baseline | C-36-PD-150 | Install Bar Millwork & Appliances/Eqp @ Pool Bar - Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Pool Deck Finishes at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-11-04 | 2027-11-17 | 10 | 68 | Exterior Envelope | Pool Deck Finishes
Baseline | C-36-PD-160 | Install Greenscreen Metal Trellis Along Face of N. Walls @ Pool Deck - 36th pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Pool Deck Finishes at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-11-04 | 2027-11-15 | 8 | 70 | Exterior Envelope | Pool Deck Finishes
Baseline | C-36-LB-FN-190 | Final Cleanup @ Elev Lobby & Corr - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > Interior Finishes at Elev Lobby at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-11-05 | 2027-11-05 | 1 | 88 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby
Baseline | C-36-PD-170 | Install Light Fixtures & Power Trim @ Pool Deck - 36th pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Pool Deck Finishes at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-11-18 | 2027-11-23 | 4 | 62 | Exterior Envelope | Pool Deck Finishes
Baseline | C-36-PL-700 | Fill Pool @ Pool - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Swim Spa Startup & Certification at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-11-18 | 2027-11-19 | 2 | 53 | Exterior Envelope | Swim Spa Startup & Certification
Baseline | C-36-JC-900 | Fill Jacuzzi @ Jacuzzi - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Jacuzzi Work at 36th Pool Lvl > Jacuzzi Startup at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-11-22 | 2027-11-22 | 1 | 54 | Exterior Envelope | Jacuzzi Startup
Baseline | C-36-PL-710 | Start-up Pool Equipment @ Pool - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Swim Spa Startup & Certification at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-11-22 | 2027-11-23 | 2 | 53 | Exterior Envelope | Swim Spa Startup & Certification
Baseline | C-36-JC-910 | Start-up Jacuzzi Equipment @ Jacuzzi - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Jacuzzi Work at 36th Pool Lvl > Jacuzzi Startup at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-11-23 | 2027-11-24 | 2 | 54 | Exterior Envelope | Jacuzzi Startup
Baseline | C-36-PD-180 | Install FA & Low Voltage Devices @ Pool Deck - 36th pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Pool Deck Finishes at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-11-24 | 2027-11-29 | 2 | 62 | Exterior Envelope | Pool Deck Finishes
Baseline | C-36-PL-720 | Balance & Test Pool Water @ Pool - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Swim Spa Startup & Certification at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-11-24 | 2027-11-30 | 3 | 53 | Exterior Envelope | Swim Spa Startup & Certification
Baseline | C-36-JC-920 | Balance & Test Jacuzzi Water @ Jacuzzi - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Jacuzzi Work at 36th Pool Lvl > Jacuzzi Startup at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-11-29 | 2027-11-29 | 1 | 54 | Exterior Envelope | Jacuzzi Startup
Baseline | C-36-PD-190 | Install FF&Es @ Pool Deck - 36th pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Pool Deck Finishes at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-11-30 | 2027-12-01 | 2 | 62 | Exterior Envelope | Pool Deck Finishes
Baseline | C-36-PL-730 | Dept. of Health Inspection & Certification of Pool & Jacuzzi | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Swim Spa Startup & Certification at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-12-01 | 2027-12-14 | 10 | 53 | Exterior Envelope | Swim Spa Startup & Certification
Baseline | C-37-ST-200 | Lay Parapet Walls @ Roof Level | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Roof Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-16 | 7 | 24 | Building Structure | Structure at Roof Lvl
Baseline | C-37-RF-200 | Install Roof Drain Bases @ Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Roof Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-25 | 2 | 24 | Exterior Envelope | Roofing at Roof Lvl
Baseline | C-37-MP-100 | Install Roof Stands & Supports for Roof Mech Eqp @ East Mech Eqp Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at East Mech Eqp Area at Roof Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-04-02 | 6 | 24 | Exterior Envelope | MEP Work at East Mech Eqp Area at Roof Lvl
Baseline | C-37-MP-300 | Install Roof Stands & Supports & Pedestals for CT-1 & CT-2 & Piping @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Task | TK_NotStart | 2027-04-05 | 2027-04-12 | 6 | 24 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Baseline | C-37-MP-310 | Set Isolators & Support Rails @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Task | TK_NotStart | 2027-04-13 | 2027-04-19 | 5 | 36 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Baseline | C-37-RF-210 | Pour Light Weight Concrete @ Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Roof Lvl | TT_Task | TK_NotStart | 2027-04-13 | 2027-04-21 | 7 | 24 | Exterior Envelope | Roofing at Roof Lvl
Baseline | C-37-RF-220 | Apply Single Ply Roofing Membrane & Flashing & Trim @ Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Roof Lvl | TT_Task | TK_NotStart | 2027-04-22 | 2027-05-05 | 10 | 24 | Exterior Envelope | Roofing at Roof Lvl
Baseline | C-37-MP-320 | Set Cooling Towers CT-1 & CT-2 @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Task | TK_NotStart | 2027-05-06 | 2027-05-10 | 3 | 24 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Baseline | C-37-RF-230 | Install Roof Drain Strainers @ Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Roof Lvl | TT_Task | TK_NotStart | 2027-05-06 | 2027-05-06 | 1 | 112 | Exterior Envelope | Roofing at Roof Lvl
Baseline | C-37-MP-110 | Set Mech DOAU-2 on Curbs @ East Mech Eqp Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at East Mech Eqp Area at Roof Lvl | TT_Task | TK_NotStart | 2027-05-07 | 2027-05-12 | 4 | 24 | Exterior Envelope | MEP Work at East Mech Eqp Area at Roof Lvl
Baseline | C-37-MP-330 | Install Mech Eqp Refrig Piping @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Task | TK_NotStart | 2027-05-11 | 2027-06-29 | 35 | 66 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Baseline | C-37-MP-220 | Install Mech Eqp Refrig Piping & Ductwork @ East Mech Eqp Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at East Mech Eqp Area at Roof Lvl | TT_Task | TK_NotStart | 2027-05-13 | 2027-06-17 | 25 | 80 | Exterior Envelope | MEP Work at East Mech Eqp Area at Roof Lvl
Baseline | C-37-MP-230 | Install Mech CUs on Walls @ East Mech Eqp Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at East Mech Eqp Area at Roof Lvl | TT_Task | TK_NotStart | 2027-05-13 | 2027-05-21 | 7 | 83 | Exterior Envelope | MEP Work at East Mech Eqp Area at Roof Lvl
Baseline | C-37-MP-240 | Set Stair Pressurization Fan SPF-01-02 @ East Mech Eqp Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at East Mech Eqp Area at Roof Lvl | TT_Task | TK_NotStart | 2027-05-13 | 2027-05-17 | 3 | 90 | Exterior Envelope | MEP Work at East Mech Eqp Area at Roof Lvl
Baseline | C-37-MP-260 | Install Mech VFDs @ East Mech Eqp Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at East Mech Eqp Area at Roof Lvl | TT_Task | TK_NotStart | 2027-05-18 | 2027-05-19 | 2 | 90 | Exterior Envelope | MEP Work at East Mech Eqp Area at Roof Lvl
Baseline | C-37-MP-270 | Install Electrical for Mech Eqp @ East Mech Eqp Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at East Mech Eqp Area at Roof Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-06-22 | 20 | 80 | Exterior Envelope | MEP Work at East Mech Eqp Area at Roof Lvl
Baseline | C-37-MP-280 | Install FPL Stacked M/U Air Intake Duct @ East Mech Eqp Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at East Mech Eqp Area at Roof Lvl | TT_Task | TK_NotStart | 2027-05-27 | 2027-06-07 | 7 | 90 | Exterior Envelope | MEP Work at East Mech Eqp Area at Roof Lvl
Baseline | C-37-MP-340 | Install Electrical for Mech Eqp @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Task | TK_NotStart | 2027-06-14 | 2027-07-02 | 15 | 66 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Baseline | C-37-MP-350 | Erect Ladders and Platforms @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Rsrc | TK_NotStart | 2027-07-06 | 2027-07-12 | 5 | 66 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Baseline | C-37-MP-360 | Check Fan Rotation @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Rsrc | TK_NotStart | 2027-07-13 | 2027-07-13 | 1 | 66 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Baseline | C-37-MP-370 | Secure & Start Fill of Mech System @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Rsrc | TK_NotStart | 2027-07-14 | 2027-07-16 | 3 | 66 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Baseline | C-37-MP-380 | Confirm Operational Status of CW Pumps @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Rsrc | TK_NotStart | 2027-07-19 | 2027-07-20 | 2 | 66 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Baseline | C-37-MP-390 | Start Water Circulation @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Rsrc | TK_NotStart | 2027-07-21 | 2027-07-22 | 2 | 66 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Baseline | C-37-MP-400 | Start CT1-1 & CT-2 Flushing @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Rsrc | TK_NotStart | 2027-07-23 | 2027-08-02 | 7 | 66 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Baseline | C-37-MP-410 | Run Cooling Tower @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Rsrc | TK_NotStart | 2027-08-03 | 2027-08-09 | 5 | 66 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Baseline | C-37-MP-600 | Prepare Room to Receive MEP Eqp @ Boiler Rm #3701 | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Boiler Rm #3702 at Roof Lvl | TT_Task | TK_NotStart | 2027-08-30 | 2027-09-27 | 20 | 67 | Exterior Envelope | MEP Work at Boiler Rm #3702 at Roof Lvl
Baseline | C-37-MP-610 | F/R/P Boiler Pad @ Boiler Rm #3701 | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Boiler Rm #3702 at Roof Lvl | TT_Task | TK_NotStart | 2027-09-28 | 2027-09-29 | 2 | 67 | Exterior Envelope | MEP Work at Boiler Rm #3702 at Roof Lvl
Baseline | C-37-MP-620 | Install Floor Drain (FD) Base @ Boiler Rm #3701 | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Boiler Rm #3702 at Roof Lvl | TT_Task | TK_NotStart | 2027-09-30 | 2027-09-30 | 1 | 67 | Exterior Envelope | MEP Work at Boiler Rm #3702 at Roof Lvl
Baseline | C-37-MP-630 | Apply Waterproofing @ Boiler Rm #3701 | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Boiler Rm #3702 at Roof Lvl | TT_Task | TK_NotStart | 2027-10-01 | 2027-10-04 | 2 | 67 | Exterior Envelope | MEP Work at Boiler Rm #3702 at Roof Lvl
Baseline | C-37-MP-640 | Setup & Connect Boiler @ Boiler Rm #3701 | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Boiler Rm #3702 at Roof Lvl | TT_Task | TK_NotStart | 2027-10-05 | 2027-11-01 | 20 | 67 | Exterior Envelope | MEP Work at Boiler Rm #3702 at Roof Lvl
Baseline | C-38-RF-200 | Install Roof Drain Bases @ Upper Roof Lvl | no |  | 38 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Upper Roof Lvl | TT_Task | TK_NotStart | 2027-03-23 | 2027-03-23 | 1 | 24 | Exterior Envelope | Roofing at Upper Roof Lvl
Baseline | C-38-MP-100 | Install Roof Stands & Supports for Roof Mech Eqp @ Upper Roof Lvl | no |  | 38 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Upper Roof Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-29 | 4 | 47 | Exterior Envelope | MEP Work at Upper Roof Lvl
Baseline | C-38-RF-210 | Pour Light Weight Concrete @ Upper Roof Lvl | no |  | 38 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Upper Roof Lvl | TT_Task | TK_NotStart | 2027-03-30 | 2027-04-01 | 3 | 47 | Exterior Envelope | Roofing at Upper Roof Lvl
Baseline | C-38-RF-220 | Apply Single Ply Roofing Membrane & Flashing & Trim @ Upper Roof Lvl | no |  | 38 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Upper Roof Lvl | TT_Task | TK_NotStart | 2027-04-02 | 2027-04-08 | 5 | 47 | Exterior Envelope | Roofing at Upper Roof Lvl
Baseline | C-38-MP-110 | Install Mech VRV-CUs @ Upper Roof Lvl | no |  | 38 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Upper Roof Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-15 | 5 | 86 | Exterior Envelope | MEP Work at Upper Roof Lvl
Baseline | C-38-RF-230 | Install Roof Drain Strainers @ Upper Roof Lvl | no |  | 38 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Upper Roof Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-09 | 1 | 130 | Exterior Envelope | Roofing at Upper Roof Lvl
Baseline | C-38-MP-130 | Set Stair Pressurization Fan SPF-02-02 @ Upper Roof Lvl | no |  | 38 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Upper Roof Lvl | TT_Task | TK_NotStart | 2027-04-16 | 2027-04-21 | 4 | 86 | Exterior Envelope | MEP Work at Upper Roof Lvl
Baseline | C-38-MP-140 | Set Mech Fans SVF-01-01 & SVF-01-02 @ Upper Roof Lvl | no |  | 38 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Upper Roof Lvl | TT_Task | TK_NotStart | 2027-04-22 | 2027-04-27 | 4 | 86 | Exterior Envelope | MEP Work at Upper Roof Lvl
Baseline | C-38-MP-150 | Set Mech Fans SEF-01 & TEF-01 @ Upper Roof Lvl | no |  | 38 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Upper Roof Lvl | TT_Task | TK_NotStart | 2027-04-28 | 2027-05-03 | 4 | 86 | Exterior Envelope | MEP Work at Upper Roof Lvl
Baseline | C-38-MP-160 | Install Mech Eqp Refrig Piping & Ductwork @ Upper Roof Lvl | no |  | 38 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Upper Roof Lvl | TT_Task | TK_NotStart | 2027-05-04 | 2027-06-08 | 25 | 86 | Exterior Envelope | MEP Work at Upper Roof Lvl
Baseline | C-38-MP-170 | Install Electrical for Mech Eqp @ Upper Roof Lvl | no |  | 38 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Upper Roof Lvl | TT_Task | TK_NotStart | 2027-06-01 | 2027-06-14 | 10 | 86 | Exterior Envelope | MEP Work at Upper Roof Lvl
Baseline | MOB-1000 | Mobilization & Temp Facilities | no |  |  | no level in the Activity ID | CONSTRUCTION > Mobilization & Site Preparation | TT_Task | TK_NotStart | 2025-10-22 | 2025-10-30 | 7 | 0 | Mobilization & Site Preparation | Mobilization & Site Preparation
Baseline | PR-MS-100 | Notice-to-Proceed (N.T.P.) | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Contract Milestones | TT_Mile | TK_NotStart | 2025-10-22 | 2025-10-22 | 0 | 0 | Contract Milestones | Contract Milestones
Baseline | PR-PS-800 | Overall Project Duration (N.T.P. to T.C.O.) | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Project Duration Summary (Cal Days) | TT_LOE | TK_NotStart | 2025-10-22 | 2028-03-21 | 882 | 0 | Project Duration Summary (Cal Days) | Project Duration Summary (Cal Days)
Baseline | PR-PS-900 | Overall Project Duration (N.T.P. to C.O.) | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Project Duration Summary (Cal Days) | TT_LOE | TK_NotStart | 2025-10-22 | 2028-05-22 | 944 | 0 | Project Duration Summary (Cal Days) | Project Duration Summary (Cal Days)
Baseline | S-0-100 | Start of Submittals | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 | TT_Mile | TK_NotStart | 2025-10-22 | 2025-10-22 | 0 | 6 |  | SUBMITTALS & PROCUREMENT1
Baseline | MOB-1010 | Prepare Site & Building Pad | no |  |  | no level in the Activity ID | CONSTRUCTION > Mobilization & Site Preparation | TT_Task | TK_NotStart | 2025-10-31 | 2025-11-10 | 7 | 0 | Mobilization & Site Preparation | Mobilization & Site Preparation
Baseline | S-03-100 | Prep & Submit Concrete Mix | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 03 - Concrete > Concrete Mix | TT_Task | TK_NotStart | 2025-11-19 | 2025-12-04 | 10 | 21 | DIV 03 - Concrete | Concrete Mix
Baseline | S-03-200 | Prep & Submit Rebar | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 03 - Concrete > Rebar | TT_Task | TK_NotStart | 2025-11-19 | 2025-12-04 | 10 | 6 | DIV 03 - Concrete | Rebar
Baseline | S-03-300 | Prep & Submit Formwork | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 03 - Concrete > Formwork | TT_Task | TK_NotStart | 2025-11-19 | 2025-12-04 | 10 | 21 | DIV 03 - Concrete | Formwork
Baseline | S-04-100 | Prep & Submit CMU | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 04 - Masonry > CMU | TT_Task | TK_NotStart | 2025-11-19 | 2025-12-04 | 10 | 111 | DIV 04 - Masonry | CMU
Baseline | S-26-200 | Prep & Submit Switchgear | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Switchgear | TT_Task | TK_NotStart | 2025-11-19 | 2026-01-19 | 40 | 31 | DIV 26 - Electrical | Switchgear
Baseline | R-03-100 | Review & Approve Concrete Mix | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 03 - Concrete > Concrete Mix | TT_Task | TK_NotStart | 2025-12-05 | 2025-12-18 | 10 | 21 | DIV 03 - Concrete | Concrete Mix
Baseline | R-03-200 | Review & Approve Rebar | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 03 - Concrete > Rebar | TT_Task | TK_NotStart | 2025-12-05 | 2025-12-18 | 10 | 6 | DIV 03 - Concrete | Rebar
Baseline | R-03-300 | Review & Approve Formwork | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 03 - Concrete > Formwork | TT_Task | TK_NotStart | 2025-12-05 | 2025-12-18 | 10 | 21 | DIV 03 - Concrete | Formwork
Baseline | R-04-100 | Review & Approve CMU | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 04 - Masonry > CMU | TT_Task | TK_NotStart | 2025-12-05 | 2025-12-18 | 10 | 111 | DIV 04 - Masonry | CMU
Baseline | S-03-400 | Prep & Submit Post Tension Calculations - L2 | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 03 - Concrete > Post Tension | TT_Task | TK_NotStart | 2025-12-05 | 2026-01-05 | 20 | 17 | DIV 03 - Concrete | Post Tension
Baseline | S-23-100 | Prep & Submit Mechanical SD | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > Mechanical SD | TT_Task | TK_NotStart | 2025-12-05 | 2026-02-02 | 40 | 117 | DIV 23 - HVAC | Mechanical SD
Baseline | F-03-200 | Fab & Deliver Rebar | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 03 - Concrete > Rebar | TT_Task | TK_NotStart | 2025-12-19 | 2026-01-12 | 15 | 6 | DIV 03 - Concrete | Rebar
Baseline | S-26-100 | Prep & Submit Electrical SD | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Electrical SD | TT_Task | TK_NotStart | 2025-12-19 | 2026-02-16 | 40 | 109 | DIV 26 - Electrical | Electrical SD
Baseline | R-03-400 | Review & Approve Post Tension Calculations - L2 | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 03 - Concrete > Post Tension | TT_Task | TK_NotStart | 2026-01-06 | 2026-01-19 | 10 | 17 | DIV 03 - Concrete | Post Tension
Baseline | S-08-100 | Prep & Submit Windows & Storefronts | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Windows & Storefronts | TT_Task | TK_NotStart | 2026-01-06 | 2026-03-02 | 40 | 40 | DIV 08 - Openings | Windows & Storefronts
Baseline | S-22-100 | Prep & Submit Plumbing SD | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Plumbing SD | TT_Task | TK_NotStart | 2026-01-06 | 2026-03-02 | 40 | 254 | DIV 22 - Plumbing | Plumbing SD
Baseline | S-26-300 | Prep & Submit Generator | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Generator | TT_Task | TK_NotStart | 2026-01-06 | 2026-02-16 | 30 | 209 | DIV 26 - Electrical | Generator
Baseline | S-26-400 | Prep & Submit Electrical Panels | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Electrical Panels | TT_Task | TK_NotStart | 2026-01-06 | 2026-03-02 | 40 | 159 | DIV 26 - Electrical | Electrical Panels
Baseline | F-03-400 | Fab & Deliver Post Tension Tendons - L2 | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 03 - Concrete > Post Tension | TT_Task | TK_NotStart | 2026-01-20 | 2026-03-02 | 30 | 17 | DIV 03 - Concrete | Post Tension
Baseline | R-26-200 | Review & Approve Switchgear | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Switchgear | TT_Task | TK_NotStart | 2026-01-20 | 2026-02-02 | 10 | 31 | DIV 26 - Electrical | Switchgear
Baseline | S-08-200 | Prep & Submit Door Frames | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Door Frames | TT_Task | TK_NotStart | 2026-01-20 | 2026-02-16 | 20 | 81 | DIV 08 - Openings | Door Frames
Baseline | S-14-100 | Prep & Submit Elevators | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 14 - Conveying Systems > Elevator | TT_Task | TK_NotStart | 2026-01-20 | 2026-03-16 | 40 | 151 | DIV 14 - Conveying Systems | Elevator
Baseline | S-23-200 | Prep & Submit Cooling Towers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > Cooling Towers | TT_Task | TK_NotStart | 2026-01-20 | 2026-03-16 | 40 | 174 | DIV 23 - HVAC | Cooling Towers
Baseline | S-23-300 | Prep & Submit DOAUs | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > Rooftop DOAUs | TT_Task | TK_NotStart | 2026-01-20 | 2026-03-16 | 40 | 116 | DIV 23 - HVAC | Rooftop DOAUs
Baseline | S-23-400 | Prep & Submit Heat Pumps & ACs & CUs | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > ACs & CUs | TT_Task | TK_NotStart | 2026-01-20 | 2026-03-02 | 30 | 73 | DIV 23 - HVAC | ACs & CUs
Baseline | S-23-500 | Prep & Submit VFDs | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > VFDs | TT_Task | TK_NotStart | 2026-01-20 | 2026-03-02 | 30 | 304 | DIV 23 - HVAC | VFDs
Baseline | F-26-200 | Fab & Deliver Switchgear | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Switchgear | TT_Task | TK_NotStart | 2026-02-03 | 2026-12-14 | 220 | 31 | DIV 26 - Electrical | Switchgear
Baseline | R-23-100 | Review & Approve Mechanical SD | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > Mechanical SD | TT_Task | TK_NotStart | 2026-02-03 | 2026-02-16 | 10 | 117 | DIV 23 - HVAC | Mechanical SD
Baseline | R-08-200 | Review & Approve Door Frames | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Door Frames | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-02 | 10 | 81 | DIV 08 - Openings | Door Frames
Baseline | R-26-100 | Review & Approve Electrical SD | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Electrical SD | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-02 | 10 | 109 | DIV 26 - Electrical | Electrical SD
Baseline | R-26-300 | Review & Approve Generator | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Generator | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-02 | 10 | 209 | DIV 26 - Electrical | Generator
Baseline | S-08-300 | Prep & Submit Doors | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Doors | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-16 | 20 | 59 | DIV 08 - Openings | Doors
Baseline | S-10-400 | Prep & Submit Shower Enclosures | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Shower Enclosures | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-16 | 20 | 81 | DIV 10 - Specialties | Shower Enclosures
Baseline | S-14-200 | Prep & Submit Trash Chute | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 14 - Conveying Systems > Trash Chute | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-30 | 30 | 148 | DIV 14 - Conveying Systems | Trash Chute
Baseline | S-14-300 | Prep & Submit Car Lifts | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 14 - Conveying Systems > Car Lifts | TT_Task | TK_NotStart | 2026-02-17 | 2026-04-13 | 40 | 268 | DIV 14 - Conveying Systems | Car Lifts
Baseline | S-21-100 | Prep & Submit Fire Pump | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 21 - Fire Suppression > Fire Pump | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-30 | 30 | 298 | DIV 21 - Fire Suppression | Fire Pump
Baseline | S-21-200 | Prep & Submit Fire Spinkler SD | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 21 - Fire Suppression > Fire Suppression | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-30 | 30 | 180 | DIV 21 - Fire Suppression | Fire Suppression
Baseline | S-22-200 | Prep & Submit Domestic Pump | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Domestic Pump | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-16 | 20 | 373 | DIV 22 - Plumbing | Domestic Pump
Baseline | S-22-300 | Prep & Submit Plumbing Fixtures | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Plumbing Fixtures | TT_Task | TK_NotStart | 2026-02-17 | 2026-04-27 | 50 | 137 | DIV 22 - Plumbing | Plumbing Fixtures
Baseline | S-26-500 | Prep & Submit Light Fixtures | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Light Fixtures | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-30 | 30 | 165 | DIV 26 - Electrical | Light Fixtures
Baseline | S-26-600 | Prep & Submit EV Charge Stations | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > EV Charging Stations | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-16 | 20 | 241 | DIV 26 - Electrical | EV Charging Stations
Baseline | S-27-100 | Prep & Submit Low Voltage | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 27 - Communications > Low Voltage | TT_Task | TK_NotStart | 2026-02-17 | 2026-04-13 | 40 | 179 | DIV 27 - Communications | Low Voltage
Baseline | S-27-200 | Prep & Submit BDA | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 27 - Communications > BDA | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-16 | 20 | 19 | DIV 27 - Communications | BDA
Baseline | S-28-100 | Prep & Submit Fire Alarm | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 28 - Electronic Safety & Security > Fire Alarm | TT_Task | TK_NotStart | 2026-02-17 | 2026-04-13 | 40 | 149 | DIV 28 - Electronic Safety & Security | Fire Alarm
Baseline | S-33-100 | Prep & Submit Water | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 33 - Utilities > Water | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-30 | 30 | 264 | DIV 33 - Utilities | Water
Baseline | S-33-200 | Prep & Submit Drainage | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 33 - Utilities > Drainage | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-30 | 30 | 289 | DIV 33 - Utilities | Drainage
Baseline | S-33-300 | Prep & Submit Fire | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 33 - Utilities > Fire | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-30 | 30 | 312 | DIV 33 - Utilities | Fire
Baseline | F-08-200 | Fab & Deliver Door Frames | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Door Frames | TT_Task | TK_NotStart | 2026-03-03 | 2026-05-11 | 50 | 81 | DIV 08 - Openings | Door Frames
Baseline | F-26-300 | Fab & Deliver Generator | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Generator | TT_Task | TK_NotStart | 2026-03-03 | 2026-12-14 | 200 | 209 | DIV 26 - Electrical | Generator
Baseline | R-08-100 | Review & Approve Windows & Storefronts & Revisions | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Windows & Storefronts | TT_Task | TK_NotStart | 2026-03-03 | 2026-03-16 | 10 | 40 | DIV 08 - Openings | Windows & Storefronts
Baseline | R-22-100 | Review & Approve Plumbing SD | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Plumbing SD | TT_Task | TK_NotStart | 2026-03-03 | 2026-03-16 | 10 | 254 | DIV 22 - Plumbing | Plumbing SD
Baseline | R-23-400 | Review & Approve Heat Pumps & ACs & CUs | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > ACs & CUs | TT_Task | TK_NotStart | 2026-03-03 | 2026-03-16 | 10 | 73 | DIV 23 - HVAC | ACs & CUs
Baseline | R-23-500 | Review & Approve VFDs | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > VFDs | TT_Task | TK_NotStart | 2026-03-03 | 2026-03-16 | 10 | 304 | DIV 23 - HVAC | VFDs
Baseline | R-26-400 | Review & Approve Electrical Panels | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Electrical Panels | TT_Task | TK_NotStart | 2026-03-03 | 2026-03-16 | 10 | 159 | DIV 26 - Electrical | Electrical Panels
Baseline | S-05-100 | Prep & Submit Misc Metals | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 05 - Metals > Misc Metals | TT_Task | TK_NotStart | 2026-03-03 | 2026-04-13 | 30 | 366 | DIV 05 - Metals | Misc Metals
Baseline | S-06-200 | Prep & Submit Kitchen Cabinets & Vanities | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 06 - Wood and Plastics > Kitchen Cabinets & Vanities | TT_Task | TK_NotStart | 2026-03-03 | 2026-04-27 | 40 | 49 | DIV 06 - Wood and Plastics | Kitchen Cabinets & Vanities
Baseline | C-CR-100 | F/R/P Foundations @ Tower Crane | no |  |  | no level in the Activity ID | CONSTRUCTION > Hoisting Equipment > Tower Crane | TT_Task | TK_NotStart | 2026-03-04 | 2026-03-19 | 12 | 2 | Hoisting Equipment | Tower Crane
Baseline | DES-KL-100 | Final Design - Lobby/Kitchen | no |  |  | no level in the Activity ID | SPECIAL DESIGN & PERMITTING > Lobby & Kitchen Design & Permit Revisions | TT_Task | TK_NotStart | 2026-03-11 | 2026-08-27 | 120 | 96 | Lobby & Kitchen Design & Permit Revisions | Lobby & Kitchen Design & Permit Revisions
Baseline | F-08-100 | Fab & Deliver Windows & Storefronts | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Windows & Storefronts | TT_Task | TK_NotStart | 2026-03-17 | 2026-06-23 | 70 | 40 | DIV 08 - Openings | Windows & Storefronts
Baseline | F-23-400 | Fab & Deliver Heat Pumps & ACs & CUs | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > ACs & CUs | TT_Task | TK_NotStart | 2026-03-17 | 2026-07-22 | 90 | 73 | DIV 23 - HVAC | ACs & CUs
Baseline | F-23-500 | Fab & Deliver VFDs | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > VFDs | TT_Task | TK_NotStart | 2026-03-17 | 2026-07-08 | 80 | 304 | DIV 23 - HVAC | VFDs
Baseline | F-26-400 | Fab & Deliver Electrical Panels | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Electrical Panels | TT_Task | TK_NotStart | 2026-03-17 | 2026-10-01 | 140 | 159 | DIV 26 - Electrical | Electrical Panels
Baseline | R-08-300 | Review & Approve Doors | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Doors | TT_Task | TK_NotStart | 2026-03-17 | 2026-03-30 | 10 | 59 | DIV 08 - Openings | Doors
Baseline | R-10-400 | Review & Approve Shower Enclosures | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Shower Enclosures | TT_Task | TK_NotStart | 2026-03-17 | 2026-03-30 | 10 | 81 | DIV 10 - Specialties | Shower Enclosures
Baseline | R-14-100 | Review & Approve Elevators | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 14 - Conveying Systems > Elevator | TT_Task | TK_NotStart | 2026-03-17 | 2026-03-30 | 10 | 151 | DIV 14 - Conveying Systems | Elevator
Baseline | R-22-200 | Review & Approve Domestic Pump | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Domestic Pump | TT_Task | TK_NotStart | 2026-03-17 | 2026-03-30 | 10 | 373 | DIV 22 - Plumbing | Domestic Pump
Baseline | R-23-200 | Review & Approve Cooling Towers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > Cooling Towers | TT_Task | TK_NotStart | 2026-03-17 | 2026-03-30 | 10 | 174 | DIV 23 - HVAC | Cooling Towers
Baseline | R-23-300 | Review & Approve DOAUs | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > Rooftop DOAUs | TT_Task | TK_NotStart | 2026-03-17 | 2026-03-30 | 10 | 116 | DIV 23 - HVAC | Rooftop DOAUs
Baseline | R-26-600 | Review & Approve EV Charge Stations | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > EV Charging Stations | TT_Task | TK_NotStart | 2026-03-17 | 2026-03-30 | 10 | 241 | DIV 26 - Electrical | EV Charging Stations
Baseline | R-27-200 | Review & Approve BDA | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 27 - Communications > BDA | TT_Task | TK_NotStart | 2026-03-17 | 2026-03-30 | 10 | 19 | DIV 27 - Communications | BDA
Baseline | S-05-110 | Prep & Submit Trellises | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 05 - Metals > Trelllises | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-27 | 30 | 355 | DIV 05 - Metals | Trelllises
Baseline | S-06-100 | Prep & Submit Millwork (Pool Bar) | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 06 - Wood and Plastics > Millwork (Pool Bar) | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-27 | 30 | 365 | DIV 06 - Wood and Plastics | Millwork (Pool Bar)
Baseline | S-07-100 | Prep & Submit Roofing | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 07 - Thermal and Moisture Protection > Roofing | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-27 | 30 | 217 | DIV 07 - Thermal and Moisture Protection | Roofing
Baseline | S-08-400 | Prep & Submit Door Hardware | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Door Hardware | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-27 | 30 | 150 | DIV 08 - Openings | Door Hardware
Baseline | S-09-100 | Prep & Submit Toilet Tiles | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Toilet Tiles | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-13 | 20 | 63 | DIV 09 - Finishes | Toilet Tiles
Baseline | S-09-200 | Prep & Submit LVT Flooring | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > LVT Flooring | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-13 | 20 | 88 | DIV 09 - Finishes | LVT Flooring
Baseline | S-09-300 | Prep & Submit Hardscape Pavers - L1 | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Hardscape Pavers - L1 | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-13 | 20 | 363 | DIV 09 - Finishes | Hardscape Pavers - L1
Baseline | S-09-400 | Prep & Submit Pool Deck Pavers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Pool Deck Pavers | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-13 | 20 | 350 | DIV 09 - Finishes | Pool Deck Pavers
Baseline | S-09-500 | Prep & Submit Wood Deck Flooring | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Wood Deck - L7 | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-13 | 20 | 390 | DIV 09 - Finishes | Wood Deck - L7
Baseline | S-10-100 | Prep & Submit Toilet Accessories | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Toilet Accessories | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-13 | 20 | 169 | DIV 10 - Specialties | Toilet Accessories
Baseline | S-10-200 | Prep & Submit Toilet Partitions | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Toilet Partitions | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-13 | 20 | 169 | DIV 10 - Specialties | Toilet Partitions
Baseline | S-10-300 | Prep & Submit Fire Extinguishers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Fire Extinguishers | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-13 | 20 | 245 | DIV 10 - Specialties | Fire Extinguishers
Baseline | S-13-100 | Prep & Submit Swim Spa Pool Eqp | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 13 - Special Construction > Swim Spa Pool | TT_Task | TK_NotStart | 2026-03-17 | 2026-05-26 | 50 | 181 | DIV 13 - Special Construction | Swim Spa Pool
Baseline | S-13-200 | Prep & Submit Jacuzzi Eqp | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 13 - Special Construction > Jacuzzi | TT_Task | TK_NotStart | 2026-03-17 | 2026-05-26 | 50 | 336 | DIV 13 - Special Construction | Jacuzzi
Baseline | S-22-400 | Prep & Submit Grease Interceptors | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Grease Interceptors | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-27 | 30 | 149 | DIV 22 - Plumbing | Grease Interceptors
Baseline | S-22-500 | Prep & Submit Trench Drains | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Trench Drains | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-13 | 20 | 234 | DIV 22 - Plumbing | Trench Drains
Baseline | S-22-600 | Prep & Submit Water Heaters | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Heat Heaters | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-13 | 20 | 167 | DIV 22 - Plumbing | Heat Heaters
Baseline | S-22-700 | Prep & Submit Boiler | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Boilers | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-27 | 30 | 342 | DIV 22 - Plumbing | Boilers
Baseline | S-22-800 | Prep & Submit Backflow Preventer | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Backflow Preventer | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-13 | 20 | 356 | DIV 22 - Plumbing | Backflow Preventer
Baseline | S-23-600 | Prep & Submit HVAC Controls | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > HVAC Control | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-27 | 30 | 138 | DIV 23 - HVAC | HVAC Control
Baseline | S-23-700 | Prep & Submit Grilles & Diffusers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > Grilles & Diffusers | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-27 | 30 | 148 | DIV 23 - HVAC | Grilles & Diffusers
Baseline | S-26-700 | Prep & Submit Site Lighting | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Site Lighting | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-27 | 30 | 393 | DIV 26 - Electrical | Site Lighting
Baseline | C-CR-200 | Erect Crane @ Tower Crane | no |  |  | no level in the Activity ID | CONSTRUCTION > Hoisting Equipment > Tower Crane | TT_Task | TK_NotStart | 2026-03-20 | 2026-03-26 | 5 | 311 | Hoisting Equipment | Tower Crane
Baseline | PR-MS-500 | Subsurface Structure Complete | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2026-03-23 | 2026-03-23 | 0 | 0 | Interim Milestones | Interim Milestones
Baseline | F-08-300 | Fab & Deliver Doors | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Doors | TT_Task | TK_NotStart | 2026-03-31 | 2026-07-22 | 80 | 59 | DIV 08 - Openings | Doors
Baseline | F-10-400 | Fab & Deliver Shower Enclosures | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Shower Enclosures | TT_Task | TK_NotStart | 2026-03-31 | 2026-07-08 | 70 | 81 | DIV 10 - Specialties | Shower Enclosures
Baseline | F-14-100 | Fab & Deliver Elevators | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 14 - Conveying Systems > Elevator | TT_Task | TK_NotStart | 2026-03-31 | 2026-11-12 | 160 | 151 | DIV 14 - Conveying Systems | Elevator
Baseline | F-22-200 | Fab & Deliver Domestic Pump | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Domestic Pump | TT_Task | TK_NotStart | 2026-03-31 | 2026-07-22 | 80 | 373 | DIV 22 - Plumbing | Domestic Pump
Baseline | F-23-200 | Fab & Deliver Cooling Towers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > Cooling Towers | TT_Task | TK_NotStart | 2026-03-31 | 2026-10-01 | 130 | 174 | DIV 23 - HVAC | Cooling Towers
Baseline | F-23-300 | Fab & Deliver DOAUs | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > Rooftop DOAUs | TT_Task | TK_NotStart | 2026-03-31 | 2026-09-17 | 120 | 116 | DIV 23 - HVAC | Rooftop DOAUs
Baseline | F-26-600 | Fab & Deliver EV Charge Stations | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > EV Charging Stations | TT_Task | TK_NotStart | 2026-03-31 | 2026-07-22 | 80 | 241 | DIV 26 - Electrical | EV Charging Stations
Baseline | F-27-200 | Fab & Deliver BDA System | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 27 - Communications > BDA | TT_Task | TK_NotStart | 2026-03-31 | 2026-07-08 | 70 | 19 | DIV 27 - Communications | BDA
Baseline | R-14-200 | Review & Approve Trash Chute | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 14 - Conveying Systems > Trash Chute | TT_Task | TK_NotStart | 2026-03-31 | 2026-04-13 | 10 | 148 | DIV 14 - Conveying Systems | Trash Chute
Baseline | R-21-100 | Review & Approve Fire Pump | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 21 - Fire Suppression > Fire Pump | TT_Task | TK_NotStart | 2026-03-31 | 2026-04-13 | 10 | 298 | DIV 21 - Fire Suppression | Fire Pump
Baseline | R-21-200 | Review & Approve Fire Spinkler SD | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 21 - Fire Suppression > Fire Suppression | TT_Task | TK_NotStart | 2026-03-31 | 2026-04-13 | 10 | 180 | DIV 21 - Fire Suppression | Fire Suppression
Baseline | R-26-500 | Review & Approve Light Fixtures | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Light Fixtures | TT_Task | TK_NotStart | 2026-03-31 | 2026-04-13 | 10 | 165 | DIV 26 - Electrical | Light Fixtures
Baseline | R-33-100 | Review & Approve Water | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 33 - Utilities > Water | TT_Task | TK_NotStart | 2026-03-31 | 2026-04-13 | 10 | 264 | DIV 33 - Utilities | Water
Baseline | R-33-200 | Review & Approve Drainage | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 33 - Utilities > Drainage | TT_Task | TK_NotStart | 2026-03-31 | 2026-04-13 | 10 | 289 | DIV 33 - Utilities | Drainage
Baseline | R-33-300 | Review & Approve Fire | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 33 - Utilities > Fire | TT_Task | TK_NotStart | 2026-03-31 | 2026-04-13 | 10 | 312 | DIV 33 - Utilities | Fire
Baseline | F-14-200 | Fab & Deliver Trash Chute | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 14 - Conveying Systems > Trash Chute | TT_Task | TK_NotStart | 2026-04-14 | 2026-09-02 | 100 | 148 | DIV 14 - Conveying Systems | Trash Chute
Baseline | F-21-100 | Fab & Deliver Fire Pump | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 21 - Fire Suppression > Fire Pump | TT_Task | TK_NotStart | 2026-04-14 | 2026-08-05 | 80 | 298 | DIV 21 - Fire Suppression | Fire Pump
Baseline | F-21-1200 | Fab & Deliver Fire Spinkler Heads | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 21 - Fire Suppression > Fire Suppression | TT_Task | TK_NotStart | 2026-04-14 | 2026-07-08 | 60 | 180 | DIV 21 - Fire Suppression | Fire Suppression
Baseline | F-26-500 | Fab & Deliver Light Fixtures | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Light Fixtures | TT_Task | TK_NotStart | 2026-04-14 | 2026-07-22 | 70 | 165 | DIV 26 - Electrical | Light Fixtures
Baseline | F-33-100 | Fab & Deliver Water Piping | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 33 - Utilities > Water | TT_Task | TK_NotStart | 2026-04-14 | 2026-06-16 | 45 | 264 | DIV 33 - Utilities | Water
Baseline | F-33-200 | Fab & Deliver Drainage Piping & Structures | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 33 - Utilities > Drainage | TT_Task | TK_NotStart | 2026-04-14 | 2026-06-16 | 45 | 289 | DIV 33 - Utilities | Drainage
Baseline | F-33-300 | Fab & Deliver Fire Lines | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 33 - Utilities > Fire | TT_Task | TK_NotStart | 2026-04-14 | 2026-06-16 | 45 | 312 | DIV 33 - Utilities | Fire
Baseline | R-05-100 | Review & Approve Misc Metals | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 05 - Metals > Misc Metals | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 366 | DIV 05 - Metals | Misc Metals
Baseline | R-09-100 | Review & Approve Toilet Tiles | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Toilet Tiles | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 63 | DIV 09 - Finishes | Toilet Tiles
Baseline | R-09-200 | Review & Approve LVT Flooring | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > LVT Flooring | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 88 | DIV 09 - Finishes | LVT Flooring
Baseline | R-09-300 | Review & Approve Hardscape Pavers - L1 | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Hardscape Pavers - L1 | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 363 | DIV 09 - Finishes | Hardscape Pavers - L1
Baseline | R-09-400 | Review & Approve Pool Deck Pavers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Pool Deck Pavers | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 350 | DIV 09 - Finishes | Pool Deck Pavers
Baseline | R-09-500 | Review & Approve Wood Deck Flooring | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Wood Deck - L7 | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 390 | DIV 09 - Finishes | Wood Deck - L7
Baseline | R-10-100 | Review & Approve Toilet Accessories | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Toilet Accessories | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 169 | DIV 10 - Specialties | Toilet Accessories
Baseline | R-10-200 | Review & Approve Toilet Partitions | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Toilet Partitions | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 169 | DIV 10 - Specialties | Toilet Partitions
Baseline | R-10-300 | Review & Approve Fire Extinguishers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Fire Extinguishers | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 245 | DIV 10 - Specialties | Fire Extinguishers
Baseline | R-14-300 | Review & Approve Car Lifts | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 14 - Conveying Systems > Car Lifts | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 268 | DIV 14 - Conveying Systems | Car Lifts
Baseline | R-22-500 | Review & Approve Trench Drains | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Trench Drains | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 234 | DIV 22 - Plumbing | Trench Drains
Baseline | R-22-600 | Review & Approve Water Heaters | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Heat Heaters | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 167 | DIV 22 - Plumbing | Heat Heaters
Baseline | R-22-800 | Review & Approve Backflow Preventer | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Backflow Preventer | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 356 | DIV 22 - Plumbing | Backflow Preventer
Baseline | R-27-100 | Review & Approve Low Voltage | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 27 - Communications > Low Voltage | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 179 | DIV 27 - Communications | Low Voltage
Baseline | R-28-100 | Review & Approve Fire Alarm | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 28 - Electronic Safety & Security > Fire Alarm | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 149 | DIV 28 - Electronic Safety & Security | Fire Alarm
Baseline | S-09-600 | Prep & Submit Paint | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Paint | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 111 | DIV 09 - Finishes | Paint
Baseline | S-11-100 | Prep & Submit Kitchen Appliances | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 11 - Equipment > Appliances | TT_Task | TK_NotStart | 2026-04-14 | 2026-05-26 | 30 | 119 | DIV 11 - Equipment | Appliances
Baseline | S-32-100 | Prep & Submit Irrigation | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 32 - Exterior Site Improvements > Irrigation | TT_Task | TK_NotStart | 2026-04-14 | 2026-05-26 | 30 | 313 | DIV 32 - Exterior Site Improvements | Irrigation
Baseline | S-32-200 | Prep & Submit Landscaping | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 32 - Exterior Site Improvements > Landscape | TT_Task | TK_NotStart | 2026-04-14 | 2026-05-26 | 30 | 340 | DIV 32 - Exterior Site Improvements | Landscape
Baseline | S-32-300 | Prep & Submit Parking Signage | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 32 - Exterior Site Improvements > Parking Signage | TT_Task | TK_NotStart | 2026-04-14 | 2026-05-26 | 30 | 254 | DIV 32 - Exterior Site Improvements | Parking Signage
Baseline | F-05-100 | Fab & Deliver Misc Metals | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 05 - Metals > Misc Metals | TT_Task | TK_NotStart | 2026-04-28 | 2026-07-22 | 60 | 366 | DIV 05 - Metals | Misc Metals
Baseline | F-09-100 | Fab & Deliver Toilet Tiles | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Toilet Tiles | TT_Task | TK_NotStart | 2026-04-28 | 2026-07-22 | 60 | 63 | DIV 09 - Finishes | Toilet Tiles
Baseline | F-09-200 | Fab & Deliver LVT Flooring | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > LVT Flooring | TT_Task | TK_NotStart | 2026-04-28 | 2026-07-22 | 60 | 88 | DIV 09 - Finishes | LVT Flooring
Baseline | F-09-300 | Fab & Deliver Hardscape Pavers - L1 | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Hardscape Pavers - L1 | TT_Task | TK_NotStart | 2026-04-28 | 2026-07-22 | 60 | 363 | DIV 09 - Finishes | Hardscape Pavers - L1
Baseline | F-09-400 | Fab & Deliver Pool Deck Pavers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Pool Deck Pavers | TT_Task | TK_NotStart | 2026-04-28 | 2026-07-22 | 60 | 350 | DIV 09 - Finishes | Pool Deck Pavers
Baseline | F-09-500 | Fab & Deliver Wood Deck Flooring | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Wood Deck - L7 | TT_Task | TK_NotStart | 2026-04-28 | 2026-07-22 | 60 | 390 | DIV 09 - Finishes | Wood Deck - L7
Baseline | F-10-100 | Fab & Deliver Toilet Accessories | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Toilet Accessories | TT_Task | TK_NotStart | 2026-04-28 | 2026-07-22 | 60 | 169 | DIV 10 - Specialties | Toilet Accessories
Baseline | F-10-200 | Fab & Deliver Toilet Partitions | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Toilet Partitions | TT_Task | TK_NotStart | 2026-04-28 | 2026-07-22 | 60 | 169 | DIV 10 - Specialties | Toilet Partitions
Baseline | F-10-300 | Fab & Deliver Fire Extinguishers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Fire Extinguishers | TT_Task | TK_NotStart | 2026-04-28 | 2026-06-23 | 40 | 245 | DIV 10 - Specialties | Fire Extinguishers
Baseline | F-14-300 | Fab & Deliver Car Lifts | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 14 - Conveying Systems > Car Lifts | TT_Task | TK_NotStart | 2026-04-28 | 2026-10-15 | 120 | 268 | DIV 14 - Conveying Systems | Car Lifts
Baseline | F-22-500 | Fab & Deliver Trench Drains | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Trench Drains | TT_Task | TK_NotStart | 2026-04-28 | 2026-07-22 | 60 | 234 | DIV 22 - Plumbing | Trench Drains
Baseline | F-22-600 | Fab & Deliver Water Heaters | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Heat Heaters | TT_Task | TK_NotStart | 2026-04-28 | 2026-07-22 | 60 | 167 | DIV 22 - Plumbing | Heat Heaters
Baseline | F-22-800 | Fab & Deliver Backflow Preventer | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Backflow Preventer | TT_Task | TK_NotStart | 2026-04-28 | 2026-07-22 | 60 | 356 | DIV 22 - Plumbing | Backflow Preventer
Baseline | F-27-100 | Fab & Deliver Low Voltage Panels & Devices | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 27 - Communications > Low Voltage | TT_Task | TK_NotStart | 2026-04-28 | 2026-09-02 | 90 | 179 | DIV 27 - Communications | Low Voltage
Baseline | F-28-100 | Fab & Deliver Fire Alarm Command Panel (FACP) | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 28 - Electronic Safety & Security > Fire Alarm | TT_Task | TK_NotStart | 2026-04-28 | 2026-10-15 | 120 | 244 | DIV 28 - Electronic Safety & Security | Fire Alarm
Baseline | F-28-110 | Fab & Deliver Fire Alarm Devices | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 28 - Electronic Safety & Security > Fire Alarm | TT_Task | TK_NotStart | 2026-04-28 | 2026-08-19 | 80 | 149 | DIV 28 - Electronic Safety & Security | Fire Alarm
Baseline | R-05-110 | Review & Approve Trellises | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 05 - Metals > Trelllises | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 355 | DIV 05 - Metals | Trelllises
Baseline | R-06-100 | Review & Approve Millwork (Pool Bar) | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 06 - Wood and Plastics > Millwork (Pool Bar) | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 365 | DIV 06 - Wood and Plastics | Millwork (Pool Bar)
Baseline | R-06-200 | Review & Approve Kitchen Cabinets & Vanities | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 06 - Wood and Plastics > Kitchen Cabinets & Vanities | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 49 | DIV 06 - Wood and Plastics | Kitchen Cabinets & Vanities
Baseline | R-07-100 | Review & Approve Roofing | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 07 - Thermal and Moisture Protection > Roofing | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 217 | DIV 07 - Thermal and Moisture Protection | Roofing
Baseline | R-08-400 | Review & Approve Door Hardware | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Door Hardware | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 150 | DIV 08 - Openings | Door Hardware
Baseline | R-09-600 | Review & Approve Paint | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Paint | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 111 | DIV 09 - Finishes | Paint
Baseline | R-22-300 | Review & Approve Plumbing Fixtures | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Plumbing Fixtures | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 137 | DIV 22 - Plumbing | Plumbing Fixtures
Baseline | R-22-400 | Review & Approve Grease Interceptors | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Grease Interceptors | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 149 | DIV 22 - Plumbing | Grease Interceptors
Baseline | R-22-700 | Review & Approve Boiler | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Boilers | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 342 | DIV 22 - Plumbing | Boilers
Baseline | R-23-600 | Review & Approve HVAC Controls | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > HVAC Control | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 138 | DIV 23 - HVAC | HVAC Control
Baseline | R-23-700 | Review & Approve Grilles & Diffusers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > Grilles & Diffusers | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 148 | DIV 23 - HVAC | Grilles & Diffusers
Baseline | R-26-700 | Review & Approve Site Lighting | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Site Lighting | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 393 | DIV 26 - Electrical | Site Lighting
Baseline | C-BH-100 | Install Buckhoists - 1st Lift | no |  |  | no level in the Activity ID | CONSTRUCTION > Hoisting Equipment > Buckhoists | TT_Task | TK_NotStart | 2026-05-08 | 2026-05-21 | 10 | 8 | Hoisting Equipment | Buckhoists
Baseline | F-05-110 | Fab & Deliver Trellises | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 05 - Metals > Trelllises | TT_Task | TK_NotStart | 2026-05-12 | 2026-08-05 | 60 | 355 | DIV 05 - Metals | Trelllises
Baseline | F-06-100 | Fab & Deliver Millwork (Pool Bar) | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 06 - Wood and Plastics > Millwork (Pool Bar) | TT_Task | TK_NotStart | 2026-05-12 | 2026-09-02 | 80 | 365 | DIV 06 - Wood and Plastics | Millwork (Pool Bar)
Baseline | F-06-200 | Fab & Deliver Kitchen Cabinets & Vanities | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 06 - Wood and Plastics > Kitchen Cabinets & Vanities | TT_Task | TK_NotStart | 2026-05-12 | 2026-08-19 | 70 | 49 | DIV 06 - Wood and Plastics | Kitchen Cabinets & Vanities
Baseline | F-07-100 | Fab & Deliver Roofing | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 07 - Thermal and Moisture Protection > Roofing | TT_Task | TK_NotStart | 2026-05-12 | 2026-06-23 | 30 | 217 | DIV 07 - Thermal and Moisture Protection | Roofing
Baseline | F-08-400 | Fab & Deliver Door Hardware | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Door Hardware | TT_Task | TK_NotStart | 2026-05-12 | 2026-08-19 | 70 | 150 | DIV 08 - Openings | Door Hardware
Baseline | F-22-300 | Fab & Deliver Plumbing Fixtures | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Plumbing Fixtures | TT_Task | TK_NotStart | 2026-05-12 | 2026-09-02 | 80 | 137 | DIV 22 - Plumbing | Plumbing Fixtures
Baseline | F-22-400 | Fab & Deliver Grease Interceptors | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Grease Interceptors | TT_Task | TK_NotStart | 2026-05-12 | 2026-09-02 | 80 | 149 | DIV 22 - Plumbing | Grease Interceptors
Baseline | F-22-700 | Fab & Deliver Boiler | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Boilers | TT_Task | TK_NotStart | 2026-05-12 | 2026-09-02 | 80 | 342 | DIV 22 - Plumbing | Boilers
Baseline | F-23-600 | Fab & Deliver HVAC Controls | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > HVAC Control | TT_Task | TK_NotStart | 2026-05-12 | 2026-09-02 | 80 | 138 | DIV 23 - HVAC | HVAC Control
Baseline | F-23-700 | Fab & Deliver Grilles & Diffusers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > Grilles & Diffusers | TT_Task | TK_NotStart | 2026-05-12 | 2026-08-19 | 70 | 148 | DIV 23 - HVAC | Grilles & Diffusers
Baseline | F-26-700 | Fab & Deliver Site Lighting | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Site Lighting | TT_Task | TK_NotStart | 2026-05-12 | 2026-08-05 | 60 | 393 | DIV 26 - Electrical | Site Lighting
Baseline | R-11-100 | Review & Approve Kitchen Appliances | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 11 - Equipment > Appliances | TT_Task | TK_NotStart | 2026-05-27 | 2026-06-09 | 10 | 119 | DIV 11 - Equipment | Appliances
Baseline | R-13-100 | Review & Approve Swim Spa Pool Eqp | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 13 - Special Construction > Swim Spa Pool | TT_Task | TK_NotStart | 2026-05-27 | 2026-06-09 | 10 | 181 | DIV 13 - Special Construction | Swim Spa Pool
Baseline | R-13-200 | Review & Approve Jacuzzi Eqp | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 13 - Special Construction > Jacuzzi | TT_Task | TK_NotStart | 2026-05-27 | 2026-06-09 | 10 | 336 | DIV 13 - Special Construction | Jacuzzi
Baseline | R-32-100 | Review & Approve Irrigation | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 32 - Exterior Site Improvements > Irrigation | TT_Task | TK_NotStart | 2026-05-27 | 2026-06-09 | 10 | 313 | DIV 32 - Exterior Site Improvements | Irrigation
Baseline | R-32-200 | Review & Approve Landscaping | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 32 - Exterior Site Improvements > Landscape | TT_Task | TK_NotStart | 2026-05-27 | 2026-06-09 | 10 | 340 | DIV 32 - Exterior Site Improvements | Landscape
Baseline | R-32-300 | Review & Approve Parking Signage | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 32 - Exterior Site Improvements > Parking Signage | TT_Task | TK_NotStart | 2026-05-27 | 2026-06-09 | 10 | 254 | DIV 32 - Exterior Site Improvements | Parking Signage
Baseline | F-11-100 | Fab & Deliver Kitchen Appliances | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 11 - Equipment > Appliances | TT_Task | TK_NotStart | 2026-06-10 | 2026-10-01 | 80 | 119 | DIV 11 - Equipment | Appliances
Baseline | F-13-100 | Fab & Deliver Swim Spa Pool Eqp | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 13 - Special Construction > Swim Spa Pool | TT_Task | TK_NotStart | 2026-06-10 | 2026-10-29 | 100 | 181 | DIV 13 - Special Construction | Swim Spa Pool
Baseline | F-13-200 | Fab & Deliver Jacuzzi Eqp | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 13 - Special Construction > Jacuzzi | TT_Task | TK_NotStart | 2026-06-10 | 2026-10-01 | 80 | 336 | DIV 13 - Special Construction | Jacuzzi
Baseline | F-32-100 | Fab & Deliver Irrigation | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 32 - Exterior Site Improvements > Irrigation | TT_Task | TK_NotStart | 2026-06-10 | 2026-08-05 | 40 | 313 | DIV 32 - Exterior Site Improvements | Irrigation
Baseline | F-32-200 | Procure Landscaping | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 32 - Exterior Site Improvements > Landscape | TT_Task | TK_NotStart | 2026-06-10 | 2026-09-02 | 60 | 340 | DIV 32 - Exterior Site Improvements | Landscape
Baseline | F-32-300 | Fab & Deliver Parking Signage | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 32 - Exterior Site Improvements > Parking Signage | TT_Task | TK_NotStart | 2026-06-10 | 2026-08-05 | 40 | 254 | DIV 32 - Exterior Site Improvements | Parking Signage
Baseline | C-BH-200 | Install Buckhoists - 2nd Lift | no |  |  | no level in the Activity ID | CONSTRUCTION > Hoisting Equipment > Buckhoists | TT_Task | TK_NotStart | 2026-07-08 | 2026-07-13 | 4 | 10 | Hoisting Equipment | Buckhoists
Baseline | C-SU-100 | Prep & Submit WM Drawings for Permitting | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > MOT Permitting & Setup | TT_Task | TK_NotStart | 2026-08-06 | 2026-09-02 | 20 | 176 | Site Utilities | MOT Permitting & Setup
Baseline | PMT-KL-100 | Master Permit Revision | no |  |  | no level in the Activity ID | SPECIAL DESIGN & PERMITTING > Lobby & Kitchen Design & Permit Revisions | TT_Task | TK_NotStart | 2026-08-28 | 2027-03-18 | 140 | 96 | Lobby & Kitchen Design & Permit Revisions | Lobby & Kitchen Design & Permit Revisions
Baseline | C-BH-300 | Install Buckhoists - 3rd Lift | no |  |  | no level in the Activity ID | CONSTRUCTION > Hoisting Equipment > Buckhoists | TT_Task | TK_NotStart | 2026-09-01 | 2026-09-04 | 4 | 6 | Hoisting Equipment | Buckhoists
Baseline | C-SU-110 | Pull City Permit for Water | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > MOT Permitting & Setup | TT_Task | TK_NotStart | 2026-09-03 | 2026-10-01 | 20 | 176 | Site Utilities | MOT Permitting & Setup
Baseline | C-SU-120 | Permit MOT Road Lanes Closure @ SW 11th St & 2nd Ave - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > MOT Permitting & Setup | TT_Task | TK_NotStart | 2026-09-03 | 2026-10-01 | 20 | 176 | Site Utilities | MOT Permitting & Setup
Baseline | C-BH-400 | Install Buckhoists - 4th Lift | no |  |  | no level in the Activity ID | CONSTRUCTION > Hoisting Equipment > Buckhoists | TT_Task | TK_NotStart | 2026-10-28 | 2026-11-02 | 4 | 6 | Hoisting Equipment | Buckhoists
Baseline | C-N-EX-300 | Prep Surface for Stucco at Drops @ North Elev - Parking Side L1 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at North Elevation > Exterior Stucco & Finishes at North Parking Side Elevation (L1-L7) | TT_Task | TK_NotStart | 2026-11-19 | 2026-11-24 | 4 | 61 | Exterior Envelope | Exterior Stucco & Finishes at North Parking Side Elevation (L1-L7)
Baseline | C-N-EX-310 | Apply Stucco Scratch/Brown/Finish Coats at Drops @ North Elev - Parking Side L1 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at North Elevation > Exterior Stucco & Finishes at North Parking Side Elevation (L1-L7) | TT_Task | TK_NotStart | 2026-11-25 | 2026-12-17 | 15 | 61 | Exterior Envelope | Exterior Stucco & Finishes at North Parking Side Elevation (L1-L7)
Baseline | C-N-EX-320 | Caulk Openings at Drops @ North Elev - Parking Side L1 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at North Elevation > Exterior Stucco & Finishes at North Parking Side Elevation (L1-L7) | TT_Task | TK_NotStart | 2026-12-18 | 2026-12-18 | 1 | 98 | Exterior Envelope | Exterior Stucco & Finishes at North Parking Side Elevation (L1-L7)
Baseline | C-W-EX-300 | Prep Surface for Stucco at Drops @ West Elev - Parking Side L1 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at West Elevation > Exterior Stucco & Finishes at West Parking Side Elevation (L1-L7) | TT_Task | TK_NotStart | 2026-12-18 | 2026-12-24 | 5 | 61 | Exterior Envelope | Exterior Stucco & Finishes at West Parking Side Elevation (L1-L7)
Baseline | C-W-EX-310 | Apply Stucco Scratch/Brown/Finish Coats at Drops @ West Elev - Parking Side L1 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at West Elevation > Exterior Stucco & Finishes at West Parking Side Elevation (L1-L7) | TT_Task | TK_NotStart | 2026-12-22 | 2027-01-18 | 18 | 61 | Exterior Envelope | Exterior Stucco & Finishes at West Parking Side Elevation (L1-L7)
Baseline | C-N-EX-330 | Paint Stucco at Drops @ North Elev - Parking Side L1 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at North Elevation > Exterior Stucco & Finishes at North Parking Side Elevation (L1-L7) | TT_Task | TK_NotStart | 2026-12-28 | 2027-01-05 | 6 | 94 | Exterior Envelope | Exterior Stucco & Finishes at North Parking Side Elevation (L1-L7)
Baseline | C-E-EX-300 | Prep Surface for Stucco at Drops @ East Elev - Parking Side L1 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at East Elevation > Exterior Stucco & Finishes at East Parking Side Elevation (L1-L7) | TT_Task | TK_NotStart | 2027-01-19 | 2027-01-21 | 3 | 61 | Exterior Envelope | Exterior Stucco & Finishes at East Parking Side Elevation (L1-L7)
Baseline | C-E-EX-310 | Apply Stucco Scratch/Brown/Finish Coats at Drops @ East Elev - Parking Side L1 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at East Elevation > Exterior Stucco & Finishes at East Parking Side Elevation (L1-L7) | TT_Task | TK_NotStart | 2027-01-22 | 2027-02-08 | 12 | 61 | Exterior Envelope | Exterior Stucco & Finishes at East Parking Side Elevation (L1-L7)
Baseline | C-W-EX-330 | Paint Stucco at Drops @ West Elev - Parking Side L1 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at West Elevation > Exterior Stucco & Finishes at West Parking Side Elevation (L1-L7) | TT_Task | TK_NotStart | 2027-01-26 | 2027-02-03 | 7 | 110 | Exterior Envelope | Exterior Stucco & Finishes at West Parking Side Elevation (L1-L7)
Baseline | C-BH-500 | Install Buckhoists - 5th Lift | no |  |  | no level in the Activity ID | CONSTRUCTION > Hoisting Equipment > Buckhoists | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-16 | 4 | 19 | Hoisting Equipment | Buckhoists
Baseline | C-E-EX-330 | Paint Stucco at Drops @ East Elev - Parking Side L1 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at East Elevation > Exterior Stucco & Finishes at East Parking Side Elevation (L1-L7) | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-19 | 4 | 61 | Exterior Envelope | Exterior Stucco & Finishes at East Parking Side Elevation (L1-L7)
Baseline | PR-MS-520 | Structure Top out | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2027-02-24 | 2027-02-24 | 0 | 64 | Interim Milestones | Interim Milestones
Baseline | C-N-EX-400 | Prep Surface for Stucco at Drops @ North Elev - Tower L3 to Roof | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at North Elevation > Exterior Stucco & Finishes at North Tower Elevation (L3-Roof) | TT_Task | TK_NotStart | 2027-02-25 | 2027-03-04 | 6 | 58 | Exterior Envelope | Exterior Stucco & Finishes at North Tower Elevation (L3-Roof)
Baseline | C-SU-200 | Setup MOT @ SW 11th St & 2nd Ave - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > MOT Permitting & Setup | TT_Task | TK_NotStart | 2027-02-25 | 2027-03-01 | 3 | 76 | Site Utilities | MOT Permitting & Setup
Baseline | C-SU-210 | Demo & Sawcut Exist Asphalt Pavement & Sidewalk @ SW 11th St & 2nd Ave - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > MOT Permitting & Setup | TT_Task | TK_NotStart | 2027-03-02 | 2027-03-11 | 8 | 76 | Site Utilities | MOT Permitting & Setup
Baseline | C-N-EX-410 | Apply Stucco Scratch/Brown/Finish Coats at Drops @ North Elev - Tower L3 to Roof | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at North Elevation > Exterior Stucco & Finishes at North Tower Elevation (L3-Roof) | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-30 | 20 | 58 | Exterior Envelope | Exterior Stucco & Finishes at North Tower Elevation (L3-Roof)
Baseline | C-SU-600 | Excavate for Water Piping @ East - Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-15 | 6 | 76 | Site Utilities | Water Site Utilities
Baseline | C-SU-610 | Install Water Main Crossings @ SW 11th St - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities | TT_Task | TK_NotStart | 2027-03-16 | 2027-03-25 | 8 | 76 | Site Utilities | Water Site Utilities
Baseline | MS-KL-100 | Kitchen/Lobby Permit Received | no |  |  | no level in the Activity ID | SPECIAL DESIGN & PERMITTING > Lobby & Kitchen Design & Permit Revisions | TT_FinMile | TK_NotStart | 2027-03-18 | 2027-03-18 | 0 | 96 | Lobby & Kitchen Design & Permit Revisions | Lobby & Kitchen Design & Permit Revisions
Baseline | C-RF-EX-700 | Prep Surface for Stucco @ Roof Elevations | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at Roof Levels | TT_Task | TK_NotStart | 2027-03-23 | 2027-04-01 | 8 | 33 | Exterior Envelope | Exterior Stucco & Finishes at Roof Levels
Baseline | PR-MS-530 | Temp For Test (FPL Power) | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_Task | TK_NotStart | 2027-03-25 | 2027-03-29 | 5 | 1 | Interim Milestones | Interim Milestones
Baseline | C-SU-620 | Install Water Main Crossings @ SW 2nd Ave - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities | TT_Task | TK_NotStart | 2027-03-26 | 2027-04-12 | 12 | 76 | Site Utilities | Water Site Utilities
Baseline | C-RF-EX-710 | Apply Stucco Scratch/Brown/Finish Coats @ Roof Elevations | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at Roof Levels | TT_Task | TK_NotStart | 2027-03-29 | 2027-04-16 | 15 | 33 | Exterior Envelope | Exterior Stucco & Finishes at Roof Levels
Baseline | PR-MS-540 | Permanent Power Available | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2027-03-29 | 2027-03-29 | 0 | 1 | Interim Milestones | Interim Milestones
Baseline | C-N-EX-420 | Caulk Openings at Drops @ North Elev - Tower L3 to Roof | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at North Elevation > Exterior Stucco & Finishes at North Tower Elevation (L3-Roof) | TT_Task | TK_NotStart | 2027-03-30 | 2027-04-01 | 3 | 61 | Exterior Envelope | Exterior Stucco & Finishes at North Tower Elevation (L3-Roof)
Baseline | C-N-EX-430 | Paint Stucco at Drops @ North Elev - Tower L3 to Roof | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at North Elevation > Exterior Stucco & Finishes at North Tower Elevation (L3-Roof) | TT_Task | TK_NotStart | 2027-04-07 | 2027-04-16 | 8 | 58 | Exterior Envelope | Exterior Stucco & Finishes at North Tower Elevation (L3-Roof)
Baseline | C-EV12-100 | Set Divider & Hoist Beams @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-13 | 3 | 47 | Vertical Conveying | Elevators #1 & #2
Baseline | PR-MS-510 | S.O.G Complete | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2027-04-13 | 2027-04-13 | 0 | 20 | Interim Milestones | Interim Milestones
Baseline | C-EV12-110 | Build Car Sling & Stack Rails @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-04-14 | 2027-05-04 | 15 | 47 | Vertical Conveying | Elevators #1 & #2
Baseline | C-W-EX-400 | Prep Surface for Stucco at Drops @ West Elev - Tower L7 to Roof | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at West Elevation > Exterior Stucco & Finishes at Tower Elevation (L7-Roof) | TT_Task | TK_NotStart | 2027-04-19 | 2027-04-22 | 4 | 58 | Exterior Envelope | Exterior Stucco & Finishes at Tower Elevation (L7-Roof)
Baseline | C-W-EX-410 | Apply Stucco Scratch/Brown/Finish Coats at Drops @ West Elev - Tower L7 to Roof | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at West Elevation > Exterior Stucco & Finishes at Tower Elevation (L7-Roof) | TT_Task | TK_NotStart | 2027-04-23 | 2027-05-13 | 15 | 58 | Exterior Envelope | Exterior Stucco & Finishes at Tower Elevation (L7-Roof)
Baseline | C-RF-EX-730 | Paint Stucco @ Roof Elevations | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at Roof Levels | TT_Task | TK_NotStart | 2027-04-26 | 2027-04-30 | 5 | 33 | Exterior Envelope | Exterior Stucco & Finishes at Roof Levels
Baseline | C-EV12-120 | Set Door Jambs @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-04-27 | 2027-05-10 | 10 | 47 | Vertical Conveying | Elevators #1 & #2
Baseline | C-EV12-130 | Install Door Frames & Blocking & Controllers @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-05-03 | 2027-05-21 | 15 | 47 | Vertical Conveying | Elevators #1 & #2
Baseline | C-EV12-170 | Set Elev Equipment & Mech A/C @ Machine Room -Roof Lvl | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-14 | 8 | 71 | Vertical Conveying | Elevators #1 & #2
Baseline | PR-PC-100 | Generator Test | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_Task | TK_NotStart | 2027-05-06 | 2027-05-12 | 5 | 177 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | C-W-EX-420 | Caulk Openings at Drops @ West Elev - Tower L7 to Roof | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at West Elevation > Exterior Stucco & Finishes at Tower Elevation (L7-Roof) | TT_Task | TK_NotStart | 2027-05-12 | 2027-05-18 | 5 | 60 | Exterior Envelope | Exterior Stucco & Finishes at Tower Elevation (L7-Roof)
Baseline | C-CR-300 | Remove Crane @ Tower Crane | no |  |  | no level in the Activity ID | CONSTRUCTION > Hoisting Equipment > Tower Crane | TT_Task | TK_NotStart | 2027-05-13 | 2027-05-19 | 5 | 24 | Hoisting Equipment | Tower Crane
Baseline | C-EV12-140 | Set Equipment & Drop Lines @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-05-18 | 2027-06-01 | 10 | 47 | Vertical Conveying | Elevators #1 & #2
Baseline | PR-MS-550 | Tower Crane Removed | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2027-05-19 | 2027-05-19 | 0 | 35 | Interim Milestones | Interim Milestones
Baseline | C-SU-300 | Install Sewer Lateral @ SW 11th St - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Sewer Site Utilities | TT_Task | TK_NotStart | 2027-05-20 | 2027-05-26 | 5 | 44 | Site Utilities | Sewer Site Utilities
Baseline | C-SU-400 | Install Drainage Trench Drains @ South - On-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Drainage Site Utilities | TT_Task | TK_NotStart | 2027-05-20 | 2027-06-10 | 15 | 24 | Site Utilities | Drainage Site Utilities
Baseline | C-W-EX-430 | Paint Stucco at Drops @ West Elev - Tower L7 to Roof | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at West Elevation > Exterior Stucco & Finishes at Tower Elevation (L7-Roof) | TT_Task | TK_NotStart | 2027-05-21 | 2027-05-28 | 6 | 58 | Exterior Envelope | Exterior Stucco & Finishes at Tower Elevation (L7-Roof)
Baseline | C-E-EX-400 | Prep Surface for Stucco at Drops @ East Elev | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at East Elevation > Exterior Stucco & Finishes at East Tower Elevation (L7-Roof) | TT_Task | TK_NotStart | 2027-06-01 | 2027-06-07 | 5 | 58 | Exterior Envelope | Exterior Stucco & Finishes at East Tower Elevation (L7-Roof)
Baseline | C-EV12-150 | Install Elevator Pit Equipment & Work @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-06-02 | 2027-06-08 | 5 | 47 | Vertical Conveying | Elevators #1 & #2
Baseline | C-EV12-160 | Build Cab @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-06-07 | 2027-06-18 | 10 | 47 | Vertical Conveying | Elevators #1 & #2
Baseline | C-E-EX-410 | Apply Stucco Scratch/Brown/Finish Coats at Drops @ East Elev | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at East Elevation > Exterior Stucco & Finishes at East Tower Elevation (L7-Roof) | TT_Task | TK_NotStart | 2027-06-08 | 2027-07-01 | 18 | 58 | Exterior Envelope | Exterior Stucco & Finishes at East Tower Elevation (L7-Roof)
Baseline | C-SU-410 | Install Drainage HDPE Pipes & Structures @ South - On-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Drainage Site Utilities | TT_Task | TK_NotStart | 2027-06-11 | 2027-07-01 | 15 | 39 | Site Utilities | Drainage Site Utilities
Baseline | C-SU-420 | Install Drainage Trench Drain @ East - On-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Drainage Site Utilities | TT_Task | TK_NotStart | 2027-06-11 | 2027-06-24 | 10 | 24 | Site Utilities | Drainage Site Utilities
Baseline | C-EV12-180 | Install Traveling Cable & Robe Cabs @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-06-14 | 2027-06-25 | 10 | 47 | Vertical Conveying | Elevators #1 & #2
Baseline | C-EV12-190 | Install Hoistway Wiring & Switches & Call Station & Fixtures @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-06-17 | 2027-06-30 | 10 | 47 | Vertical Conveying | Elevators #1 & #2
Baseline | C-EV34-100 | Set Divider & Hoist Beams @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-06-21 | 2027-06-23 | 3 | 64 | Vertical Conveying | Elevators #3 & #4
Baseline | C-EV34-110 | Build Car Sling & Stack Rails @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-06-24 | 2027-07-15 | 15 | 64 | Vertical Conveying | Elevators #3 & #4
Baseline | C-SU-310 | Install Sewer Manholes, Piping, & Cleanouts @ SW 2nd Ave - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Sewer Site Utilities | TT_Task | TK_NotStart | 2027-06-25 | 2027-07-16 | 15 | 24 | Site Utilities | Sewer Site Utilities
Baseline | C-E-EX-420 | Caulk Openings at Drops @ East Elev | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at East Elevation > Exterior Stucco & Finishes at East Tower Elevation (L7-Roof) | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-06 | 3 | 61 | Exterior Envelope | Exterior Stucco & Finishes at East Tower Elevation (L7-Roof)
Baseline | C-EV12-300 | Partial Fire Alarm Integration @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-08 | 5 | 47 | Vertical Conveying | Elevators #1 & #2
Baseline | C-EV34-120 | Set Door Jambs @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-07-08 | 2027-07-21 | 10 | 64 | Vertical Conveying | Elevators #3 & #4
Baseline | C-EV12-310 | Adjust & Align ELev. Doors @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-16 | 6 | 47 | Vertical Conveying | Elevators #1 & #2
Baseline | C-E-EX-430 | Paint Stucco at Drops @ East Elev | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at East Elevation > Exterior Stucco & Finishes at East Tower Elevation (L7-Roof) | TT_Task | TK_NotStart | 2027-07-12 | 2027-07-19 | 6 | 58 | Exterior Envelope | Exterior Stucco & Finishes at East Tower Elevation (L7-Roof)
Baseline | C-EV34-130 | Install Door Frames & Blocking & Controllers @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-07-14 | 2027-08-03 | 15 | 64 | Vertical Conveying | Elevators #3 & #4
Baseline | C-EV12-320 | In-House Test Elevator @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-07-19 | 2027-07-21 | 3 | 47 | Vertical Conveying | Elevators #1 & #2
Baseline | C-SU-320 | F/RP Concrete Slab at Sewer Laterals @ SW 11th St - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Sewer Site Utilities | TT_Task | TK_NotStart | 2027-07-19 | 2027-07-30 | 10 | 24 | Site Utilities | Sewer Site Utilities
Baseline | C-SU-430 | Install Drainage HDPE Pipes & Structure @ SW 11th St - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Drainage Site Utilities | TT_Task | TK_NotStart | 2027-07-19 | 2027-07-23 | 5 | 29 | Site Utilities | Drainage Site Utilities
Baseline | C-SU-500 | Install Fire Lines @ East - On-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Fire Lines | TT_Task | TK_NotStart | 2027-07-19 | 2027-07-30 | 10 | 37 | Site Utilities | Fire Lines
Baseline | PR-MS-570 | Exterior Glazing Complete | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2027-07-19 | 2027-07-19 | 0 | 21 | Interim Milestones | Interim Milestones
Baseline | C-S-EX-400 | Prep Surface for Stucco at Drops @ South Elev - Tower L1 to Roof | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at South Elevation (L1-Roof) > Exterior Stucco at South Elevation (Excl Comeback Drops) | TT_Task | TK_NotStart | 2027-07-20 | 2027-07-29 | 8 | 81 | Exterior Envelope | Exterior Stucco at South Elevation (Excl Comeback Drops)
Baseline | C-EV12-330 | Elevator Burn-in Time @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-07-22 | 2027-07-23 | 2 | 47 | Vertical Conveying | Elevators #1 & #2
Baseline | C-EV12-340 | Elevators Ready for Construction Use @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_FinMile | TK_NotStart | 2027-07-23 | 2027-07-23 | 0 | 47 | Vertical Conveying | Elevators #1 & #2
Baseline | C-BH-600 | Remove Buckhoists | no |  |  | no level in the Activity ID | CONSTRUCTION > Hoisting Equipment > Buckhoists | TT_Task | TK_NotStart | 2027-07-26 | 2027-08-13 | 15 | 47 | Hoisting Equipment | Buckhoists
Baseline | C-S-EX-410 | Apply Stucco Scratch/Brown/Finish Coats at Drops @ South Elev - Tower L1 to Roof | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at South Elevation (L1-Roof) > Exterior Stucco at South Elevation (Excl Comeback Drops) | TT_Task | TK_NotStart | 2027-07-26 | 2027-08-13 | 15 | 81 | Exterior Envelope | Exterior Stucco at South Elevation (Excl Comeback Drops)
Baseline | C-SR1-100 | Prep Concrete & CMU Surface @ East Stair #1 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Stairs > Stair #1 - East | TT_Task | TK_NotStart | 2027-07-26 | 2027-08-13 | 15 | 96 | Vertical Conveying | Stair #1 - East
Baseline | C-SU-440 | Install Drainage HDPE Pipes & Structures @ East - On-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Drainage Site Utilities | TT_Task | TK_NotStart | 2027-07-26 | 2027-08-06 | 10 | 44 | Site Utilities | Drainage Site Utilities
Baseline | C-EV34-140 | Set Equipment & Drop Lines @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-07-29 | 2027-08-11 | 10 | 64 | Vertical Conveying | Elevators #3 & #4
Baseline | PR-MS-590 | Complete Exterior Balcony Work | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2027-07-30 | 2027-07-30 | 0 | 123 | Interim Milestones | Interim Milestones
Baseline | C-N-EX-440 | Install Exterior Facade Lighting @ North Elev - Tower L3 to Roof | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at North Elevation > Exterior Stucco & Finishes at North Tower Elevation (L3-Roof) | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-13 | 10 | 89 | Exterior Envelope | Exterior Stucco & Finishes at North Tower Elevation (L3-Roof)
Baseline | C-SU-510 | Install FDCs @ East - On-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Fire Lines | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-06 | 5 | 37 | Site Utilities | Fire Lines
Baseline | C-SU-900 | Backfill & Compact Utilities @ SW 11th St & 2nd Ave - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > MOT Permitting & Setup | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-11 | 8 | 24 | Site Utilities | MOT Permitting & Setup
Baseline | C-SR1-110 | Install Guardrails & Handrails @ East Stair #1 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Stairs > Stair #1 - East | TT_Task | TK_NotStart | 2027-08-04 | 2027-08-24 | 15 | 104 | Vertical Conveying | Stair #1 - East
Baseline | PR-PC-130 | Start-up HVAC Cooling Towers & DAOUs Equipment | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_Task | TK_NotStart | 2027-08-10 | 2027-08-16 | 5 | 66 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | C-EV34-150 | Install Elevator Pit Equipment & Work @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-08-12 | 2027-08-18 | 5 | 64 | Vertical Conveying | Elevators #3 & #4
Baseline | C-SU-910 | Lay Limerock Base @ SW 11th St & 2nd Ave - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > MOT Permitting & Setup | TT_Task | TK_NotStart | 2027-08-12 | 2027-08-19 | 6 | 24 | Site Utilities | MOT Permitting & Setup
Baseline | PR-MS-580 | Buckhoists Removed | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2027-08-13 | 2027-08-13 | 0 | 68 | Interim Milestones | Interim Milestones
Baseline | C-BH1-EX-100 | Lay Exterior CMU & Balcony Edges @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Exterior Envelope at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-16 | 2027-08-18 | 3 | 47 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L2 to L7
Baseline | C-S-EX-420 | Caulk Openings at Drops @ South Elev - Tower L1 to Roof | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at South Elevation (L1-Roof) > Exterior Stucco at South Elevation (Excl Comeback Drops) | TT_Task | TK_NotStart | 2027-08-16 | 2027-08-16 | 1 | 85 | Exterior Envelope | Exterior Stucco at South Elevation (Excl Comeback Drops)
Baseline | C-SR2-100 | Prep Concrete & CMU Surface @ West Stair #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Stairs > Stair #2 - West | TT_Task | TK_NotStart | 2027-08-16 | 2027-09-03 | 15 | 96 | Vertical Conveying | Stair #2 - West
Baseline | C-W-EX-440 | Install Exterior Facade Lighting @ West Elev - Tower L7 to Roof | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at West Elevation > Exterior Stucco & Finishes at Tower Elevation (L7-Roof) | TT_Task | TK_NotStart | 2027-08-16 | 2027-08-24 | 7 | 89 | Exterior Envelope | Exterior Stucco & Finishes at Tower Elevation (L7-Roof)
Baseline | C-BH1-FN-100 | Install Remaining Drywall Framing @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Wall Framing at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-17 | 2027-08-24 | 6 | 67 | Comeback Work at Buckhoist Area Units | Wall Framing at Comeback Units at L2 to L7
Baseline | C-EV34-160 | Build Cab @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-08-17 | 2027-08-30 | 10 | 64 | Vertical Conveying | Elevators #3 & #4
Baseline | C-BH1-EX-110 | Install Exterior Glazing @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Exterior Envelope at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-20 | 3 | 47 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L2 to L7
Baseline | C-BH1-MP-100 | Install Remaining MEP Rough @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > MEP Rough at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-19 | 2027-09-01 | 10 | 67 | Comeback Work at Buckhoist Area Units | MEP Rough at Comeback Units at L2 to L7
Baseline | PR-MS-200 | Contract MS #1 (22 months): Unit Key Delivery @ L2 to L15 (08/21/27) | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Contract Milestones | TT_FinMile | TK_NotStart | 2027-08-19 | 2027-08-19 | 0 | 2 | Contract Milestones | Contract Milestones
Baseline | C-SU-920 | Temporary Resurface Exit Pavement @ SW 11th St & 2nd Ave - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > MOT Permitting & Setup | TT_Task | TK_NotStart | 2027-08-20 | 2027-08-25 | 4 | 24 | Site Utilities | MOT Permitting & Setup
Baseline | C-BH1-EX-120 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Comeback Balconies - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Exterior Envelope at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-23 | 2027-08-31 | 7 | 87 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L2 to L7
Baseline | C-BH2-EX-100 | Lay Exterior CMU & Balcony Edges @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Exterior Envelope at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-08-23 | 2027-08-26 | 4 | 47 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L8 to L15
Baseline | C-S-EX-430 | Paint Stucco at Drops @ South Elev - Tower L1 to Roof | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at South Elevation (L1-Roof) > Exterior Stucco at South Elevation (Excl Comeback Drops) | TT_Task | TK_NotStart | 2027-08-23 | 2027-09-03 | 10 | 81 | Exterior Envelope | Exterior Stucco at South Elevation (Excl Comeback Drops)
Baseline | C-BH1-FN-110 | Install Door Frames @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Wall Framing at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-24 | 2027-08-25 | 2 | 74 | Comeback Work at Buckhoist Area Units | Wall Framing at Comeback Units at L2 to L7
Baseline | C-EV34-180 | Install Traveling Cable & Robe Cabs @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-08-24 | 2027-09-07 | 10 | 64 | Vertical Conveying | Elevators #3 & #4
Baseline | C-BH2-FN-100 | Install Remaining Drywall Framing @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Wall Framing at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-08-25 | 2027-09-03 | 8 | 50 | Comeback Work at Buckhoist Area Units | Wall Framing at Comeback Units at L8 to L15
Baseline | C-E-EX-440 | Install Exterior Facade Lighting @ East Elev | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at East Elevation > Exterior Stucco & Finishes at East Tower Elevation (L7-Roof) | TT_Task | TK_NotStart | 2027-08-25 | 2027-09-01 | 6 | 89 | Exterior Envelope | Exterior Stucco & Finishes at East Tower Elevation (L7-Roof)
Baseline | C-SR1-120 | Install Stair Doors & Hardware @ East Stair #1 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Stairs > Stair #1 - East | TT_Task | TK_NotStart | 2027-08-25 | 2027-09-02 | 7 | 104 | Vertical Conveying | Stair #1 - East
Baseline | C-SR2-110 | Install Guardrails & Handrails @ West Stair #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Stairs > Stair #2 - West | TT_Task | TK_NotStart | 2027-08-25 | 2027-09-15 | 15 | 96 | Vertical Conveying | Stair #2 - West
Baseline | C-BH2-EX-110 | Install Exterior Glazing @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Exterior Envelope at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-08-26 | 2027-08-31 | 4 | 47 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L8 to L15
Baseline | C-SU-700 | Perform Flush & Pressure & Chloronation Tests @ Water | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities > Water Testing | TT_Task | TK_NotStart | 2027-08-26 | 2027-09-01 | 5 | 36 | Site Utilities | Water Testing
Baseline | C-SU-800 | Prep As-Built Submittal | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities > Conveyance Process | TT_Task | TK_NotStart | 2027-08-26 | 2027-09-23 | 20 | 24 | Site Utilities | Conveyance Process
Baseline | C-SU-930 | Remove MOT @ SW 11th St & 2nd Ave - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > MOT Permitting & Setup | TT_Task | TK_NotStart | 2027-08-26 | 2027-09-01 | 5 | 26 | Site Utilities | MOT Permitting & Setup
Baseline | C-EV34-190 | Install Hoistway Wiring & Switches & Call Station & Fixtures @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-08-27 | 2027-09-10 | 10 | 64 | Vertical Conveying | Elevators #3 & #4
Baseline | C-BH2-MP-100 | Install Remaining MEP Rough @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > MEP Rough at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-08-31 | 2027-09-16 | 12 | 50 | Comeback Work at Buckhoist Area Units | MEP Rough at Comeback Units at L8 to L15
Baseline | C-BH1-EX-130 | Apply Waterproofing & Install Tiles @ Comeback Balconies - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Exterior Envelope at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-01 | 2027-09-07 | 4 | 87 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L2 to L7
Baseline | C-BH2-EX-120 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Comeback Balconies - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Exterior Envelope at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-01 | 2027-09-13 | 8 | 81 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L8 to L15
Baseline | C-BH3-EX-100 | Lay Exterior CMU & Balcony Edges @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Exterior Envelope at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-09-01 | 2027-09-07 | 4 | 47 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L16 to L25
Baseline | C-BH3-FN-100 | Install Remaining Drywall Framing @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Wall Framing at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-09-01 | 2027-09-15 | 10 | 49 | Comeback Work at Buckhoist Area Units | Wall Framing at Comeback Units at L16 to L25
Baseline | PR-MS-560 | Complete Site Utilities Work | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2027-09-01 | 2027-09-01 | 0 | 39 | Interim Milestones | Interim Milestones
Baseline | C-BH1-MP-110 | Inspect MEP Rough @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > MEP Rough at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-02 | 2027-09-03 | 2 | 67 | Comeback Work at Buckhoist Area Units | MEP Rough at Comeback Units at L2 to L7
Baseline | C-SU-710 | Provide Pressure Test Report by WASD/City | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities > Water Testing | TT_Task | TK_NotStart | 2027-09-02 | 2027-09-09 | 5 | 36 | Site Utilities | Water Testing
Baseline | C-BH2-FN-110 | Install Door Frames @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Wall Framing at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-07 | 2 | 58 | Comeback Work at Buckhoist Area Units | Wall Framing at Comeback Units at L8 to L15
Baseline | C-SR1-130 | Install Light Fixtures & Exit Signs @ East Stair #1 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Stairs > Stair #1 - East | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-14 | 7 | 104 | Vertical Conveying | Stair #1 - East
Baseline | C-BH1-FN-200 | Install Drywall One Side @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-07 | 2027-09-13 | 5 | 67 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Baseline | C-BH3-EX-110 | Install Exterior Glazing @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Exterior Envelope at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-09-07 | 2027-09-10 | 4 | 47 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L16 to L25
Baseline | C-BH3-MP-100 | Install Remaining MEP Rough @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > MEP Rough at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-09-07 | 2027-09-27 | 15 | 49 | Comeback Work at Buckhoist Area Units | MEP Rough at Comeback Units at L16 to L25
Baseline | C-N-EX-350 | Install Exterior Decorative Metal Louvers @ North Elev - L2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at North Elevation > Exterior Stucco & Finishes at North Parking Side Elevation (L1-L7) | TT_Task | TK_NotStart | 2027-09-07 | 2027-09-09 | 3 | 81 | Exterior Envelope | Exterior Stucco & Finishes at North Parking Side Elevation (L1-L7)
Baseline | C-S-EX-440 | Install Exterior Facade Lighting @ South Elev - Tower L1 to Roof | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at South Elevation (L1-Roof) > Exterior Stucco at South Elevation (Excl Comeback Drops) | TT_Task | TK_NotStart | 2027-09-07 | 2027-09-20 | 10 | 87 | Exterior Envelope | Exterior Stucco at South Elevation (Excl Comeback Drops)
Baseline | C-S-EX-500 | Prep Surface for Stucco at Drops @ South Elev - Tower L1 to Roof (Comeback) | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at South Elevation (L1-Roof) > Exterior Stucco at South Elevation (Comeback Drops after Crane/Buckhoist Removal) | TT_Task | TK_NotStart | 2027-09-07 | 2027-09-10 | 4 | 81 | Exterior Envelope | Exterior Stucco at South Elevation (Comeback Drops after Crane/Buckhoist Removal)
Baseline | C-S-EX-510 | Apply Stucco Scratch/Brown/Finish Coats at Drops @ South Elev - Tower L1 to Roof (Comeback) | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at South Elevation (L1-Roof) > Exterior Stucco at South Elevation (Comeback Drops after Crane/Buckhoist Removal) | TT_Task | TK_NotStart | 2027-09-07 | 2027-09-22 | 12 | 81 | Exterior Envelope | Exterior Stucco at South Elevation (Comeback Drops after Crane/Buckhoist Removal)
Baseline | C-BH1-EX-140 | Paint Stucco Walls & Ceilings @ Comeback Balconies - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Exterior Envelope at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-08 | 2027-09-10 | 3 | 87 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L2 to L7
Baseline | C-E-EX-350 | Install Exterior Decorative Metal Louvers @ East Elev - L2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at East Elevation > Exterior Stucco & Finishes at East Parking Side Elevation (L1-L7) | TT_Task | TK_NotStart | 2027-09-10 | 2027-09-20 | 7 | 81 | Exterior Envelope | Exterior Stucco & Finishes at East Parking Side Elevation (L1-L7)
Baseline | C-SU-720 | Perform Bact-T Test @ Water | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities > Water Testing | TT_Task | TK_NotStart | 2027-09-10 | 2027-09-14 | 3 | 36 | Site Utilities | Water Testing
Baseline | C-BH1-EX-150 | Install Balcony Glass Railings @ Comeback Balconies - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Exterior Envelope at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-13 | 2027-09-16 | 4 | 87 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L2 to L7
Baseline | C-BH1-FN-210 | Install Drywall Insulation @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-13 | 2027-09-14 | 2 | 67 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Baseline | C-BH3-EX-120 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Comeback Balconies - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Exterior Envelope at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-09-13 | 2027-09-24 | 10 | 75 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L16 to L25
Baseline | C-BH4-EX-100 | Lay Exterior CMU & Balcony Edges @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Exterior Envelope at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-09-13 | 2027-09-16 | 4 | 47 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L26 to L35
Baseline | C-BH4-FN-100 | Install Remaining Drywall Framing @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Wall Framing at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-09-13 | 2027-09-24 | 10 | 47 | Comeback Work at Buckhoist Area Units | Wall Framing at Comeback Units at L26 to L35
Baseline | C-EV34-300 | Partial Fire Alarm Integration @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-09-13 | 2027-09-17 | 5 | 64 | Vertical Conveying | Elevators #3 & #4
Baseline | C-BH1-FN-220 | Hang Drywall @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-14 | 2027-09-17 | 4 | 67 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Baseline | C-BH2-EX-130 | Apply Waterproofing & Install Tiles @ Comeback Balconies - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Exterior Envelope at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-14 | 2027-09-20 | 5 | 81 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L8 to L15
Baseline | C-BH1-FN-230 | Frame GWB Drop Ceilings/Soffits @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-15 | 2027-09-21 | 5 | 67 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Baseline | C-BH3-FN-110 | Install Door Frames @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Wall Framing at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-09-15 | 2027-09-16 | 2 | 58 | Comeback Work at Buckhoist Area Units | Wall Framing at Comeback Units at L16 to L25
Baseline | C-SR1-140 | Install Signage @ East Stair #1 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Stairs > Stair #1 - East | TT_Task | TK_NotStart | 2027-09-15 | 2027-09-17 | 3 | 108 | Vertical Conveying | Stair #1 - East
Baseline | C-SU-730 | Prepare Force Main & Water Clearance Letter for HRS by EOR | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities > Water Testing | TT_Task | TK_NotStart | 2027-09-15 | 2027-09-21 | 5 | 36 | Site Utilities | Water Testing
Baseline | C-BH1-FN-240 | Tape & Finish Drywall @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-16 | 2027-09-21 | 4 | 75 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Baseline | C-BH4-EX-110 | Install Exterior Glazing @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Exterior Envelope at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-09-16 | 2027-09-21 | 4 | 64 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L26 to L35
Baseline | C-BH4-MP-100 | Install Remaining MEP Rough @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > MEP Rough at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-09-16 | 2027-10-06 | 15 | 47 | Comeback Work at Buckhoist Area Units | MEP Rough at Comeback Units at L26 to L35
Baseline | C-SR2-120 | Install Stair Doors & Hardware @ West Stair #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Stairs > Stair #2 - West | TT_Task | TK_NotStart | 2027-09-16 | 2027-09-24 | 7 | 96 | Vertical Conveying | Stair #2 - West
Baseline | C-BH2-MP-110 | Inspect MEP Rough @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > MEP Rough at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-17 | 2027-09-20 | 2 | 50 | Comeback Work at Buckhoist Area Units | MEP Rough at Comeback Units at L8 to L15
Baseline | C-BH2-FN-200 | Install Drywall One Side @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-20 | 2027-09-28 | 7 | 50 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Baseline | C-EV34-310 | Adjust & Align ELev. Doors @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-09-20 | 2027-09-27 | 6 | 64 | Vertical Conveying | Elevators #3 & #4
Baseline | PR-PC-110 | Commission Fire Pump | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_Task | TK_NotStart | 2027-09-20 | 2027-10-15 | 20 | 68 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | C-BH2-EX-140 | Paint Stucco Walls & Ceilings @ Comeback Balconies - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Exterior Envelope at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-21 | 2027-09-24 | 4 | 81 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L8 to L15
Baseline | C-RF-EX-750 | Install Exterior Facade Lighting @ Roof Elevations | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at Roof Levels | TT_Task | TK_NotStart | 2027-09-21 | 2027-09-29 | 7 | 87 | Exterior Envelope | Exterior Stucco & Finishes at Roof Levels
Baseline | C-S-EX-450 | Install Exterior Decorative Metal Louvers @ South Elev - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at South Elevation (L1-Roof) > Exterior Stucco at South Elevation (Excl Comeback Drops) | TT_Task | TK_NotStart | 2027-09-21 | 2027-10-12 | 16 | 81 | Exterior Envelope | Exterior Stucco at South Elevation (Excl Comeback Drops)
Baseline | C-BH1-FN-250 | Hang GWB Drop Ceilings/Soffits @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-22 | 2027-09-28 | 5 | 67 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Baseline | C-BH4-EX-120 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Comeback Balconies - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Exterior Envelope at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-09-22 | 2027-10-05 | 10 | 74 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L26 to L35
Baseline | C-SU-740 | HRS Certification & Release | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities > Water Testing | TT_Task | TK_NotStart | 2027-09-22 | 2027-10-19 | 20 | 36 | Site Utilities | Water Testing
Baseline | C-BH1-FN-260 | Tape & Finish GWB Drop Ceilings/Soffits @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-24 | 2027-09-29 | 4 | 67 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Baseline | C-BH4-FN-110 | Install Door Frames @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Wall Framing at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-09-24 | 2027-09-27 | 2 | 56 | Comeback Work at Buckhoist Area Units | Wall Framing at Comeback Units at L26 to L35
Baseline | C-SU-810 | Review & Submit Water As-Built Submittal by EOR | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities > Conveyance Process | TT_Task | TK_NotStart | 2027-09-24 | 2027-10-07 | 10 | 24 | Site Utilities | Conveyance Process
Baseline | C-BH2-EX-150 | Install Balcony Glass Railings @ Comeback Balconies - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Exterior Envelope at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-27 | 2027-10-01 | 5 | 81 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L8 to L15
Baseline | C-BH3-EX-130 | Apply Waterproofing & Install Tiles @ Comeback Balconies - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Exterior Envelope at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-09-27 | 2027-10-04 | 6 | 75 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L16 to L25
Baseline | C-SR2-130 | Install Light Fixtures & Exit Signs @ West Stair #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Stairs > Stair #2 - West | TT_Task | TK_NotStart | 2027-09-27 | 2027-10-05 | 7 | 96 | Vertical Conveying | Stair #2 - West
Baseline | C-BH2-FN-210 | Install Drywall Insulation @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-28 | 2027-09-30 | 3 | 50 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Baseline | C-BH3-MP-110 | Inspect MEP Rough @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > MEP Rough at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-09-28 | 2027-09-29 | 2 | 49 | Comeback Work at Buckhoist Area Units | MEP Rough at Comeback Units at L16 to L25
Baseline | C-EV34-320 | In-House Test Elevator @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-09-28 | 2027-09-30 | 3 | 64 | Vertical Conveying | Elevators #3 & #4
Baseline | C-BH1-FN-270 | Hang Interior Doors @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-29 | 2027-09-30 | 2 | 67 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Baseline | C-BH1-FN-280 | Paint Drywall @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-30 | 2027-10-05 | 4 | 67 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Baseline | C-BH2-FN-220 | Hang Drywall @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-30 | 2027-10-06 | 5 | 50 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Baseline | C-BH3-FN-200 | Install Drywall One Side @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-09-30 | 2027-10-08 | 7 | 49 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Baseline | C-RF-EX-760 | Install Exterior Bldg Signage @ North Elev - Roof | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at Roof Levels | TT_Task | TK_NotStart | 2027-09-30 | 2027-10-13 | 10 | 87 | Exterior Envelope | Exterior Stucco & Finishes at Roof Levels
Baseline | C-S-EX-530 | Paint Stucco at Drops @ South Elev - Tower L1 to Roof (Comeback) | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at South Elevation (L1-Roof) > Exterior Stucco at South Elevation (Comeback Drops after Crane/Buckhoist Removal) | TT_Task | TK_NotStart | 2027-09-30 | 2027-10-05 | 4 | 81 | Exterior Envelope | Exterior Stucco at South Elevation (Comeback Drops after Crane/Buckhoist Removal)
Baseline | C-BH1-FN-500 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 > Bathrooms at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-10-04 | 2027-10-11 | 6 | 67 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L2 to L7
Baseline | C-BH1-MP-200 | Install HVAC Trim & Control @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > MEP Trim at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-10-04 | 2027-10-06 | 3 | 77 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L2 to L7
Baseline | C-BH2-FN-230 | Frame GWB Drop Ceilings/Soffits @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-10-04 | 2027-10-11 | 6 | 50 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Baseline | C-BH1-MP-210 | Install FP Sprinkler Heads @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > MEP Trim at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-10-05 | 2027-10-06 | 2 | 75 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L2 to L7
Baseline | C-BH2-FN-240 | Tape & Finish Drywall @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-10-05 | 2027-10-11 | 5 | 60 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Baseline | C-BH3-EX-140 | Paint Stucco Walls & Ceilings @ Comeback Balconies - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Exterior Envelope at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-10-05 | 2027-10-11 | 5 | 75 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L16 to L25
Baseline | C-BH1-FN-300 | Install Kitchen Cabinets & Countertops @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-10-06 | 2027-10-13 | 6 | 68 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Baseline | C-BH1-FN-310 | Install Door Hardware @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-10-06 | 2027-10-07 | 2 | 77 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Baseline | C-BH1-MP-220 | Install Electrical Power Trim @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > MEP Trim at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-10-06 | 2027-10-07 | 2 | 75 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L2 to L7
Baseline | C-BH3-FN-210 | Install Drywall Insulation @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-10-06 | 2027-10-11 | 4 | 49 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Baseline | C-BH4-EX-130 | Apply Waterproofing & Install Tiles @ Comeback Balconies - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Exterior Envelope at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-10-06 | 2027-10-13 | 6 | 74 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L26 to L35
Baseline | C-S-EX-540 | Install Exterior Facade Lighting @ South Elev - Tower L1 to Roof (Comeback) | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at South Elevation (L1-Roof) > Exterior Stucco at South Elevation (Comeback Drops after Crane/Buckhoist Removal) | TT_Task | TK_NotStart | 2027-10-06 | 2027-10-12 | 5 | 81 | Exterior Envelope | Exterior Stucco at South Elevation (Comeback Drops after Crane/Buckhoist Removal)
Baseline | C-SR2-140 | Install Signage @ West Stair #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Stairs > Stair #2 - West | TT_Task | TK_NotStart | 2027-10-06 | 2027-10-12 | 5 | 96 | Vertical Conveying | Stair #2 - West
Baseline | C-BH1-MP-230 | Install Light Fixtures @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > MEP Trim at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-10-07 | 2027-10-11 | 3 | 75 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L2 to L7
Baseline | C-BH3-FN-220 | Hang Drywall @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-10-07 | 2027-10-15 | 7 | 49 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Baseline | C-BH4-MP-110 | Inspect MEP Rough @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > MEP Rough at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-10-07 | 2027-10-08 | 2 | 47 | Comeback Work at Buckhoist Area Units | MEP Rough at Comeback Units at L26 to L35
Baseline | C-BH1-MP-240 | Install FA & Low Voltage Devices @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > MEP Trim at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-10-08 | 2027-10-08 | 1 | 75 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L2 to L7
Baseline | C-SU-820 | Review & Approve Water As-Built Submittal by WASD | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities > Conveyance Process | TT_Task | TK_NotStart | 2027-10-08 | 2027-11-04 | 20 | 24 | Site Utilities | Conveyance Process
Baseline | C-BH3-FN-230 | Frame GWB Drop Ceilings/Soffits @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-10-11 | 2027-10-19 | 7 | 49 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Baseline | C-BH4-FN-200 | Install Drywall One Side @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-10-11 | 2027-10-19 | 7 | 47 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Baseline | PR-PC-190 | Stair Pressurization Test | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_Task | TK_NotStart | 2027-10-11 | 2027-10-15 | 5 | 33 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | C-BH1-FN-510 | Install Vanities & Mirrors @ B/Rs - Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 > Bathrooms at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-10-12 | 2027-10-13 | 2 | 67 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L2 to L7
Baseline | C-BH2-FN-250 | Hang GWB Drop Ceilings/Soffits @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-10-12 | 2027-10-19 | 6 | 50 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Baseline | C-BH3-EX-150 | Install Balcony Glass Railings @ Comeback Balconies - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Exterior Envelope at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-10-12 | 2027-10-19 | 6 | 75 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L16 to L25
Baseline | C-BH3-FN-240 | Tape & Finish Drywall @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-10-12 | 2027-10-19 | 6 | 55 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Baseline | C-BH3-FN-250 | Hang GWB Drop Ceilings/Soffits @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-10-13 | 2027-10-21 | 7 | 49 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Baseline | C-S-EX-550 | Install Exterior Decorative Metal Louvers @ South Elev - L2 (Comeback) | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at South Elevation (L1-Roof) > Exterior Stucco at South Elevation (Comeback Drops after Crane/Buckhoist Removal) | TT_Task | TK_NotStart | 2027-10-13 | 2027-10-21 | 7 | 81 | Exterior Envelope | Exterior Stucco at South Elevation (Comeback Drops after Crane/Buckhoist Removal)
Baseline | C-BH1-FN-320 | Install Flooring & Base @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-10-14 | 2027-10-20 | 5 | 68 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Baseline | C-BH1-FN-520 | Install Shower Enclosures @ B/Rs Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 > Bathrooms at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-10-14 | 2027-10-18 | 3 | 67 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L2 to L7
Baseline | C-BH4-EX-140 | Paint Stucco Walls & Ceilings @ Comeback Balconies - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Exterior Envelope at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-10-14 | 2027-10-20 | 5 | 74 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L26 to L35
Baseline | C-BH2-FN-260 | Tape & Finish GWB Drop Ceilings/Soffits @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-10-15 | 2027-10-21 | 5 | 50 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Baseline | C-BH3-FN-260 | Tape & Finish GWB Drop Ceilings/Soffits @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-10-15 | 2027-10-22 | 6 | 49 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Baseline | C-BH4-FN-210 | Install Drywall Insulation @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-10-15 | 2027-10-20 | 4 | 47 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Baseline | C-BH1-MP-530 | Install Plumbing Fixtures @ B/Rs - Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 > Bathrooms at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-10-18 | 2027-10-20 | 3 | 67 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L2 to L7
Baseline | C-BH4-FN-220 | Hang Drywall @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-10-18 | 2027-10-26 | 7 | 47 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Baseline | C-BH1-FN-330 | Install Kitchen Appliances @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-10-19 | 2027-10-20 | 2 | 68 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Baseline | C-BH1-FN-540 | Install Toilet Accessories @ B/Rs - Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 > Bathrooms at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-10-19 | 2027-10-20 | 2 | 67 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L2 to L7
Baseline | C-BH4-FN-230 | Frame GWB Drop Ceilings/Soffits @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-10-20 | 2027-10-28 | 7 | 47 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Baseline | C-BH1-FN-400 | Rough Cleanup @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-10-21 | 2027-10-21 | 1 | 67 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Baseline | C-BH2-FN-270 | Hang Interior Doors @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-10-21 | 2027-10-22 | 2 | 50 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Baseline | C-BH3-FN-270 | Hang Interior Doors @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-10-21 | 2027-10-25 | 3 | 49 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Baseline | C-BH4-EX-150 | Install Balcony Glass Railings @ Comeback Balconies - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Exterior Envelope at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-10-21 | 2027-10-28 | 6 | 74 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L26 to L35
Baseline | C-BH4-FN-240 | Tape & Finish Drywall @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-10-21 | 2027-10-28 | 6 | 53 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Baseline | PR-MS-300 | Contract MS #2 (24 months): Unit Key Delivery @ L16 to L25 (10/21/27) | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Contract Milestones | TT_FinMile | TK_NotStart | 2027-10-21 | 2027-10-21 | 0 | 0 | Contract Milestones | Contract Milestones
Baseline | C-BH1-PC-900 | Partial MEP Systems Inspections @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Partial Inspections & Punchout at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-10-22 | 2027-10-26 | 3 | 67 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L2 to L7
Baseline | C-BH2-FN-280 | Paint Drywall @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-10-22 | 2027-10-28 | 5 | 50 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Baseline | C-BH3-FN-280 | Paint Drywall @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-10-22 | 2027-10-29 | 6 | 49 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Baseline | C-BH4-FN-250 | Hang GWB Drop Ceilings/Soffits @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-10-22 | 2027-11-01 | 7 | 47 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Baseline | C-S-EX-560 | Install Exterior Bldg Signage @ South Elev - L2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation Stucco Finishes (Excluding Balconies) > Exterior Stucco & Finishes at South Elevation (L1-Roof) > Exterior Stucco at South Elevation (Comeback Drops after Crane/Buckhoist Removal) | TT_Task | TK_NotStart | 2027-10-22 | 2027-11-02 | 8 | 81 | Exterior Envelope | Exterior Stucco at South Elevation (Comeback Drops after Crane/Buckhoist Removal)
Baseline | C-BH3-FN-300 | Install Kitchen Cabinets & Countertops @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-10-26 | 2027-11-08 | 10 | 57 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Baseline | C-BH4-FN-260 | Tape & Finish GWB Drop Ceilings/Soffits @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-10-26 | 2027-11-02 | 6 | 47 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Baseline | C-BH1-PC-910 | Subcontractor Punch List & Punch Paint @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Partial Inspections & Punchout at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-10-27 | 2027-11-02 | 5 | 67 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L2 to L7
Baseline | C-BH2-FN-500 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 > Bathrooms at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-10-27 | 2027-11-05 | 8 | 50 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L8 to L15
Baseline | C-BH2-MP-200 | Install HVAC Trim & Control @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > MEP Trim at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-10-27 | 2027-11-01 | 4 | 63 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L8 to L15
Baseline | C-BH3-FN-500 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 > Bathrooms at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-10-27 | 2027-11-05 | 8 | 49 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L16 to L25
Baseline | C-BH3-MP-200 | Install HVAC Trim & Control @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > MEP Trim at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-10-27 | 2027-11-02 | 5 | 64 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L16 to L25
Baseline | C-BH3-MP-210 | Install FP Sprinkler Heads @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > MEP Trim at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-10-27 | 2027-11-01 | 4 | 61 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L16 to L25
Baseline | C-BH2-MP-210 | Install FP Sprinkler Heads @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > MEP Trim at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-10-28 | 2027-11-01 | 3 | 60 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L8 to L15
Baseline | C-BH3-FN-310 | Install Door Hardware @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-10-28 | 2027-11-01 | 3 | 66 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Baseline | C-BH2-FN-310 | Install Door Hardware @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-10-29 | 2027-11-01 | 2 | 64 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Baseline | C-BH3-MP-220 | Install Electrical Power Trim @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > MEP Trim at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-10-29 | 2027-11-03 | 4 | 61 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L16 to L25
Baseline | C-BH2-MP-220 | Install Electrical Power Trim @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > MEP Trim at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-11-01 | 2027-11-03 | 3 | 60 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L8 to L15
Baseline | C-BH3-FN-320 | Install Flooring & Base @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-11-01 | 2027-11-12 | 10 | 56 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Baseline | C-BH3-MP-230 | Install Light Fixtures @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > MEP Trim at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-11-01 | 2027-11-05 | 5 | 62 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L16 to L25
Baseline | C-BH4-FN-270 | Hang Interior Doors @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-11-01 | 2027-11-03 | 3 | 47 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Baseline | C-BH2-MP-230 | Install Light Fixtures @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > MEP Trim at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-11-02 | 2027-11-05 | 4 | 60 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L8 to L15
Baseline | C-BH4-FN-280 | Paint Drywall @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-11-02 | 2027-11-09 | 6 | 47 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Baseline | PR-MS-610 | Complete Exterior Elevations Work | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2027-11-02 | 2027-11-02 | 0 | 119 | Interim Milestones | Interim Milestones
Baseline | C-BH1-PC-920 | GC Punchlist @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Partial Inspections & Punchout at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-11-03 | 2027-11-09 | 5 | 67 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L2 to L7
Baseline | C-BH2-FN-300 | Install Kitchen Cabinets & Countertops @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-11-03 | 2027-11-12 | 8 | 52 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Baseline | C-BH2-MP-240 | Install FA & Low Voltage Devices @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > MEP Trim at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-11-03 | 2027-11-04 | 2 | 60 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L8 to L15
Baseline | C-BH3-MP-240 | Install FA & Low Voltage Devices @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > MEP Trim at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-11-04 | 2027-11-05 | 2 | 61 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L16 to L25
Baseline | C-BH4-FN-300 | Install Kitchen Cabinets & Countertops @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-11-04 | 2027-11-17 | 10 | 55 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Baseline | PR-PC-200 | Fire Damper Testing | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_Task | TK_NotStart | 2027-11-04 | 2027-11-17 | 10 | 10 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | C-BH4-FN-500 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 > Bathrooms at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-11-05 | 2027-11-16 | 8 | 47 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L26 to L35
Baseline | C-BH4-MP-200 | Install HVAC Trim & Control @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > MEP Trim at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-11-05 | 2027-11-11 | 5 | 62 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L26 to L35
Baseline | C-BH4-MP-210 | Install FP Sprinkler Heads @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > MEP Trim at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-11-05 | 2027-11-10 | 4 | 59 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L26 to L35
Baseline | C-SU-830 | Prepare Full Conveyance Package | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities > Conveyance Process | TT_Task | TK_NotStart | 2027-11-05 | 2027-11-18 | 10 | 24 | Site Utilities | Conveyance Process
Baseline | C-BH2-FN-320 | Install Flooring & Base @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-11-08 | 2027-11-16 | 7 | 52 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Baseline | C-BH2-FN-510 | Install Vanities & Mirrors @ B/Rs - Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 > Bathrooms at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-11-08 | 2027-11-09 | 2 | 50 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L8 to L15
Baseline | C-BH3-FN-510 | Install Vanities & Mirrors @ B/Rs - Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 > Bathrooms at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-11-08 | 2027-11-10 | 3 | 49 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L16 to L25
Baseline | C-BH4-FN-310 | Install Door Hardware @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-11-08 | 2027-11-10 | 3 | 64 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Baseline | C-SU-630 | Install Backflow Preventers @ Drop-off Area - L1 | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities | TT_Task | TK_NotStart | 2027-11-08 | 2027-11-16 | 7 | 27 | Site Utilities | Water Site Utilities
Baseline | C-BH4-MP-220 | Install Electrical Power Trim @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > MEP Trim at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-11-09 | 2027-11-12 | 4 | 59 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L26 to L35
Baseline | C-BH1-PC-930 | Final Cleanup @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Partial Inspections & Punchout at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-11-10 | 2027-11-11 | 2 | 67 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L2 to L7
Baseline | C-BH2-FN-520 | Install Shower Enclosures @ B/Rs Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 > Bathrooms at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-11-10 | 2027-11-15 | 4 | 50 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L8 to L15
Baseline | C-BH4-FN-320 | Install Flooring & Base @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-11-10 | 2027-11-23 | 10 | 54 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Baseline | C-BH4-MP-230 | Install Light Fixtures @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > MEP Trim at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-11-10 | 2027-11-16 | 5 | 60 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L26 to L35
Baseline | C-BH3-FN-330 | Install Kitchen Appliances @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-11-11 | 2027-11-15 | 3 | 56 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Baseline | C-BH3-FN-520 | Install Shower Enclosures @ B/Rs Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 > Bathrooms at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-11-11 | 2027-11-17 | 5 | 49 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L16 to L25
Baseline | PR-PC-120 | Commission Fire Alarm System (Fire Command Work) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_Task | TK_NotStart | 2027-11-11 | 2028-01-11 | 40 | 0 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | PR-PC-140 | Commission Generator | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_Task | TK_NotStart | 2027-11-11 | 2027-12-10 | 20 | 15 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | C-BH1-PC-940 | Touchup Paint @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Partial Inspections & Punchout at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-11-12 | 2027-11-15 | 2 | 67 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L2 to L7
Baseline | C-BH2-MP-530 | Install Plumbing Fixtures @ B/Rs - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 > Bathrooms at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-11-12 | 2027-11-17 | 4 | 50 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L8 to L15
Baseline | C-BH2-FN-330 | Install Kitchen Appliances @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-11-15 | 2027-11-17 | 3 | 52 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Baseline | C-BH4-MP-240 | Install FA & Low Voltage Devices @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > MEP Trim at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-11-15 | 2027-11-16 | 2 | 59 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L26 to L35
Baseline | C-BH1-PC-950 | Owner/Arch Punch List @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Partial Inspections & Punchout at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-11-16 | 2027-11-22 | 5 | 67 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L2 to L7
Baseline | C-BH2-FN-540 | Install Toilet Accessories @ B/Rs - Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 > Bathrooms at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-11-16 | 2027-11-18 | 3 | 50 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L8 to L15
Baseline | C-BH3-MP-530 | Install Plumbing Fixtures @ B/Rs - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 > Bathrooms at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-11-16 | 2027-11-22 | 5 | 49 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L16 to L25
Baseline | C-BH4-FN-510 | Install Vanities & Mirrors @ B/Rs - Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 > Bathrooms at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-11-17 | 2027-11-19 | 3 | 47 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L26 to L35
Baseline | PR-PC-210 | Fire Smoke Test | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_Task | TK_NotStart | 2027-11-18 | 2027-12-03 | 10 | 10 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | C-BH2-FN-400 | Rough Cleanup @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-11-19 | 2027-11-19 | 1 | 50 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Baseline | C-BH3-FN-540 | Install Toilet Accessories @ B/Rs - Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 > Bathrooms at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-11-19 | 2027-11-23 | 3 | 49 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L16 to L25
Baseline | C-SU-840 | Review & Approval of Full Conveyance Package by WASD | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities > Conveyance Process | TT_Task | TK_NotStart | 2027-11-19 | 2027-12-20 | 20 | 24 | Site Utilities | Conveyance Process
Baseline | C-BH2-PC-900 | Partial MEP Systems Inspections @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Partial Inspections & Punchout at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-11-22 | 2027-11-24 | 3 | 50 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L8 to L15
Baseline | C-BH4-FN-330 | Install Kitchen Appliances @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-11-22 | 2027-11-24 | 3 | 54 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Baseline | C-BH4-FN-520 | Install Shower Enclosures @ B/Rs Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 > Bathrooms at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-11-22 | 2027-11-30 | 5 | 47 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L26 to L35
Baseline | C-BH3-FN-400 | Rough Cleanup @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-11-24 | 2027-11-29 | 2 | 49 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Baseline | C-BH2-PC-910 | Subcontractor Punch List & Punch Paint @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Partial Inspections & Punchout at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-11-29 | 2027-12-03 | 5 | 50 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L8 to L15
Baseline | C-BH4-MP-530 | Install Plumbing Fixtures @ B/Rs - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 > Bathrooms at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-11-29 | 2027-12-03 | 5 | 47 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L26 to L35
Baseline | C-BH3-PC-900 | Partial MEP Systems Inspections @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Partial Inspections & Punchout at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-11-30 | 2027-12-02 | 3 | 49 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L16 to L25
Baseline | PR-MS-620 | Complete Roof Deck Work at 7th Lvl | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2027-12-01 | 2027-12-01 | 0 | 90 | Interim Milestones | Interim Milestones
Baseline | PR-MS-630 | Complete Pool & Pool Deck Work at 36th Pool Level | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2027-12-01 | 2027-12-01 | 0 | 90 | Interim Milestones | Interim Milestones
Baseline | C-BH4-FN-540 | Install Toilet Accessories @ B/Rs - Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 > Bathrooms at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-12-02 | 2027-12-06 | 3 | 47 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L26 to L35
Baseline | C-BH3-PC-910 | Subcontractor Punch List & Punch Paint @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Partial Inspections & Punchout at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-12-03 | 2027-12-09 | 5 | 49 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L16 to L25
Baseline | C-BH2-PC-920 | GC Punchlist @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Partial Inspections & Punchout at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-12-06 | 2027-12-10 | 5 | 50 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L8 to L15
Baseline | PR-PC-220 | Smoke Test Report | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_Task | TK_NotStart | 2027-12-06 | 2027-12-10 | 5 | 30 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | PR-PC-230 | Test & Balance Report | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_Task | TK_NotStart | 2027-12-06 | 2027-12-17 | 10 | 10 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | PR-PC-600 | Final Fire Suppression Inspections | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_Task | TK_NotStart | 2027-12-06 | 2027-12-15 | 8 | 52 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | C-BH4-FN-400 | Rough Cleanup @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-12-07 | 2027-12-08 | 2 | 47 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Baseline | C-BH4-PC-900 | Partial MEP Systems Inspections @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Partial Inspections & Punchout at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-12-09 | 2027-12-13 | 3 | 47 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L26 to L35
Baseline | C-BH3-PC-920 | GC Punchlist @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Partial Inspections & Punchout at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-12-10 | 2027-12-16 | 5 | 49 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L16 to L25
Baseline | C-BH2-PC-930 | Final Cleanup @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Partial Inspections & Punchout at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-12-13 | 2027-12-15 | 3 | 50 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L8 to L15
Baseline | PR-PC-150 | Elevator Transfer & Load Test (Elev #1 & #2) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_Task | TK_NotStart | 2027-12-13 | 2027-12-17 | 5 | 50 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | PR-PC-160 | Elevator Transfer & Load Test (Elev #3 & #4) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_Task | TK_NotStart | 2027-12-13 | 2027-12-17 | 5 | 15 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | C-BH4-PC-910 | Subcontractor Punch List & Punch Paint @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Partial Inspections & Punchout at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-12-14 | 2027-12-20 | 5 | 47 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L26 to L35
Baseline | C-BH2-PC-940 | Touchup Paint @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Partial Inspections & Punchout at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-12-16 | 2027-12-17 | 2 | 50 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L8 to L15
Baseline | C-BH3-PC-930 | Final Cleanup @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Partial Inspections & Punchout at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-12-17 | 2027-12-21 | 3 | 49 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L16 to L25
Baseline | C-BH2-PC-950 | Owner/Arch Punch List @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Partial Inspections & Punchout at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-12-20 | 2027-12-27 | 5 | 50 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L8 to L15
Baseline | PR-PC-240 | Test & Balance HVAC | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_Task | TK_NotStart | 2027-12-20 | 2028-01-18 | 20 | 10 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | C-BH4-PC-920 | GC Punchlist @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Partial Inspections & Punchout at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-12-21 | 2027-12-28 | 5 | 47 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L26 to L35
Baseline | C-SU-850 | Schedule & Install Water Meter @ East - Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities > Conveyance Process | TT_Task | TK_NotStart | 2027-12-21 | 2028-01-05 | 10 | 24 | Site Utilities | Conveyance Process
Baseline | PR-MS-400 | Contract MS #3 (26 months): Unit Key Delivery @ L26 to L35 (12/21/27) | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Contract Milestones | TT_FinMile | TK_NotStart | 2027-12-21 | 2027-12-21 | 0 | 0 | Contract Milestones | Contract Milestones
Baseline | C-BH3-PC-940 | Touchup Paint @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Partial Inspections & Punchout at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-12-22 | 2027-12-28 | 4 | 49 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L16 to L25
Baseline | C-BH3-PC-950 | Owner/Arch Punch List @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Partial Inspections & Punchout at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-12-29 | 2028-01-05 | 5 | 49 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L16 to L25
Baseline | C-BH4-PC-930 | Final Cleanup @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Partial Inspections & Punchout at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-12-29 | 2028-01-03 | 3 | 47 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L26 to L35
Baseline | C-BH4-PC-940 | Touchup Paint @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Partial Inspections & Punchout at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2028-01-04 | 2028-01-07 | 4 | 47 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L26 to L35
Baseline | PR-MS-600 | Complete Conveyance & Water Meter Work | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2028-01-05 | 2028-01-05 | 0 | 34 | Interim Milestones | Interim Milestones
Baseline | PR-PC-180 | Final Plumbing Inspections | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_Task | TK_NotStart | 2028-01-06 | 2028-01-26 | 15 | 24 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | C-BH4-PC-950 | Owner/Arch Punch List @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Partial Inspections & Punchout at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2028-01-10 | 2028-01-14 | 5 | 47 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L26 to L35
Baseline | PR-PC-170 | Fire Alarm Testing | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_Task | TK_NotStart | 2028-01-12 | 2028-01-25 | 10 | 0 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | PR-PC-630 | Final Mechanical Inspections | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_Task | TK_NotStart | 2028-01-19 | 2028-02-15 | 20 | 10 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | PR-PC-500 | Life Safety Testing & Commissioning Complete | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_FinMile | TK_NotStart | 2028-01-25 | 2028-01-25 | 0 | 0 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | PR-PC-610 | Final FA & Low Voltage Inspections | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_Task | TK_NotStart | 2028-01-26 | 2028-02-15 | 15 | 10 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | PR-PC-620 | Final Electrical Inspections | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_Task | TK_NotStart | 2028-01-26 | 2028-02-29 | 25 | 0 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | PR-PC-700 | Life Safety Final Complete | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_FinMile | TK_NotStart | 2028-02-15 | 2028-02-15 | 0 | 10 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | PR-PC-800 | Building Final | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_Task | TK_NotStart | 2028-03-01 | 2028-03-21 | 15 | 0 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | PR-MS-800 | Substantial Completion (T.C.O.) (03/21/28) | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Contract Milestones | TT_FinMile | TK_NotStart | 2028-03-21 | 2028-03-21 | 0 | 0 | Contract Milestones | Contract Milestones
Baseline | PR-PC-900 | Final Punchout | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_Task | TK_NotStart | 2028-03-22 | 2028-05-22 | 62 | 0 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | PR-PC-990 | Project Closeout | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT | TT_Task | TK_NotStart | 2028-03-22 | 2028-05-22 | 62 | 0 |  | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT
Baseline | PR-MS-900 | Final Completion (C.O.) (05/22/28) | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Contract Milestones | TT_FinMile | TK_NotStart | 2028-05-22 | 2028-05-22 | 0 | 0 | Contract Milestones | Contract Milestones
Phased TCO | C-02-ST-100 | Form Prestressed Elevated Slab @ L2 | yes | Structure | 2 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 2nd Lvl | TT_Task | TK_NotStart | 2026-03-24 | 2026-03-25 | 2 | 0 | Building Structure | Structure
Phased TCO | C-02-ST-110 | Rebar & PT Tendons for Elevated Slab @ L2 | yes | Structure | 2 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 2nd Lvl | TT_Task | TK_NotStart | 2026-03-25 | 2026-03-30 | 4 | 0 | Building Structure | Structure
Phased TCO | C-02-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L2 | yes | Structure | 2 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 2nd Lvl | TT_Task | TK_NotStart | 2026-03-26 | 2026-03-27 | 2 | 1 | Building Structure | Structure
Phased TCO | C-02-ST-130 | Pour Elevated Slab @ L2 | yes | Structure | 2 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 2nd Lvl | TT_Task | TK_NotStart | 2026-03-31 | 2026-03-31 | 1 | 0 | Building Structure | Structure
Phased TCO | C-02-ST-140 | F/R/P Columns & Shear Walls @ L2 | yes | Structure | 2 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 2nd Lvl | TT_Task | TK_NotStart | 2026-04-01 | 2026-04-03 | 3 | 0 | Building Structure | Structure
Phased TCO | C-02-ST-150 | Stress PT @ L2 | yes | Structure | 2 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 2nd Lvl | TT_Task | TK_NotStart | 2026-04-02 | 2026-04-02 | 1 | 6 | Building Structure | Structure
Phased TCO | C-03-ST-100 | Form Prestressed Elevated Slab @ L3 | yes | Structure | 3 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 3rd Lvl | TT_Task | TK_NotStart | 2026-04-06 | 2026-04-07 | 2 | 0 | Building Structure | Structure
Phased TCO | C-03-ST-110 | Rebar & PT Tendons for Elevated Slab @ L3 | yes | Structure | 3 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 3rd Lvl | TT_Task | TK_NotStart | 2026-04-07 | 2026-04-10 | 4 | 0 | Building Structure | Structure
Phased TCO | C-03-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L3 | yes | Structure | 3 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 3rd Lvl | TT_Task | TK_NotStart | 2026-04-08 | 2026-04-09 | 2 | 1 | Building Structure | Structure
Phased TCO | C-03-ST-130 | Pour Elevated Slab @ L3 | yes | Structure | 3 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 3rd Lvl | TT_Task | TK_NotStart | 2026-04-13 | 2026-04-13 | 1 | 0 | Building Structure | Structure
Phased TCO | C-03-ST-140 | F/R/P Columns & Shear Walls @ L3 | yes | Structure | 3 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 3rd Lvl | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-16 | 3 | 0 | Building Structure | Structure
Phased TCO | C-03-ST-150 | Stress PT @ L3 | yes | Structure | 3 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 3rd Lvl | TT_Task | TK_NotStart | 2026-04-15 | 2026-04-15 | 1 | 8 | Building Structure | Structure
Phased TCO | C-04-ST-100 | Form Prestressed Elevated Slab @ L4 | yes | Structure | 4 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 4th Lvl | TT_Task | TK_NotStart | 2026-04-17 | 2026-04-22 | 4 | 0 | Building Structure | Structure
Phased TCO | C-04-ST-110 | Rebar & PT Tendons for Elevated Slab @ L4 | yes | Structure | 4 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 4th Lvl | TT_Task | TK_NotStart | 2026-04-22 | 2026-04-27 | 4 | 0 | Building Structure | Structure
Phased TCO | C-04-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L4 | yes | Structure | 4 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 4th Lvl | TT_Task | TK_NotStart | 2026-04-23 | 2026-04-24 | 2 | 1 | Building Structure | Structure
Phased TCO | C-04-ST-130 | Pour Elevated Slab @ L4 | yes | Structure | 4 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 4th Lvl | TT_Task | TK_NotStart | 2026-04-28 | 2026-04-28 | 1 | 0 | Building Structure | Structure
Phased TCO | C-04-ST-140 | F/R/P Columns & Shear Walls @ L4 | yes | Structure | 4 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 4th Lvl | TT_Task | TK_NotStart | 2026-04-29 | 2026-05-01 | 3 | 0 | Building Structure | Structure
Phased TCO | C-04-ST-150 | Stress PT @ L4 | yes | Structure | 4 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 4th Lvl | TT_Task | TK_NotStart | 2026-04-30 | 2026-04-30 | 1 | 8 | Building Structure | Structure
Phased TCO | C-05-ST-100 | Form Prestressed Elevated Slab @ L5 | yes | Structure | 5 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 5th Lvl | TT_Task | TK_NotStart | 2026-05-04 | 2026-05-07 | 4 | 0 | Building Structure | Structure
Phased TCO | C-05-ST-110 | Rebar & PT Tendons for Elevated Slab @ L5 | yes | Structure | 5 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 5th Lvl | TT_Task | TK_NotStart | 2026-05-07 | 2026-05-12 | 4 | 0 | Building Structure | Structure
Phased TCO | C-05-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L5 | yes | Structure | 5 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 5th Lvl | TT_Task | TK_NotStart | 2026-05-08 | 2026-05-11 | 2 | 1 | Building Structure | Structure
Phased TCO | C-05-ST-130 | Pour Elevated Slab @ L5 | yes | Structure | 5 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 5th Lvl | TT_Task | TK_NotStart | 2026-05-13 | 2026-05-13 | 1 | 0 | Building Structure | Structure
Phased TCO | C-05-ST-140 | F/R/P Columns & Shear Walls @ L5 | yes | Structure | 5 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 5th Lvl | TT_Task | TK_NotStart | 2026-05-14 | 2026-05-18 | 3 | 0 | Building Structure | Structure
Phased TCO | C-05-ST-150 | Stress PT @ L5 | yes | Structure | 5 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 5th Lvl | TT_Task | TK_NotStart | 2026-05-15 | 2026-05-15 | 1 | 8 | Building Structure | Structure
Phased TCO | C-06-ST-100 | Form Prestressed Elevated Slab @ L6 | yes | Structure | 6 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 6th Lvl | TT_Task | TK_NotStart | 2026-05-19 | 2026-05-22 | 4 | 0 | Building Structure | Structure
Phased TCO | C-06-ST-110 | Rebar & PT Tendons for Elevated Slab @ L6 | yes | Structure | 6 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 6th Lvl | TT_Task | TK_NotStart | 2026-05-22 | 2026-05-28 | 4 | 0 | Building Structure | Structure
Phased TCO | C-06-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L6 | yes | Structure | 6 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 6th Lvl | TT_Task | TK_NotStart | 2026-05-26 | 2026-05-27 | 2 | 1 | Building Structure | Structure
Phased TCO | C-06-ST-130 | Pour Elevated Slab @ L6 | yes | Structure | 6 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 6th Lvl | TT_Task | TK_NotStart | 2026-05-29 | 2026-05-29 | 1 | 0 | Building Structure | Structure
Phased TCO | C-06-ST-140 | F/R/P Columns & Shear Walls @ L6 | yes | Structure | 6 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 6th Lvl | TT_Task | TK_NotStart | 2026-06-01 | 2026-06-03 | 3 | 0 | Building Structure | Structure
Phased TCO | C-06-ST-150 | Stress PT @ L6 | yes | Structure | 6 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 6th Lvl | TT_Task | TK_NotStart | 2026-06-02 | 2026-06-02 | 1 | 8 | Building Structure | Structure
Phased TCO | C-07-ST-100 | Form Prestressed Elevated Slab @ L7 | yes | Structure | 7 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 7th Lvl | TT_Task | TK_NotStart | 2026-06-04 | 2026-06-09 | 4 | 0 | Building Structure | Structure
Phased TCO | C-07-ST-110 | Rebar & PT Tendons for Elevated Slab @ L7 | yes | Structure | 7 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 7th Lvl | TT_Task | TK_NotStart | 2026-06-09 | 2026-06-12 | 4 | 0 | Building Structure | Structure
Phased TCO | C-07-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L7 | yes | Structure | 7 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 7th Lvl | TT_Task | TK_NotStart | 2026-06-10 | 2026-06-11 | 2 | 1 | Building Structure | Structure
Phased TCO | C-07-ST-130 | Pour Elevated Slab @ L7 | yes | Structure | 7 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 7th Lvl | TT_Task | TK_NotStart | 2026-06-15 | 2026-06-15 | 1 | 0 | Building Structure | Structure
Phased TCO | C-07-ST-140 | F/R/P Columns & Shear Walls @ L7 | yes | Structure | 7 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 7th Lvl | TT_Task | TK_NotStart | 2026-06-16 | 2026-06-17 | 2 | 0 | Building Structure | Structure
Phased TCO | C-07-ST-150 | Stress PT @ L7 | yes | Structure | 7 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 7th Lvl | TT_Task | TK_NotStart | 2026-06-17 | 2026-06-17 | 1 | 5 | Building Structure | Structure
Phased TCO | C-08-ST-100 | Form Prestressed Elevated Slab @ L8 | yes | Structure | 8 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 8th Lvl | TT_Task | TK_NotStart | 2026-06-18 | 2026-06-23 | 4 | 0 | Building Structure | Structure
Phased TCO | C-08-ST-110 | Rebar & PT Tendons for Elevated Slab @ L8 | yes | Structure | 8 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 8th Lvl | TT_Task | TK_NotStart | 2026-06-23 | 2026-06-24 | 2 | 0 | Building Structure | Structure
Phased TCO | C-08-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L8 | yes | Structure | 8 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 8th Lvl | TT_Task | TK_NotStart | 2026-06-24 | 2026-06-24 | 1 | 0 | Building Structure | Structure
Phased TCO | C-08-ST-130 | Pour Elevated Slab @ L8 | yes | Structure | 8 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 8th Lvl | TT_Task | TK_NotStart | 2026-06-25 | 2026-06-25 | 1 | 0 | Building Structure | Structure
Phased TCO | C-08-ST-140 | F/R/P Columns & Shear Walls @ L8 | yes | Structure | 8 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 8th Lvl | TT_Task | TK_NotStart | 2026-06-26 | 2026-06-29 | 2 | 0 | Building Structure | Structure
Phased TCO | C-08-ST-150 | Stress PT @ L8 | yes | Structure | 8 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 8th Lvl | TT_Task | TK_NotStart | 2026-06-29 | 2026-06-29 | 1 | 2 | Building Structure | Structure
Phased TCO | C-09-ST-100 | Form Prestressed Elevated Slab @ L9 | yes | Structure | 9 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 9th Lvl | TT_Task | TK_NotStart | 2026-06-29 | 2026-06-30 | 2 | 0 | Building Structure | Structure
Phased TCO | C-09-ST-110 | Rebar & PT Tendons for Elevated Slab @ L9 | yes | Structure | 9 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 9th Lvl | TT_Task | TK_NotStart | 2026-06-30 | 2026-07-01 | 2 | 0 | Building Structure | Structure
Phased TCO | C-09-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L9 | yes | Structure | 9 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 9th Lvl | TT_Task | TK_NotStart | 2026-07-01 | 2026-07-01 | 1 | 0 | Building Structure | Structure
Phased TCO | C-09-ST-130 | Pour Elevated Slab @ L9 | yes | Structure | 9 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 9th Lvl | TT_Task | TK_NotStart | 2026-07-02 | 2026-07-02 | 1 | 0 | Building Structure | Structure
Phased TCO | C-09-ST-140 | F/R/P Columns & Shear Walls @ L9 | yes | Structure | 9 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 9th Lvl | TT_Task | TK_NotStart | 2026-07-06 | 2026-07-07 | 2 | 0 | Building Structure | Structure
Phased TCO | C-09-ST-150 | Stress PT @ L9 | yes | Structure | 9 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 9th Lvl | TT_Task | TK_NotStart | 2026-07-07 | 2026-07-07 | 1 | 2 | Building Structure | Structure
Phased TCO | C-10-ST-100 | Form Prestressed Elevated Slab @ L10 | yes | Structure | 10 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 10th Lvl | TT_Task | TK_NotStart | 2026-07-07 | 2026-07-08 | 2 | 0 | Building Structure | Structure
Phased TCO | C-10-ST-110 | Rebar & PT Tendons for Elevated Slab @ L10 | yes | Structure | 10 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 10th Lvl | TT_Task | TK_NotStart | 2026-07-08 | 2026-07-09 | 2 | 0 | Building Structure | Structure
Phased TCO | C-10-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L10 | yes | Structure | 10 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 10th Lvl | TT_Task | TK_NotStart | 2026-07-09 | 2026-07-09 | 1 | 0 | Building Structure | Structure
Phased TCO | C-10-ST-130 | Pour Elevated Slab @ L10 | yes | Structure | 10 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 10th Lvl | TT_Task | TK_NotStart | 2026-07-10 | 2026-07-10 | 1 | 0 | Building Structure | Structure
Phased TCO | C-10-ST-140 | F/R/P Columns & Shear Walls @ L10 | yes | Structure | 10 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 10th Lvl | TT_Task | TK_NotStart | 2026-07-13 | 2026-07-14 | 2 | 0 | Building Structure | Structure
Phased TCO | C-10-ST-150 | Stress PT @ L10 | yes | Structure | 10 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 10th Lvl | TT_Task | TK_NotStart | 2026-07-14 | 2026-07-14 | 1 | 2 | Building Structure | Structure
Phased TCO | C-11-ST-100 | Form Prestressed Elevated Slab @ L11 | yes | Structure | 11 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 11th Lvl | TT_Task | TK_NotStart | 2026-07-14 | 2026-07-15 | 2 | 0 | Building Structure | Structure
Phased TCO | C-11-ST-110 | Rebar & PT Tendons for Elevated Slab @ L11 | yes | Structure | 11 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 11th Lvl | TT_Task | TK_NotStart | 2026-07-15 | 2026-07-16 | 2 | 0 | Building Structure | Structure
Phased TCO | C-11-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L11 | yes | Structure | 11 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 11th Lvl | TT_Task | TK_NotStart | 2026-07-16 | 2026-07-16 | 1 | 0 | Building Structure | Structure
Phased TCO | C-11-ST-130 | Pour Elevated Slab @ L11 | yes | Structure | 11 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 11th Lvl | TT_Task | TK_NotStart | 2026-07-17 | 2026-07-17 | 1 | 0 | Building Structure | Structure
Phased TCO | C-11-ST-140 | F/R/P Columns & Shear Walls @ L11 | yes | Structure | 11 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 11th Lvl | TT_Task | TK_NotStart | 2026-07-20 | 2026-07-21 | 2 | 0 | Building Structure | Structure
Phased TCO | C-11-ST-150 | Stress PT @ L11 | yes | Structure | 11 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 11th Lvl | TT_Task | TK_NotStart | 2026-07-21 | 2026-07-21 | 1 | 2 | Building Structure | Structure
Phased TCO | C-12-ST-100 | Form Prestressed Elevated Slab @ L12 | yes | Structure | 12 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 12th Lvl | TT_Task | TK_NotStart | 2026-07-21 | 2026-07-22 | 2 | 0 | Building Structure | Structure
Phased TCO | C-12-ST-110 | Rebar & PT Tendons for Elevated Slab @ L12 | yes | Structure | 12 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 12th Lvl | TT_Task | TK_NotStart | 2026-07-22 | 2026-07-23 | 2 | 0 | Building Structure | Structure
Phased TCO | C-12-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L12 | yes | Structure | 12 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 12th Lvl | TT_Task | TK_NotStart | 2026-07-23 | 2026-07-23 | 1 | 0 | Building Structure | Structure
Phased TCO | C-12-ST-130 | Pour Elevated Slab @ L12 | yes | Structure | 12 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 12th Lvl | TT_Task | TK_NotStart | 2026-07-24 | 2026-07-24 | 1 | 0 | Building Structure | Structure
Phased TCO | C-12-ST-140 | F/R/P Columns & Shear Walls @ L12 | yes | Structure | 12 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 12th Lvl | TT_Task | TK_NotStart | 2026-07-27 | 2026-07-28 | 2 | 0 | Building Structure | Structure
Phased TCO | C-12-ST-150 | Stress PT @ L12 | yes | Structure | 12 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 12th Lvl | TT_Task | TK_NotStart | 2026-07-28 | 2026-07-28 | 1 | 3 | Building Structure | Structure
Phased TCO | C-14-ST-100 | Form Prestressed Elevated Slab @ L14 | yes | Structure | 14 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 14th Lvl | TT_Task | TK_NotStart | 2026-07-29 | 2026-07-30 | 2 | 0 | Building Structure | Structure
Phased TCO | C-14-ST-110 | Rebar & PT Tendons for Elevated Slab @ L14 | yes | Structure | 14 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 14th Lvl | TT_Task | TK_NotStart | 2026-07-30 | 2026-07-31 | 2 | 0 | Building Structure | Structure
Phased TCO | C-14-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L14 | yes | Structure | 14 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 14th Lvl | TT_Task | TK_NotStart | 2026-07-31 | 2026-07-31 | 1 | 0 | Building Structure | Structure
Phased TCO | C-14-ST-130 | Pour Elevated Slab @ L14 | yes | Structure | 14 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 14th Lvl | TT_Task | TK_NotStart | 2026-08-03 | 2026-08-03 | 1 | 0 | Building Structure | Structure
Phased TCO | C-14-ST-140 | F/R/P Columns & Shear Walls @ L14 | yes | Structure | 14 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 14th Lvl | TT_Task | TK_NotStart | 2026-08-04 | 2026-08-05 | 2 | 0 | Building Structure | Structure
Phased TCO | C-14-ST-150 | Stress PT @ L14 | yes | Structure | 14 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 14th Lvl | TT_Task | TK_NotStart | 2026-08-05 | 2026-08-05 | 1 | 2 | Building Structure | Structure
Phased TCO | C-15-ST-100 | Form Prestressed Elevated Slab @ L15 | yes | Structure | 15 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 15th Lvl | TT_Task | TK_NotStart | 2026-08-05 | 2026-08-06 | 2 | 0 | Building Structure | Structure
Phased TCO | C-15-ST-110 | Rebar & PT Tendons for Elevated Slab @ L15 | yes | Structure | 15 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 15th Lvl | TT_Task | TK_NotStart | 2026-08-06 | 2026-08-07 | 2 | 0 | Building Structure | Structure
Phased TCO | C-15-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L15 | yes | Structure | 15 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 15th Lvl | TT_Task | TK_NotStart | 2026-08-07 | 2026-08-07 | 1 | 0 | Building Structure | Structure
Phased TCO | C-15-ST-130 | Pour Elevated Slab @ L15 | yes | Structure | 15 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 15th Lvl | TT_Task | TK_NotStart | 2026-08-10 | 2026-08-10 | 1 | 0 | Building Structure | Structure
Phased TCO | C-15-ST-140 | F/R/P Columns & Shear Walls @ L15 | yes | Structure | 15 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 15th Lvl | TT_Task | TK_NotStart | 2026-08-11 | 2026-08-12 | 2 | 0 | Building Structure | Structure
Phased TCO | C-15-ST-150 | Stress PT @ L15 | yes | Structure | 15 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 15th Lvl | TT_Task | TK_NotStart | 2026-08-12 | 2026-08-12 | 1 | 2 | Building Structure | Structure
Phased TCO | C-16-ST-100 | Form Prestressed Elevated Slab @ L16 | yes | Structure | 16 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 16th Lvl | TT_Task | TK_NotStart | 2026-08-12 | 2026-08-13 | 2 | 0 | Building Structure | Structure
Phased TCO | C-16-ST-110 | Rebar & PT Tendons for Elevated Slab @ L16 | yes | Structure | 16 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 16th Lvl | TT_Task | TK_NotStart | 2026-08-13 | 2026-08-14 | 2 | 0 | Building Structure | Structure
Phased TCO | C-16-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L16 | yes | Structure | 16 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 16th Lvl | TT_Task | TK_NotStart | 2026-08-14 | 2026-08-14 | 1 | 0 | Building Structure | Structure
Phased TCO | C-16-ST-130 | Pour Elevated Slab @ L16 | yes | Structure | 16 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 16th Lvl | TT_Task | TK_NotStart | 2026-08-17 | 2026-08-17 | 1 | 0 | Building Structure | Structure
Phased TCO | C-16-ST-140 | F/R/P Columns & Shear Walls @ L16 | yes | Structure | 16 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 16th Lvl | TT_Task | TK_NotStart | 2026-08-18 | 2026-08-19 | 2 | 0 | Building Structure | Structure
Phased TCO | C-16-ST-150 | Stress PT @ L16 | yes | Structure | 16 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 16th Lvl | TT_Task | TK_NotStart | 2026-08-19 | 2026-08-19 | 1 | 2 | Building Structure | Structure
Phased TCO | C-17-ST-100 | Form Prestressed Elevated Slab @ L17 | yes | Structure | 17 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 17th Lvl | TT_Task | TK_NotStart | 2026-08-19 | 2026-08-20 | 2 | 0 | Building Structure | Structure
Phased TCO | C-17-ST-110 | Rebar & PT Tendons for Elevated Slab @ L17 | yes | Structure | 17 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 17th Lvl | TT_Task | TK_NotStart | 2026-08-20 | 2026-08-21 | 2 | 0 | Building Structure | Structure
Phased TCO | C-17-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L17 | yes | Structure | 17 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 17th Lvl | TT_Task | TK_NotStart | 2026-08-21 | 2026-08-21 | 1 | 0 | Building Structure | Structure
Phased TCO | C-17-ST-130 | Pour Elevated Slab @ L17 | yes | Structure | 17 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 17th Lvl | TT_Task | TK_NotStart | 2026-08-24 | 2026-08-24 | 1 | 0 | Building Structure | Structure
Phased TCO | C-17-ST-140 | F/R/P Columns & Shear Walls @ L17 | yes | Structure | 17 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 17th Lvl | TT_Task | TK_NotStart | 2026-08-25 | 2026-08-26 | 2 | 0 | Building Structure | Structure
Phased TCO | C-17-ST-150 | Stress PT @ L17 | yes | Structure | 17 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 17th Lvl | TT_Task | TK_NotStart | 2026-08-26 | 2026-08-26 | 1 | 2 | Building Structure | Structure
Phased TCO | C-18-ST-100 | Form Prestressed Elevated Slab @ L18 | yes | Structure | 18 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 18th Lvl | TT_Task | TK_NotStart | 2026-08-26 | 2026-08-27 | 2 | 0 | Building Structure | Structure
Phased TCO | C-18-ST-110 | Rebar & PT Tendons for Elevated Slab @ L18 | yes | Structure | 18 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 18th Lvl | TT_Task | TK_NotStart | 2026-08-27 | 2026-08-28 | 2 | 0 | Building Structure | Structure
Phased TCO | C-18-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L18 | yes | Structure | 18 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 18th Lvl | TT_Task | TK_NotStart | 2026-08-28 | 2026-08-28 | 1 | 0 | Building Structure | Structure
Phased TCO | C-18-ST-130 | Pour Elevated Slab @ L18 | yes | Structure | 18 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 18th Lvl | TT_Task | TK_NotStart | 2026-08-31 | 2026-08-31 | 1 | 0 | Building Structure | Structure
Phased TCO | C-18-ST-140 | F/R/P Columns & Shear Walls @ L18 | yes | Structure | 18 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 18th Lvl | TT_Task | TK_NotStart | 2026-09-01 | 2026-09-02 | 2 | 0 | Building Structure | Structure
Phased TCO | C-18-ST-150 | Stress PT @ L18 | yes | Structure | 18 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 18th Lvl | TT_Task | TK_NotStart | 2026-09-02 | 2026-09-02 | 1 | 2 | Building Structure | Structure
Phased TCO | C-19-ST-100 | Form Prestressed Elevated Slab @ L19 | yes | Structure | 19 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 19th Lvl | TT_Task | TK_NotStart | 2026-09-02 | 2026-09-03 | 2 | 0 | Building Structure | Structure
Phased TCO | C-19-ST-110 | Rebar & PT Tendons for Elevated Slab @ L19 | yes | Structure | 19 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 19th Lvl | TT_Task | TK_NotStart | 2026-09-03 | 2026-09-04 | 2 | 0 | Building Structure | Structure
Phased TCO | C-19-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L19 | yes | Structure | 19 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 19th Lvl | TT_Task | TK_NotStart | 2026-09-04 | 2026-09-04 | 1 | 0 | Building Structure | Structure
Phased TCO | C-19-ST-130 | Pour Elevated Slab @ L19 | yes | Structure | 19 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 19th Lvl | TT_Task | TK_NotStart | 2026-09-08 | 2026-09-08 | 1 | 0 | Building Structure | Structure
Phased TCO | C-19-ST-140 | F/R/P Columns & Shear Walls @ L19 | yes | Structure | 19 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 19th Lvl | TT_Task | TK_NotStart | 2026-09-09 | 2026-09-10 | 2 | 0 | Building Structure | Structure
Phased TCO | C-19-ST-150 | Stress PT @ L19 | yes | Structure | 19 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 19th Lvl | TT_Task | TK_NotStart | 2026-09-10 | 2026-09-10 | 1 | 2 | Building Structure | Structure
Phased TCO | C-20-ST-100 | Form Prestressed Elevated Slab @ L20 | yes | Structure | 20 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 20th Lvl | TT_Task | TK_NotStart | 2026-09-10 | 2026-09-11 | 2 | 0 | Building Structure | Structure
Phased TCO | C-20-ST-110 | Rebar & PT Tendons for Elevated Slab @ L20 | yes | Structure | 20 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 20th Lvl | TT_Task | TK_NotStart | 2026-09-11 | 2026-09-14 | 2 | 0 | Building Structure | Structure
Phased TCO | C-20-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L20 | yes | Structure | 20 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 20th Lvl | TT_Task | TK_NotStart | 2026-09-14 | 2026-09-14 | 1 | 0 | Building Structure | Structure
Phased TCO | C-20-ST-130 | Pour Elevated Slab @ L20 | yes | Structure | 20 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 20th Lvl | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-15 | 1 | 0 | Building Structure | Structure
Phased TCO | C-20-ST-140 | F/R/P Columns & Shear Walls @ L20 | yes | Structure | 20 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 20th Lvl | TT_Task | TK_NotStart | 2026-09-16 | 2026-09-17 | 2 | 0 | Building Structure | Structure
Phased TCO | C-20-ST-150 | Stress PT @ L20 | yes | Structure | 20 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 20th Lvl | TT_Task | TK_NotStart | 2026-09-17 | 2026-09-17 | 1 | 2 | Building Structure | Structure
Phased TCO | C-21-ST-100 | Form Prestressed Elevated Slab @ L21 | yes | Structure | 21 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 21st Lvl | TT_Task | TK_NotStart | 2026-09-17 | 2026-09-18 | 2 | 0 | Building Structure | Structure
Phased TCO | C-21-ST-110 | Rebar & PT Tendons for Elevated Slab @ L21 | yes | Structure | 21 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 21st Lvl | TT_Task | TK_NotStart | 2026-09-18 | 2026-09-21 | 2 | 0 | Building Structure | Structure
Phased TCO | C-21-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L21 | yes | Structure | 21 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 21st Lvl | TT_Task | TK_NotStart | 2026-09-21 | 2026-09-21 | 1 | 0 | Building Structure | Structure
Phased TCO | C-21-ST-130 | Pour Elevated Slab @ L21 | yes | Structure | 21 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 21st Lvl | TT_Task | TK_NotStart | 2026-09-22 | 2026-09-22 | 1 | 0 | Building Structure | Structure
Phased TCO | C-21-ST-140 | F/R/P Columns & Shear Walls @ L21 | yes | Structure | 21 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 21st Lvl | TT_Task | TK_NotStart | 2026-09-23 | 2026-09-24 | 2 | 0 | Building Structure | Structure
Phased TCO | C-21-ST-150 | Stress PT @ L21 | yes | Structure | 21 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 21st Lvl | TT_Task | TK_NotStart | 2026-09-24 | 2026-09-24 | 1 | 2 | Building Structure | Structure
Phased TCO | C-22-ST-100 | Form Prestressed Elevated Slab @ L22 | yes | Structure | 22 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 22nd Lvl | TT_Task | TK_NotStart | 2026-09-24 | 2026-09-25 | 2 | 0 | Building Structure | Structure
Phased TCO | C-22-ST-110 | Rebar & PT Tendons for Elevated Slab @ L22 | yes | Structure | 22 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 22nd Lvl | TT_Task | TK_NotStart | 2026-09-25 | 2026-09-28 | 2 | 0 | Building Structure | Structure
Phased TCO | C-22-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L22 | yes | Structure | 22 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 22nd Lvl | TT_Task | TK_NotStart | 2026-09-28 | 2026-09-28 | 1 | 0 | Building Structure | Structure
Phased TCO | C-22-ST-130 | Pour Elevated Slab @ L22 | yes | Structure | 22 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 22nd Lvl | TT_Task | TK_NotStart | 2026-09-29 | 2026-09-29 | 1 | 0 | Building Structure | Structure
Phased TCO | C-22-ST-140 | F/R/P Columns & Shear Walls @ L22 | yes | Structure | 22 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 22nd Lvl | TT_Task | TK_NotStart | 2026-09-30 | 2026-10-01 | 2 | 0 | Building Structure | Structure
Phased TCO | C-22-ST-150 | Stress PT @ L22 | yes | Structure | 22 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 22nd Lvl | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-01 | 1 | 2 | Building Structure | Structure
Phased TCO | C-23-ST-100 | Form Prestressed Elevated Slab @ L23 | yes | Structure | 23 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 23rd Lvl | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-02 | 2 | 0 | Building Structure | Structure
Phased TCO | C-23-ST-110 | Rebar & PT Tendons for Elevated Slab @ L23 | yes | Structure | 23 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 23rd Lvl | TT_Task | TK_NotStart | 2026-10-02 | 2026-10-05 | 2 | 0 | Building Structure | Structure
Phased TCO | C-23-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L23 | yes | Structure | 23 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 23rd Lvl | TT_Task | TK_NotStart | 2026-10-05 | 2026-10-05 | 1 | 0 | Building Structure | Structure
Phased TCO | C-23-ST-130 | Pour Elevated Slab @ L23 | yes | Structure | 23 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 23rd Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-06 | 1 | 0 | Building Structure | Structure
Phased TCO | C-23-ST-140 | F/R/P Columns & Shear Walls @ L23 | yes | Structure | 23 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 23rd Lvl | TT_Task | TK_NotStart | 2026-10-07 | 2026-10-08 | 2 | 0 | Building Structure | Structure
Phased TCO | C-23-ST-150 | Stress PT @ L23 | yes | Structure | 23 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 23rd Lvl | TT_Task | TK_NotStart | 2026-10-08 | 2026-10-08 | 1 | 2 | Building Structure | Structure
Phased TCO | C-24-ST-100 | Form Prestressed Elevated Slab @ L24 | yes | Structure | 24 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 24th Lvl | TT_Task | TK_NotStart | 2026-10-08 | 2026-10-09 | 2 | 0 | Building Structure | Structure
Phased TCO | C-24-ST-110 | Rebar & PT Tendons for Elevated Slab @ L24 | yes | Structure | 24 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 24th Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-12 | 2 | 0 | Building Structure | Structure
Phased TCO | C-24-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L24 | yes | Structure | 24 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 24th Lvl | TT_Task | TK_NotStart | 2026-10-12 | 2026-10-12 | 1 | 0 | Building Structure | Structure
Phased TCO | C-24-ST-130 | Pour Elevated Slab @ L24 | yes | Structure | 24 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 24th Lvl | TT_Task | TK_NotStart | 2026-10-13 | 2026-10-13 | 1 | 0 | Building Structure | Structure
Phased TCO | C-24-ST-140 | F/R/P Columns & Shear Walls @ L24 | yes | Structure | 24 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 24th Lvl | TT_Task | TK_NotStart | 2026-10-14 | 2026-10-15 | 2 | 0 | Building Structure | Structure
Phased TCO | C-24-ST-150 | Stress PT @ L24 | yes | Structure | 24 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 24th Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-15 | 1 | 2 | Building Structure | Structure
Phased TCO | C-25-ST-100 | Form Prestressed Elevated Slab @ L25 | yes | Structure | 25 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 25th Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-16 | 2 | 0 | Building Structure | Structure
Phased TCO | C-25-ST-110 | Rebar & PT Tendons for Elevated Slab @ L25 | yes | Structure | 25 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 25th Lvl | TT_Task | TK_NotStart | 2026-10-16 | 2026-10-19 | 2 | 0 | Building Structure | Structure
Phased TCO | C-25-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L25 | yes | Structure | 25 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 25th Lvl | TT_Task | TK_NotStart | 2026-10-19 | 2026-10-19 | 1 | 0 | Building Structure | Structure
Phased TCO | C-25-ST-130 | Pour Elevated Slab @ L25 | yes | Structure | 25 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 25th Lvl | TT_Task | TK_NotStart | 2026-10-20 | 2026-10-20 | 1 | 0 | Building Structure | Structure
Phased TCO | C-25-ST-140 | F/R/P Columns & Shear Walls @ L25 | yes | Structure | 25 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 25th Lvl | TT_Task | TK_NotStart | 2026-10-21 | 2026-10-22 | 2 | 0 | Building Structure | Structure
Phased TCO | C-25-ST-150 | Stress PT @ L25 | yes | Structure | 25 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 25th Lvl | TT_Task | TK_NotStart | 2026-10-22 | 2026-10-22 | 1 | 2 | Building Structure | Structure
Phased TCO | C-26-ST-100 | Form Prestressed Elevated Slab @ L26 | yes | Structure | 26 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 26th Lvl | TT_Task | TK_NotStart | 2026-10-22 | 2026-10-23 | 2 | 0 | Building Structure | Structure
Phased TCO | C-26-ST-110 | Rebar & PT Tendons for Elevated Slab @ L26 | yes | Structure | 26 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 26th Lvl | TT_Task | TK_NotStart | 2026-10-23 | 2026-10-26 | 2 | 0 | Building Structure | Structure
Phased TCO | C-26-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L26 | yes | Structure | 26 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 26th Lvl | TT_Task | TK_NotStart | 2026-10-26 | 2026-10-26 | 1 | 0 | Building Structure | Structure
Phased TCO | C-26-ST-130 | Pour Elevated Slab @ L26 | yes | Structure | 26 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 26th Lvl | TT_Task | TK_NotStart | 2026-10-27 | 2026-10-27 | 1 | 0 | Building Structure | Structure
Phased TCO | C-26-ST-140 | F/R/P Columns & Shear Walls @ L26 | yes | Structure | 26 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 26th Lvl | TT_Task | TK_NotStart | 2026-10-28 | 2026-10-29 | 2 | 0 | Building Structure | Structure
Phased TCO | C-26-ST-150 | Stress PT @ L26 | yes | Structure | 26 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 26th Lvl | TT_Task | TK_NotStart | 2026-10-29 | 2026-10-29 | 1 | 2 | Building Structure | Structure
Phased TCO | C-27-ST-100 | Form Prestressed Elevated Slab @ L27 | yes | Structure | 27 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 27th Lvl | TT_Task | TK_NotStart | 2026-10-29 | 2026-10-30 | 2 | 0 | Building Structure | Structure
Phased TCO | C-27-ST-110 | Rebar & PT Tendons for Elevated Slab @ L27 | yes | Structure | 27 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 27th Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-02 | 2 | 0 | Building Structure | Structure
Phased TCO | C-27-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L27 | yes | Structure | 27 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 27th Lvl | TT_Task | TK_NotStart | 2026-11-02 | 2026-11-02 | 1 | 0 | Building Structure | Structure
Phased TCO | C-27-ST-130 | Pour Elevated Slab @ L27 | yes | Structure | 27 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 27th Lvl | TT_Task | TK_NotStart | 2026-11-03 | 2026-11-03 | 1 | 0 | Building Structure | Structure
Phased TCO | C-27-ST-140 | F/R/P Columns & Shear Walls @ L27 | yes | Structure | 27 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 27th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-05 | 2 | 0 | Building Structure | Structure
Phased TCO | C-27-ST-150 | Stress PT @ L27 | yes | Structure | 27 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 27th Lvl | TT_Task | TK_NotStart | 2026-11-05 | 2026-11-05 | 1 | 2 | Building Structure | Structure
Phased TCO | C-28-ST-100 | Form Prestressed Elevated Slab @ L28 | yes | Structure | 28 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 28th Lvl | TT_Task | TK_NotStart | 2026-11-05 | 2026-11-06 | 2 | 0 | Building Structure | Structure
Phased TCO | C-28-ST-110 | Rebar & PT Tendons for Elevated Slab @ L28 | yes | Structure | 28 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 28th Lvl | TT_Task | TK_NotStart | 2026-11-06 | 2026-11-09 | 2 | 0 | Building Structure | Structure
Phased TCO | C-28-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L28 | yes | Structure | 28 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 28th Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-09 | 1 | 0 | Building Structure | Structure
Phased TCO | C-28-ST-130 | Pour Elevated Slab @ L28 | yes | Structure | 28 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 28th Lvl | TT_Task | TK_NotStart | 2026-11-10 | 2026-11-10 | 1 | 0 | Building Structure | Structure
Phased TCO | C-28-ST-140 | F/R/P Columns & Shear Walls @ L28 | yes | Structure | 28 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 28th Lvl | TT_Task | TK_NotStart | 2026-11-11 | 2026-11-12 | 2 | 0 | Building Structure | Structure
Phased TCO | C-28-ST-150 | Stress PT @ L28 | yes | Structure | 28 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 28th Lvl | TT_Task | TK_NotStart | 2026-11-12 | 2026-11-12 | 1 | 2 | Building Structure | Structure
Phased TCO | C-29-ST-100 | Form Prestressed Elevated Slab @ L29 | yes | Structure | 29 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 29th Lvl | TT_Task | TK_NotStart | 2026-11-12 | 2026-11-13 | 2 | 0 | Building Structure | Structure
Phased TCO | C-29-ST-110 | Rebar & PT Tendons for Elevated Slab @ L29 | yes | Structure | 29 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 29th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-16 | 2 | 0 | Building Structure | Structure
Phased TCO | C-29-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L29 | yes | Structure | 29 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 29th Lvl | TT_Task | TK_NotStart | 2026-11-16 | 2026-11-16 | 1 | 0 | Building Structure | Structure
Phased TCO | C-29-ST-130 | Pour Elevated Slab @ L29 | yes | Structure | 29 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 29th Lvl | TT_Task | TK_NotStart | 2026-11-17 | 2026-11-17 | 1 | 0 | Building Structure | Structure
Phased TCO | C-29-ST-140 | F/R/P Columns & Shear Walls @ L29 | yes | Structure | 29 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 29th Lvl | TT_Task | TK_NotStart | 2026-11-18 | 2026-11-19 | 2 | 0 | Building Structure | Structure
Phased TCO | C-29-ST-150 | Stress PT @ L29 | yes | Structure | 29 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 29th Lvl | TT_Task | TK_NotStart | 2026-11-19 | 2026-11-19 | 1 | 2 | Building Structure | Structure
Phased TCO | C-30-ST-100 | Form Prestressed Elevated Slab @ L30 | yes | Structure | 30 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 30th Lvl | TT_Task | TK_NotStart | 2026-11-19 | 2026-11-20 | 2 | 0 | Building Structure | Structure
Phased TCO | C-30-ST-110 | Rebar & PT Tendons for Elevated Slab @ L30 | yes | Structure | 30 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 30th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-11-23 | 2 | 0 | Building Structure | Structure
Phased TCO | C-30-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L30 | yes | Structure | 30 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 30th Lvl | TT_Task | TK_NotStart | 2026-11-23 | 2026-11-23 | 1 | 0 | Building Structure | Structure
Phased TCO | C-30-ST-130 | Pour Elevated Slab @ L30 | yes | Structure | 30 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 30th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-11-24 | 1 | 0 | Building Structure | Structure
Phased TCO | C-30-ST-140 | F/R/P Columns & Shear Walls @ L30 | yes | Structure | 30 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 30th Lvl | TT_Task | TK_NotStart | 2026-11-25 | 2026-11-30 | 2 | 0 | Building Structure | Structure
Phased TCO | C-30-ST-150 | Stress PT @ L30 | yes | Structure | 30 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 30th Lvl | TT_Task | TK_NotStart | 2026-11-30 | 2026-11-30 | 1 | 2 | Building Structure | Structure
Phased TCO | C-31-ST-100 | Form Prestressed Elevated Slab @ L31 | yes | Structure | 31 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 31st Lvl | TT_Task | TK_NotStart | 2026-11-30 | 2026-12-01 | 2 | 0 | Building Structure | Structure
Phased TCO | C-31-ST-110 | Rebar & PT Tendons for Elevated Slab @ L31 | yes | Structure | 31 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 31st Lvl | TT_Task | TK_NotStart | 2026-12-01 | 2026-12-02 | 2 | 0 | Building Structure | Structure
Phased TCO | C-31-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L31 | yes | Structure | 31 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 31st Lvl | TT_Task | TK_NotStart | 2026-12-02 | 2026-12-02 | 1 | 0 | Building Structure | Structure
Phased TCO | C-31-ST-130 | Pour Elevated Slab @ L31 | yes | Structure | 31 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 31st Lvl | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-03 | 1 | 0 | Building Structure | Structure
Phased TCO | C-31-ST-140 | F/R/P Columns & Shear Walls @ L31 | yes | Structure | 31 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 31st Lvl | TT_Task | TK_NotStart | 2026-12-04 | 2026-12-07 | 2 | 0 | Building Structure | Structure
Phased TCO | C-31-ST-150 | Stress PT @ L31 | yes | Structure | 31 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 31st Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-07 | 1 | 2 | Building Structure | Structure
Phased TCO | C-32-ST-100 | Form Prestressed Elevated Slab @ L32 | yes | Structure | 32 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 32nd Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-08 | 2 | 0 | Building Structure | Structure
Phased TCO | C-32-ST-110 | Rebar & PT Tendons for Elevated Slab @ L32 | yes | Structure | 32 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 32nd Lvl | TT_Task | TK_NotStart | 2026-12-08 | 2026-12-09 | 2 | 0 | Building Structure | Structure
Phased TCO | C-32-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L32 | yes | Structure | 32 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 32nd Lvl | TT_Task | TK_NotStart | 2026-12-09 | 2026-12-09 | 1 | 0 | Building Structure | Structure
Phased TCO | C-32-ST-130 | Pour Elevated Slab @ L32 | yes | Structure | 32 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 32nd Lvl | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-10 | 1 | 0 | Building Structure | Structure
Phased TCO | C-32-ST-140 | F/R/P Columns & Shear Walls @ L32 | yes | Structure | 32 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 32nd Lvl | TT_Task | TK_NotStart | 2026-12-11 | 2026-12-14 | 2 | 0 | Building Structure | Structure
Phased TCO | C-32-ST-150 | Stress PT @ L32 | yes | Structure | 32 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 32nd Lvl | TT_Task | TK_NotStart | 2026-12-14 | 2026-12-14 | 1 | 3 | Building Structure | Structure
Phased TCO | C-33-ST-100 | Form Prestressed Elevated Slab @ L33 | yes | Structure | 33 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 33rd Lvl | TT_Task | TK_NotStart | 2026-12-14 | 2026-12-15 | 2 | 0 | Building Structure | Structure
Phased TCO | C-33-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L33 | yes | Structure | 33 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 33rd Lvl | TT_Task | TK_NotStart | 2026-12-16 | 2026-12-16 | 1 | 1 | Building Structure | Structure
Phased TCO | C-33-ST-110 | Rebar & PT Tendons for Elevated Slab @ L33 | yes | Structure | 33 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 33rd Lvl | TT_Task | TK_NotStart | 2026-12-16 | 2026-12-17 | 2 | 0 | Building Structure | Structure
Phased TCO | C-33-ST-130 | Pour Elevated Slab @ L33 | yes | Structure | 33 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 33rd Lvl | TT_Task | TK_NotStart | 2026-12-18 | 2026-12-18 | 1 | 0 | Building Structure | Structure
Phased TCO | C-33-ST-140 | F/R/P Columns & Shear Walls @ L33 | yes | Structure | 33 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 33rd Lvl | TT_Task | TK_NotStart | 2026-12-21 | 2026-12-22 | 2 | 0 | Building Structure | Structure
Phased TCO | C-33-ST-150 | Stress PT @ L33 | yes | Structure | 33 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 33rd Lvl | TT_Task | TK_NotStart | 2026-12-22 | 2026-12-22 | 1 | 3 | Building Structure | Structure
Phased TCO | C-34-ST-100 | Form Prestressed Elevated Slab @ L34 | yes | Structure | 34 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 34th Lvl | TT_Task | TK_NotStart | 2026-12-22 | 2026-12-23 | 2 | 0 | Building Structure | Structure
Phased TCO | C-34-ST-110 | Rebar & PT Tendons for Elevated Slab @ L34 | yes | Structure | 34 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 34th Lvl | TT_Task | TK_NotStart | 2026-12-24 | 2026-12-28 | 2 | 0 | Building Structure | Structure
Phased TCO | C-34-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L34 | yes | Structure | 34 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 34th Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2026-12-28 | 1 | 0 | Building Structure | Structure
Phased TCO | C-34-ST-130 | Pour Elevated Slab @ L34 | yes | Structure | 34 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 34th Lvl | TT_Task | TK_NotStart | 2026-12-29 | 2026-12-29 | 1 | 0 | Building Structure | Structure
Phased TCO | C-34-ST-140 | F/R/P Columns & Shear Walls @ L34 | yes | Structure | 34 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 34th Lvl | TT_Task | TK_NotStart | 2026-12-30 | 2026-12-31 | 2 | 0 | Building Structure | Structure
Phased TCO | C-34-ST-150 | Stress PT @ L34 | yes | Structure | 34 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 34th Lvl | TT_Task | TK_NotStart | 2026-12-31 | 2026-12-31 | 1 | 2 | Building Structure | Structure
Phased TCO | C-35-ST-100 | Form Prestressed Elevated Slab @ L35 | yes | Structure | 35 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 35th Lvl | TT_Task | TK_NotStart | 2026-12-31 | 2027-01-04 | 2 | 0 | Building Structure | Structure
Phased TCO | C-35-ST-110 | Rebar & PT Tendons for Elevated Slab @ L35 | yes | Structure | 35 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 35th Lvl | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-05 | 2 | 0 | Building Structure | Structure
Phased TCO | C-35-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ L35 | yes | Structure | 35 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 35th Lvl | TT_Task | TK_NotStart | 2027-01-05 | 2027-01-05 | 1 | 0 | Building Structure | Structure
Phased TCO | C-35-ST-130 | Pour Elevated Slab @ L35 | yes | Structure | 35 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 35th Lvl | TT_Task | TK_NotStart | 2027-01-06 | 2027-01-06 | 1 | 0 | Building Structure | Structure
Phased TCO | C-35-ST-140 | F/R/P Columns & Shear Walls @ L35 | yes | Structure | 35 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 35th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-08 | 2 | 0 | Building Structure | Structure
Phased TCO | C-35-ST-150 | Stress PT @ L35 | yes | Structure | 35 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 35th Lvl | TT_Task | TK_NotStart | 2027-01-08 | 2027-01-08 | 1 | 2 | Building Structure | Structure
Phased TCO | C-36-ST-100 | Form Pool Slab/Beams/Walls @ Low Pool (Interstitial) Lvl | yes | Structure | 36 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-01-08 | 2027-01-11 | 2 | 0 | Building Structure | Structure at Lower
Phased TCO | C-36-MP-120 | Install MEP Inserts & Sleeves at Pool Slab/Beams/Walls @ Low Pool (Interstitial) Lvl | yes | Structure | 36 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-01-11 | 2027-01-12 | 2 | 0 | Building Structure | Structure at Lower
Phased TCO | C-36-ST-110 | Rebar Pool Slab/Beams/Walls @ Low Pool (Interstitial) Lvl | yes | Structure | 36 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-01-11 | 2027-01-12 | 2 | 0 | Building Structure | Structure at Lower
Phased TCO | C-36-ST-130 | Pour Pool Slab/Beams/Walls @ Low Pool Level (Interstitial) Lvl | yes | Structure | 36 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-01-13 | 2027-01-13 | 1 | 0 | Building Structure | Structure at Lower
Phased TCO | C-36-ST-140 | Form Prestressed Elevated Slab @ 36th Pool Lvl | yes | Structure | 36 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-01-14 | 2027-01-15 | 2 | 0 | Building Structure | Structure at Lower
Phased TCO | C-36-ST-150 | Rebar & PT Tendons for Elevated Slab @ 36th Pool Lvl | yes | Structure | 36 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-01-15 | 2027-01-18 | 2 | 0 | Building Structure | Structure at Lower
Phased TCO | C-36-ST-170 | Pour Elevated Slab @ 36th Pool Lvl | yes | Structure | 36 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-01-19 | 2027-01-19 | 1 | 0 | Building Structure | Structure at Lower
Phased TCO | C-36-ST-180 | F/R/P Columns & Shear Walls @ 36th Pool Lvl | yes | Structure | 36 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-01-21 | 2 | 0 | Building Structure | Structure at Lower
Phased TCO | C-36-ST-190 | Stress PT @ 36th Pool Lvl | yes | Structure | 36 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-01-21 | 2027-01-21 | 1 | 5 | Building Structure | Structure at Lower
Phased TCO | C-37-ST-100 | Form Prestressed Elevated Slab @ Roof Lvl | yes | Structure | 37 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Roof Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-01-27 | 1 | 0 | Building Structure | Structure at Roof Lvl
Phased TCO | C-37-ST-110 | Rebar & PT Tendons for Elevated Slab @ Roof Lvl | yes | Structure | 37 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Roof Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-01-28 | 2 | 0 | Building Structure | Structure at Roof Lvl
Phased TCO | C-37-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ Roof Lvl | yes | Structure | 37 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Roof Lvl | TT_Task | TK_NotStart | 2027-01-28 | 2027-01-28 | 1 | 0 | Building Structure | Structure at Roof Lvl
Phased TCO | C-37-ST-130 | Pour Elevated Slab @ Roof Lvl | yes | Structure | 37 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Roof Lvl | TT_Task | TK_NotStart | 2027-01-29 | 2027-01-29 | 1 | 0 | Building Structure | Structure at Roof Lvl
Phased TCO | C-37-ST-140 | F/R/P Columns & Shear Wall @ Roof Lvl | yes | Structure | 37 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Roof Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-03 | 2 | 0 | Building Structure | Structure at Roof Lvl
Phased TCO | C-37-ST-150 | Stress PT @ Roof Lvl | yes | Structure | 37 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Roof Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-02 | 1 | 0 | Building Structure | Structure at Roof Lvl
Phased TCO | C-37-ST-190 | Lay Parapet Walls @ High Roof Level | yes | Structure | 37 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at High Roof Lvl | TT_Task | TK_NotStart | 2027-02-18 | 2027-02-23 | 4 | 0 | Building Structure | Structure at High Roof Lvl
Phased TCO | C-38-ST-100 | Form Prestressed Elevated Slab @ High Roof Lvl | yes | Structure | 38 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at High Roof Lvl | TT_Task | TK_NotStart | 2027-02-04 | 2027-02-04 | 1 | 0 | Building Structure | Structure at High Roof Lvl
Phased TCO | C-38-ST-110 | Rebar & PT Tendons for Elevated Slab @ High Roof Lvl | yes | Structure | 38 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at High Roof Lvl | TT_Task | TK_NotStart | 2027-02-04 | 2027-02-05 | 2 | 0 | Building Structure | Structure at High Roof Lvl
Phased TCO | C-38-MP-120 | Install MEP Inserts & Sleeves at Elevated Slab @ High Roof Lvl | yes | Structure | 38 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at High Roof Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-05 | 1 | 0 | Building Structure | Structure at High Roof Lvl
Phased TCO | C-38-ST-130 | Pour Elevated Slab @ High Roof Lvl | yes | Structure | 38 |  | CONSTRUCTION > Building Structure > Building Superstructure > Structure at High Roof Lvl | TT_Task | TK_NotStart | 2027-02-08 | 2027-02-08 | 1 | 0 | Building Structure | Structure at High Roof Lvl
Phased TCO | C-01-ST-400 | Lay Exterior & Interior CMU Walls @ L1 | yes | Envelope | 1 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-03-19 | 2027-03-29 | 7 | 0 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-01-EX-100 | Install Exterior Storefronts & Doors @ L1 | yes | Envelope | 1 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-03-30 | 2027-04-14 | 12 | 39 | Exterior Envelope | Exterior Glazing
Phased TCO | C-02-ST-400 | Lay Exterior & Interior CMU Walls & Balcony Edges @ L2 | yes | Envelope | 2 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-06-04 | 2026-06-12 | 7 | 60 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-02-EX-100 | Install Exterior Glazing @ L2 | yes | Envelope | 2 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-06-30 | 2026-07-07 | 5 | 63 | Exterior Envelope | Exterior Glazing
Phased TCO | C-03-ST-400 | Lay Exterior & Interior CMU Walls & Balcony Edges @ L3 | yes | Envelope | 3 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-06-19 | 2026-06-29 | 7 | 56 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-03-EX-100 | Install Exterior Glazing @ L3 | yes | Envelope | 3 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-07-13 | 2026-07-17 | 5 | 60 | Exterior Envelope | Exterior Glazing
Phased TCO | C-04-ST-400 | Lay Exterior & Interior CMU Walls & Balcony Edges @ L4 | yes | Envelope | 4 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-07-01 | 2026-07-10 | 7 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-04-EX-100 | Install Exterior Glazing @ L4 | yes | Envelope | 4 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-07-22 | 2026-07-28 | 5 | 58 | Exterior Envelope | Exterior Glazing
Phased TCO | C-05-ST-400 | Lay Exterior & Interior CMU Walls & Balcony Edges @ L5 | yes | Envelope | 5 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-07-13 | 2026-07-21 | 7 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-05-EX-100 | Install Exterior Glazing @ L5 | yes | Envelope | 5 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-07-31 | 2026-08-06 | 5 | 56 | Exterior Envelope | Exterior Glazing
Phased TCO | C-06-ST-400 | Lay Exterior & Interior CMU Walls & Balcony Edges @ L6 | yes | Envelope | 6 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-07-22 | 2026-07-30 | 7 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-06-EX-100 | Install Exterior Glazing @ L6 | yes | Envelope | 6 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-08-10 | 2026-08-14 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-07-ST-400 | Lay Exterior & Interior CMU Walls & Balcony Edges @ L7 | yes | Envelope | 7 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-07-31 | 2026-08-07 | 6 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-07-EX-100 | Install Exterior Glazing @ L7 | yes | Envelope | 7 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-08-17 | 2026-08-21 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-08-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L8 | yes | Envelope | 8 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-08-10 | 2026-08-14 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-08-EX-100 | Install Exterior Glazing @ L8 | yes | Envelope | 8 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-08-24 | 2026-08-28 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-09-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L9 | yes | Envelope | 9 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-08-17 | 2026-08-21 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-09-EX-100 | Install Exterior Glazing @ L9 | yes | Envelope | 9 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-08-31 | 2026-09-04 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-10-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L10 | yes | Envelope | 10 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-08-24 | 2026-08-28 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-10-EX-100 | Install Exterior Glazing @ L10 | yes | Envelope | 10 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-09-08 | 2026-09-14 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-11-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L11 | yes | Envelope | 11 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-08-31 | 2026-09-04 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-11-EX-100 | Install Exterior Glazing @ L11 | yes | Envelope | 11 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-21 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-12-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L12 | yes | Envelope | 12 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-09-08 | 2026-09-14 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-12-EX-100 | Install Exterior Glazing @ L12 | yes | Envelope | 12 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-09-22 | 2026-09-28 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-14-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L14 | yes | Envelope | 14 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-21 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-14-EX-100 | Install Exterior Glazing @ L14 | yes | Envelope | 14 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-09-29 | 2026-10-05 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-15-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L15 | yes | Envelope | 15 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-09-22 | 2026-09-28 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-15-EX-100 | Install Exterior Glazing @ L15 | yes | Envelope | 15 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-12 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-16-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L16 | yes | Envelope | 16 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-09-29 | 2026-10-05 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-16-EX-100 | Install Exterior Glazing @ L16 | yes | Envelope | 16 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-10-13 | 2026-10-19 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-17-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L17 | yes | Envelope | 17 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-12 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-17-EX-100 | Install Exterior Glazing @ L17 | yes | Envelope | 17 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-10-20 | 2026-10-26 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-18-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L18 | yes | Envelope | 18 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-10-13 | 2026-10-19 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-18-EX-100 | Install Exterior Glazing @ L18 | yes | Envelope | 18 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-10-27 | 2026-11-02 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-19-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L19 | yes | Envelope | 19 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-10-20 | 2026-10-26 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-19-EX-100 | Install Exterior Glazing @ L19 | yes | Envelope | 19 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-11-03 | 2026-11-09 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-20-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L20 | yes | Envelope | 20 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-10-27 | 2026-11-02 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-20-EX-100 | Install Exterior Glazing @ L20 | yes | Envelope | 20 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-11-10 | 2026-11-16 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-21-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L21 | yes | Envelope | 21 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-11-03 | 2026-11-09 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-21-EX-100 | Install Exterior Glazing @ L21 | yes | Envelope | 21 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-11-17 | 2026-11-23 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-22-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L22 | yes | Envelope | 22 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-11-10 | 2026-11-16 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-22-EX-100 | Install Exterior Glazing @ L22 | yes | Envelope | 22 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-11-24 | 2026-12-02 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-23-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L23 | yes | Envelope | 23 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-11-17 | 2026-11-23 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-23-EX-100 | Install Exterior Glazing @ L23 | yes | Envelope | 23 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-09 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-24-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L24 | yes | Envelope | 24 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-11-24 | 2026-12-02 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-24-EX-100 | Install Exterior Glazing @ L24 | yes | Envelope | 24 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-16 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-25-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L25 | yes | Envelope | 25 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-09 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-25-EX-100 | Install Exterior Glazing @ L25 | yes | Envelope | 25 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-12-17 | 2026-12-23 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-26-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L26 | yes | Envelope | 26 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-16 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-26-EX-100 | Install Exterior Glazing @ L26 | yes | Envelope | 26 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2026-12-24 | 2026-12-31 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-27-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L27 | yes | Envelope | 27 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-12-17 | 2026-12-23 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-27-EX-100 | Install Exterior Glazing @ L27 | yes | Envelope | 27 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-08 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-28-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L28 | yes | Envelope | 28 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2026-12-24 | 2026-12-31 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-28-EX-100 | Install Exterior Glazing @ L28 | yes | Envelope | 28 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-01-11 | 2027-01-15 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-29-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L29 | yes | Envelope | 29 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-08 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-29-EX-100 | Install Exterior Glazing @ L29 | yes | Envelope | 29 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-22 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-30-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L30 | yes | Envelope | 30 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-01-11 | 2027-01-15 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-30-EX-100 | Install Exterior Glazing @ L30 | yes | Envelope | 30 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-01-25 | 2027-01-29 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-31-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L31 | yes | Envelope | 31 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-22 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-31-EX-100 | Install Exterior Glazing @ L31 | yes | Envelope | 31 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-02-01 | 2027-02-05 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-32-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L32 | yes | Envelope | 32 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-01-25 | 2027-01-29 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-32-EX-100 | Install Exterior Glazing @ L32 | yes | Envelope | 32 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-02-08 | 2027-02-12 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-33-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L33 | yes | Envelope | 33 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-02-01 | 2027-02-05 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-33-EX-100 | Install Exterior Glazing @ L33 | yes | Envelope | 33 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-02-15 | 2027-02-19 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-34-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L34 | yes | Envelope | 34 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-02-08 | 2027-02-12 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-34-EX-100 | Install Exterior Glazing @ L34 | yes | Envelope | 34 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-02-22 | 2027-02-26 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-35-ST-400 | Lay Exterior CMU Walls & Balcony Edges @ L35 | yes | Envelope | 35 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-02-15 | 2027-02-19 | 5 | 55 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-35-EX-100 | Install Exterior Glazing @ L35 | yes | Envelope | 35 |  | CONSTRUCTION > Exterior Envelope > Exterior Glazing | TT_Task | TK_NotStart | 2027-03-01 | 2027-03-05 | 5 | 55 | Exterior Envelope | Exterior Glazing
Phased TCO | C-36-ST-400 | Lay Exterior CMU Walls @ 36th Pool Lvl | yes | Envelope | 36 |  | CONSTRUCTION > Building Structure > Exterior & Interior Masonry | TT_Task | TK_NotStart | 2027-02-22 | 2027-02-25 | 4 | 98 | Building Structure | Exterior & Interior Masonry
Phased TCO | C-01-UC-FN-100 | Layout & Install Top Tracks @ Whole L1 | yes | Framing and MEP rough-in | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior Wall Framing & MEP Rough at Whole 1st Lvl > Wall Layout & Framing at Whole 1st Lvl | TT_Task | TK_NotStart | 2027-03-30 | 2027-03-31 | 2 | 0 | Interior MEPs & Finishes | Wall Layout & Framing
Phased TCO | C-01-UC-FN-120 | Install Drywall Framing & Furring @ Whole L1 | yes | Framing and MEP rough-in | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior Wall Framing & MEP Rough at Whole 1st Lvl > Wall Layout & Framing at Whole 1st Lvl | TT_Task | TK_NotStart | 2027-03-31 | 2027-04-13 | 10 | 0 | Interior MEPs & Finishes | Wall Layout & Framing
Phased TCO | C-01-UC-MP-140 | Install Plumbing Rough @ Whole L1 | yes | Framing and MEP rough-in | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior Wall Framing & MEP Rough at Whole 1st Lvl > MEP Rough at Whole 1st Lvl | TT_Task | TK_NotStart | 2027-04-07 | 2027-04-27 | 15 | 0 | Interior MEPs & Finishes | MEP Rough
Phased TCO | C-01-UC-MP-150 | Install FP Rough @ Whole L1 | yes | Framing and MEP rough-in | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior Wall Framing & MEP Rough at Whole 1st Lvl > MEP Rough at Whole 1st Lvl | TT_Task | TK_NotStart | 2027-04-19 | 2027-04-30 | 10 | 0 | Interior MEPs & Finishes | MEP Rough
Phased TCO | C-01-UC-MP-160 | Install HVAC Ductwork @ Whole L1 | yes | Framing and MEP rough-in | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior Wall Framing & MEP Rough at Whole 1st Lvl > MEP Rough at Whole 1st Lvl | TT_Task | TK_NotStart | 2027-04-29 | 2027-05-14 | 12 | 0 | Interior MEPs & Finishes | MEP Rough
Phased TCO | C-01-UC-MP-170 | Install Electrical Rough @ Whole L1 | yes | Framing and MEP rough-in | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior Wall Framing & MEP Rough at Whole 1st Lvl > MEP Rough at Whole 1st Lvl | TT_Task | TK_NotStart | 2027-05-11 | 2027-05-24 | 10 | 0 | Interior MEPs & Finishes | MEP Rough
Phased TCO | C-01-UC-MP-180 | Install FA & Low Voltage Rough @ Whole L1 | yes | Framing and MEP rough-in | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior Wall Framing & MEP Rough at Whole 1st Lvl > MEP Rough at Whole 1st Lvl | TT_Task | TK_NotStart | 2027-05-17 | 2027-05-26 | 8 | 0 | Interior MEPs & Finishes | MEP Rough
Phased TCO | C-01-UC-MP-190 | Inspect MEP Rough @ Whole L1 | yes | Framing and MEP rough-in | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior Wall Framing & MEP Rough at Whole 1st Lvl > MEP Rough at Whole 1st Lvl | TT_Task | TK_NotStart | 2027-05-27 | 2027-05-28 | 2 | 0 | Interior MEPs & Finishes | MEP Rough
Phased TCO | C-02-UC-MP-100 | Install Plumbing Risers @ L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > MEP Risers & Rough at Units & Common Areas at 2nd Lvl > MEP Risers at 2nd Lvl | TT_Task | TK_NotStart | 2026-04-29 | 2026-04-30 | 2 | 104 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-02-UC-MP-120 | Install FP Risers @ L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > MEP Risers & Rough at Units & Common Areas at 2nd Lvl > MEP Risers at 2nd Lvl | TT_Task | TK_NotStart | 2026-05-01 | 2026-05-04 | 2 | 104 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-02-UC-MP-130 | Install Mech Risers @ L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > MEP Risers & Rough at Units & Common Areas at 2nd Lvl > MEP Risers at 2nd Lvl | TT_Task | TK_NotStart | 2026-05-05 | 2026-05-06 | 2 | 104 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-02-UC-FN-100 | Layout Interior Walls @ Units & Common Areas - L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > Wall Layout & Framing at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-06-04 | 2026-06-04 | 1 | 74 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Common Areas
Phased TCO | C-02-UC-FN-110 | Install Top Tracks @ Units & Common Areas - L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > Wall Layout & Framing at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-06-04 | 2026-06-05 | 2 | 74 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Common Areas
Phased TCO | C-02-UC-FN-120 | Install Drywall Framing @ Units & Common Areas - L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > Wall Layout & Framing at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-06-08 | 2026-06-12 | 5 | 74 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Common Areas
Phased TCO | C-02-UC-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > MEP Risers & Rough at Units & Common Areas at 2nd Lvl > MEP Risers at 2nd Lvl | TT_Task | TK_NotStart | 2026-06-08 | 2026-06-10 | 3 | 79 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-02-UC-MP-150 | Install FP Rough @ Units & Common Areas - L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > MEP Risers & Rough at Units & Common Areas at 2nd Lvl > MEP Rough at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-06-10 | 2026-06-15 | 4 | 79 | Interior MEPs & Finishes | MEP Rough at Units & Common Areas
Phased TCO | C-02-UC-MP-160 | Install HVAC Ductwork @ Units & Common Areas - L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > MEP Risers & Rough at Units & Common Areas at 2nd Lvl > MEP Rough at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-06-12 | 2026-06-18 | 5 | 79 | Interior MEPs & Finishes | MEP Rough at Units & Common Areas
Phased TCO | C-02-UC-MP-140 | Install Plumbing Rough @ Units & Common Areas - L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > MEP Risers & Rough at Units & Common Areas at 2nd Lvl > MEP Rough at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-06-15 | 2026-06-19 | 5 | 74 | Interior MEPs & Finishes | MEP Rough at Units & Common Areas
Phased TCO | C-02-UC-MP-170 | Install Electrical Rough @ Units & Common Areas - L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > MEP Risers & Rough at Units & Common Areas at 2nd Lvl > MEP Rough at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-06-18 | 2026-06-24 | 5 | 74 | Interior MEPs & Finishes | MEP Rough at Units & Common Areas
Phased TCO | C-02-UC-MP-180 | Install FA & Low Voltage Rough @ Units & Common Areas - L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > MEP Risers & Rough at Units & Common Areas at 2nd Lvl > MEP Rough at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-06-22 | 2026-06-25 | 4 | 74 | Interior MEPs & Finishes | MEP Rough at Units & Common Areas
Phased TCO | C-02-UC-MP-190 | Inspect MEP Rough @ Units & Common Areas - L2 | yes | Framing and MEP rough-in | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > MEP Risers & Rough at Units & Common Areas at 2nd Lvl > MEP Rough at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-06-26 | 2026-06-26 | 1 | 74 | Interior MEPs & Finishes | MEP Rough at Units & Common Areas
Phased TCO | C-03-U-MP-100 | Install Plumbing Risers @ L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units Corridors at 3rd Lvl > MEP Risers & Rough at Units & Corridors at 3rd Lvl > MEP Risers at 3rd Lvl | TT_Task | TK_NotStart | 2026-05-14 | 2026-05-15 | 2 | 99 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-03-U-MP-120 | Install FP Risers @ L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units Corridors at 3rd Lvl > MEP Risers & Rough at Units & Corridors at 3rd Lvl > MEP Risers at 3rd Lvl | TT_Task | TK_NotStart | 2026-05-18 | 2026-05-19 | 2 | 99 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-03-U-MP-130 | Install Mech Risers @ L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units Corridors at 3rd Lvl > MEP Risers & Rough at Units & Corridors at 3rd Lvl > MEP Risers at 3rd Lvl | TT_Task | TK_NotStart | 2026-05-20 | 2026-05-21 | 2 | 99 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-03-U-FN-100 | Layout Interior Walls @ Units & Corridors - L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units Corridors at 3rd Lvl > Wall Layout & Framing at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-06-19 | 2026-06-19 | 1 | 69 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-03-U-FN-110 | Install Top Tracks @ Units & Corridors - L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units Corridors at 3rd Lvl > Wall Layout & Framing at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-06-19 | 2026-06-22 | 2 | 69 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-03-U-FN-120 | Install Drywall Framing @ Units & Corridors - L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units Corridors at 3rd Lvl > Wall Layout & Framing at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-06-23 | 2026-06-29 | 5 | 69 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-03-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units Corridors at 3rd Lvl > MEP Risers & Rough at Units & Corridors at 3rd Lvl > MEP Risers at 3rd Lvl | TT_Task | TK_NotStart | 2026-06-23 | 2026-06-25 | 3 | 74 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-03-U-MP-150 | Install FP Rough @ Units & Corridors - L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units Corridors at 3rd Lvl > MEP Risers & Rough at Units & Corridors at 3rd Lvl > MEP Rough at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-06-25 | 2026-06-30 | 4 | 74 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-03-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units Corridors at 3rd Lvl > MEP Risers & Rough at Units & Corridors at 3rd Lvl > MEP Rough at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-06-29 | 2026-07-06 | 5 | 74 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-03-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units Corridors at 3rd Lvl > MEP Risers & Rough at Units & Corridors at 3rd Lvl > MEP Rough at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-06-30 | 2026-07-07 | 5 | 69 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-03-U-MP-170 | Install Electrical Rough @ Units & Corridors - L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units Corridors at 3rd Lvl > MEP Risers & Rough at Units & Corridors at 3rd Lvl > MEP Rough at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-07-06 | 2026-07-10 | 5 | 69 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-03-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units Corridors at 3rd Lvl > MEP Risers & Rough at Units & Corridors at 3rd Lvl > MEP Rough at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-07-08 | 2026-07-13 | 4 | 69 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-03-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L3 | yes | Framing and MEP rough-in | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units Corridors at 3rd Lvl > MEP Risers & Rough at Units & Corridors at 3rd Lvl > MEP Rough at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-07-14 | 2026-07-14 | 1 | 69 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-04-U-MP-100 | Install Plumbing Risers @ L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > MEP Risers & Rough at Units & Corridors at 4th Lvl > MEP Risers at 4th Lvl | TT_Task | TK_NotStart | 2026-06-01 | 2026-06-02 | 2 | 94 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-04-U-MP-120 | Install FP Risers @ L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > MEP Risers & Rough at Units & Corridors at 4th Lvl > MEP Risers at 4th Lvl | TT_Task | TK_NotStart | 2026-06-03 | 2026-06-04 | 2 | 94 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-04-U-MP-130 | Install Mech Risers @ L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > MEP Risers & Rough at Units & Corridors at 4th Lvl > MEP Risers at 4th Lvl | TT_Task | TK_NotStart | 2026-06-05 | 2026-06-08 | 2 | 94 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-04-U-FN-100 | Layout Interior Walls @ Units & Corridors - L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > Wall Layout & Framing at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-07-01 | 2026-07-01 | 1 | 67 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-04-U-FN-110 | Install Top Tracks @ Units & Corridors - L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > Wall Layout & Framing at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-07-01 | 2026-07-02 | 2 | 67 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-04-U-FN-120 | Install Drywall Framing @ Units & Corridors - L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > Wall Layout & Framing at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-07-06 | 2026-07-10 | 5 | 67 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-04-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > MEP Risers & Rough at Units & Corridors at 4th Lvl > MEP Risers at 4th Lvl | TT_Task | TK_NotStart | 2026-07-06 | 2026-07-08 | 3 | 72 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-04-U-MP-150 | Install FP Rough @ Units & Corridors - L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > MEP Risers & Rough at Units & Corridors at 4th Lvl > MEP Rough at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-07-08 | 2026-07-13 | 4 | 72 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-04-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > MEP Risers & Rough at Units & Corridors at 4th Lvl > MEP Rough at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-07-10 | 2026-07-16 | 5 | 72 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-04-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > MEP Risers & Rough at Units & Corridors at 4th Lvl > MEP Rough at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-07-13 | 2026-07-17 | 5 | 67 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-04-U-MP-170 | Install Electrical Rough @ Units & Corridors - L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > MEP Risers & Rough at Units & Corridors at 4th Lvl > MEP Rough at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-07-16 | 2026-07-22 | 5 | 67 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-04-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > MEP Risers & Rough at Units & Corridors at 4th Lvl > MEP Rough at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-07-20 | 2026-07-23 | 4 | 67 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-04-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L4 | yes | Framing and MEP rough-in | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > MEP Risers & Rough at Units & Corridors at 4th Lvl > MEP Rough at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-07-24 | 2026-07-24 | 1 | 67 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-05-U-MP-100 | Install Plumbing Risers @ L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > MEP Risers & Rough at Units & Corridors at 5th Lvl > MEP Risers at 5th Lvl | TT_Task | TK_NotStart | 2026-06-16 | 2026-06-17 | 2 | 89 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-05-U-MP-120 | Install FP Risers @ L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > MEP Risers & Rough at Units & Corridors at 5th Lvl > MEP Risers at 5th Lvl | TT_Task | TK_NotStart | 2026-06-18 | 2026-06-19 | 2 | 89 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-05-U-MP-130 | Install Mech Risers @ L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > MEP Risers & Rough at Units & Corridors at 5th Lvl > MEP Risers at 5th Lvl | TT_Task | TK_NotStart | 2026-06-22 | 2026-06-23 | 2 | 89 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-05-U-FN-100 | Layout Interior Walls @ Units & Corridors - L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > Wall Layout & Framing at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-07-09 | 2026-07-09 | 1 | 68 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-05-U-FN-110 | Install Top Tracks @ Units & Corridors - L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > Wall Layout & Framing at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-07-09 | 2026-07-10 | 2 | 68 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-05-U-FN-120 | Install Drywall Framing @ Units & Corridors - L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > Wall Layout & Framing at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-07-13 | 2026-07-17 | 5 | 68 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-05-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > MEP Risers & Rough at Units & Corridors at 5th Lvl > MEP Risers at 5th Lvl | TT_Task | TK_NotStart | 2026-07-13 | 2026-07-15 | 3 | 73 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-05-U-MP-150 | Install FP Rough @ Units & Corridors - L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > MEP Risers & Rough at Units & Corridors at 5th Lvl > MEP Rough at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-07-15 | 2026-07-20 | 4 | 73 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-05-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > MEP Risers & Rough at Units & Corridors at 5th Lvl > MEP Rough at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-07-17 | 2026-07-23 | 5 | 73 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-05-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > MEP Risers & Rough at Units & Corridors at 5th Lvl > MEP Rough at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-07-20 | 2026-07-24 | 5 | 68 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-05-U-MP-170 | Install Electrical Rough @ Units & Corridors - L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > MEP Risers & Rough at Units & Corridors at 5th Lvl > MEP Rough at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-07-23 | 2026-07-29 | 5 | 68 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-05-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > MEP Risers & Rough at Units & Corridors at 5th Lvl > MEP Rough at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-07-27 | 2026-07-30 | 4 | 68 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-05-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L5 | yes | Framing and MEP rough-in | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > MEP Risers & Rough at Units & Corridors at 5th Lvl > MEP Rough at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-07-31 | 2026-07-31 | 1 | 68 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-06-U-MP-100 | Install Plumbing Risers @ L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > MEP Risers & Rough at Units & Corridors at 6th Lvl > MEP Risers at 6th Lvl | TT_Task | TK_NotStart | 2026-06-26 | 2026-06-29 | 2 | 89 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-06-U-MP-120 | Install FP Risers @ L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > MEP Risers & Rough at Units & Corridors at 6th Lvl > MEP Risers at 6th Lvl | TT_Task | TK_NotStart | 2026-06-30 | 2026-07-01 | 2 | 89 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-06-U-MP-130 | Install Mech Risers @ L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > MEP Risers & Rough at Units & Corridors at 6th Lvl > MEP Risers at 6th Lvl | TT_Task | TK_NotStart | 2026-07-02 | 2026-07-06 | 2 | 89 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-06-U-FN-100 | Layout Interior Walls @ Units & Corridors - L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > Wall Layout & Framing at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-07-16 | 2026-07-16 | 1 | 69 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-06-U-FN-110 | Install Top Tracks @ Units & Corridors - L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > Wall Layout & Framing at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-07-16 | 2026-07-17 | 2 | 69 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-06-U-FN-120 | Install Drywall Framing @ Units & Corridors - L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > Wall Layout & Framing at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-07-20 | 2026-07-24 | 5 | 69 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-06-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > MEP Risers & Rough at Units & Corridors at 6th Lvl > MEP Risers at 6th Lvl | TT_Task | TK_NotStart | 2026-07-20 | 2026-07-22 | 3 | 76 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-06-U-MP-150 | Install FP Rough @ Units & Corridors - L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > MEP Risers & Rough at Units & Corridors at 6th Lvl > MEP Rough at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-07-22 | 2026-07-27 | 4 | 76 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-06-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > MEP Risers & Rough at Units & Corridors at 6th Lvl > MEP Rough at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-07-24 | 2026-07-30 | 5 | 76 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-06-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > MEP Risers & Rough at Units & Corridors at 6th Lvl > MEP Rough at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-07-27 | 2026-07-31 | 5 | 71 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-06-U-MP-170 | Install Electrical Rough @ Units & Corridors - L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > MEP Risers & Rough at Units & Corridors at 6th Lvl > MEP Rough at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-07-30 | 2026-08-05 | 5 | 71 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-06-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > MEP Risers & Rough at Units & Corridors at 6th Lvl > MEP Rough at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-08-03 | 2026-08-06 | 4 | 71 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-06-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L6 | yes | Framing and MEP rough-in | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > MEP Risers & Rough at Units & Corridors at 6th Lvl > MEP Rough at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-08-07 | 2026-08-07 | 1 | 71 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-07-U-MP-100 | Install Plumbing Risers @ L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > MEP Risers & Rough at Units & Corridors at 7th Lvl > MEP Risers at 7th Lvl | TT_Task | TK_NotStart | 2026-07-06 | 2026-07-07 | 2 | 87 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-07-U-MP-120 | Install FP Risers @ L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > MEP Risers & Rough at Units & Corridors at 7th Lvl > MEP Risers at 7th Lvl | TT_Task | TK_NotStart | 2026-07-08 | 2026-07-09 | 2 | 87 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-07-U-MP-130 | Install Mech Risers @ L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > MEP Risers & Rough at Units & Corridors at 7th Lvl > MEP Risers at 7th Lvl | TT_Task | TK_NotStart | 2026-07-10 | 2026-07-13 | 2 | 88 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-07-U-FN-100 | Layout Interior Walls @ Units & Corridors - L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > Wall Layout & Framing at Units & Corridors at 7th Lvl | TT_Task | TK_NotStart | 2026-07-23 | 2026-07-23 | 1 | 69 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-07-U-FN-110 | Install Top Tracks @ Units & Corridors - L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > Wall Layout & Framing at Units & Corridors at 7th Lvl | TT_Task | TK_NotStart | 2026-07-23 | 2026-07-24 | 2 | 69 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-07-U-FN-120 | Install Drywall Framing @ Units & Corridors - L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > Wall Layout & Framing at Units & Corridors at 7th Lvl | TT_Task | TK_NotStart | 2026-07-27 | 2026-08-03 | 6 | 69 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-07-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > MEP Risers & Rough at Units & Corridors at 7th Lvl > MEP Risers at 7th Lvl | TT_Task | TK_NotStart | 2026-07-27 | 2026-07-29 | 3 | 75 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-07-U-MP-150 | Install FP Rough @ Units & Corridors - L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > MEP Risers & Rough at Units & Corridors at 7th Lvl > MEP Rough at Units & Corridors at 78th Lvl | TT_Task | TK_NotStart | 2026-07-29 | 2026-08-04 | 5 | 74 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-07-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > MEP Risers & Rough at Units & Corridors at 7th Lvl > MEP Rough at Units & Corridors at 78th Lvl | TT_Task | TK_NotStart | 2026-08-03 | 2026-08-10 | 6 | 74 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-07-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > MEP Risers & Rough at Units & Corridors at 7th Lvl > MEP Rough at Units & Corridors at 78th Lvl | TT_Task | TK_NotStart | 2026-08-04 | 2026-08-12 | 7 | 69 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-07-U-MP-170 | Install Electrical Rough @ Units & Corridors - L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > MEP Risers & Rough at Units & Corridors at 7th Lvl > MEP Rough at Units & Corridors at 78th Lvl | TT_Task | TK_NotStart | 2026-08-07 | 2026-08-14 | 6 | 69 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-07-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > MEP Risers & Rough at Units & Corridors at 7th Lvl > MEP Rough at Units & Corridors at 78th Lvl | TT_Task | TK_NotStart | 2026-08-11 | 2026-08-17 | 5 | 69 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-07-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L7 | yes | Framing and MEP rough-in | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > MEP Risers & Rough at Units & Corridors at 7th Lvl > MEP Rough at Units & Corridors at 78th Lvl | TT_Task | TK_NotStart | 2026-08-18 | 2026-08-18 | 1 | 69 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-08-U-FN-100 | Layout Interior Walls @ Units & Corridors - L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > Wall Layout & Framing at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-07-29 | 2026-07-29 | 1 | 72 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-08-U-FN-110 | Install Top Tracks @ Units & Corridors - L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > Wall Layout & Framing at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-07-29 | 2026-07-30 | 2 | 72 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-08-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > MEP Risers & Rough at Units & Corridors at 8th Lvl > MEP Risers at 8th Lvl | TT_Task | TK_NotStart | 2026-07-31 | 2026-08-04 | 3 | 78 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-08-U-FN-120 | Install Drywall Framing @ Units & Corridors - L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > Wall Layout & Framing at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-08-04 | 2026-08-11 | 6 | 70 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-08-U-MP-100 | Install Plumbing Risers @ L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > MEP Risers & Rough at Units & Corridors at 8th Lvl > MEP Risers at 8th Lvl | TT_Task | TK_NotStart | 2026-08-12 | 2026-08-13 | 2 | 67 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-08-U-MP-120 | Install FP Risers @ L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > MEP Risers & Rough at Units & Corridors at 8th Lvl > MEP Risers at 8th Lvl | TT_Task | TK_NotStart | 2026-08-14 | 2026-08-17 | 2 | 67 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-08-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > MEP Risers & Rough at Units & Corridors at 8th Lvl > MEP Rough at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-08-14 | 2026-08-24 | 7 | 68 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-08-U-MP-130 | Install Mech Risers @ L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > MEP Risers & Rough at Units & Corridors at 8th Lvl > MEP Risers at 8th Lvl | TT_Task | TK_NotStart | 2026-08-18 | 2026-08-19 | 2 | 68 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-08-U-MP-150 | Install FP Rough @ Units & Corridors - L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > MEP Risers & Rough at Units & Corridors at 8th Lvl > MEP Rough at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-08-18 | 2026-08-24 | 5 | 67 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-08-U-MP-170 | Install Electrical Rough @ Units & Corridors - L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > MEP Risers & Rough at Units & Corridors at 8th Lvl > MEP Rough at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-08-19 | 2026-08-26 | 6 | 68 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-08-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > MEP Risers & Rough at Units & Corridors at 8th Lvl > MEP Rough at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-08-21 | 2026-08-28 | 6 | 67 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-08-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > MEP Risers & Rough at Units & Corridors at 8th Lvl > MEP Rough at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-08-21 | 2026-08-27 | 5 | 68 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-08-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L8 | yes | Framing and MEP rough-in | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > MEP Risers & Rough at Units & Corridors at 8th Lvl > MEP Rough at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-08-31 | 2026-08-31 | 1 | 67 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-09-U-FN-100 | Layout Interior Walls @ Units & Corridors - L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > Wall Layout & Framing at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-08-06 | 2026-08-06 | 1 | 73 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-09-U-FN-110 | Install Top Tracks @ Units & Corridors - L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > Wall Layout & Framing at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-08-06 | 2026-08-07 | 2 | 73 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-09-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > MEP Risers & Rough at Units & Corridors at 9th Lvl > MEP Risers at 9th Lvl | TT_Task | TK_NotStart | 2026-08-10 | 2026-08-12 | 3 | 79 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-09-U-FN-120 | Install Drywall Framing @ Units & Corridors - L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > Wall Layout & Framing at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-08-12 | 2026-08-19 | 6 | 71 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-09-U-MP-100 | Install Plumbing Risers @ L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > MEP Risers & Rough at Units & Corridors at 9th Lvl > MEP Risers at 9th Lvl | TT_Task | TK_NotStart | 2026-08-14 | 2026-08-17 | 2 | 72 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-09-U-MP-120 | Install FP Risers @ L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > MEP Risers & Rough at Units & Corridors at 9th Lvl > MEP Risers at 9th Lvl | TT_Task | TK_NotStart | 2026-08-18 | 2026-08-19 | 2 | 72 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-09-U-MP-130 | Install Mech Risers @ L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > MEP Risers & Rough at Units & Corridors at 9th Lvl > MEP Risers at 9th Lvl | TT_Task | TK_NotStart | 2026-08-20 | 2026-08-21 | 2 | 73 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-09-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > MEP Risers & Rough at Units & Corridors at 9th Lvl > MEP Rough at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-08-20 | 2026-08-28 | 7 | 71 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-09-U-MP-150 | Install FP Rough @ Units & Corridors - L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > MEP Risers & Rough at Units & Corridors at 9th Lvl > MEP Rough at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-08-20 | 2026-08-26 | 5 | 72 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-09-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > MEP Risers & Rough at Units & Corridors at 9th Lvl > MEP Rough at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-08-25 | 2026-09-01 | 6 | 72 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-09-U-MP-170 | Install Electrical Rough @ Units & Corridors - L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > MEP Risers & Rough at Units & Corridors at 9th Lvl > MEP Rough at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-08-25 | 2026-09-01 | 6 | 71 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-09-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > MEP Risers & Rough at Units & Corridors at 9th Lvl > MEP Rough at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-08-27 | 2026-09-02 | 5 | 71 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-09-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L9 | yes | Framing and MEP rough-in | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > MEP Risers & Rough at Units & Corridors at 9th Lvl > MEP Rough at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-09-03 | 2026-09-03 | 1 | 71 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-10-U-FN-100 | Layout Interior Walls @ Units & Corridors - L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > Wall Layout & Framing at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-08-13 | 2026-08-13 | 1 | 75 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-10-U-FN-110 | Install Top Tracks @ Units & Corridors - L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > Wall Layout & Framing at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-08-13 | 2026-08-14 | 2 | 75 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-10-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > MEP Risers & Rough at Units & Corridors at 10th Lvl > MEP Risers at 10th Lvl | TT_Task | TK_NotStart | 2026-08-17 | 2026-08-19 | 3 | 81 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-10-U-MP-100 | Install Plumbing Risers @ L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > MEP Risers & Rough at Units & Corridors at 10th Lvl > MEP Risers at 10th Lvl | TT_Task | TK_NotStart | 2026-08-18 | 2026-08-19 | 2 | 77 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-10-U-FN-120 | Install Drywall Framing @ Units & Corridors - L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > Wall Layout & Framing at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-08-20 | 2026-08-27 | 6 | 72 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-10-U-MP-120 | Install FP Risers @ L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > MEP Risers & Rough at Units & Corridors at 10th Lvl > MEP Risers at 10th Lvl | TT_Task | TK_NotStart | 2026-08-20 | 2026-08-21 | 2 | 77 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-10-U-MP-130 | Install Mech Risers @ L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > MEP Risers & Rough at Units & Corridors at 10th Lvl > MEP Risers at 10th Lvl | TT_Task | TK_NotStart | 2026-08-24 | 2026-08-25 | 2 | 78 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-10-U-MP-150 | Install FP Rough @ Units & Corridors - L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > MEP Risers & Rough at Units & Corridors at 10th Lvl > MEP Rough at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-08-24 | 2026-08-28 | 5 | 77 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-10-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > MEP Risers & Rough at Units & Corridors at 10th Lvl > MEP Rough at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-08-27 | 2026-09-03 | 6 | 77 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-10-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > MEP Risers & Rough at Units & Corridors at 10th Lvl > MEP Rough at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-08-28 | 2026-09-08 | 7 | 72 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-10-U-MP-170 | Install Electrical Rough @ Units & Corridors - L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > MEP Risers & Rough at Units & Corridors at 10th Lvl > MEP Rough at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-09-02 | 2026-09-10 | 6 | 72 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-10-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > MEP Risers & Rough at Units & Corridors at 10th Lvl > MEP Rough at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-09-04 | 2026-09-11 | 5 | 72 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-10-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L10 | yes | Framing and MEP rough-in | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > MEP Risers & Rough at Units & Corridors at 10th Lvl > MEP Rough at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-09-14 | 2026-09-14 | 1 | 72 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-11-U-FN-100 | Layout Interior Walls @ Units & Corridors - L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > Wall Layout & Framing at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-08-20 | 2026-08-20 | 1 | 77 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-11-U-FN-110 | Install Top Tracks @ Units & Corridors - L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > Wall Layout & Framing at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-08-20 | 2026-08-21 | 2 | 77 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-11-U-MP-100 | Install Plumbing Risers @ L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > MEP Risers & Rough at Units & Corridors at 11th Lvl > MEP Risers at 11th Lvl | TT_Task | TK_NotStart | 2026-08-20 | 2026-08-21 | 2 | 82 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-11-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > MEP Risers & Rough at Units & Corridors at 11th Lvl > MEP Risers at 11th Lvl | TT_Task | TK_NotStart | 2026-08-24 | 2026-08-26 | 3 | 83 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-11-U-MP-120 | Install FP Risers @ L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > MEP Risers & Rough at Units & Corridors at 11th Lvl > MEP Risers at 11th Lvl | TT_Task | TK_NotStart | 2026-08-24 | 2026-08-25 | 2 | 82 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-11-U-MP-130 | Install Mech Risers @ L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > MEP Risers & Rough at Units & Corridors at 11th Lvl > MEP Risers at 11th Lvl | TT_Task | TK_NotStart | 2026-08-26 | 2026-08-27 | 2 | 83 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-11-U-FN-120 | Install Drywall Framing @ Units & Corridors - L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > Wall Layout & Framing at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-08-28 | 2026-09-04 | 6 | 73 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-11-U-MP-150 | Install FP Rough @ Units & Corridors - L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > MEP Risers & Rough at Units & Corridors at 11th Lvl > MEP Rough at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-09-01 | 2026-09-08 | 5 | 78 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-11-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > MEP Risers & Rough at Units & Corridors at 11th Lvl > MEP Rough at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-09-04 | 2026-09-14 | 6 | 78 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-11-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > MEP Risers & Rough at Units & Corridors at 11th Lvl > MEP Rough at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-09-08 | 2026-09-16 | 7 | 73 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-11-U-MP-170 | Install Electrical Rough @ Units & Corridors - L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > MEP Risers & Rough at Units & Corridors at 11th Lvl > MEP Rough at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-09-11 | 2026-09-18 | 6 | 73 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-11-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > MEP Risers & Rough at Units & Corridors at 11th Lvl > MEP Rough at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-21 | 5 | 73 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-11-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L11 | yes | Framing and MEP rough-in | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > MEP Risers & Rough at Units & Corridors at 11th Lvl > MEP Rough at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-09-22 | 2026-09-22 | 1 | 73 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-12-U-MP-100 | Install Plumbing Risers @ L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > MEP Risers & Rough at Units & Corridors at 12th Lvl > MEP Risers at 12th Lvl | TT_Task | TK_NotStart | 2026-08-24 | 2026-08-25 | 2 | 87 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-12-U-MP-120 | Install FP Risers @ L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > MEP Risers & Rough at Units & Corridors at 12th Lvl > MEP Risers at 12th Lvl | TT_Task | TK_NotStart | 2026-08-26 | 2026-08-27 | 2 | 87 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-12-U-FN-100 | Layout Interior Walls @ Units & Corridors - L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > Wall Layout & Framing at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-08-27 | 2026-08-27 | 1 | 79 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-12-U-FN-110 | Install Top Tracks @ Units & Corridors - L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > Wall Layout & Framing at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-08-27 | 2026-08-28 | 2 | 79 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-12-U-MP-130 | Install Mech Risers @ L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > MEP Risers & Rough at Units & Corridors at 12th Lvl > MEP Risers at 12th Lvl | TT_Task | TK_NotStart | 2026-08-28 | 2026-08-31 | 2 | 88 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-12-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > MEP Risers & Rough at Units & Corridors at 12th Lvl > MEP Risers at 12th Lvl | TT_Task | TK_NotStart | 2026-08-31 | 2026-09-02 | 3 | 85 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-12-U-FN-120 | Install Drywall Framing @ Units & Corridors - L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > Wall Layout & Framing at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-09-08 | 2026-09-15 | 6 | 74 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-12-U-MP-150 | Install FP Rough @ Units & Corridors - L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > MEP Risers & Rough at Units & Corridors at 12th Lvl > MEP Rough at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-09-10 | 2026-09-16 | 5 | 79 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-12-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > MEP Risers & Rough at Units & Corridors at 12th Lvl > MEP Rough at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-22 | 6 | 79 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-12-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > MEP Risers & Rough at Units & Corridors at 12th Lvl > MEP Rough at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-09-16 | 2026-09-24 | 7 | 74 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-12-U-MP-170 | Install Electrical Rough @ Units & Corridors - L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > MEP Risers & Rough at Units & Corridors at 12th Lvl > MEP Rough at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-09-21 | 2026-09-28 | 6 | 74 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-12-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > MEP Risers & Rough at Units & Corridors at 12th Lvl > MEP Rough at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-09-23 | 2026-09-29 | 5 | 74 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-12-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L12 | yes | Framing and MEP rough-in | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > MEP Risers & Rough at Units & Corridors at 12th Lvl > MEP Rough at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-09-30 | 2026-09-30 | 1 | 74 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-14-U-MP-100 | Install Plumbing Risers @ L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > MEP Risers & Rough at Units & Corridors at 14th Lvl > MEP Risers at 14th Lvl | TT_Task | TK_NotStart | 2026-08-26 | 2026-08-27 | 2 | 92 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-14-U-MP-120 | Install FP Risers @ L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > MEP Risers & Rough at Units & Corridors at 14th Lvl > MEP Risers at 14th Lvl | TT_Task | TK_NotStart | 2026-08-28 | 2026-08-31 | 2 | 92 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-14-U-MP-130 | Install Mech Risers @ L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > MEP Risers & Rough at Units & Corridors at 14th Lvl > MEP Risers at 14th Lvl | TT_Task | TK_NotStart | 2026-09-01 | 2026-09-02 | 2 | 93 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-14-U-FN-100 | Layout Interior Walls @ Units & Corridors - L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > Wall Layout & Framing at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-09-03 | 2026-09-03 | 1 | 81 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-14-U-FN-110 | Install Top Tracks @ Units & Corridors - L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > Wall Layout & Framing at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-09-03 | 2026-09-04 | 2 | 81 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-14-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > MEP Risers & Rough at Units & Corridors at 14th Lvl > MEP Risers at 14th Lvl | TT_Task | TK_NotStart | 2026-09-08 | 2026-09-10 | 3 | 87 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-14-U-FN-120 | Install Drywall Framing @ Units & Corridors - L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > Wall Layout & Framing at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-09-16 | 2026-09-23 | 6 | 75 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-14-U-MP-150 | Install FP Rough @ Units & Corridors - L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > MEP Risers & Rough at Units & Corridors at 14th Lvl > MEP Rough at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-09-18 | 2026-09-24 | 5 | 80 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-14-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > MEP Risers & Rough at Units & Corridors at 14th Lvl > MEP Rough at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-09-23 | 2026-09-30 | 6 | 80 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-14-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > MEP Risers & Rough at Units & Corridors at 14th Lvl > MEP Rough at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-09-24 | 2026-10-02 | 7 | 75 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-14-U-MP-170 | Install Electrical Rough @ Units & Corridors - L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > MEP Risers & Rough at Units & Corridors at 14th Lvl > MEP Rough at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-09-29 | 2026-10-06 | 6 | 75 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-14-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > MEP Risers & Rough at Units & Corridors at 14th Lvl > MEP Rough at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-07 | 5 | 75 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-14-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L14 | yes | Framing and MEP rough-in | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > MEP Risers & Rough at Units & Corridors at 14th Lvl > MEP Rough at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-10-08 | 2026-10-08 | 1 | 75 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-15-U-MP-100 | Install Plumbing Risers @ L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > MEP Risers & Rough at Units & Corridors at 15th Lvl > MEP Risers at 15th Lvl | TT_Task | TK_NotStart | 2026-08-28 | 2026-08-31 | 2 | 97 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-15-U-MP-120 | Install FP Risers @ L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > MEP Risers & Rough at Units & Corridors at 15th Lvl > MEP Risers at 15th Lvl | TT_Task | TK_NotStart | 2026-09-01 | 2026-09-02 | 2 | 97 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-15-U-MP-130 | Install Mech Risers @ L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > MEP Risers & Rough at Units & Corridors at 15th Lvl > MEP Risers at 15th Lvl | TT_Task | TK_NotStart | 2026-09-03 | 2026-09-04 | 2 | 98 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-15-U-FN-100 | Layout Interior Walls @ Units & Corridors - L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > Wall Layout & Framing at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-09-11 | 2026-09-11 | 1 | 83 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-15-U-FN-110 | Install Top Tracks @ Units & Corridors - L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > Wall Layout & Framing at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-09-11 | 2026-09-14 | 2 | 83 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-15-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > MEP Risers & Rough at Units & Corridors at 15th Lvl > MEP Risers at 15th Lvl | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-17 | 3 | 89 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-15-U-FN-120 | Install Drywall Framing @ Units & Corridors - L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > Wall Layout & Framing at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-09-24 | 2026-10-01 | 6 | 76 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-15-U-MP-150 | Install FP Rough @ Units & Corridors - L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > MEP Risers & Rough at Units & Corridors at 15th Lvl > MEP Rough at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-09-28 | 2026-10-02 | 5 | 81 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-15-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > MEP Risers & Rough at Units & Corridors at 15th Lvl > MEP Rough at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-08 | 6 | 81 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-15-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > MEP Risers & Rough at Units & Corridors at 15th Lvl > MEP Rough at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-10-02 | 2026-10-12 | 7 | 76 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-15-U-MP-170 | Install Electrical Rough @ Units & Corridors - L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > MEP Risers & Rough at Units & Corridors at 15th Lvl > MEP Rough at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-10-07 | 2026-10-14 | 6 | 76 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-15-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > MEP Risers & Rough at Units & Corridors at 15th Lvl > MEP Rough at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-15 | 5 | 76 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-15-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L15 | yes | Framing and MEP rough-in | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > MEP Risers & Rough at Units & Corridors at 15th Lvl > MEP Rough at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-10-16 | 2026-10-16 | 1 | 76 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-16-U-MP-100 | Install Plumbing Risers @ L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > MEP Risers & Rough at Units & Corridors at 16th Lvl > MEP Risers at 16th Lvl | TT_Task | TK_NotStart | 2026-09-01 | 2026-09-02 | 2 | 102 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-16-U-MP-120 | Install FP Risers @ L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > MEP Risers & Rough at Units & Corridors at 16th Lvl > MEP Risers at 16th Lvl | TT_Task | TK_NotStart | 2026-09-03 | 2026-09-04 | 2 | 102 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-16-U-MP-130 | Install Mech Risers @ L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > MEP Risers & Rough at Units & Corridors at 16th Lvl > MEP Risers at 16th Lvl | TT_Task | TK_NotStart | 2026-09-08 | 2026-09-09 | 2 | 103 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-16-U-FN-100 | Layout Interior Walls @ Units & Corridors - L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > Wall Layout & Framing at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2026-09-18 | 2026-09-18 | 1 | 85 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-16-U-FN-110 | Install Top Tracks @ Units & Corridors - L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > Wall Layout & Framing at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2026-09-18 | 2026-09-21 | 2 | 85 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-16-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > MEP Risers & Rough at Units & Corridors at 16th Lvl > MEP Risers at 16th Lvl | TT_Task | TK_NotStart | 2026-09-22 | 2026-09-24 | 3 | 91 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-16-U-FN-120 | Install Drywall Framing @ Units & Corridors - L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > Wall Layout & Framing at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2026-10-02 | 2026-10-09 | 6 | 77 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-16-U-MP-150 | Install FP Rough @ Units & Corridors - L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > MEP Risers & Rough at Units & Corridors at 16th Lvl > MEP Rough at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-12 | 5 | 82 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-16-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > MEP Risers & Rough at Units & Corridors at 16th Lvl > MEP Rough at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-16 | 6 | 82 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-16-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > MEP Risers & Rough at Units & Corridors at 16th Lvl > MEP Rough at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2026-10-12 | 2026-10-20 | 7 | 77 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-16-U-MP-170 | Install Electrical Rough @ Units & Corridors - L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > MEP Risers & Rough at Units & Corridors at 16th Lvl > MEP Rough at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-22 | 6 | 77 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-16-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > MEP Risers & Rough at Units & Corridors at 16th Lvl > MEP Rough at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2026-10-19 | 2026-10-23 | 5 | 77 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-16-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L16 | yes | Framing and MEP rough-in | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > MEP Risers & Rough at Units & Corridors at 16th Lvl > MEP Rough at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2026-10-26 | 2026-10-26 | 1 | 77 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-17-U-MP-100 | Install Plumbing Risers @ L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > MEP Risers & Rough at Units & Corridors at 17th Lvl > MEP Risers at 17th Lvl | TT_Task | TK_NotStart | 2026-09-09 | 2026-09-10 | 2 | 104 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-17-U-MP-120 | Install FP Risers @ L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > MEP Risers & Rough at Units & Corridors at 17th Lvl > MEP Risers at 17th Lvl | TT_Task | TK_NotStart | 2026-09-11 | 2026-09-14 | 2 | 104 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-17-U-MP-130 | Install Mech Risers @ L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > MEP Risers & Rough at Units & Corridors at 17th Lvl > MEP Risers at 17th Lvl | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-16 | 2 | 105 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-17-U-FN-100 | Layout Interior Walls @ Units & Corridors - L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > Wall Layout & Framing at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2026-09-25 | 2026-09-25 | 1 | 87 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-17-U-FN-110 | Install Top Tracks @ Units & Corridors - L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > Wall Layout & Framing at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2026-09-25 | 2026-09-28 | 2 | 87 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-17-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > MEP Risers & Rough at Units & Corridors at 17th Lvl > MEP Risers at 17th Lvl | TT_Task | TK_NotStart | 2026-09-29 | 2026-10-01 | 3 | 93 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-17-U-FN-120 | Install Drywall Framing @ Units & Corridors - L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > Wall Layout & Framing at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2026-10-12 | 2026-10-19 | 6 | 78 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-17-U-MP-150 | Install FP Rough @ Units & Corridors - L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > MEP Risers & Rough at Units & Corridors at 17th Lvl > MEP Rough at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2026-10-14 | 2026-10-20 | 5 | 83 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-17-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > MEP Risers & Rough at Units & Corridors at 17th Lvl > MEP Rough at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2026-10-19 | 2026-10-26 | 6 | 83 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-17-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > MEP Risers & Rough at Units & Corridors at 17th Lvl > MEP Rough at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2026-10-20 | 2026-10-28 | 7 | 78 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-17-U-MP-170 | Install Electrical Rough @ Units & Corridors - L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > MEP Risers & Rough at Units & Corridors at 17th Lvl > MEP Rough at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2026-10-23 | 2026-10-30 | 6 | 78 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-17-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > MEP Risers & Rough at Units & Corridors at 17th Lvl > MEP Rough at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2026-10-27 | 2026-11-02 | 5 | 78 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-17-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L17 | yes | Framing and MEP rough-in | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > MEP Risers & Rough at Units & Corridors at 17th Lvl > MEP Rough at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2026-11-03 | 2026-11-03 | 1 | 78 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-18-U-MP-100 | Install Plumbing Risers @ L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > MEP Risers & Rough at Units & Corridors at 18th Lvl > MEP Risers at 18th Lvl | TT_Task | TK_NotStart | 2026-09-16 | 2026-09-17 | 2 | 106 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-18-U-MP-120 | Install FP Risers @ L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > MEP Risers & Rough at Units & Corridors at 18th Lvl > MEP Risers at 18th Lvl | TT_Task | TK_NotStart | 2026-09-18 | 2026-09-21 | 2 | 106 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-18-U-MP-130 | Install Mech Risers @ L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > MEP Risers & Rough at Units & Corridors at 18th Lvl > MEP Risers at 18th Lvl | TT_Task | TK_NotStart | 2026-09-22 | 2026-09-23 | 2 | 107 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-18-U-FN-100 | Layout Interior Walls @ Units & Corridors - L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > Wall Layout & Framing at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2026-10-02 | 2026-10-02 | 1 | 89 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-18-U-FN-110 | Install Top Tracks @ Units & Corridors - L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > Wall Layout & Framing at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2026-10-02 | 2026-10-05 | 2 | 89 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-18-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > MEP Risers & Rough at Units & Corridors at 18th Lvl > MEP Risers at 18th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-08 | 3 | 95 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-18-U-FN-120 | Install Drywall Framing @ Units & Corridors - L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > Wall Layout & Framing at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2026-10-20 | 2026-10-27 | 6 | 79 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-18-U-MP-150 | Install FP Rough @ Units & Corridors - L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > MEP Risers & Rough at Units & Corridors at 18th Lvl > MEP Rough at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2026-10-22 | 2026-10-28 | 5 | 84 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-18-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > MEP Risers & Rough at Units & Corridors at 18th Lvl > MEP Rough at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2026-10-27 | 2026-11-03 | 6 | 84 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-18-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > MEP Risers & Rough at Units & Corridors at 18th Lvl > MEP Rough at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2026-10-28 | 2026-11-05 | 7 | 79 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-18-U-MP-170 | Install Electrical Rough @ Units & Corridors - L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > MEP Risers & Rough at Units & Corridors at 18th Lvl > MEP Rough at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2026-11-02 | 2026-11-09 | 6 | 79 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-18-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > MEP Risers & Rough at Units & Corridors at 18th Lvl > MEP Rough at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-10 | 5 | 79 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-18-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L18 | yes | Framing and MEP rough-in | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > MEP Risers & Rough at Units & Corridors at 18th Lvl > MEP Rough at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2026-11-11 | 2026-11-11 | 1 | 79 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-19-U-MP-100 | Install Plumbing Risers @ L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > MEP Risers & Rough at Units & Corridors at 19th Lvl > MEP Risers at 19th Lvl | TT_Task | TK_NotStart | 2026-09-23 | 2026-09-24 | 2 | 108 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-19-U-MP-120 | Install FP Risers @ L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > MEP Risers & Rough at Units & Corridors at 19th Lvl > MEP Risers at 19th Lvl | TT_Task | TK_NotStart | 2026-09-25 | 2026-09-28 | 2 | 108 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-19-U-MP-130 | Install Mech Risers @ L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > MEP Risers & Rough at Units & Corridors at 19th Lvl > MEP Risers at 19th Lvl | TT_Task | TK_NotStart | 2026-09-29 | 2026-09-30 | 2 | 109 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-19-U-FN-100 | Layout Interior Walls @ Units & Corridors - L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > Wall Layout & Framing at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-09 | 1 | 91 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-19-U-FN-110 | Install Top Tracks @ Units & Corridors - L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > Wall Layout & Framing at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-12 | 2 | 91 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-19-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > MEP Risers & Rough at Units & Corridors at 19th Lvl > MEP Risers at 19th Lvl | TT_Task | TK_NotStart | 2026-10-13 | 2026-10-15 | 3 | 97 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-19-U-FN-120 | Install Drywall Framing @ Units & Corridors - L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > Wall Layout & Framing at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2026-10-28 | 2026-11-04 | 6 | 80 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-19-U-MP-150 | Install FP Rough @ Units & Corridors - L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > MEP Risers & Rough at Units & Corridors at 19th Lvl > MEP Rough at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-05 | 5 | 85 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-19-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > MEP Risers & Rough at Units & Corridors at 19th Lvl > MEP Rough at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-11 | 6 | 85 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-19-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > MEP Risers & Rough at Units & Corridors at 19th Lvl > MEP Rough at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2026-11-05 | 2026-11-13 | 7 | 80 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-19-U-MP-170 | Install Electrical Rough @ Units & Corridors - L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > MEP Risers & Rough at Units & Corridors at 19th Lvl > MEP Rough at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2026-11-10 | 2026-11-17 | 6 | 80 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-19-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > MEP Risers & Rough at Units & Corridors at 19th Lvl > MEP Rough at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2026-11-12 | 2026-11-18 | 5 | 80 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-19-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L19 | yes | Framing and MEP rough-in | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > MEP Risers & Rough at Units & Corridors at 19th Lvl > MEP Rough at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2026-11-19 | 2026-11-19 | 1 | 80 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-20-U-MP-100 | Install Plumbing Risers @ L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > MEP Risers & Rough at Units & Corridors at 20th Lvl > MEP Risers at 20th Lvl | TT_Task | TK_NotStart | 2026-09-30 | 2026-10-01 | 2 | 110 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-20-U-MP-120 | Install FP Risers @ L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > MEP Risers & Rough at Units & Corridors at 20th Lvl > MEP Risers at 20th Lvl | TT_Task | TK_NotStart | 2026-10-02 | 2026-10-05 | 2 | 110 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-20-U-MP-130 | Install Mech Risers @ L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > MEP Risers & Rough at Units & Corridors at 20th Lvl > MEP Risers at 20th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-07 | 2 | 111 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-20-U-FN-100 | Layout Interior Walls @ Units & Corridors - L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > Wall Layout & Framing at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2026-10-16 | 2026-10-16 | 1 | 93 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-20-U-FN-110 | Install Top Tracks @ Units & Corridors - L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > Wall Layout & Framing at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2026-10-16 | 2026-10-19 | 2 | 93 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-20-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > MEP Risers & Rough at Units & Corridors at 20th Lvl > MEP Risers at 20th Lvl | TT_Task | TK_NotStart | 2026-10-20 | 2026-10-22 | 3 | 99 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-20-U-FN-120 | Install Drywall Framing @ Units & Corridors - L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > Wall Layout & Framing at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2026-11-05 | 2026-11-12 | 6 | 81 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-20-U-MP-150 | Install FP Rough @ Units & Corridors - L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > MEP Risers & Rough at Units & Corridors at 20th Lvl > MEP Rough at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-13 | 5 | 86 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-20-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > MEP Risers & Rough at Units & Corridors at 20th Lvl > MEP Rough at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2026-11-12 | 2026-11-19 | 6 | 86 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-20-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > MEP Risers & Rough at Units & Corridors at 20th Lvl > MEP Rough at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-23 | 7 | 81 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-20-U-MP-170 | Install Electrical Rough @ Units & Corridors - L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > MEP Risers & Rough at Units & Corridors at 20th Lvl > MEP Rough at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2026-11-18 | 2026-11-25 | 6 | 81 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-20-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > MEP Risers & Rough at Units & Corridors at 20th Lvl > MEP Rough at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-11-30 | 5 | 81 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-20-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L20 | yes | Framing and MEP rough-in | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > MEP Risers & Rough at Units & Corridors at 20th Lvl > MEP Rough at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2026-12-01 | 2026-12-01 | 1 | 81 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-21-U-MP-100 | Install Plumbing Risers @ L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > MEP Risers & Rough at Units & Corridors at 21st Lvl > MEP Risers at 21st Lvl | TT_Task | TK_NotStart | 2026-10-07 | 2026-10-08 | 2 | 112 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-21-U-MP-120 | Install FP Risers @ L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > MEP Risers & Rough at Units & Corridors at 21st Lvl > MEP Risers at 21st Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-12 | 2 | 112 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-21-U-MP-130 | Install Mech Risers @ L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > MEP Risers & Rough at Units & Corridors at 21st Lvl > MEP Risers at 21st Lvl | TT_Task | TK_NotStart | 2026-10-13 | 2026-10-14 | 2 | 113 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-21-U-FN-100 | Layout Interior Walls @ Units & Corridors - L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > Wall Layout & Framing at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2026-10-23 | 2026-10-23 | 1 | 95 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-21-U-FN-110 | Install Top Tracks @ Units & Corridors - L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > Wall Layout & Framing at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2026-10-23 | 2026-10-26 | 2 | 95 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-21-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > MEP Risers & Rough at Units & Corridors at 21st Lvl > MEP Risers at 21st Lvl | TT_Task | TK_NotStart | 2026-10-27 | 2026-10-29 | 3 | 101 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-21-U-FN-120 | Install Drywall Framing @ Units & Corridors - L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > Wall Layout & Framing at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-20 | 6 | 82 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-21-U-MP-150 | Install FP Rough @ Units & Corridors - L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > MEP Risers & Rough at Units & Corridors at 21st Lvl > MEP Rough at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2026-11-17 | 2026-11-23 | 5 | 87 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-21-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > MEP Risers & Rough at Units & Corridors at 21st Lvl > MEP Rough at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-12-01 | 6 | 87 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-21-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > MEP Risers & Rough at Units & Corridors at 21st Lvl > MEP Rough at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2026-11-23 | 2026-12-03 | 7 | 82 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-21-U-MP-170 | Install Electrical Rough @ Units & Corridors - L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > MEP Risers & Rough at Units & Corridors at 21st Lvl > MEP Rough at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2026-11-30 | 2026-12-07 | 6 | 82 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-21-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > MEP Risers & Rough at Units & Corridors at 21st Lvl > MEP Rough at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2026-12-02 | 2026-12-08 | 5 | 82 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-21-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L21 | yes | Framing and MEP rough-in | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > MEP Risers & Rough at Units & Corridors at 21st Lvl > MEP Rough at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2026-12-09 | 2026-12-09 | 1 | 82 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-22-U-MP-100 | Install Plumbing Risers @ L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > MEP Risers & Rough at Units & Corridors at 22nd Lvl > MEP Risers at 22nd Lvl | TT_Task | TK_NotStart | 2026-10-14 | 2026-10-15 | 2 | 114 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-22-U-MP-120 | Install FP Risers @ L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > MEP Risers & Rough at Units & Corridors at 22nd Lvl > MEP Risers at 22nd Lvl | TT_Task | TK_NotStart | 2026-10-16 | 2026-10-19 | 2 | 114 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-22-U-MP-130 | Install Mech Risers @ L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > MEP Risers & Rough at Units & Corridors at 22nd Lvl > MEP Risers at 22nd Lvl | TT_Task | TK_NotStart | 2026-10-20 | 2026-10-21 | 2 | 115 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-22-U-FN-100 | Layout Interior Walls @ Units & Corridors - L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > Wall Layout & Framing at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-10-30 | 1 | 97 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-22-U-FN-110 | Install Top Tracks @ Units & Corridors - L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > Wall Layout & Framing at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-02 | 2 | 97 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-22-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > MEP Risers & Rough at Units & Corridors at 22nd Lvl > MEP Risers at 22nd Lvl | TT_Task | TK_NotStart | 2026-11-03 | 2026-11-05 | 3 | 103 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-22-U-FN-120 | Install Drywall Framing @ Units & Corridors - L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > Wall Layout & Framing at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2026-11-23 | 2026-12-02 | 6 | 83 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-22-U-MP-150 | Install FP Rough @ Units & Corridors - L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > MEP Risers & Rough at Units & Corridors at 22nd Lvl > MEP Rough at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2026-11-25 | 2026-12-03 | 5 | 88 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-22-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > MEP Risers & Rough at Units & Corridors at 22nd Lvl > MEP Rough at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2026-12-02 | 2026-12-09 | 6 | 88 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-22-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > MEP Risers & Rough at Units & Corridors at 22nd Lvl > MEP Rough at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-11 | 7 | 83 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-22-U-MP-170 | Install Electrical Rough @ Units & Corridors - L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > MEP Risers & Rough at Units & Corridors at 22nd Lvl > MEP Rough at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2026-12-08 | 2026-12-15 | 6 | 83 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-22-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > MEP Risers & Rough at Units & Corridors at 22nd Lvl > MEP Rough at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-16 | 5 | 83 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-22-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L22 | yes | Framing and MEP rough-in | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > MEP Risers & Rough at Units & Corridors at 22nd Lvl > MEP Rough at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2026-12-17 | 2026-12-17 | 1 | 83 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-23-U-MP-100 | Install Plumbing Risers @ L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > MEP Risers & Rough at Units & Corridors at 23rd Lvl > MEP Risers at 23rd Lvl | TT_Task | TK_NotStart | 2026-10-21 | 2026-10-22 | 2 | 116 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-23-U-MP-120 | Install FP Risers @ L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > MEP Risers & Rough at Units & Corridors at 23rd Lvl > MEP Risers at 23rd Lvl | TT_Task | TK_NotStart | 2026-10-23 | 2026-10-26 | 2 | 116 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-23-U-MP-130 | Install Mech Risers @ L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > MEP Risers & Rough at Units & Corridors at 23rd Lvl > MEP Risers at 23rd Lvl | TT_Task | TK_NotStart | 2026-10-27 | 2026-10-28 | 2 | 117 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-23-U-FN-100 | Layout Interior Walls @ Units & Corridors - L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > Wall Layout & Framing at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2026-11-06 | 2026-11-06 | 1 | 99 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-23-U-FN-110 | Install Top Tracks @ Units & Corridors - L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > Wall Layout & Framing at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2026-11-06 | 2026-11-09 | 2 | 99 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-23-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > MEP Risers & Rough at Units & Corridors at 23rd Lvl > MEP Risers at 23rd Lvl | TT_Task | TK_NotStart | 2026-11-10 | 2026-11-12 | 3 | 105 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-23-U-FN-120 | Install Drywall Framing @ Units & Corridors - L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > Wall Layout & Framing at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-10 | 6 | 84 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-23-U-MP-150 | Install FP Rough @ Units & Corridors - L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > MEP Risers & Rough at Units & Corridors at 23rd Lvl > MEP Rough at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-11 | 5 | 89 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-23-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > MEP Risers & Rough at Units & Corridors at 23rd Lvl > MEP Rough at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-17 | 6 | 89 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-23-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > MEP Risers & Rough at Units & Corridors at 23rd Lvl > MEP Rough at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2026-12-11 | 2026-12-21 | 7 | 84 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-23-U-MP-170 | Install Electrical Rough @ Units & Corridors - L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > MEP Risers & Rough at Units & Corridors at 23rd Lvl > MEP Rough at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2026-12-16 | 2026-12-23 | 6 | 84 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-23-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > MEP Risers & Rough at Units & Corridors at 23rd Lvl > MEP Rough at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2026-12-18 | 2026-12-24 | 5 | 84 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-23-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L23 | yes | Framing and MEP rough-in | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > MEP Risers & Rough at Units & Corridors at 23rd Lvl > MEP Rough at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2026-12-28 | 1 | 84 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-24-U-MP-100 | Install Plumbing Risers @ L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > MEP Risers & Rough at Units & Corridors at 24th Lvl > MEP Risers at 24th Lvl | TT_Task | TK_NotStart | 2026-10-28 | 2026-10-29 | 2 | 118 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-24-U-MP-120 | Install FP Risers @ L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > MEP Risers & Rough at Units & Corridors at 24th Lvl > MEP Risers at 24th Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-02 | 2 | 118 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-24-U-MP-130 | Install Mech Risers @ L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > MEP Risers & Rough at Units & Corridors at 24th Lvl > MEP Risers at 24th Lvl | TT_Task | TK_NotStart | 2026-11-03 | 2026-11-04 | 2 | 119 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-24-U-FN-100 | Layout Interior Walls @ Units & Corridors - L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > Wall Layout & Framing at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-13 | 1 | 101 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-24-U-FN-110 | Install Top Tracks @ Units & Corridors - L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > Wall Layout & Framing at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-16 | 2 | 101 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-24-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > MEP Risers & Rough at Units & Corridors at 24th Lvl > MEP Risers at 24th Lvl | TT_Task | TK_NotStart | 2026-11-17 | 2026-11-19 | 3 | 107 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-24-U-FN-120 | Install Drywall Framing @ Units & Corridors - L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > Wall Layout & Framing at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2026-12-11 | 2026-12-18 | 6 | 85 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-24-U-MP-150 | Install FP Rough @ Units & Corridors - L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > MEP Risers & Rough at Units & Corridors at 24th Lvl > MEP Rough at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2026-12-15 | 2026-12-21 | 5 | 90 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-24-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > MEP Risers & Rough at Units & Corridors at 24th Lvl > MEP Rough at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2026-12-18 | 2026-12-28 | 6 | 90 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-24-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > MEP Risers & Rough at Units & Corridors at 24th Lvl > MEP Rough at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2026-12-21 | 2026-12-30 | 7 | 85 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-24-U-MP-170 | Install Electrical Rough @ Units & Corridors - L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > MEP Risers & Rough at Units & Corridors at 24th Lvl > MEP Rough at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2026-12-24 | 2027-01-04 | 6 | 85 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-24-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > MEP Risers & Rough at Units & Corridors at 24th Lvl > MEP Rough at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2026-12-29 | 2027-01-05 | 5 | 85 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-24-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L24 | yes | Framing and MEP rough-in | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > MEP Risers & Rough at Units & Corridors at 24th Lvl > MEP Rough at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2027-01-06 | 2027-01-06 | 1 | 85 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-25-U-MP-100 | Install Plumbing Risers @ L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > MEP Risers & Rough at Units & Corridors at 25th Lvl > MEP Risers at 25th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-05 | 2 | 120 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-25-U-MP-120 | Install FP Risers @ L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > MEP Risers & Rough at Units & Corridors at 25th Lvl > MEP Risers at 25th Lvl | TT_Task | TK_NotStart | 2026-11-06 | 2026-11-09 | 2 | 120 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-25-U-MP-130 | Install Mech Risers @ L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > MEP Risers & Rough at Units & Corridors at 25th Lvl > MEP Risers at 25th Lvl | TT_Task | TK_NotStart | 2026-11-10 | 2026-11-11 | 2 | 121 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-25-U-FN-100 | Layout Interior Walls @ Units & Corridors - L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > Wall Layout & Framing at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-11-20 | 1 | 103 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-25-U-FN-110 | Install Top Tracks @ Units & Corridors - L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > Wall Layout & Framing at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-11-23 | 2 | 103 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-25-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > MEP Risers & Rough at Units & Corridors at 25th Lvl > MEP Risers at 25th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-11-30 | 3 | 109 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-25-U-FN-120 | Install Drywall Framing @ Units & Corridors - L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > Wall Layout & Framing at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2026-12-21 | 2026-12-29 | 6 | 86 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-25-U-MP-150 | Install FP Rough @ Units & Corridors - L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > MEP Risers & Rough at Units & Corridors at 25th Lvl > MEP Rough at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2026-12-23 | 2026-12-30 | 5 | 91 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-25-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > MEP Risers & Rough at Units & Corridors at 25th Lvl > MEP Rough at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2026-12-29 | 2027-01-06 | 6 | 91 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-25-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > MEP Risers & Rough at Units & Corridors at 25th Lvl > MEP Rough at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2026-12-30 | 2027-01-08 | 7 | 86 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-25-U-MP-170 | Install Electrical Rough @ Units & Corridors - L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > MEP Risers & Rough at Units & Corridors at 25th Lvl > MEP Rough at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2027-01-05 | 2027-01-12 | 6 | 86 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-25-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > MEP Risers & Rough at Units & Corridors at 25th Lvl > MEP Rough at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-13 | 5 | 86 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-25-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L25 | yes | Framing and MEP rough-in | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > MEP Risers & Rough at Units & Corridors at 25th Lvl > MEP Rough at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2027-01-14 | 2027-01-14 | 1 | 86 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-26-U-MP-100 | Install Plumbing Risers @ L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > MEP Risers & Rough at Units & Corridors at 26th Lvl > MEP Risers at 26th Lvl | TT_Task | TK_NotStart | 2026-11-11 | 2026-11-12 | 2 | 122 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-26-U-MP-120 | Install FP Risers @ L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > MEP Risers & Rough at Units & Corridors at 26th Lvl > MEP Risers at 26th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-16 | 2 | 122 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-26-U-MP-130 | Install Mech Risers @ L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > MEP Risers & Rough at Units & Corridors at 26th Lvl > MEP Risers at 26th Lvl | TT_Task | TK_NotStart | 2026-11-17 | 2026-11-18 | 2 | 123 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-26-U-FN-100 | Layout Interior Walls @ Units & Corridors - L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > Wall Layout & Framing at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2026-12-01 | 2026-12-01 | 1 | 105 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-26-U-FN-110 | Install Top Tracks @ Units & Corridors - L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > Wall Layout & Framing at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2026-12-01 | 2026-12-02 | 2 | 105 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-26-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > MEP Risers & Rough at Units & Corridors at 26th Lvl > MEP Risers at 26th Lvl | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-07 | 3 | 111 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-26-U-FN-120 | Install Drywall Framing @ Units & Corridors - L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > Wall Layout & Framing at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2026-12-30 | 2027-01-07 | 6 | 87 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-26-U-MP-150 | Install FP Rough @ Units & Corridors - L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > MEP Risers & Rough at Units & Corridors at 26th Lvl > MEP Rough at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-08 | 5 | 92 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-26-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > MEP Risers & Rough at Units & Corridors at 26th Lvl > MEP Rough at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-14 | 6 | 92 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-26-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > MEP Risers & Rough at Units & Corridors at 26th Lvl > MEP Rough at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2027-01-08 | 2027-01-18 | 7 | 87 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-26-U-MP-170 | Install Electrical Rough @ Units & Corridors - L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > MEP Risers & Rough at Units & Corridors at 26th Lvl > MEP Rough at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2027-01-13 | 2027-01-20 | 6 | 87 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-26-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > MEP Risers & Rough at Units & Corridors at 26th Lvl > MEP Rough at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2027-01-15 | 2027-01-21 | 5 | 87 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-26-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L26 | yes | Framing and MEP rough-in | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > MEP Risers & Rough at Units & Corridors at 26th Lvl > MEP Rough at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2027-01-22 | 2027-01-22 | 1 | 87 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-27-U-MP-100 | Install Plumbing Risers @ L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > MEP Risers & Rough at Units & Corridors at 27th Lvl > MEP Risers at 27th Lvl | TT_Task | TK_NotStart | 2026-11-18 | 2026-11-19 | 2 | 124 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-27-U-MP-120 | Install FP Risers @ L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > MEP Risers & Rough at Units & Corridors at 27th Lvl > MEP Risers at 27th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-11-23 | 2 | 124 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-27-U-MP-130 | Install Mech Risers @ L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > MEP Risers & Rough at Units & Corridors at 27th Lvl > MEP Risers at 27th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-11-25 | 2 | 125 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-27-U-FN-100 | Layout Interior Walls @ Units & Corridors - L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > Wall Layout & Framing at Units & Corridors at 8t27th h Lvl | TT_Task | TK_NotStart | 2026-12-08 | 2026-12-08 | 1 | 107 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors at 8t27th h Lvl
Phased TCO | C-27-U-FN-110 | Install Top Tracks @ Units & Corridors - L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > Wall Layout & Framing at Units & Corridors at 8t27th h Lvl | TT_Task | TK_NotStart | 2026-12-08 | 2026-12-09 | 2 | 107 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors at 8t27th h Lvl
Phased TCO | C-27-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > MEP Risers & Rough at Units & Corridors at 27th Lvl > MEP Risers at 27th Lvl | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-14 | 3 | 113 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-27-U-FN-120 | Install Drywall Framing @ Units & Corridors - L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > Wall Layout & Framing at Units & Corridors at 8t27th h Lvl | TT_Task | TK_NotStart | 2027-01-08 | 2027-01-15 | 6 | 88 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors at 8t27th h Lvl
Phased TCO | C-27-U-MP-150 | Install FP Rough @ Units & Corridors - L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > MEP Risers & Rough at Units & Corridors at 27th Lvl > MEP Rough at Units & Corridors at 27th Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-18 | 5 | 93 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-27-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > MEP Risers & Rough at Units & Corridors at 27th Lvl > MEP Rough at Units & Corridors at 27th Lvl | TT_Task | TK_NotStart | 2027-01-15 | 2027-01-22 | 6 | 93 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-27-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > MEP Risers & Rough at Units & Corridors at 27th Lvl > MEP Rough at Units & Corridors at 27th Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-26 | 7 | 88 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-27-U-MP-170 | Install Electrical Rough @ Units & Corridors - L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > MEP Risers & Rough at Units & Corridors at 27th Lvl > MEP Rough at Units & Corridors at 27th Lvl | TT_Task | TK_NotStart | 2027-01-21 | 2027-01-28 | 6 | 88 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-27-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > MEP Risers & Rough at Units & Corridors at 27th Lvl > MEP Rough at Units & Corridors at 27th Lvl | TT_Task | TK_NotStart | 2027-01-25 | 2027-01-29 | 5 | 88 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-27-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L27 | yes | Framing and MEP rough-in | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > MEP Risers & Rough at Units & Corridors at 27th Lvl > MEP Rough at Units & Corridors at 27th Lvl | TT_Task | TK_NotStart | 2027-02-01 | 2027-02-01 | 1 | 88 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-28-U-MP-100 | Install Plumbing Risers @ L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > MEP Risers & Rough at Units & Corridors at 28th Lvl > MEP Risers at 28th Lvl | TT_Task | TK_NotStart | 2026-11-25 | 2026-11-30 | 2 | 126 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-28-U-MP-120 | Install FP Risers @ L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > MEP Risers & Rough at Units & Corridors at 28th Lvl > MEP Risers at 28th Lvl | TT_Task | TK_NotStart | 2026-12-01 | 2026-12-02 | 2 | 126 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-28-U-MP-130 | Install Mech Risers @ L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > MEP Risers & Rough at Units & Corridors at 28th Lvl > MEP Risers at 28th Lvl | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-04 | 2 | 127 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-28-U-FN-100 | Layout Interior Walls @ Units & Corridors - L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > Wall Layout & Framing at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2026-12-15 | 2026-12-15 | 1 | 109 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-28-U-FN-110 | Install Top Tracks @ Units & Corridors - L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > Wall Layout & Framing at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2026-12-15 | 2026-12-16 | 2 | 109 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-28-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > MEP Risers & Rough at Units & Corridors at 28th Lvl > MEP Risers at 28th Lvl | TT_Task | TK_NotStart | 2026-12-17 | 2026-12-21 | 3 | 115 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-28-U-FN-120 | Install Drywall Framing @ Units & Corridors - L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > Wall Layout & Framing at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-25 | 6 | 89 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-28-U-MP-150 | Install FP Rough @ Units & Corridors - L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > MEP Risers & Rough at Units & Corridors at 28th Lvl > MEP Rough at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-01-26 | 5 | 94 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-28-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > MEP Risers & Rough at Units & Corridors at 28th Lvl > MEP Rough at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2027-01-25 | 2027-02-01 | 6 | 94 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-28-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > MEP Risers & Rough at Units & Corridors at 28th Lvl > MEP Rough at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2027-01-26 | 2027-02-03 | 7 | 89 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-28-U-MP-170 | Install Electrical Rough @ Units & Corridors - L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > MEP Risers & Rough at Units & Corridors at 28th Lvl > MEP Rough at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2027-01-29 | 2027-02-05 | 6 | 89 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-28-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > MEP Risers & Rough at Units & Corridors at 28th Lvl > MEP Rough at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-08 | 5 | 89 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-28-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L28 | yes | Framing and MEP rough-in | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > MEP Risers & Rough at Units & Corridors at 28th Lvl > MEP Rough at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-09 | 1 | 89 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-29-U-MP-100 | Install Plumbing Risers @ L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > MEP Risers & Rough at Units & Corridors at 29th Lvl > MEP Risers at 29th Lvl | TT_Task | TK_NotStart | 2026-12-04 | 2026-12-07 | 2 | 128 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-29-U-MP-120 | Install FP Risers @ L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > MEP Risers & Rough at Units & Corridors at 29th Lvl > MEP Risers at 29th Lvl | TT_Task | TK_NotStart | 2026-12-08 | 2026-12-09 | 2 | 128 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-29-U-MP-130 | Install Mech Risers @ L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > MEP Risers & Rough at Units & Corridors at 29th Lvl > MEP Risers at 29th Lvl | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-11 | 2 | 129 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-29-U-FN-100 | Layout Interior Walls @ Units & Corridors - L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > Wall Layout & Framing at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2026-12-23 | 2026-12-23 | 1 | 110 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-29-U-FN-110 | Install Top Tracks @ Units & Corridors - L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > Wall Layout & Framing at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2026-12-23 | 2026-12-24 | 2 | 110 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-29-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > MEP Risers & Rough at Units & Corridors at 29th Lvl > MEP Risers at 29th Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2026-12-30 | 3 | 116 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-29-U-FN-120 | Install Drywall Framing @ Units & Corridors - L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > Wall Layout & Framing at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2027-01-26 | 2027-02-02 | 6 | 90 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-29-U-MP-150 | Install FP Rough @ Units & Corridors - L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > MEP Risers & Rough at Units & Corridors at 29th Lvl > MEP Rough at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2027-01-28 | 2027-02-03 | 5 | 95 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-29-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > MEP Risers & Rough at Units & Corridors at 29th Lvl > MEP Rough at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-09 | 6 | 95 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-29-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > MEP Risers & Rough at Units & Corridors at 29th Lvl > MEP Rough at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2027-02-03 | 2027-02-11 | 7 | 90 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-29-U-MP-170 | Install Electrical Rough @ Units & Corridors - L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > MEP Risers & Rough at Units & Corridors at 29th Lvl > MEP Rough at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2027-02-08 | 2027-02-15 | 6 | 90 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-29-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > MEP Risers & Rough at Units & Corridors at 29th Lvl > MEP Rough at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2027-02-10 | 2027-02-16 | 5 | 90 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-29-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L29 | yes | Framing and MEP rough-in | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > MEP Risers & Rough at Units & Corridors at 29th Lvl > MEP Rough at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2027-02-17 | 2027-02-17 | 1 | 90 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-30-U-MP-100 | Install Plumbing Risers @ L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > MEP Risers & Rough at Units & Corridors at 30th Lvl > MEP Risers at 30th Lvl | TT_Task | TK_NotStart | 2026-12-11 | 2026-12-14 | 2 | 130 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-30-U-MP-120 | Install FP Risers @ L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > MEP Risers & Rough at Units & Corridors at 30th Lvl > MEP Risers at 30th Lvl | TT_Task | TK_NotStart | 2026-12-15 | 2026-12-16 | 2 | 130 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-30-U-MP-130 | Install Mech Risers @ L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > MEP Risers & Rough at Units & Corridors at 30th Lvl > MEP Risers at 30th Lvl | TT_Task | TK_NotStart | 2026-12-17 | 2026-12-18 | 2 | 131 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-30-U-FN-100 | Layout Interior Walls @ Units & Corridors - L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > Wall Layout & Framing at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2026-12-31 | 2026-12-31 | 1 | 112 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-30-U-FN-110 | Install Top Tracks @ Units & Corridors - L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > Wall Layout & Framing at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2026-12-31 | 2027-01-04 | 2 | 112 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-30-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > MEP Risers & Rough at Units & Corridors at 30th Lvl > MEP Risers at 30th Lvl | TT_Task | TK_NotStart | 2027-01-05 | 2027-01-07 | 3 | 118 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-30-U-FN-120 | Install Drywall Framing @ Units & Corridors - L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > Wall Layout & Framing at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2027-02-03 | 2027-02-10 | 6 | 91 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-30-U-MP-150 | Install FP Rough @ Units & Corridors - L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > MEP Risers & Rough at Units & Corridors at 30th Lvl > MEP Rough at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-11 | 5 | 96 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-30-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > MEP Risers & Rough at Units & Corridors at 30th Lvl > MEP Rough at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2027-02-10 | 2027-02-17 | 6 | 96 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-30-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > MEP Risers & Rough at Units & Corridors at 30th Lvl > MEP Rough at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-19 | 7 | 91 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-30-U-MP-170 | Install Electrical Rough @ Units & Corridors - L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > MEP Risers & Rough at Units & Corridors at 30th Lvl > MEP Rough at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-23 | 6 | 91 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-30-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > MEP Risers & Rough at Units & Corridors at 30th Lvl > MEP Rough at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2027-02-18 | 2027-02-24 | 5 | 91 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-30-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L30 | yes | Framing and MEP rough-in | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > MEP Risers & Rough at Units & Corridors at 30th Lvl > MEP Rough at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-02-25 | 1 | 91 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-31-U-MP-100 | Install Plumbing Risers @ L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > MEP Risers & Rough at Units & Corridors at 31st Lvl > MEP Risers at 31st Lvl | TT_Task | TK_NotStart | 2026-12-21 | 2026-12-22 | 2 | 131 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-31-U-MP-120 | Install FP Risers @ L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > MEP Risers & Rough at Units & Corridors at 31st Lvl > MEP Risers at 31st Lvl | TT_Task | TK_NotStart | 2026-12-23 | 2026-12-24 | 2 | 131 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-31-U-MP-130 | Install Mech Risers @ L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > MEP Risers & Rough at Units & Corridors at 31st Lvl > MEP Risers at 31st Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2026-12-29 | 2 | 132 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-31-U-FN-100 | Layout Interior Walls @ Units & Corridors - L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > Wall Layout & Framing at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-01-11 | 2027-01-11 | 1 | 113 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-31-U-FN-110 | Install Top Tracks @ Units & Corridors - L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > Wall Layout & Framing at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-01-11 | 2027-01-12 | 2 | 113 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-31-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > MEP Risers & Rough at Units & Corridors at 31st Lvl > MEP Risers at 31st Lvl | TT_Task | TK_NotStart | 2027-01-13 | 2027-01-15 | 3 | 119 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-31-U-FN-120 | Install Drywall Framing @ Units & Corridors - L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > Wall Layout & Framing at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-18 | 6 | 92 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-31-U-MP-150 | Install FP Rough @ Units & Corridors - L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > MEP Risers & Rough at Units & Corridors at 31st Lvl > MEP Rough at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-02-15 | 2027-02-19 | 5 | 97 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-31-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > MEP Risers & Rough at Units & Corridors at 31st Lvl > MEP Rough at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-02-18 | 2027-02-25 | 6 | 97 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-31-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > MEP Risers & Rough at Units & Corridors at 31st Lvl > MEP Rough at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-02-19 | 2027-03-01 | 7 | 92 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-31-U-MP-170 | Install Electrical Rough @ Units & Corridors - L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > MEP Risers & Rough at Units & Corridors at 31st Lvl > MEP Rough at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-02-24 | 2027-03-03 | 6 | 92 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-31-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > MEP Risers & Rough at Units & Corridors at 31st Lvl > MEP Rough at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-02-26 | 2027-03-04 | 5 | 92 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-31-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L31 | yes | Framing and MEP rough-in | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > MEP Risers & Rough at Units & Corridors at 31st Lvl > MEP Rough at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-03-05 | 2027-03-05 | 1 | 92 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-32-U-MP-100 | Install Plumbing Risers @ L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > MEP Risers & Rough at Units & Corridors at 32nd Lvl > MEP Risers at 32nd Lvl | TT_Task | TK_NotStart | 2026-12-30 | 2026-12-31 | 2 | 132 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-32-U-MP-120 | Install FP Risers @ L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > MEP Risers & Rough at Units & Corridors at 32nd Lvl > MEP Risers at 32nd Lvl | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-05 | 2 | 132 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-32-U-MP-130 | Install Mech Risers @ L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > MEP Risers & Rough at Units & Corridors at 32nd Lvl > MEP Risers at 32nd Lvl | TT_Task | TK_NotStart | 2027-01-06 | 2027-01-07 | 2 | 133 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-32-U-FN-100 | Layout Interior Walls @ Units & Corridors - L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > Wall Layout & Framing at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-01-20 | 1 | 113 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-32-U-FN-110 | Install Top Tracks @ Units & Corridors - L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > Wall Layout & Framing at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-01-21 | 2 | 113 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-32-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > MEP Risers & Rough at Units & Corridors at 32nd Lvl > MEP Risers at 32nd Lvl | TT_Task | TK_NotStart | 2027-01-22 | 2027-01-26 | 3 | 119 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-32-U-FN-120 | Install Drywall Framing @ Units & Corridors - L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > Wall Layout & Framing at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-02-19 | 2027-02-26 | 6 | 93 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-32-U-MP-150 | Install FP Rough @ Units & Corridors - L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > MEP Risers & Rough at Units & Corridors at 32nd Lvl > MEP Rough at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-03-01 | 5 | 98 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-32-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > MEP Risers & Rough at Units & Corridors at 32nd Lvl > MEP Rough at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-02-26 | 2027-03-05 | 6 | 98 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-32-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > MEP Risers & Rough at Units & Corridors at 32nd Lvl > MEP Rough at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-03-01 | 2027-03-09 | 7 | 93 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-32-U-MP-170 | Install Electrical Rough @ Units & Corridors - L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > MEP Risers & Rough at Units & Corridors at 32nd Lvl > MEP Rough at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-03-04 | 2027-03-11 | 6 | 93 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-32-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > MEP Risers & Rough at Units & Corridors at 32nd Lvl > MEP Rough at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-12 | 5 | 93 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-32-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L32 | yes | Framing and MEP rough-in | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > MEP Risers & Rough at Units & Corridors at 32nd Lvl > MEP Rough at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-03-15 | 2027-03-15 | 1 | 93 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-33-U-MP-100 | Install Plumbing Risers @ L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > MEP Risers & Rough at Units & Corridors at 33rd Lvl > MEP Risers at 33rd Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-08 | 2 | 134 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-33-U-MP-120 | Install FP Risers @ L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > MEP Risers & Rough at Units & Corridors at 33rd Lvl > MEP Risers at 33rd Lvl | TT_Task | TK_NotStart | 2027-01-11 | 2027-01-12 | 2 | 134 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-33-U-MP-130 | Install Mech Risers @ L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > MEP Risers & Rough at Units & Corridors at 33rd Lvl > MEP Risers at 33rd Lvl | TT_Task | TK_NotStart | 2027-01-13 | 2027-01-14 | 2 | 135 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-33-U-FN-100 | Layout Interior Walls @ Units & Corridors - L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > Wall Layout & Framing at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-01-22 | 2027-01-22 | 1 | 118 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-33-U-FN-110 | Install Top Tracks @ Units & Corridors - L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > Wall Layout & Framing at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-01-22 | 2027-01-25 | 2 | 118 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-33-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > MEP Risers & Rough at Units & Corridors at 33rd Lvl > MEP Risers at 33rd Lvl | TT_Task | TK_NotStart | 2027-01-26 | 2027-01-28 | 3 | 124 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-33-U-FN-120 | Install Drywall Framing @ Units & Corridors - L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > Wall Layout & Framing at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-03-01 | 2027-03-08 | 6 | 94 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-33-U-MP-150 | Install FP Rough @ Units & Corridors - L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > MEP Risers & Rough at Units & Corridors at 33rd Lvl > MEP Rough at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-09 | 5 | 99 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-33-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > MEP Risers & Rough at Units & Corridors at 33rd Lvl > MEP Rough at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-15 | 6 | 99 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-33-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > MEP Risers & Rough at Units & Corridors at 33rd Lvl > MEP Rough at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-03-09 | 2027-03-17 | 7 | 94 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-33-U-MP-170 | Install Electrical Rough @ Units & Corridors - L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > MEP Risers & Rough at Units & Corridors at 33rd Lvl > MEP Rough at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-03-12 | 2027-03-19 | 6 | 94 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-33-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > MEP Risers & Rough at Units & Corridors at 33rd Lvl > MEP Rough at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-03-16 | 2027-03-22 | 5 | 94 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-33-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L33 | yes | Framing and MEP rough-in | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > MEP Risers & Rough at Units & Corridors at 33rd Lvl > MEP Rough at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-03-23 | 2027-03-23 | 1 | 94 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-34-U-MP-100 | Install Plumbing Risers @ L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > MEP Risers & Rough at Units & Corridors at 34th Lvl > MEP Risers at 34th Lvl | TT_Task | TK_NotStart | 2027-01-14 | 2027-01-15 | 2 | 136 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-34-U-MP-120 | Install FP Risers @ L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > MEP Risers & Rough at Units & Corridors at 34th Lvl > MEP Risers at 34th Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-19 | 2 | 136 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-34-U-MP-130 | Install Mech Risers @ L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > MEP Risers & Rough at Units & Corridors at 34th Lvl > MEP Risers at 34th Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-01-21 | 2 | 137 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-34-U-FN-100 | Layout Interior Walls @ Units & Corridors - L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > Wall Layout & Framing at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-02-01 | 2027-02-01 | 1 | 119 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-34-U-FN-110 | Install Top Tracks @ Units & Corridors - L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > Wall Layout & Framing at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-02-01 | 2027-02-02 | 2 | 119 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-34-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > MEP Risers & Rough at Units & Corridors at 34th Lvl > MEP Risers at 34th Lvl | TT_Task | TK_NotStart | 2027-02-03 | 2027-02-05 | 3 | 125 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-34-U-FN-120 | Install Drywall Framing @ Units & Corridors - L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > Wall Layout & Framing at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-03-09 | 2027-03-16 | 6 | 95 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-34-U-MP-150 | Install FP Rough @ Units & Corridors - L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > MEP Risers & Rough at Units & Corridors at 34th Lvl > MEP Rough at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-17 | 5 | 100 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-34-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > MEP Risers & Rough at Units & Corridors at 34th Lvl > MEP Rough at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-03-16 | 2027-03-23 | 6 | 100 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-34-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > MEP Risers & Rough at Units & Corridors at 34th Lvl > MEP Rough at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-25 | 7 | 95 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-34-U-MP-170 | Install Electrical Rough @ Units & Corridors - L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > MEP Risers & Rough at Units & Corridors at 34th Lvl > MEP Rough at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-03-22 | 2027-03-29 | 6 | 95 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-34-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > MEP Risers & Rough at Units & Corridors at 34th Lvl > MEP Rough at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-30 | 5 | 95 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-34-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L34 | yes | Framing and MEP rough-in | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > MEP Risers & Rough at Units & Corridors at 34th Lvl > MEP Rough at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-03-31 | 2027-03-31 | 1 | 95 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-35-U-MP-100 | Install Plumbing Risers @ L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > MEP Risers & Rough at Units & Corridors at 35th Lvl > MEP Risers at 35th Lvl | TT_Task | TK_NotStart | 2027-02-01 | 2027-02-02 | 2 | 131 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-35-U-MP-120 | Install FP Risers @ L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > MEP Risers & Rough at Units & Corridors at 35th Lvl > MEP Risers at 35th Lvl | TT_Task | TK_NotStart | 2027-02-03 | 2027-02-04 | 2 | 131 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-35-U-MP-130 | Install Mech Risers @ L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > MEP Risers & Rough at Units & Corridors at 35th Lvl > MEP Risers at 35th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-08 | 2 | 132 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-35-U-FN-100 | Layout Interior Walls @ Units & Corridors - L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > Wall Layout & Framing at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-09 | 1 | 120 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-35-U-FN-110 | Install Top Tracks @ Units & Corridors - L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > Wall Layout & Framing at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-10 | 2 | 120 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-35-U-MP-110 | Install Electrical & Low Voltage & BDA Risers @ L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > MEP Risers & Rough at Units & Corridors at 35th Lvl > MEP Risers at 35th Lvl | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-15 | 3 | 126 | Interior MEPs & Finishes | MEP Risers
Phased TCO | C-35-U-FN-120 | Install Drywall Framing @ Units & Corridors - L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > Wall Layout & Framing at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-24 | 6 | 96 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-35-U-MP-150 | Install FP Rough @ Units & Corridors - L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > MEP Risers & Rough at Units & Corridors at 35th Lvl > MEP Rough at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-03-19 | 2027-03-25 | 5 | 101 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-35-U-MP-160 | Install HVAC Ductwork @ Units & Corridors - L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > MEP Risers & Rough at Units & Corridors at 35th Lvl > MEP Rough at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-31 | 6 | 101 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-35-U-MP-140 | Install Plumbing Rough @ Units & Corridors - L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > MEP Risers & Rough at Units & Corridors at 35th Lvl > MEP Rough at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-03-25 | 2027-04-02 | 7 | 96 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-35-U-MP-170 | Install Electrical Rough @ Units & Corridors - L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > MEP Risers & Rough at Units & Corridors at 35th Lvl > MEP Rough at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-03-30 | 2027-04-06 | 6 | 96 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-35-U-MP-180 | Install FA & Low Voltage Rough @ Units & Corridors - L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > MEP Risers & Rough at Units & Corridors at 35th Lvl > MEP Rough at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-07 | 5 | 96 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-35-U-MP-190 | Inspect MEP Rough @ Units & Corridors - L35 | yes | Framing and MEP rough-in | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > MEP Risers & Rough at Units & Corridors at 35th Lvl > MEP Rough at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-04-08 | 2027-04-08 | 1 | 96 | Interior MEPs & Finishes | MEP Rough at Units & Corridors
Phased TCO | C-36-IN-MP-100 | Install Plumbing Risers @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > MEP Risers & Rough at Indoor 36th Pool Lvl > MEP Risers at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-10 | 2 | 160 | Interior MEPs & Finishes | MEP Risers at Indoor
Phased TCO | C-36-IN-MP-120 | Install FP Risers @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > MEP Risers & Rough at Indoor 36th Pool Lvl > MEP Risers at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-12 | 2 | 160 | Interior MEPs & Finishes | MEP Risers at Indoor
Phased TCO | C-36-IN-MP-130 | Install Mech Risers @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > MEP Risers & Rough at Indoor 36th Pool Lvl > MEP Risers at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-02-15 | 2027-02-16 | 2 | 160 | Interior MEPs & Finishes | MEP Risers at Indoor
Phased TCO | C-36-IN-FN-100 | Layout Interior Walls @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > Wall Layout & Framing at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-04-29 | 2027-04-29 | 1 | 100 | Interior MEPs & Finishes | Wall Layout & Framing at Indoor
Phased TCO | C-36-IN-FN-110 | Install Top Tracks @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > Wall Layout & Framing at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-04-29 | 2027-04-29 | 1 | 100 | Interior MEPs & Finishes | Wall Layout & Framing at Indoor
Phased TCO | C-36-IN-FN-120 | Install Drywall Framing @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > Wall Layout & Framing at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-04-30 | 2027-05-05 | 4 | 100 | Interior MEPs & Finishes | Wall Layout & Framing at Indoor
Phased TCO | C-36-IN-MP-110 | Install Electrical & Low Voltage & BDA Risers @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > MEP Risers & Rough at Indoor 36th Pool Lvl > MEP Risers at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-04-30 | 2027-05-04 | 3 | 104 | Interior MEPs & Finishes | MEP Risers at Indoor
Phased TCO | C-36-IN-MP-150 | Install FP Rough @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > MEP Risers & Rough at Indoor 36th Pool Lvl > MEP Rough at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-05-04 | 2027-05-07 | 4 | 104 | Interior MEPs & Finishes | MEP Rough at Indoor
Phased TCO | C-36-IN-MP-140 | Install Plumbing Rough @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > MEP Risers & Rough at Indoor 36th Pool Lvl > MEP Rough at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-05-06 | 2027-05-12 | 5 | 100 | Interior MEPs & Finishes | MEP Rough at Indoor
Phased TCO | C-36-IN-MP-160 | Install HVAC Ductwork @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > MEP Risers & Rough at Indoor 36th Pool Lvl > MEP Rough at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-05-06 | 2027-05-12 | 5 | 104 | Interior MEPs & Finishes | MEP Rough at Indoor
Phased TCO | C-36-IN-MP-170 | Install Electrical Rough @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > MEP Risers & Rough at Indoor 36th Pool Lvl > MEP Rough at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-05-11 | 2027-05-17 | 5 | 100 | Interior MEPs & Finishes | MEP Rough at Indoor
Phased TCO | C-36-IN-MP-180 | Install FA & Low Voltage Rough @ Indoor - L36 | yes | Framing and MEP rough-in | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > MEP Risers & Rough at Indoor 36th Pool Lvl > MEP Rough at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-05-13 | 2027-05-18 | 4 | 100 | Interior MEPs & Finishes | MEP Rough at Indoor
Phased TCO | C-01-UC-FN-200 | Install Drywall One Side & Insulation @ L1 | yes | Drywall and prime paint | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Interior Finishes at 1st Lvl | TT_Task | TK_NotStart | 2027-06-01 | 2027-06-04 | 4 | 7 | Interior MEPs & Finishes | Interior Finishes
Phased TCO | C-01-UC-FN-210 | Hang Drywall @ L1 | yes | Drywall and prime paint | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Interior Finishes at 1st Lvl | TT_Task | TK_NotStart | 2027-06-07 | 2027-06-14 | 6 | 7 | Interior MEPs & Finishes | Interior Finishes
Phased TCO | C-01-UC-FN-230 | Tape & Finish Drywall @ L1 | yes | Drywall and prime paint | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Interior Finishes at 1st Lvl | TT_Task | TK_NotStart | 2027-06-09 | 2027-06-15 | 5 | 7 | Interior MEPs & Finishes | Interior Finishes
Phased TCO | C-01-UC-FN-270 | Paint Drywall - 1st Coat @ L1 | yes | Drywall and prime paint | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Interior Finishes at 1st Lvl | TT_Task | TK_NotStart | 2027-06-11 | 2027-06-16 | 4 | 14 | Interior MEPs & Finishes | Interior Finishes
Phased TCO | C-01-UC-FN-260 | Hang Interior Doors @ L1 | yes | Drywall and prime paint | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Interior Finishes at 1st Lvl | TT_Task | TK_NotStart | 2027-06-17 | 2027-06-18 | 2 | 24 | Interior MEPs & Finishes | Interior Finishes
Phased TCO | C-02-UC-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units & Common Areas - L2 | yes | Drywall and prime paint | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior Wall Framing & MEP Rough at Units & Common Areas & Corridors at 2nd Lvl > Wall Layout & Framing at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-06-09 | 2026-06-15 | 5 | 157 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Common Areas
Phased TCO | C-02-UC-FN-200 | Install Drywall One Side & Insulation @ Units & Common Areas - L2 | yes | Drywall and prime paint | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-07-08 | 2026-07-14 | 5 | 130 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Phased TCO | C-02-UC-FN-210 | Hang Drywall @ Units & Common Areas - L2 | yes | Drywall and prime paint | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-07-15 | 2026-07-21 | 5 | 130 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Phased TCO | C-02-UC-FN-230 | Tape & Finish Drywall @ Units & Common Areas - L2 | yes | Drywall and prime paint | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-07-16 | 2026-07-22 | 5 | 135 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Phased TCO | C-02-UC-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units & Common Areas - L2 | yes | Drywall and prime paint | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-07-22 | 2026-07-28 | 5 | 130 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Phased TCO | C-02-UC-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units & Common Areas - L2 | yes | Drywall and prime paint | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-07-27 | 2026-07-31 | 5 | 130 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Phased TCO | C-02-UC-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units & Common Areas - L2 | yes | Drywall and prime paint | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-07-30 | 2026-08-04 | 4 | 130 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Phased TCO | C-02-UC-FN-270 | Paint Drywall - 1st Coat @ Units & Common Areas - L2 | yes | Drywall and prime paint | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-04 | 2026-08-07 | 4 | 130 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Phased TCO | C-03-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units & Corridors - L3 | yes | Drywall and prime paint | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior Wall Framing & MEP Rough at Units Corridors at 3rd Lvl > Wall Layout & Framing at Units & Corridors at 3rd Lvl | TT_Task | TK_NotStart | 2026-06-24 | 2026-06-30 | 5 | 95 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-03-U-FN-200 | Install Drywall One Side & Insulation @ Units - L3 | yes | Drywall and prime paint | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-07-20 | 2026-07-24 | 5 | 71 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-03-U-FN-210 | Hang Drywall @ Units - L3 | yes | Drywall and prime paint | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-07-27 | 2026-07-31 | 5 | 71 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-03-U-FN-230 | Tape & Finish Drywall @ Units - L3 | yes | Drywall and prime paint | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-07-28 | 2026-08-03 | 5 | 76 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-03-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L3 | yes | Drywall and prime paint | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-03 | 2026-08-07 | 5 | 71 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-03-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L3 | yes | Drywall and prime paint | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-06 | 2026-08-12 | 5 | 71 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-03-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L3 | yes | Drywall and prime paint | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-11 | 2026-08-14 | 4 | 71 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-03-U-FN-270 | Paint Drywall - 1st Coat @ Units - L3 | yes | Drywall and prime paint | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-14 | 2026-08-19 | 4 | 71 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-04-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units & Corridors - L4 | yes | Drywall and prime paint | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 4th Lvl > Wall Layout & Framing at Units & Corridors at 4th Lvl | TT_Task | TK_NotStart | 2026-07-07 | 2026-07-13 | 5 | 92 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-04-U-FN-200 | Install Drywall One Side & Insulation @ Units - L4 | yes | Drywall and prime paint | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-07-29 | 2026-08-04 | 5 | 69 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-04-U-FN-210 | Hang Drywall @ Units - L4 | yes | Drywall and prime paint | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-08-05 | 2026-08-11 | 5 | 69 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-04-U-FN-230 | Tape & Finish Drywall @ Units - L4 | yes | Drywall and prime paint | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-08-06 | 2026-08-12 | 5 | 74 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-04-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L4 | yes | Drywall and prime paint | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-08-12 | 2026-08-18 | 5 | 69 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-04-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L4 | yes | Drywall and prime paint | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-08-17 | 2026-08-21 | 5 | 69 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-04-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L4 | yes | Drywall and prime paint | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-08-20 | 2026-08-25 | 4 | 69 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-04-U-FN-270 | Paint Drywall - 1st Coat @ Units - L4 | yes | Drywall and prime paint | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-08-25 | 2026-08-28 | 4 | 69 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-05-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units & Corridors - L5 | yes | Drywall and prime paint | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 5th Lvl > Wall Layout & Framing at Units & Corridors at 5th Lvl | TT_Task | TK_NotStart | 2026-07-14 | 2026-07-20 | 5 | 92 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-05-U-FN-200 | Install Drywall One Side & Insulation @ Units - L5 | yes | Drywall and prime paint | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-08-07 | 2026-08-13 | 5 | 67 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-05-U-FN-210 | Hang Drywall @ Units - L5 | yes | Drywall and prime paint | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-08-14 | 2026-08-20 | 5 | 67 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-05-U-FN-230 | Tape & Finish Drywall @ Units - L5 | yes | Drywall and prime paint | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-08-17 | 2026-08-21 | 5 | 72 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-05-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L5 | yes | Drywall and prime paint | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-08-21 | 2026-08-27 | 5 | 67 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-05-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L5 | yes | Drywall and prime paint | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-08-26 | 2026-09-01 | 5 | 67 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-05-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L5 | yes | Drywall and prime paint | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-08-31 | 2026-09-03 | 4 | 67 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-05-U-FN-270 | Paint Drywall - 1st Coat @ Units - L5 | yes | Drywall and prime paint | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-09-03 | 2026-09-09 | 4 | 67 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-06-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units & Corridors - L6 | yes | Drywall and prime paint | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 6th Lvl > Wall Layout & Framing at Units & Corridors at 6th Lvl | TT_Task | TK_NotStart | 2026-07-21 | 2026-07-27 | 5 | 92 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-06-U-FN-200 | Install Drywall One Side & Insulation @ Units - L6 | yes | Drywall and prime paint | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-08-17 | 2026-08-21 | 5 | 66 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-06-U-FN-210 | Hang Drywall @ Units - L6 | yes | Drywall and prime paint | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-08-24 | 2026-08-28 | 5 | 66 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-06-U-FN-230 | Tape & Finish Drywall @ Units - L6 | yes | Drywall and prime paint | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-08-25 | 2026-08-31 | 5 | 71 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-06-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L6 | yes | Drywall and prime paint | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-08-31 | 2026-09-04 | 5 | 66 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-06-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L6 | yes | Drywall and prime paint | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-09-03 | 2026-09-10 | 5 | 66 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-06-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L6 | yes | Drywall and prime paint | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-09-09 | 2026-09-14 | 4 | 66 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-06-U-FN-270 | Paint Drywall - 1st Coat @ Units - L6 | yes | Drywall and prime paint | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-09-14 | 2026-09-17 | 4 | 66 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-07-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L7 | yes | Drywall and prime paint | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 7th Lvl > Wall Layout & Framing at Units & Corridors at 7th Lvl | TT_Task | TK_NotStart | 2026-07-28 | 2026-08-04 | 6 | 87 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-07-U-FN-200 | Install Drywall One Side & Insulation @ Units - L7 | yes | Drywall and prime paint | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-08-24 | 2026-08-26 | 3 | 66 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-07-U-FN-210 | Hang Drywall @ Units - L7 | yes | Drywall and prime paint | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-08-27 | 2026-09-03 | 6 | 66 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-07-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L7 | yes | Drywall and prime paint | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-08-27 | 2026-09-03 | 6 | 71 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-07-U-FN-230 | Tape & Finish Drywall @ Units - L7 | yes | Drywall and prime paint | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-09-04 | 2026-09-14 | 6 | 66 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-07-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L7 | yes | Drywall and prime paint | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-09-04 | 2026-09-14 | 6 | 71 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-07-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L7 | yes | Drywall and prime paint | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-18 | 4 | 66 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-07-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L7 | yes | Drywall and prime paint | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-09-18 | 2026-09-24 | 5 | 66 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-08-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L8 | yes | Drywall and prime paint | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 8th Lvl > Wall Layout & Framing at Units & Corridors at 8th Lvl | TT_Task | TK_NotStart | 2026-08-05 | 2026-08-12 | 6 | 88 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-08-U-FN-200 | Install Drywall One Side & Insulation @ Units - L8 | yes | Drywall and prime paint | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-09-01 | 2026-09-03 | 3 | 67 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-08-U-FN-210 | Hang Drywall @ Units - L8 | yes | Drywall and prime paint | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-09-04 | 2026-09-14 | 6 | 67 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-08-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L8 | yes | Drywall and prime paint | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-09-04 | 2026-09-14 | 6 | 72 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-08-U-FN-230 | Tape & Finish Drywall @ Units - L8 | yes | Drywall and prime paint | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-22 | 6 | 67 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-08-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L8 | yes | Drywall and prime paint | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-22 | 6 | 72 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-08-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L8 | yes | Drywall and prime paint | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-09-23 | 2026-09-28 | 4 | 67 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-08-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L8 | yes | Drywall and prime paint | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-09-28 | 2026-10-02 | 5 | 67 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-09-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L9 | yes | Drywall and prime paint | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 9th Lvl > Wall Layout & Framing at Units & Corridors at 9th Lvl | TT_Task | TK_NotStart | 2026-08-13 | 2026-08-20 | 6 | 89 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-09-U-FN-200 | Install Drywall One Side & Insulation @ Units - L9 | yes | Drywall and prime paint | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-09-08 | 2026-09-10 | 3 | 70 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-09-U-FN-210 | Hang Drywall @ Units - L9 | yes | Drywall and prime paint | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-09-11 | 2026-09-18 | 6 | 70 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-09-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L9 | yes | Drywall and prime paint | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-09-11 | 2026-09-18 | 6 | 75 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-09-U-FN-230 | Tape & Finish Drywall @ Units - L9 | yes | Drywall and prime paint | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-09-21 | 2026-09-28 | 6 | 70 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-09-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L9 | yes | Drywall and prime paint | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-09-21 | 2026-09-28 | 6 | 75 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-09-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L9 | yes | Drywall and prime paint | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-09-29 | 2026-10-02 | 4 | 70 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-09-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L9 | yes | Drywall and prime paint | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-10-02 | 2026-10-08 | 5 | 70 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-10-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L10 | yes | Drywall and prime paint | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 10th Lvl > Wall Layout & Framing at Units & Corridors at 10th Lvl | TT_Task | TK_NotStart | 2026-08-21 | 2026-08-28 | 6 | 90 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-10-U-FN-200 | Install Drywall One Side & Insulation @ Units - L10 | yes | Drywall and prime paint | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-17 | 3 | 72 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-10-U-FN-210 | Hang Drywall @ Units - L10 | yes | Drywall and prime paint | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-09-18 | 2026-09-25 | 6 | 72 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-10-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L10 | yes | Drywall and prime paint | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-09-18 | 2026-09-25 | 6 | 77 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-10-U-FN-230 | Tape & Finish Drywall @ Units - L10 | yes | Drywall and prime paint | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-09-28 | 2026-10-05 | 6 | 72 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-10-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L10 | yes | Drywall and prime paint | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-09-28 | 2026-10-05 | 6 | 77 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-10-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L10 | yes | Drywall and prime paint | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-09 | 4 | 72 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-10-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L10 | yes | Drywall and prime paint | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-15 | 5 | 72 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-11-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L11 | yes | Drywall and prime paint | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 11th Lvl > Wall Layout & Framing at Units & Corridors at 11th Lvl | TT_Task | TK_NotStart | 2026-08-31 | 2026-09-08 | 6 | 91 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-11-U-FN-200 | Install Drywall One Side & Insulation @ Units - L11 | yes | Drywall and prime paint | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-09-23 | 2026-09-25 | 3 | 73 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-11-U-FN-210 | Hang Drywall @ Units - L11 | yes | Drywall and prime paint | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-09-28 | 2026-10-05 | 6 | 73 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-11-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L11 | yes | Drywall and prime paint | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-09-28 | 2026-10-05 | 6 | 78 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-11-U-FN-230 | Tape & Finish Drywall @ Units - L11 | yes | Drywall and prime paint | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-13 | 6 | 73 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-11-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L11 | yes | Drywall and prime paint | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-13 | 6 | 78 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-11-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L11 | yes | Drywall and prime paint | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-10-14 | 2026-10-19 | 4 | 73 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-11-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L11 | yes | Drywall and prime paint | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-10-19 | 2026-10-23 | 5 | 73 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-12-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L12 | yes | Drywall and prime paint | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 12th Lvl > Wall Layout & Framing at Units & Corridors at 12th Lvl | TT_Task | TK_NotStart | 2026-09-09 | 2026-09-16 | 6 | 92 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-12-U-FN-200 | Install Drywall One Side & Insulation @ Units - L12 | yes | Drywall and prime paint | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-05 | 3 | 74 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-12-U-FN-210 | Hang Drywall @ Units - L12 | yes | Drywall and prime paint | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-13 | 6 | 74 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-12-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L12 | yes | Drywall and prime paint | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-13 | 6 | 79 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-12-U-FN-230 | Tape & Finish Drywall @ Units - L12 | yes | Drywall and prime paint | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-10-14 | 2026-10-21 | 6 | 74 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-12-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L12 | yes | Drywall and prime paint | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-10-14 | 2026-10-21 | 6 | 79 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-12-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L12 | yes | Drywall and prime paint | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-10-22 | 2026-10-27 | 4 | 74 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-12-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L12 | yes | Drywall and prime paint | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-10-27 | 2026-11-02 | 5 | 74 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-14-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L14 | yes | Drywall and prime paint | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 14th Lvl > Wall Layout & Framing at Units & Corridors at 14th Lvl | TT_Task | TK_NotStart | 2026-09-17 | 2026-09-24 | 6 | 93 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-14-U-FN-200 | Install Drywall One Side & Insulation @ Units - L14 | yes | Drywall and prime paint | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-13 | 3 | 75 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-14-U-FN-210 | Hang Drywall @ Units - L14 | yes | Drywall and prime paint | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2026-10-14 | 2026-10-21 | 6 | 75 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-14-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L14 | yes | Drywall and prime paint | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2026-10-14 | 2026-10-21 | 6 | 80 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-14-U-FN-230 | Tape & Finish Drywall @ Units - L14 | yes | Drywall and prime paint | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2026-10-22 | 2026-10-29 | 6 | 75 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-14-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L14 | yes | Drywall and prime paint | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2026-10-22 | 2026-10-29 | 6 | 80 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-14-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L14 | yes | Drywall and prime paint | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-04 | 4 | 75 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-14-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L14 | yes | Drywall and prime paint | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-10 | 5 | 75 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-15-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L15 | yes | Drywall and prime paint | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 15th Lvl > Wall Layout & Framing at Units & Corridors at 15th Lvl | TT_Task | TK_NotStart | 2026-09-25 | 2026-10-02 | 6 | 94 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-15-U-FN-200 | Install Drywall One Side & Insulation @ Units - L15 | yes | Drywall and prime paint | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2026-10-19 | 2026-10-21 | 3 | 76 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-15-U-FN-210 | Hang Drywall @ Units - L15 | yes | Drywall and prime paint | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2026-10-22 | 2026-10-29 | 6 | 76 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-15-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L15 | yes | Drywall and prime paint | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2026-10-22 | 2026-10-29 | 6 | 81 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-15-U-FN-230 | Tape & Finish Drywall @ Units - L15 | yes | Drywall and prime paint | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-06 | 6 | 76 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-15-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L15 | yes | Drywall and prime paint | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-06 | 6 | 81 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-15-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L15 | yes | Drywall and prime paint | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-12 | 4 | 76 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-15-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L15 | yes | Drywall and prime paint | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2026-11-12 | 2026-11-18 | 5 | 76 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-16-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L16 | yes | Drywall and prime paint | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 16th Lvl > Wall Layout & Framing at Units & Corridors at 16th Lvl | TT_Task | TK_NotStart | 2026-10-05 | 2026-10-12 | 6 | 95 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-16-U-FN-200 | Install Drywall One Side & Insulation @ Units - L16 | yes | Drywall and prime paint | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2026-10-27 | 2026-10-29 | 3 | 77 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-16-U-FN-210 | Hang Drywall @ Units - L16 | yes | Drywall and prime paint | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-06 | 6 | 77 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-16-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L16 | yes | Drywall and prime paint | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-06 | 6 | 82 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-16-U-FN-230 | Tape & Finish Drywall @ Units - L16 | yes | Drywall and prime paint | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-16 | 6 | 77 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-16-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L16 | yes | Drywall and prime paint | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-16 | 6 | 82 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-16-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L16 | yes | Drywall and prime paint | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2026-11-17 | 2026-11-20 | 4 | 77 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-16-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L16 | yes | Drywall and prime paint | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-11-30 | 5 | 77 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-17-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L17 | yes | Drywall and prime paint | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 17th Lvl > Wall Layout & Framing at Units & Corridors at 17th Lvl | TT_Task | TK_NotStart | 2026-10-13 | 2026-10-20 | 6 | 96 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-17-U-FN-200 | Install Drywall One Side & Insulation @ Units - L17 | yes | Drywall and prime paint | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-06 | 3 | 78 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-17-U-FN-210 | Hang Drywall @ Units - L17 | yes | Drywall and prime paint | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-16 | 6 | 78 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-17-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L17 | yes | Drywall and prime paint | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-16 | 6 | 83 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-17-U-FN-230 | Tape & Finish Drywall @ Units - L17 | yes | Drywall and prime paint | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2026-11-17 | 2026-11-24 | 6 | 78 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-17-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L17 | yes | Drywall and prime paint | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2026-11-17 | 2026-11-24 | 6 | 83 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-17-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L17 | yes | Drywall and prime paint | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2026-11-25 | 2026-12-02 | 4 | 78 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-17-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L17 | yes | Drywall and prime paint | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2026-12-02 | 2026-12-08 | 5 | 78 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-18-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L18 | yes | Drywall and prime paint | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 18th Lvl > Wall Layout & Framing at Units & Corridors at 18th Lvl | TT_Task | TK_NotStart | 2026-10-21 | 2026-10-28 | 6 | 97 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-18-U-FN-200 | Install Drywall One Side & Insulation @ Units - L18 | yes | Drywall and prime paint | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2026-11-12 | 2026-11-16 | 3 | 79 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-18-U-FN-210 | Hang Drywall @ Units - L18 | yes | Drywall and prime paint | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2026-11-17 | 2026-11-24 | 6 | 79 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-18-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L18 | yes | Drywall and prime paint | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2026-11-17 | 2026-11-24 | 6 | 84 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-18-U-FN-230 | Tape & Finish Drywall @ Units - L18 | yes | Drywall and prime paint | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2026-11-25 | 2026-12-04 | 6 | 79 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-18-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L18 | yes | Drywall and prime paint | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2026-11-25 | 2026-12-04 | 6 | 84 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-18-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L18 | yes | Drywall and prime paint | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-10 | 4 | 79 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-18-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L18 | yes | Drywall and prime paint | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-16 | 5 | 79 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-19-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L19 | yes | Drywall and prime paint | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 19th Lvl > Wall Layout & Framing at Units & Corridors at 19th Lvl | TT_Task | TK_NotStart | 2026-10-29 | 2026-11-05 | 6 | 98 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-19-U-FN-200 | Install Drywall One Side & Insulation @ Units - L19 | yes | Drywall and prime paint | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-11-24 | 3 | 80 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-19-U-FN-210 | Hang Drywall @ Units - L19 | yes | Drywall and prime paint | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2026-11-25 | 2026-12-04 | 6 | 80 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-19-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L19 | yes | Drywall and prime paint | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2026-11-25 | 2026-12-04 | 6 | 85 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-19-U-FN-230 | Tape & Finish Drywall @ Units - L19 | yes | Drywall and prime paint | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-14 | 6 | 80 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-19-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L19 | yes | Drywall and prime paint | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-14 | 6 | 85 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-19-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L19 | yes | Drywall and prime paint | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2026-12-15 | 2026-12-18 | 4 | 80 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-19-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L19 | yes | Drywall and prime paint | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2026-12-18 | 2026-12-24 | 5 | 80 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-20-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L20 | yes | Drywall and prime paint | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 20th Lvl > Wall Layout & Framing at Units & Corridors at 20th Lvl | TT_Task | TK_NotStart | 2026-11-06 | 2026-11-13 | 6 | 99 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-20-U-FN-200 | Install Drywall One Side & Insulation @ Units - L20 | yes | Drywall and prime paint | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2026-12-02 | 2026-12-04 | 3 | 81 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-20-U-FN-210 | Hang Drywall @ Units - L20 | yes | Drywall and prime paint | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-14 | 6 | 81 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-20-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L20 | yes | Drywall and prime paint | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-14 | 6 | 86 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-20-U-FN-230 | Tape & Finish Drywall @ Units - L20 | yes | Drywall and prime paint | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2026-12-15 | 2026-12-22 | 6 | 81 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-20-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L20 | yes | Drywall and prime paint | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2026-12-15 | 2026-12-22 | 6 | 86 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-20-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L20 | yes | Drywall and prime paint | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2026-12-23 | 2026-12-29 | 4 | 81 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-20-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L20 | yes | Drywall and prime paint | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2026-12-29 | 2027-01-05 | 5 | 81 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-21-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L21 | yes | Drywall and prime paint | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 21st Lvl > Wall Layout & Framing at Units & Corridors at 21st Lvl | TT_Task | TK_NotStart | 2026-11-16 | 2026-11-23 | 6 | 100 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-21-U-FN-200 | Install Drywall One Side & Insulation @ Units - L21 | yes | Drywall and prime paint | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-14 | 3 | 82 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-21-U-FN-210 | Hang Drywall @ Units - L21 | yes | Drywall and prime paint | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2026-12-15 | 2026-12-22 | 6 | 82 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-21-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L21 | yes | Drywall and prime paint | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2026-12-15 | 2026-12-22 | 6 | 87 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-21-U-FN-230 | Tape & Finish Drywall @ Units - L21 | yes | Drywall and prime paint | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2026-12-23 | 2026-12-31 | 6 | 82 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-21-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L21 | yes | Drywall and prime paint | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2026-12-23 | 2026-12-31 | 6 | 87 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-21-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L21 | yes | Drywall and prime paint | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-07 | 4 | 82 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-21-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L21 | yes | Drywall and prime paint | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-13 | 5 | 82 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-22-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L22 | yes | Drywall and prime paint | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 22nd Lvl > Wall Layout & Framing at Units & Corridors at 22nd Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-12-03 | 6 | 101 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-22-U-FN-200 | Install Drywall One Side & Insulation @ Units - L22 | yes | Drywall and prime paint | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2026-12-18 | 2026-12-22 | 3 | 83 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-22-U-FN-210 | Hang Drywall @ Units - L22 | yes | Drywall and prime paint | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2026-12-23 | 2026-12-31 | 6 | 83 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-22-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L22 | yes | Drywall and prime paint | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2026-12-23 | 2026-12-31 | 6 | 88 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-22-U-FN-230 | Tape & Finish Drywall @ Units - L22 | yes | Drywall and prime paint | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-11 | 6 | 83 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-22-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L22 | yes | Drywall and prime paint | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-11 | 6 | 88 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-22-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L22 | yes | Drywall and prime paint | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-15 | 4 | 83 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-22-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L22 | yes | Drywall and prime paint | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-01-15 | 2027-01-21 | 5 | 83 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-23-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L23 | yes | Drywall and prime paint | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 23rd Lvl > Wall Layout & Framing at Units & Corridors at 23rd Lvl | TT_Task | TK_NotStart | 2026-12-04 | 2026-12-11 | 6 | 102 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-23-U-FN-200 | Install Drywall One Side & Insulation @ Units - L23 | yes | Drywall and prime paint | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2026-12-29 | 2026-12-31 | 3 | 84 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-23-U-FN-210 | Hang Drywall @ Units - L23 | yes | Drywall and prime paint | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-11 | 6 | 84 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-23-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L23 | yes | Drywall and prime paint | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-11 | 6 | 89 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-23-U-FN-230 | Tape & Finish Drywall @ Units - L23 | yes | Drywall and prime paint | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-19 | 6 | 84 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-23-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L23 | yes | Drywall and prime paint | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-19 | 6 | 89 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-23-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L23 | yes | Drywall and prime paint | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-01-25 | 4 | 84 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-23-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L23 | yes | Drywall and prime paint | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-01-25 | 2027-01-29 | 5 | 84 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-24-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L24 | yes | Drywall and prime paint | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 24th Lvl > Wall Layout & Framing at Units & Corridors at 24th Lvl | TT_Task | TK_NotStart | 2026-12-14 | 2026-12-21 | 6 | 103 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-24-U-FN-200 | Install Drywall One Side & Insulation @ Units - L24 | yes | Drywall and prime paint | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-11 | 3 | 85 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-24-U-FN-210 | Hang Drywall @ Units - L24 | yes | Drywall and prime paint | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-19 | 6 | 85 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-24-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L24 | yes | Drywall and prime paint | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-19 | 6 | 90 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-24-U-FN-230 | Tape & Finish Drywall @ Units - L24 | yes | Drywall and prime paint | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-01-27 | 6 | 85 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-24-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L24 | yes | Drywall and prime paint | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-01-27 | 6 | 90 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-24-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L24 | yes | Drywall and prime paint | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-01-28 | 2027-02-02 | 4 | 85 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-24-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L24 | yes | Drywall and prime paint | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-08 | 5 | 85 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-25-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L25 | yes | Drywall and prime paint | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 25th Lvl > Wall Layout & Framing at Units & Corridors at 25th Lvl | TT_Task | TK_NotStart | 2026-12-22 | 2026-12-30 | 6 | 104 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-25-U-FN-200 | Install Drywall One Side & Insulation @ Units - L25 | yes | Drywall and prime paint | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-01-15 | 2027-01-19 | 3 | 86 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-25-U-FN-210 | Hang Drywall @ Units - L25 | yes | Drywall and prime paint | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-01-27 | 6 | 86 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-25-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L25 | yes | Drywall and prime paint | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-01-27 | 6 | 91 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-25-U-FN-230 | Tape & Finish Drywall @ Units - L25 | yes | Drywall and prime paint | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-01-28 | 2027-02-04 | 6 | 86 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-25-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L25 | yes | Drywall and prime paint | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-01-28 | 2027-02-04 | 6 | 91 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-25-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L25 | yes | Drywall and prime paint | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-10 | 4 | 86 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-25-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L25 | yes | Drywall and prime paint | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-02-10 | 2027-02-16 | 5 | 86 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-26-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L26 | yes | Drywall and prime paint | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 26th Lvl > Wall Layout & Framing at Units & Corridors at 26th Lvl | TT_Task | TK_NotStart | 2026-12-31 | 2027-01-08 | 6 | 105 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-26-U-FN-200 | Install Drywall One Side & Insulation @ Units - L26 | yes | Drywall and prime paint | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-01-25 | 2027-01-27 | 3 | 87 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-26-U-FN-210 | Hang Drywall @ Units - L26 | yes | Drywall and prime paint | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-01-28 | 2027-02-04 | 6 | 87 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-26-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L26 | yes | Drywall and prime paint | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-01-28 | 2027-02-04 | 6 | 92 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-26-U-FN-230 | Tape & Finish Drywall @ Units - L26 | yes | Drywall and prime paint | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-12 | 6 | 87 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-26-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L26 | yes | Drywall and prime paint | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-12 | 6 | 92 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-26-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L26 | yes | Drywall and prime paint | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-02-15 | 2027-02-18 | 4 | 87 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-26-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L26 | yes | Drywall and prime paint | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-02-18 | 2027-02-24 | 5 | 87 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-27-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L27 | yes | Drywall and prime paint | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 27th Lvl > Wall Layout & Framing at Units & Corridors at 8t27th h Lvl | TT_Task | TK_NotStart | 2027-01-11 | 2027-01-18 | 6 | 106 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors at 8t27th h Lvl
Phased TCO | C-27-U-FN-200 | Install Drywall One Side & Insulation @ Units - L27 | yes | Drywall and prime paint | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-04 | 3 | 88 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-27-U-FN-210 | Hang Drywall @ Units - L27 | yes | Drywall and prime paint | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-12 | 6 | 88 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-27-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L27 | yes | Drywall and prime paint | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-12 | 6 | 93 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-27-U-FN-230 | Tape & Finish Drywall @ Units - L27 | yes | Drywall and prime paint | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-02-15 | 2027-02-22 | 6 | 88 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-27-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L27 | yes | Drywall and prime paint | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-02-15 | 2027-02-22 | 6 | 93 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-27-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L27 | yes | Drywall and prime paint | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-02-26 | 4 | 88 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-27-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L27 | yes | Drywall and prime paint | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-02-26 | 2027-03-04 | 5 | 88 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-28-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L28 | yes | Drywall and prime paint | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 28th Lvl > Wall Layout & Framing at Units & Corridors at 28th Lvl | TT_Task | TK_NotStart | 2027-01-19 | 2027-01-26 | 6 | 107 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-28-U-FN-200 | Install Drywall One Side & Insulation @ Units - L28 | yes | Drywall and prime paint | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-02-10 | 2027-02-12 | 3 | 89 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-28-U-FN-210 | Hang Drywall @ Units - L28 | yes | Drywall and prime paint | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-02-15 | 2027-02-22 | 6 | 89 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-28-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L28 | yes | Drywall and prime paint | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-02-15 | 2027-02-22 | 6 | 94 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-28-U-FN-230 | Tape & Finish Drywall @ Units - L28 | yes | Drywall and prime paint | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-03-02 | 6 | 89 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-28-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L28 | yes | Drywall and prime paint | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-03-02 | 6 | 94 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-28-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L28 | yes | Drywall and prime paint | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-08 | 4 | 89 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-28-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L28 | yes | Drywall and prime paint | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-12 | 5 | 89 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-29-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L29 | yes | Drywall and prime paint | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 29th Lvl > Wall Layout & Framing at Units & Corridors at 29th Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-02-03 | 6 | 108 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-29-U-FN-200 | Install Drywall One Side & Insulation @ Units - L29 | yes | Drywall and prime paint | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-02-18 | 2027-02-22 | 3 | 90 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-29-U-FN-210 | Hang Drywall @ Units - L29 | yes | Drywall and prime paint | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-03-02 | 6 | 90 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-29-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L29 | yes | Drywall and prime paint | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-03-02 | 6 | 95 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-29-U-FN-230 | Tape & Finish Drywall @ Units - L29 | yes | Drywall and prime paint | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-10 | 6 | 90 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-29-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L29 | yes | Drywall and prime paint | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-10 | 6 | 95 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-29-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L29 | yes | Drywall and prime paint | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-16 | 4 | 90 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-29-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L29 | yes | Drywall and prime paint | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-03-16 | 2027-03-22 | 5 | 90 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-30-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L30 | yes | Drywall and prime paint | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 30th Lvl > Wall Layout & Framing at Units & Corridors at 30th Lvl | TT_Task | TK_NotStart | 2027-02-04 | 2027-02-11 | 6 | 109 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-30-U-FN-200 | Install Drywall One Side & Insulation @ Units - L30 | yes | Drywall and prime paint | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-02-26 | 2027-03-02 | 3 | 91 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-30-U-FN-210 | Hang Drywall @ Units - L30 | yes | Drywall and prime paint | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-10 | 6 | 91 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-30-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L30 | yes | Drywall and prime paint | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-10 | 6 | 96 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-30-U-FN-230 | Tape & Finish Drywall @ Units - L30 | yes | Drywall and prime paint | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-18 | 6 | 91 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-30-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L30 | yes | Drywall and prime paint | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-18 | 6 | 96 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-30-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L30 | yes | Drywall and prime paint | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-03-19 | 2027-03-24 | 4 | 91 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-30-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L30 | yes | Drywall and prime paint | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-30 | 5 | 91 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-31-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L31 | yes | Drywall and prime paint | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 31st Lvl > Wall Layout & Framing at Units & Corridors at 31st Lvl | TT_Task | TK_NotStart | 2027-02-12 | 2027-02-19 | 6 | 110 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-31-U-FN-200 | Install Drywall One Side & Insulation @ Units - L31 | yes | Drywall and prime paint | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-10 | 3 | 92 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-31-U-FN-210 | Hang Drywall @ Units - L31 | yes | Drywall and prime paint | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-18 | 6 | 92 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-31-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L31 | yes | Drywall and prime paint | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-18 | 6 | 97 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-31-U-FN-230 | Tape & Finish Drywall @ Units - L31 | yes | Drywall and prime paint | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-03-19 | 2027-03-26 | 6 | 92 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-31-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L31 | yes | Drywall and prime paint | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-03-19 | 2027-03-26 | 6 | 97 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-31-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L31 | yes | Drywall and prime paint | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-03-29 | 2027-04-01 | 4 | 92 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-31-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L31 | yes | Drywall and prime paint | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-07 | 5 | 92 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-32-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L32 | yes | Drywall and prime paint | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 32nd Lvl > Wall Layout & Framing at Units & Corridors at 32nd Lvl | TT_Task | TK_NotStart | 2027-02-22 | 2027-03-01 | 6 | 111 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-32-U-FN-200 | Install Drywall One Side & Insulation @ Units - L32 | yes | Drywall and prime paint | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-03-16 | 2027-03-18 | 3 | 93 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-32-U-FN-210 | Hang Drywall @ Units - L32 | yes | Drywall and prime paint | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-03-19 | 2027-03-26 | 6 | 93 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-32-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L32 | yes | Drywall and prime paint | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-03-19 | 2027-03-26 | 6 | 98 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-32-U-FN-230 | Tape & Finish Drywall @ Units - L32 | yes | Drywall and prime paint | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-03-29 | 2027-04-05 | 6 | 93 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-32-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L32 | yes | Drywall and prime paint | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-03-29 | 2027-04-05 | 6 | 98 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-32-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L32 | yes | Drywall and prime paint | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-09 | 4 | 93 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-32-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L32 | yes | Drywall and prime paint | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-15 | 5 | 93 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-33-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L33 | yes | Drywall and prime paint | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 33rd Lvl > Wall Layout & Framing at Units & Corridors at 33rd Lvl | TT_Task | TK_NotStart | 2027-03-02 | 2027-03-09 | 6 | 112 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-33-U-FN-200 | Install Drywall One Side & Insulation @ Units - L33 | yes | Drywall and prime paint | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-26 | 3 | 94 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-33-U-FN-210 | Hang Drywall @ Units - L33 | yes | Drywall and prime paint | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-03-29 | 2027-04-05 | 6 | 94 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-33-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L33 | yes | Drywall and prime paint | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-03-29 | 2027-04-05 | 6 | 99 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-33-U-FN-230 | Tape & Finish Drywall @ Units - L33 | yes | Drywall and prime paint | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-13 | 6 | 94 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-33-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L33 | yes | Drywall and prime paint | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-13 | 6 | 99 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-33-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L33 | yes | Drywall and prime paint | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-04-14 | 2027-04-19 | 4 | 94 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-33-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L33 | yes | Drywall and prime paint | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-04-19 | 2027-04-23 | 5 | 94 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-34-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L34 | yes | Drywall and prime paint | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 34th Lvl > Wall Layout & Framing at Units & Corridors at 34th Lvl | TT_Task | TK_NotStart | 2027-03-10 | 2027-03-17 | 6 | 113 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-34-U-FN-200 | Install Drywall One Side & Insulation @ Units - L34 | yes | Drywall and prime paint | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-05 | 3 | 95 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-34-U-FN-210 | Hang Drywall @ Units - L34 | yes | Drywall and prime paint | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-13 | 6 | 95 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-34-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L34 | yes | Drywall and prime paint | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-13 | 6 | 100 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-34-U-FN-230 | Tape & Finish Drywall @ Units - L34 | yes | Drywall and prime paint | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-04-14 | 2027-04-21 | 6 | 95 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-34-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L34 | yes | Drywall and prime paint | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-04-14 | 2027-04-21 | 6 | 100 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-34-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L34 | yes | Drywall and prime paint | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-04-22 | 2027-04-27 | 4 | 95 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-34-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L34 | yes | Drywall and prime paint | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-04-27 | 2027-05-03 | 5 | 95 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-35-U-FN-220 | Frame GWB Drop Ceilings/Soffits @ Units - L35 | yes | Drywall and prime paint | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior Wall Framing & MEP Rough at Units & Corridors at 35th Lvl > Wall Layout & Framing at Units & Corridors at 35th Lvl | TT_Task | TK_NotStart | 2027-03-18 | 2027-03-25 | 6 | 114 | Interior MEPs & Finishes | Wall Layout & Framing at Units & Corridors
Phased TCO | C-35-U-FN-200 | Install Drywall One Side & Insulation @ Units - L35 | yes | Drywall and prime paint | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-13 | 3 | 96 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-35-U-FN-210 | Hang Drywall @ Units - L35 | yes | Drywall and prime paint | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-04-14 | 2027-04-21 | 6 | 96 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-35-U-FN-240 | Hang GWB Drop Ceilings/Soffits/Drywall @ Units - L35 | yes | Drywall and prime paint | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-04-14 | 2027-04-21 | 6 | 101 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-35-U-FN-230 | Tape & Finish Drywall @ Units - L35 | yes | Drywall and prime paint | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-04-22 | 2027-04-29 | 6 | 96 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-35-U-FN-250 | Tape & Finish GWB Drop Ceilings/Soffits @ Units - L35 | yes | Drywall and prime paint | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-04-22 | 2027-04-29 | 6 | 101 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-35-U-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Units - L35 | yes | Drywall and prime paint | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-04-30 | 2027-05-05 | 4 | 96 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-35-U-FN-270 | Paint Drywall - Prime & 1st Coat @ Units - L35 | yes | Drywall and prime paint | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-11 | 5 | 96 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-36-IN-FN-220 | Frame GWB Ceilings @ Indoor - L36 | yes | Drywall and prime paint | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > Wall Layout & Framing at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-05-03 | 2027-05-06 | 4 | 111 | Interior MEPs & Finishes | Wall Layout & Framing at Indoor
Phased TCO | C-36-IN-FN-200 | Install Drywall One Side & Insulation @ Indoor - L36 | yes | Drywall and prime paint | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-05-20 | 2027-05-21 | 2 | 100 | Interior MEPs & Finishes | Interior Finishes at Indoor
Phased TCO | C-36-IN-FN-240 | Hang GWB Ceilings @ Indoor - L36 | yes | Drywall and prime paint | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-05-20 | 2027-05-24 | 3 | 104 | Interior MEPs & Finishes | Interior Finishes at Indoor
Phased TCO | C-36-IN-FN-210 | Hang Drywall @ Indoor - L36 | yes | Drywall and prime paint | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-05-24 | 2027-05-27 | 4 | 100 | Interior MEPs & Finishes | Interior Finishes at Indoor
Phased TCO | C-36-IN-FN-250 | Tape & Finish GWB Ceilings @ Indoor - L36 | yes | Drywall and prime paint | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-05-27 | 3 | 104 | Interior MEPs & Finishes | Interior Finishes at Indoor
Phased TCO | C-36-IN-FN-230 | Tape & Finish Drywall @ Indoor - L36 | yes | Drywall and prime paint | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-05-27 | 2027-06-01 | 3 | 100 | Interior MEPs & Finishes | Interior Finishes at Indoor
Phased TCO | C-36-IN-FN-260 | Install Knockdown Door Frame & Hang Interior Doors @ Indoor - L36 | yes | Drywall and prime paint | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-02 | 2027-06-03 | 2 | 100 | Interior MEPs & Finishes | Interior Finishes at Indoor
Phased TCO | C-36-IN-FN-270 | Paint Drywall - 1st Coat @ Indoor - L36 | yes | Drywall and prime paint | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-04 | 2027-06-09 | 4 | 100 | Interior MEPs & Finishes | Interior Finishes at Indoor
Phased TCO | C-01-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > Interior Finishes at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-06-17 | 2027-06-23 | 5 | 14 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridors
Phased TCO | C-01-UC-MP-200 | Install Mech Heat Pump & Eqp @ Future Tenant - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > MEP Eqp & Trim at 1st Lvl | TT_Task | TK_NotStart | 2027-06-17 | 2027-06-23 | 5 | 34 | Interior MEPs & Finishes | MEP Eqp & Trim
Phased TCO | C-01-UC-FN-310 | Paint Final Coat @ L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Interior Finishes at 1st Lvl | TT_Task | TK_NotStart | 2027-06-21 | 2027-06-24 | 4 | 24 | Interior MEPs & Finishes | Interior Finishes
Phased TCO | C-01-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > Interior Finishes at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-29 | 4 | 14 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridors
Phased TCO | C-01-UC-FN-320 | Install Lockers & Shelving @ Packages Rm #119 - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Interior Finishes at 1st Lvl | TT_Task | TK_NotStart | 2027-06-25 | 2027-06-30 | 4 | 29 | Interior MEPs & Finishes | Interior Finishes
Phased TCO | C-01-UC-FN-330 | Install Door Hardware @ L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Interior Finishes at 1st Lvl | TT_Task | TK_NotStart | 2027-06-25 | 2027-06-25 | 1 | 32 | Interior MEPs & Finishes | Interior Finishes
Phased TCO | C-01-UC-FN-370 | Install Flooring & Base @ L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Interior Finishes at 1st Lvl | TT_Task | TK_NotStart | 2027-06-25 | 2027-07-02 | 6 | 27 | Interior MEPs & Finishes | Interior Finishes
Phased TCO | C-01-UC-MP-400 | Install HVAC Trim & Control @ L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > MEP Eqp & Trim at 1st Lvl | TT_Task | TK_NotStart | 2027-06-25 | 2027-07-01 | 5 | 28 | Interior MEPs & Finishes | MEP Eqp & Trim
Phased TCO | C-01-UC-MP-410 | Install Electrical Power Trim @ L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > MEP Eqp & Trim at 1st Lvl | TT_Task | TK_NotStart | 2027-06-25 | 2027-06-30 | 4 | 24 | Interior MEPs & Finishes | MEP Eqp & Trim
Phased TCO | C-01-UC-MP-420 | Install Light Fixtures @ L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > MEP Eqp & Trim at 1st Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-07-08 | 7 | 24 | Interior MEPs & Finishes | MEP Eqp & Trim
Phased TCO | C-01-C-FN-120 | Frame GWB Ceiling @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > Interior Finishes at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-06-30 | 2027-07-06 | 4 | 14 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridors
Phased TCO | C-01-UC-MP-430 | Install FA & Low Voltage Devices @ L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > MEP Eqp & Trim at 1st Lvl | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-06 | 3 | 26 | Interior MEPs & Finishes | MEP Eqp & Trim
Phased TCO | C-01-UC-MP-440 | Install FP Sprinkler Heads @ L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > MEP Eqp & Trim at 1st Lvl | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-02 | 2 | 27 | Interior MEPs & Finishes | MEP Eqp & Trim
Phased TCO | C-01-C-FN-140 | Hang/Tape/Finish GWB Ceiling @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > Interior Finishes at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-07-02 | 2027-07-08 | 4 | 14 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridors
Phased TCO | C-01-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > Interior Finishes at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-14 | 4 | 14 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridors
Phased TCO | C-01-UC-FN-400 | Rough Cleanup @ L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Interior Finishes at 1st Lvl | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-12 | 2 | 24 | Interior MEPs & Finishes | Interior Finishes
Phased TCO | C-01-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > Interior Finishes at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-15 | 1 | 19 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridors
Phased TCO | C-01-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > Interior Finishes at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-20 | 4 | 16 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridors
Phased TCO | C-01-C-MP-120 | Install HVAC EFs & Trim @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > MEP Eqp & Trim at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-20 | 4 | 14 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridors
Phased TCO | C-01-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > MEP Eqp & Trim at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-16 | 2 | 15 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridors
Phased TCO | C-01-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > MEP Eqp & Trim at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-07-19 | 2027-07-20 | 2 | 15 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridors
Phased TCO | C-01-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > MEP Eqp & Trim at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-07-20 | 2027-07-21 | 2 | 15 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridors
Phased TCO | C-01-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > MEP Eqp & Trim at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-07-21 | 2027-07-22 | 2 | 14 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridors
Phased TCO | C-01-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L1 | yes | Finishes and equipment | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > Interior Finishes at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-07-23 | 2027-07-26 | 2 | 14 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridors
Phased TCO | C-02-UC-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-07 | 2026-08-12 | 4 | 131 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Phased TCO | C-02-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > Interior Finishes at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-10 | 2026-08-11 | 2 | 205 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-02-UC-MP-200 | Install Mech Heat Pumps & Eqp @ Units & Common Areas - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > MEP Eqp at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-10 | 2026-08-19 | 8 | 130 | Interior MEPs & Finishes | MEP Eqp at Units & Common Areas
Phased TCO | C-02-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > Interior Finishes at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-12 | 2026-08-13 | 2 | 205 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-02-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > Interior Finishes at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-14 | 2026-08-17 | 2 | 212 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-02-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > Interior Finishes at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-14 | 2026-08-18 | 3 | 212 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-02-UC-FN-290 | Install Vanities & Mirrors @ B/Rs - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-20 | 2026-08-21 | 2 | 126 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Phased TCO | C-02-UC-FN-370 | Install Flooring & Base @ Units & Common Areas - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-20 | 2026-08-25 | 4 | 130 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Phased TCO | C-02-UC-FN-300 | Install Shower Enclosures @ B/Rs L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-24 | 2026-08-25 | 2 | 126 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Phased TCO | C-02-UC-FN-310 | Paint Final Coat @ Units & Common Areas - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-26 | 2026-08-31 | 4 | 126 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Phased TCO | C-02-UC-FN-320 | Install Storage Lockers @ Storage Locker Rm #229 - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-01 | 2026-09-15 | 10 | 196 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Phased TCO | C-02-UC-FN-330 | Install Door Hardware @ Units & Common Areas - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-01 | 2026-09-02 | 2 | 204 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Phased TCO | C-02-UC-FN-350 | Install Kitchen Cabinets & & Countertops & Millwork @ Units & Common Areas - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-01 | 2026-09-09 | 6 | 126 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Phased TCO | C-02-UC-FN-360 | Install Laundry Eqp @ Laundry Rm #224 - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-01 | 2026-09-03 | 3 | 202 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Phased TCO | C-02-C-FN-130 | Install Trash Chute @ Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > Interior Finishes at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-03 | 2026-09-03 | 1 | 200 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-02-UC-MP-210 | Install Plumbing Fixtures @ B/Rs - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > MEP Eqp at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-03 | 2026-09-04 | 2 | 199 | Interior MEPs & Finishes | MEP Eqp at Units & Common Areas
Phased TCO | C-02-UC-MP-400 | Install HVAC Trim & Control @ Units & Common Areas - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > MEP Trim at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-03 | 2026-09-08 | 3 | 203 | Interior MEPs & Finishes | MEP Trim at Units & Common Areas
Phased TCO | C-02-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > Interior Finishes at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-04 | 2026-09-08 | 2 | 200 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-02-UC-FN-340 | Install Toilet Partitions & Accessories @ B/Rs - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-08 | 2026-09-10 | 3 | 199 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Phased TCO | C-02-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > Interior Finishes at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-09 | 2026-09-09 | 1 | 207 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-02-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > Interior Finishes at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-09 | 2026-09-11 | 3 | 205 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-02-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-09 | 2026-09-09 | 1 | 200 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-02-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-09 | 2026-09-10 | 2 | 204 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-02-UC-MP-410 | Install Electrical Power Trim @ Units & Common Areas - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > MEP Trim at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-10 | 2026-09-14 | 3 | 197 | Interior MEPs & Finishes | MEP Trim at Units & Common Areas
Phased TCO | C-02-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-11 | 2026-09-14 | 2 | 204 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-02-UC-MP-420 | Install Light Fixtures @ Units & Common Areas - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > MEP Trim at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-11 | 2026-09-16 | 4 | 197 | Interior MEPs & Finishes | MEP Trim at Units & Common Areas
Phased TCO | C-02-UC-MP-430 | Install FA & Low Voltage Devices @ Units & Common Areas - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > MEP Trim at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-16 | 2 | 197 | Interior MEPs & Finishes | MEP Trim at Units & Common Areas
Phased TCO | C-02-UC-MP-440 | Install FP Sprinkler Heads @ Units & Common Areas - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > MEP Trim at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-16 | 2 | 197 | Interior MEPs & Finishes | MEP Trim at Units & Common Areas
Phased TCO | C-02-C-MP-100 | Install Elect & Low Voltage Panels & Eqp @ Telecomm/Elect Rm #221- L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-02 | 2026-10-19 | 12 | 171 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-02-UC-FN-390 | Install Kitchen Appliances @ Units - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-02 | 2026-10-02 | 1 | 183 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Phased TCO | C-02-UC-FN-450 | Install Laundry Eqp @ Laundry Rm #224 - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-05 | 2026-10-06 | 2 | 183 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Phased TCO | C-02-UC-FN-400 | Touch-up Paint @ L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Interior Finishes at Units & Common Areas at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-07 | 2026-10-08 | 2 | 187 | Interior MEPs & Finishes | Interior Finishes at Units & Common Areas
Phased TCO | C-02-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-20 | 2026-10-20 | 1 | 171 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-02-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-21 | 2026-10-21 | 1 | 171 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-02-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-21 | 2026-10-22 | 2 | 171 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-02-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L2 | yes | Finishes and equipment | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > Interior Finishes at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-23 | 2026-10-23 | 1 | 176 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-03-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-19 | 2026-08-24 | 4 | 128 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-03-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > Interior Finishes at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-20 | 2026-08-21 | 2 | 201 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-03-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > MEP Eqp at Units t 3rd Lvl | TT_Task | TK_NotStart | 2026-08-20 | 2026-08-31 | 8 | 71 | Interior MEPs & Finishes | MEP Eqp at Units t
Phased TCO | C-03-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > Interior Finishes at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-24 | 2026-08-25 | 2 | 201 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-03-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-25 | 2026-08-26 | 2 | 129 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-03-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > Interior Finishes at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-26 | 2026-08-27 | 2 | 208 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-03-C-FN-130 | Install Trash Chute @ Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > Interior Finishes at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-26 | 2026-08-26 | 1 | 210 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-03-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > Interior Finishes at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-26 | 2026-08-28 | 3 | 208 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-03-C-MP-100 | Install Elect Panels & Stack Meters @ Stack Vault #321- L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-26 | 2026-09-11 | 12 | 201 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-03-U-FN-300 | Install Shower Enclosures @ B/Rs L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-27 | 2026-08-28 | 2 | 129 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-03-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > MEP Eqp at Units t 3rd Lvl | TT_Task | TK_NotStart | 2026-08-27 | 2026-08-28 | 2 | 214 | Interior MEPs & Finishes | MEP Eqp at Units t
Phased TCO | C-03-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > Interior Finishes at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-31 | 2026-09-01 | 2 | 208 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-03-U-FN-310 | Paint Final Coat @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-31 | 2026-09-03 | 4 | 129 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-03-U-FN-370 | Install Flooring & Base @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-01 | 2026-09-04 | 4 | 128 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-03-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > Interior Finishes at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-02 | 2026-09-02 | 1 | 215 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-03-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-02 | 2026-09-02 | 1 | 208 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-03-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-02 | 2026-09-03 | 2 | 212 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-03-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-04 | 2026-09-08 | 2 | 212 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-03-U-FN-330 | Install Door Hardware @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-04 | 2026-09-08 | 2 | 211 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-03-U-FN-340 | Install Toilet Partitions & Accessories @ B/Rs - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-04 | 2026-09-09 | 3 | 210 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-03-U-MP-400 | Install HVAC Trim & Control @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > MEP Trim at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-04 | 2026-09-09 | 3 | 206 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-03-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > Interior Finishes at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-08 | 2026-09-10 | 3 | 210 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-03-U-FN-350 | Install Kitchen Cabinets & & Countertops & Millwork @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-10 | 2026-09-17 | 6 | 126 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-03-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-14 | 2026-09-14 | 1 | 201 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-03-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-15 | 1 | 201 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-03-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-16 | 2 | 201 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-03-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > Interior Finishes at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-17 | 2026-09-17 | 1 | 206 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-03-U-FN-390 | Install Kitchen Appliances @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-18 | 2026-09-18 | 1 | 203 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-03-U-MP-410 | Install Electrical Power Trim @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > MEP Trim at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-18 | 2026-09-22 | 3 | 195 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-03-U-FN-400 | Touch-up Paint @ L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > Interior Finishes at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-21 | 2026-09-22 | 2 | 203 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-03-U-MP-420 | Install Light Fixtures @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > MEP Trim at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-21 | 2026-09-24 | 4 | 195 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-03-U-MP-430 | Install FA & Low Voltage Devices @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > MEP Trim at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-23 | 2026-09-24 | 2 | 195 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-03-U-MP-440 | Install FP Sprinkler Heads @ Units - L3 | yes | Finishes and equipment | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > MEP Trim at Units at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-23 | 2026-09-24 | 2 | 195 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-04-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-08-28 | 2026-09-02 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-04-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > Interior Finishes at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-08-31 | 2026-09-01 | 2 | 198 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-04-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > MEP Eqp at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-08-31 | 2026-09-10 | 8 | 69 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-04-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > Interior Finishes at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-09-02 | 2026-09-03 | 2 | 198 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-04-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-09-03 | 2026-09-04 | 2 | 128 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-04-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > Interior Finishes at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-09-04 | 2026-09-08 | 2 | 205 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-04-C-FN-130 | Install Trash Chute @ Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > Interior Finishes at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-09-04 | 2026-09-04 | 1 | 207 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-04-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > Interior Finishes at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-09-04 | 2026-09-09 | 3 | 205 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-04-C-MP-100 | Install Elect Panels & Eqp @ Elect. Rm #421- L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-09-04 | 2026-09-22 | 12 | 198 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-04-U-FN-300 | Install Shower Enclosures @ B/Rs L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-09-08 | 2026-09-09 | 2 | 128 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-04-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > MEP Eqp at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-09-08 | 2026-09-09 | 2 | 211 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-04-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > Interior Finishes at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-09-10 | 2026-09-11 | 2 | 205 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-04-U-FN-310 | Paint Final Coat @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-09-10 | 2026-09-15 | 4 | 128 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-04-U-FN-370 | Install Flooring & Base @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-09-11 | 2026-09-16 | 4 | 127 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-04-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > Interior Finishes at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-09-14 | 2026-09-14 | 1 | 212 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-04-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-09-14 | 2026-09-14 | 1 | 205 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-04-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-09-14 | 2026-09-15 | 2 | 209 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-04-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-09-16 | 2026-09-17 | 2 | 209 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-04-U-FN-330 | Install Door Hardware @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-09-16 | 2026-09-17 | 2 | 208 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-04-U-FN-340 | Install Toilet Partitions & Accessories @ B/Rs - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-09-16 | 2026-09-18 | 3 | 207 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-04-U-MP-400 | Install HVAC Trim & Control @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > MEP Trim at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-09-16 | 2026-09-18 | 3 | 203 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-04-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > Interior Finishes at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-09-17 | 2026-09-21 | 3 | 207 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-04-U-FN-350 | Install Kitchen Cabinets & & Countertops & Millwork @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-09-18 | 2026-09-25 | 6 | 126 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-04-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-09-23 | 2026-09-23 | 1 | 198 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-04-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-09-24 | 2026-09-24 | 1 | 198 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-04-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-09-24 | 2026-09-25 | 2 | 198 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-04-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > Interior Finishes at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2026-09-28 | 2026-09-28 | 1 | 203 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-04-U-FN-390 | Install Kitchen Appliances @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-09-28 | 2026-09-28 | 1 | 201 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-04-U-MP-410 | Install Electrical Power Trim @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > MEP Trim at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-09-28 | 2026-09-30 | 3 | 193 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-04-U-FN-400 | Touch-up Paint @ L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > Interior Finishes at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-09-29 | 2026-09-30 | 2 | 201 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-04-U-MP-420 | Install Light Fixtures @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > MEP Trim at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-09-29 | 2026-10-02 | 4 | 193 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-04-U-MP-430 | Install FA & Low Voltage Devices @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > MEP Trim at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-02 | 2 | 193 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-04-U-MP-440 | Install FP Sprinkler Heads @ Units - L4 | yes | Finishes and equipment | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > MEP Trim at Units at 4th Lvl | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-02 | 2 | 193 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-05-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-09-09 | 2026-09-14 | 4 | 122 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-05-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > Interior Finishes at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-09-10 | 2026-09-11 | 2 | 195 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-05-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > MEP Eqp at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-09-10 | 2026-09-21 | 8 | 67 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-05-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > Interior Finishes at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-09-14 | 2026-09-15 | 2 | 195 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-05-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-16 | 2 | 127 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-05-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > Interior Finishes at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-09-16 | 2026-09-17 | 2 | 202 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-05-C-FN-130 | Install Trash Chute @ Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > Interior Finishes at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-09-16 | 2026-09-16 | 1 | 204 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-05-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > Interior Finishes at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-09-16 | 2026-09-18 | 3 | 202 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-05-C-MP-100 | Install Elect & Low Voltage Panels & Eqp @ Telecom/Elect Rm #521- L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-09-16 | 2026-10-01 | 12 | 195 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-05-U-FN-300 | Install Shower Enclosures @ B/Rs L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-09-17 | 2026-09-18 | 2 | 127 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-05-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > MEP Eqp at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-09-17 | 2026-09-18 | 2 | 208 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-05-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > Interior Finishes at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-09-21 | 2026-09-22 | 2 | 202 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-05-U-FN-310 | Paint Final Coat @ Units - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-09-21 | 2026-09-24 | 4 | 127 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-05-U-FN-370 | Install Flooring & Base @ Units - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-09-22 | 2026-09-25 | 4 | 126 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-05-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > Interior Finishes at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-09-23 | 2026-09-23 | 1 | 209 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-05-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-09-23 | 2026-09-23 | 1 | 202 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-05-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-09-23 | 2026-09-24 | 2 | 206 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-05-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-09-25 | 2026-09-28 | 2 | 206 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-05-U-FN-330 | Install Door Hardware @ Units - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-09-25 | 2026-09-28 | 2 | 205 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-05-U-FN-340 | Install Toilet Partitions & Accessories @ B/Rs - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-09-25 | 2026-09-29 | 3 | 204 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-05-U-MP-400 | Install HVAC Trim & Control @ Units - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > MEP Trim at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-09-25 | 2026-09-29 | 3 | 200 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-05-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > Interior Finishes at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-09-28 | 2026-09-30 | 3 | 204 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-05-U-FN-350 | Install Kitchen Cabinets & & Countertops & Millwork @ Units - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-09-28 | 2026-10-05 | 6 | 126 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-05-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-10-02 | 2026-10-02 | 1 | 195 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-05-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-10-05 | 2026-10-05 | 1 | 195 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-05-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-10-05 | 2026-10-06 | 2 | 195 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-05-U-FN-390 | Install Kitchen Appliances @ Units - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-06 | 1 | 199 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-05-U-MP-410 | Install Electrical Power Trim @ Units - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > MEP Trim at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-08 | 3 | 191 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-05-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > Interior Finishes at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2026-10-07 | 2026-10-07 | 1 | 200 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-05-U-FN-400 | Touch-up Paint @ L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > Interior Finishes at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-10-07 | 2026-10-08 | 2 | 199 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-05-U-MP-420 | Install Light Fixtures @ Units - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > MEP Trim at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-10-07 | 2026-10-12 | 4 | 191 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-05-U-MP-430 | Install FA & Low Voltage Devices @ Units - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > MEP Trim at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-12 | 2 | 191 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-05-U-MP-440 | Install FP Sprinkler Heads @ Units - L5 | yes | Finishes and equipment | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > MEP Trim at Units at 5th Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-12 | 2 | 191 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-06-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-09-17 | 2026-09-22 | 4 | 120 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-06-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > Interior Finishes at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-09-18 | 2026-09-21 | 2 | 193 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-06-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > MEP Eqp at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-09-18 | 2026-09-29 | 8 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-06-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > Interior Finishes at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-09-22 | 2026-09-23 | 2 | 193 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-06-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-09-23 | 2026-09-24 | 2 | 127 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-06-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > Interior Finishes at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-09-24 | 2026-09-25 | 2 | 200 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-06-C-FN-130 | Install Trash Chute @ Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > Interior Finishes at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-09-24 | 2026-09-24 | 1 | 202 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-06-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > Interior Finishes at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-09-24 | 2026-09-28 | 3 | 200 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-06-C-MP-100 | Install Elect Panels & Stack Meters @ Stack Vault #621- L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-09-24 | 2026-10-09 | 12 | 193 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-06-U-FN-300 | Install Shower Enclosures @ B/Rs L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-09-25 | 2026-09-28 | 2 | 127 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-06-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > MEP Eqp at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-09-25 | 2026-09-28 | 2 | 206 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-06-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > Interior Finishes at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-09-29 | 2026-09-30 | 2 | 200 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-06-U-FN-310 | Paint Final Coat @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-09-29 | 2026-10-02 | 4 | 127 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-06-U-FN-370 | Install Flooring & Base @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-09-30 | 2026-10-05 | 4 | 126 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-06-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > Interior Finishes at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-01 | 1 | 207 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-06-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-01 | 1 | 200 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-06-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-02 | 2 | 204 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-06-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-10-05 | 2026-10-06 | 2 | 204 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-06-U-FN-330 | Install Door Hardware @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-10-05 | 2026-10-06 | 2 | 203 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-06-U-FN-340 | Install Toilet Partitions & Accessories @ B/Rs - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-10-05 | 2026-10-07 | 3 | 202 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-06-U-MP-400 | Install HVAC Trim & Control @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > MEP Trim at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-10-05 | 2026-10-07 | 3 | 198 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-06-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > Interior Finishes at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-08 | 3 | 202 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-06-U-FN-350 | Install Kitchen Cabinets & & Countertops & Millwork @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-13 | 6 | 126 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-06-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-10-12 | 2026-10-12 | 1 | 193 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-06-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-10-13 | 2026-10-13 | 1 | 193 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-06-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-10-13 | 2026-10-14 | 2 | 193 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-06-U-FN-390 | Install Kitchen Appliances @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-10-14 | 2026-10-14 | 1 | 197 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-06-U-MP-410 | Install Electrical Power Trim @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > MEP Trim at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-10-14 | 2026-10-16 | 3 | 189 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-06-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > Interior Finishes at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-15 | 1 | 198 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-06-U-FN-400 | Touch-up Paint @ L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > Interior Finishes at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-16 | 2 | 197 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-06-U-MP-420 | Install Light Fixtures @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > MEP Trim at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-20 | 4 | 189 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-06-U-MP-430 | Install FA & Low Voltage Devices @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > MEP Trim at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-10-19 | 2026-10-20 | 2 | 189 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-06-U-MP-440 | Install FP Sprinkler Heads @ Units - L6 | yes | Finishes and equipment | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > MEP Trim at Units at 6th Lvl | TT_Task | TK_NotStart | 2026-10-19 | 2026-10-20 | 2 | 189 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-07-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-09-23 | 2026-10-01 | 7 | 120 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-07-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > MEP Eqp at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-09-25 | 2026-10-08 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-07-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-10-02 | 2026-10-05 | 2 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-07-U-FN-300 | Install Shower Enclosures @ B/Rs L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-08 | 3 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-07-U-FN-370 | Install Flooring & Base @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-12 | 5 | 127 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-07-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > MEP Eqp at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-09 | 4 | 199 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-07-U-FN-310 | Paint Final Coat @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-14 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-07-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > Interior Finishes at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-19 | 3 | 175 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-07-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > Interior Finishes at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-16 | 2 | 188 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-07-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > Interior Finishes at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-19 | 3 | 188 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-07-U-FN-320 | Install Flooring @ Gym - 7th FL | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-16 | 2 | 189 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-07-U-FN-330 | Install Door Hardware @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-19 | 3 | 196 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-07-U-FN-340 | Install Toilet Accessories @ B/Rs - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-16 | 2 | 197 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-07-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-28 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-07-U-MP-400 | Install HVAC Trim & Control @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > MEP Trim at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-21 | 5 | 191 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-07-U-MP-440 | Install FP Sprinkler Heads @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > MEP Trim at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-21 | 5 | 191 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-07-U-FN-360 | Install Gym Millwork & Eqp @ Gym - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-10-19 | 2026-10-28 | 8 | 189 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-07-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > Interior Finishes at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2026-10-20 | 2026-10-22 | 3 | 175 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-07-C-FN-130 | Install Trash Chute @ Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > Interior Finishes at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2026-10-23 | 2026-10-23 | 1 | 184 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-07-C-MP-100 | Install Low Voltage Panels @ Telecom Rm #821- L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2026-10-23 | 2026-11-09 | 12 | 175 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-07-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > Interior Finishes at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2026-10-26 | 2026-10-28 | 3 | 184 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-07-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > Interior Finishes at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2026-10-29 | 2026-10-29 | 1 | 191 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-07-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > Interior Finishes at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2026-10-29 | 2026-11-02 | 3 | 189 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-07-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2026-10-29 | 2026-10-29 | 1 | 191 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-07-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2026-10-29 | 2026-10-30 | 2 | 184 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-07-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2026-10-29 | 2026-10-30 | 2 | 184 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-07-U-MP-410 | Install Electrical Power Trim @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > MEP Trim at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-10-29 | 2026-10-30 | 2 | 179 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-07-U-FN-390 | Install Kitchen Appliances @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-11-02 | 2026-11-03 | 2 | 185 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-07-U-MP-420 | Install Light Fixtures @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > MEP Trim at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-11-02 | 2026-11-06 | 5 | 179 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-07-U-MP-430 | Install FA & Low Voltage Devices @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > MEP Trim at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-11-02 | 2026-11-05 | 4 | 180 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-07-U-FN-400 | Rough Cleanup @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-10 | 2 | 182 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-07-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2026-11-10 | 2026-11-10 | 1 | 175 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-07-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2026-11-11 | 2026-11-12 | 2 | 175 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-07-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2026-11-11 | 2026-11-12 | 2 | 175 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-07-U-FN-410 | Touch-up Paint @ Units - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Interior Finishes at Units at 7th Lvl | TT_Task | TK_NotStart | 2026-11-11 | 2026-11-12 | 2 | 182 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-07-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L7 | yes | Finishes and equipment | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > Interior Finishes at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-13 | 1 | 181 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-08-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-09 | 7 | 119 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-08-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > MEP Eqp at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-19 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-08-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-10-12 | 2026-10-13 | 2 | 126 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-08-U-FN-370 | Install Flooring & Base @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-10-13 | 2026-10-19 | 5 | 129 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-08-U-FN-300 | Install Shower Enclosures @ B/Rs L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-10-14 | 2026-10-16 | 3 | 126 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-08-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > MEP Eqp at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-10-14 | 2026-10-19 | 4 | 198 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-08-U-FN-310 | Paint Final Coat @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-10-20 | 2026-10-23 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-08-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > Interior Finishes at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2026-10-26 | 2026-10-28 | 3 | 173 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-08-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > Interior Finishes at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2026-10-26 | 2026-10-27 | 2 | 186 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-08-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > Interior Finishes at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2026-10-26 | 2026-10-28 | 3 | 186 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-08-U-FN-330 | Install Door Hardware @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-10-26 | 2026-10-28 | 3 | 194 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-08-U-FN-340 | Install Toilet Accessories @ B/Rs - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-10-26 | 2026-10-27 | 2 | 195 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-08-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-10-26 | 2026-11-06 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-08-U-MP-400 | Install HVAC Trim & Control @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > MEP Trim at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-10-26 | 2026-10-30 | 5 | 189 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-08-U-MP-440 | Install FP Sprinkler Heads @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > MEP Trim at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-10-26 | 2026-10-30 | 5 | 189 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-08-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > Interior Finishes at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2026-10-29 | 2026-11-02 | 3 | 173 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-08-C-FN-130 | Install Trash Chute @ Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > Interior Finishes at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2026-11-03 | 2026-11-03 | 1 | 182 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-08-C-MP-100 | Install Low Voltage Panels @ Telecom Rm #821- L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2026-11-03 | 2026-11-18 | 12 | 173 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-08-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > Interior Finishes at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-06 | 3 | 182 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-08-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > Interior Finishes at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-09 | 1 | 189 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-08-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > Interior Finishes at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-11 | 3 | 187 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-08-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-09 | 1 | 189 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-08-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-10 | 2 | 182 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-08-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-10 | 2 | 182 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-08-U-MP-410 | Install Electrical Power Trim @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > MEP Trim at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-10 | 2 | 177 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-08-U-FN-390 | Install Kitchen Appliances @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-11-11 | 2026-11-12 | 2 | 183 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-08-U-MP-420 | Install Light Fixtures @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > MEP Trim at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-11-11 | 2026-11-17 | 5 | 177 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-08-U-MP-430 | Install FA & Low Voltage Devices @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > MEP Trim at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-11-11 | 2026-11-16 | 4 | 178 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-08-U-FN-400 | Rough Cleanup @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-11-18 | 2026-11-19 | 2 | 180 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-08-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2026-11-19 | 2026-11-19 | 1 | 173 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-08-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-11-23 | 2 | 173 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-08-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-11-23 | 2 | 173 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-08-U-FN-410 | Touch-up Paint @ Units - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Interior Finishes at Units at 8th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-11-23 | 2 | 180 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-08-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L8 | yes | Finishes and equipment | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > Interior Finishes at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-11-24 | 1 | 179 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-09-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-10-08 | 2026-10-16 | 7 | 119 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-09-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > MEP Eqp at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-28 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-09-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-10-19 | 2026-10-20 | 2 | 128 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-09-U-FN-370 | Install Flooring & Base @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-10-20 | 2026-10-26 | 5 | 131 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-09-U-FN-300 | Install Shower Enclosures @ B/Rs L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-10-21 | 2026-10-23 | 3 | 128 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-09-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > MEP Eqp at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-10-21 | 2026-10-26 | 4 | 198 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-09-U-FN-310 | Paint Final Coat @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-10-29 | 2026-11-03 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-09-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > Interior Finishes at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-06 | 3 | 171 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-09-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > Interior Finishes at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-05 | 2 | 184 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-09-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > Interior Finishes at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-06 | 3 | 184 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-09-U-FN-330 | Install Door Hardware @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-06 | 3 | 192 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-09-U-FN-340 | Install Toilet Accessories @ B/Rs - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-05 | 2 | 193 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-09-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-17 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-09-U-MP-400 | Install HVAC Trim & Control @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > MEP Trim at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-10 | 5 | 187 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-09-U-MP-440 | Install FP Sprinkler Heads @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > MEP Trim at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-10 | 5 | 187 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-09-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > Interior Finishes at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-11 | 3 | 171 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-09-C-FN-130 | Install Trash Chute @ Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > Interior Finishes at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2026-11-12 | 2026-11-12 | 1 | 180 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-09-C-MP-100 | Install Elect Panels & Stack Meters @ Stack Vault #921- L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2026-11-12 | 2026-12-01 | 12 | 171 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-09-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > Interior Finishes at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-17 | 3 | 180 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-09-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > Interior Finishes at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2026-11-18 | 2026-11-18 | 1 | 187 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-09-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > Interior Finishes at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2026-11-18 | 2026-11-20 | 3 | 185 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-09-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2026-11-18 | 2026-11-18 | 1 | 187 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-09-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2026-11-18 | 2026-11-19 | 2 | 180 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-09-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2026-11-18 | 2026-11-19 | 2 | 180 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-09-U-MP-410 | Install Electrical Power Trim @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > MEP Trim at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-11-18 | 2026-11-19 | 2 | 175 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-09-U-FN-390 | Install Kitchen Appliances @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-11-23 | 2 | 181 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-09-U-MP-420 | Install Light Fixtures @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > MEP Trim at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-11-30 | 5 | 175 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-09-U-MP-430 | Install FA & Low Voltage Devices @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > MEP Trim at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-11-25 | 4 | 176 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-09-U-FN-400 | Rough Cleanup @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-12-01 | 2026-12-02 | 2 | 178 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-09-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2026-12-02 | 2026-12-02 | 1 | 171 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-09-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-04 | 2 | 171 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-09-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-04 | 2 | 171 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-09-U-FN-410 | Touch-up Paint @ Units - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Interior Finishes at Units at 9th Lvl | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-04 | 2 | 178 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-09-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L9 | yes | Finishes and equipment | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > Interior Finishes at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-07 | 1 | 177 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-10-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-10-15 | 2026-10-23 | 7 | 119 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-10-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-10-26 | 2026-10-27 | 2 | 130 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-10-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > MEP Eqp at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-10-26 | 2026-11-06 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-10-U-FN-370 | Install Flooring & Base @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-10-27 | 2026-11-02 | 5 | 133 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-10-U-FN-300 | Install Shower Enclosures @ B/Rs L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-10-28 | 2026-10-30 | 3 | 130 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-10-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > MEP Eqp at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-10-28 | 2026-11-02 | 4 | 198 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-10-U-FN-310 | Paint Final Coat @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-12 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-10-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > Interior Finishes at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-17 | 3 | 172 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-10-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > Interior Finishes at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-16 | 2 | 181 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-10-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > Interior Finishes at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-17 | 3 | 181 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-10-U-FN-330 | Install Door Hardware @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-17 | 3 | 190 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-10-U-FN-340 | Install Toilet Accessories @ B/Rs - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-16 | 2 | 191 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-10-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-30 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-10-U-MP-400 | Install HVAC Trim & Control @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > MEP Trim at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-19 | 5 | 185 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-10-U-MP-440 | Install FP Sprinkler Heads @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > MEP Trim at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-19 | 5 | 185 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-10-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > Interior Finishes at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2026-11-18 | 2026-11-20 | 3 | 172 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-10-C-FN-130 | Install Trash Chute @ Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > Interior Finishes at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2026-11-23 | 2026-11-23 | 1 | 177 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-10-C-MP-100 | Install Mech Eqp @ Mech Eqp Rm #1021- L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2026-11-23 | 2026-12-08 | 10 | 172 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-10-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > Interior Finishes at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-11-30 | 3 | 177 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-10-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > Interior Finishes at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2026-12-01 | 2026-12-01 | 1 | 185 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-10-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > Interior Finishes at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2026-12-01 | 2026-12-03 | 3 | 183 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-10-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2026-12-01 | 2026-12-01 | 1 | 185 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-10-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2026-12-01 | 2026-12-02 | 2 | 178 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-10-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2026-12-01 | 2026-12-01 | 1 | 177 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-10-U-MP-410 | Install Electrical Power Trim @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > MEP Trim at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-12-01 | 2026-12-02 | 2 | 173 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-10-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2026-12-02 | 2026-12-03 | 2 | 177 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-10-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2026-12-02 | 2026-12-03 | 2 | 177 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-10-U-FN-390 | Install Kitchen Appliances @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-04 | 2 | 179 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-10-U-MP-420 | Install Light Fixtures @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > MEP Trim at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-09 | 5 | 173 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-10-U-MP-430 | Install FA & Low Voltage Devices @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > MEP Trim at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-08 | 4 | 174 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-10-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > Interior Finishes at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2026-12-04 | 2026-12-04 | 1 | 183 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-10-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2026-12-09 | 2026-12-10 | 2 | 172 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-10-U-FN-400 | Rough Cleanup @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-11 | 2 | 176 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-10-U-FN-410 | Touch-up Paint @ Units - L10 | yes | Finishes and equipment | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Interior Finishes at Units at 10th Lvl | TT_Task | TK_NotStart | 2026-12-14 | 2026-12-15 | 2 | 176 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-11-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-10-22 | 2026-10-30 | 7 | 119 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-11-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-11-02 | 2026-11-03 | 2 | 132 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-11-U-FN-370 | Install Flooring & Base @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-11-03 | 2026-11-09 | 5 | 135 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-11-U-FN-300 | Install Shower Enclosures @ B/Rs L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-06 | 3 | 132 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-11-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > MEP Eqp at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-17 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-11-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > MEP Eqp at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-09 | 4 | 198 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-11-U-FN-310 | Paint Final Coat @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-11-18 | 2026-11-23 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-11-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > Interior Finishes at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-11-30 | 3 | 167 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-11-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > Interior Finishes at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-11-25 | 2 | 180 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-11-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > Interior Finishes at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-11-30 | 3 | 180 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-11-U-FN-330 | Install Door Hardware @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-11-30 | 3 | 188 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-11-U-FN-340 | Install Toilet Accessories @ B/Rs - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-11-25 | 2 | 189 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-11-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-12-09 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-11-U-MP-400 | Install HVAC Trim & Control @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > MEP Trim at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-12-02 | 5 | 183 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-11-U-MP-440 | Install FP Sprinkler Heads @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > MEP Trim at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-12-02 | 5 | 183 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-11-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > Interior Finishes at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2026-12-01 | 2026-12-03 | 3 | 167 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-11-C-FN-130 | Install Trash Chute @ Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > Interior Finishes at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2026-12-04 | 2026-12-04 | 1 | 176 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-11-C-MP-100 | Install Elect & Low Voltage Panels @ Telecom/Elect Rm #1121- L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2026-12-04 | 2026-12-21 | 12 | 167 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-11-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > Interior Finishes at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-09 | 3 | 176 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-11-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > Interior Finishes at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-10 | 1 | 183 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-11-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > Interior Finishes at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-14 | 3 | 181 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-11-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-10 | 1 | 183 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-11-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-11 | 2 | 176 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-11-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-11 | 2 | 176 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-11-U-MP-410 | Install Electrical Power Trim @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > MEP Trim at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-11 | 2 | 171 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-11-U-FN-390 | Install Kitchen Appliances @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-12-14 | 2026-12-15 | 2 | 177 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-11-U-MP-420 | Install Light Fixtures @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > MEP Trim at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-12-14 | 2026-12-18 | 5 | 171 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-11-U-MP-430 | Install FA & Low Voltage Devices @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > MEP Trim at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-12-14 | 2026-12-17 | 4 | 172 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-11-U-FN-400 | Rough Cleanup @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-12-21 | 2026-12-22 | 2 | 174 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-11-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2026-12-22 | 2026-12-22 | 1 | 167 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-11-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2026-12-23 | 2026-12-24 | 2 | 167 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-11-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2026-12-23 | 2026-12-24 | 2 | 167 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-11-U-FN-410 | Touch-up Paint @ Units - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Interior Finishes at Units at 11th Lvl | TT_Task | TK_NotStart | 2026-12-23 | 2026-12-24 | 2 | 174 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-11-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L11 | yes | Finishes and equipment | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > Interior Finishes at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2026-12-28 | 1 | 173 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-12-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-09 | 7 | 118 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-12-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-11-10 | 2026-11-11 | 2 | 133 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-12-U-FN-370 | Install Flooring & Base @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-11-10 | 2026-11-16 | 5 | 137 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-12-U-FN-300 | Install Shower Enclosures @ B/Rs L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-11-12 | 2026-11-16 | 3 | 133 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-12-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > MEP Eqp at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-11-12 | 2026-11-17 | 4 | 197 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-12-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > MEP Eqp at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-11-13 | 2026-11-30 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-12-U-FN-310 | Paint Final Coat @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-12-01 | 2026-12-04 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-12-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > Interior Finishes at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-09 | 3 | 165 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-12-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > Interior Finishes at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-08 | 2 | 178 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-12-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > Interior Finishes at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-09 | 3 | 178 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-12-U-FN-330 | Install Door Hardware @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-09 | 3 | 186 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-12-U-FN-340 | Install Toilet Accessories @ B/Rs - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-08 | 2 | 187 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-12-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-18 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-12-U-MP-400 | Install HVAC Trim & Control @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > MEP Trim at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-11 | 5 | 181 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-12-U-MP-440 | Install FP Sprinkler Heads @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > MEP Trim at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-11 | 5 | 181 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-12-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > Interior Finishes at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-14 | 3 | 165 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-12-C-FN-130 | Install Trash Chute @ Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > Interior Finishes at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2026-12-15 | 2026-12-15 | 1 | 174 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-12-C-MP-100 | Install Elect & Low Voltage Panels @ Telecom/Elect Rm #1221- L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2026-12-15 | 2026-12-31 | 12 | 165 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-12-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > Interior Finishes at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2026-12-16 | 2026-12-18 | 3 | 174 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-12-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > Interior Finishes at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2026-12-21 | 2026-12-21 | 1 | 181 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-12-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > Interior Finishes at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2026-12-21 | 2026-12-23 | 3 | 179 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-12-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2026-12-21 | 2026-12-21 | 1 | 181 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-12-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2026-12-21 | 2026-12-22 | 2 | 174 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-12-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2026-12-21 | 2026-12-22 | 2 | 174 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-12-U-MP-410 | Install Electrical Power Trim @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > MEP Trim at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-12-21 | 2026-12-22 | 2 | 169 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-12-U-FN-390 | Install Kitchen Appliances @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-12-23 | 2026-12-24 | 2 | 175 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-12-U-MP-420 | Install Light Fixtures @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > MEP Trim at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-12-23 | 2026-12-30 | 5 | 169 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-12-U-MP-430 | Install FA & Low Voltage Devices @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > MEP Trim at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-12-23 | 2026-12-29 | 4 | 170 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-12-U-FN-400 | Rough Cleanup @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2026-12-31 | 2027-01-04 | 2 | 172 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-12-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-04 | 1 | 165 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-12-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2027-01-05 | 2027-01-06 | 2 | 165 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-12-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2027-01-05 | 2027-01-06 | 2 | 165 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-12-U-FN-410 | Touch-up Paint @ Units - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Interior Finishes at Units at 12th Lvl | TT_Task | TK_NotStart | 2027-01-05 | 2027-01-06 | 2 | 172 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-12-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L12 | yes | Finishes and equipment | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > Interior Finishes at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-07 | 1 | 171 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-14-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2026-11-09 | 2026-11-17 | 7 | 117 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-14-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2026-11-18 | 2026-11-19 | 2 | 134 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-14-U-FN-370 | Install Flooring & Base @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2026-11-18 | 2026-11-24 | 5 | 138 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-14-U-FN-300 | Install Shower Enclosures @ B/Rs L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-11-24 | 3 | 134 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-14-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > MEP Eqp at Units at 14th Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-11-25 | 4 | 196 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-14-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > MEP Eqp at Units at 14th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-12-09 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-14-U-FN-310 | Paint Final Coat @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-15 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-14-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > Interior Finishes at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2026-12-16 | 2026-12-18 | 3 | 166 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-14-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > Interior Finishes at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2026-12-16 | 2026-12-17 | 2 | 175 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-14-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > Interior Finishes at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2026-12-16 | 2026-12-18 | 3 | 175 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-14-U-FN-330 | Install Door Hardware @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2026-12-16 | 2026-12-18 | 3 | 184 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-14-U-FN-340 | Install Toilet Accessories @ B/Rs - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2026-12-16 | 2026-12-17 | 2 | 185 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-14-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2026-12-16 | 2026-12-30 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-14-U-MP-400 | Install HVAC Trim & Control @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > MEP Trim at Units at 14th Lvl | TT_Task | TK_NotStart | 2026-12-16 | 2026-12-22 | 5 | 179 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-14-U-MP-440 | Install FP Sprinkler Heads @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > MEP Trim at Units at 14th Lvl | TT_Task | TK_NotStart | 2026-12-16 | 2026-12-22 | 5 | 179 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-14-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > Interior Finishes at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2026-12-21 | 2026-12-23 | 3 | 166 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-14-C-FN-130 | Install Trash Chute @ Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > Interior Finishes at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2026-12-24 | 2026-12-24 | 1 | 171 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-14-C-MP-100 | Install Mech Eqp @ Mech Eqp Rm #1421 - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2026-12-24 | 2027-01-08 | 10 | 166 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-14-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > Interior Finishes at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2026-12-30 | 3 | 171 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-14-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > Interior Finishes at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2026-12-31 | 2026-12-31 | 1 | 179 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-14-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > Interior Finishes at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2026-12-31 | 2027-01-05 | 3 | 177 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-14-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2026-12-31 | 2026-12-31 | 1 | 179 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-14-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2026-12-31 | 2027-01-04 | 2 | 172 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-14-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2026-12-31 | 2026-12-31 | 1 | 171 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-14-U-MP-410 | Install Electrical Power Trim @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > MEP Trim at Units at 14th Lvl | TT_Task | TK_NotStart | 2026-12-31 | 2027-01-04 | 2 | 167 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-14-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-05 | 2 | 171 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-14-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-05 | 2 | 171 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-14-U-FN-390 | Install Kitchen Appliances @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-01-05 | 2027-01-06 | 2 | 173 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-14-U-MP-420 | Install Light Fixtures @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > MEP Trim at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-01-05 | 2027-01-11 | 5 | 167 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-14-U-MP-430 | Install FA & Low Voltage Devices @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > MEP Trim at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-01-05 | 2027-01-08 | 4 | 168 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-14-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > Interior Finishes at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2027-01-06 | 2027-01-06 | 1 | 177 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-14-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2027-01-11 | 2027-01-12 | 2 | 166 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-14-U-FN-400 | Rough Cleanup @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-13 | 2 | 170 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-14-U-FN-410 | Touch-up Paint @ Units - L14 | yes | Finishes and equipment | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Interior Finishes at Units at 14th Lvl | TT_Task | TK_NotStart | 2027-01-14 | 2027-01-15 | 2 | 170 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-15-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2026-11-17 | 2026-11-25 | 7 | 116 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-15-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2026-11-30 | 2026-12-01 | 2 | 135 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-15-U-FN-370 | Install Flooring & Base @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2026-11-30 | 2026-12-04 | 5 | 139 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-15-U-FN-300 | Install Shower Enclosures @ B/Rs L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2026-12-02 | 2026-12-04 | 3 | 135 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-15-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > MEP Eqp at Units at 15th Lvl | TT_Task | TK_NotStart | 2026-12-02 | 2026-12-07 | 4 | 195 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-15-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > MEP Eqp at Units at 15th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-18 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-15-U-FN-310 | Paint Final Coat @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2026-12-21 | 2026-12-24 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-15-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > Interior Finishes at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2026-12-30 | 3 | 161 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-15-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > Interior Finishes at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2026-12-29 | 2 | 174 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-15-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > Interior Finishes at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2026-12-30 | 3 | 174 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-15-U-FN-330 | Install Door Hardware @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2026-12-30 | 3 | 182 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-15-U-FN-340 | Install Toilet Accessories @ B/Rs - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2026-12-29 | 2 | 183 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-15-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2027-01-11 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-15-U-MP-400 | Install HVAC Trim & Control @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > MEP Trim at Units at 15th Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2027-01-04 | 5 | 177 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-15-U-MP-440 | Install FP Sprinkler Heads @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > MEP Trim at Units at 15th Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2027-01-04 | 5 | 177 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-15-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > Interior Finishes at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2026-12-31 | 2027-01-05 | 3 | 161 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-15-C-FN-130 | Install Trash Chute @ Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > Interior Finishes at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-01-06 | 2027-01-06 | 1 | 170 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-15-C-MP-100 | Install Low Voltage Panels @ Telecom Rm #1521- L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-01-06 | 2027-01-21 | 12 | 161 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-15-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > Interior Finishes at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-11 | 3 | 170 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-15-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > Interior Finishes at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-12 | 1 | 177 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-15-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > Interior Finishes at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-14 | 3 | 175 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-15-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-12 | 1 | 177 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-15-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-13 | 2 | 170 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-15-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-13 | 2 | 170 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-15-U-MP-410 | Install Electrical Power Trim @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > MEP Trim at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-13 | 2 | 165 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-15-U-FN-390 | Install Kitchen Appliances @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-01-14 | 2027-01-15 | 2 | 171 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-15-U-MP-420 | Install Light Fixtures @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > MEP Trim at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-01-14 | 2027-01-20 | 5 | 165 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-15-U-MP-430 | Install FA & Low Voltage Devices @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > MEP Trim at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-01-14 | 2027-01-19 | 4 | 166 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-15-U-FN-400 | Rough Cleanup @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-01-21 | 2027-01-22 | 2 | 168 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-15-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-01-22 | 2027-01-22 | 1 | 161 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-15-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-01-25 | 2027-01-26 | 2 | 161 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-15-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-01-25 | 2027-01-26 | 2 | 161 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-15-U-FN-410 | Touch-up Paint @ Units - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Interior Finishes at Units at 15th Lvl | TT_Task | TK_NotStart | 2027-01-25 | 2027-01-26 | 2 | 168 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-15-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L15 | yes | Finishes and equipment | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > Interior Finishes at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-01-27 | 1 | 167 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-16-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2026-11-25 | 2026-12-07 | 7 | 115 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-16-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2026-12-08 | 2026-12-09 | 2 | 136 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-16-U-FN-370 | Install Flooring & Base @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2026-12-08 | 2026-12-14 | 5 | 140 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-16-U-FN-300 | Install Shower Enclosures @ B/Rs L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-14 | 3 | 136 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-16-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > MEP Eqp at Units at 16th Lvl | TT_Task | TK_NotStart | 2026-12-10 | 2026-12-15 | 4 | 194 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-16-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > MEP Eqp at Units at 16th Lvl | TT_Task | TK_NotStart | 2026-12-16 | 2026-12-30 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-16-U-FN-310 | Paint Final Coat @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2026-12-31 | 2027-01-06 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-16-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > Interior Finishes at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-11 | 3 | 159 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-16-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > Interior Finishes at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-08 | 2 | 172 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-16-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > Interior Finishes at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-11 | 3 | 172 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-16-U-FN-330 | Install Door Hardware @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-11 | 3 | 180 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-16-U-FN-340 | Install Toilet Accessories @ B/Rs - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-08 | 2 | 181 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-16-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-20 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-16-U-MP-400 | Install HVAC Trim & Control @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > MEP Trim at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-13 | 5 | 175 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-16-U-MP-440 | Install FP Sprinkler Heads @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > MEP Trim at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-13 | 5 | 175 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-16-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > Interior Finishes at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-14 | 3 | 159 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-16-C-FN-130 | Install Trash Chute @ Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > Interior Finishes at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-01-15 | 2027-01-15 | 1 | 168 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-16-C-MP-100 | Install Elect Panels & Stack Meters @ Stack Vault #1621- L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-01-15 | 2027-02-01 | 12 | 159 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-16-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > Interior Finishes at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-20 | 3 | 168 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-16-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > Interior Finishes at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-01-21 | 2027-01-21 | 1 | 175 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-16-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > Interior Finishes at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-01-21 | 2027-01-25 | 3 | 173 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-16-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-01-21 | 2027-01-21 | 1 | 175 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-16-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-01-21 | 2027-01-22 | 2 | 168 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-16-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-01-21 | 2027-01-22 | 2 | 168 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-16-U-MP-410 | Install Electrical Power Trim @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > MEP Trim at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-01-21 | 2027-01-22 | 2 | 163 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-16-U-FN-390 | Install Kitchen Appliances @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-01-25 | 2027-01-26 | 2 | 169 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-16-U-MP-420 | Install Light Fixtures @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > MEP Trim at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-01-25 | 2027-01-29 | 5 | 163 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-16-U-MP-430 | Install FA & Low Voltage Devices @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > MEP Trim at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-01-25 | 2027-01-28 | 4 | 164 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-16-U-FN-400 | Rough Cleanup @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-02-01 | 2027-02-02 | 2 | 166 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-16-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-02 | 1 | 159 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-16-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-02-03 | 2027-02-04 | 2 | 159 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-16-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-02-03 | 2027-02-04 | 2 | 159 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-16-U-FN-410 | Touch-up Paint @ Units - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Interior Finishes at Units at 16th Lvl | TT_Task | TK_NotStart | 2027-02-03 | 2027-02-04 | 2 | 166 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-16-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L16 | yes | Finishes and equipment | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > Interior Finishes at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-05 | 1 | 165 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-17-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-15 | 7 | 114 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-17-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2026-12-16 | 2026-12-17 | 2 | 137 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-17-U-FN-370 | Install Flooring & Base @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2026-12-16 | 2026-12-22 | 5 | 141 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-17-U-FN-300 | Install Shower Enclosures @ B/Rs L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2026-12-18 | 2026-12-22 | 3 | 137 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-17-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > MEP Eqp at Units at 17th Lvl | TT_Task | TK_NotStart | 2026-12-18 | 2026-12-23 | 4 | 193 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-17-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > MEP Eqp at Units at 17th Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2027-01-11 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-17-U-FN-310 | Paint Final Coat @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-15 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-17-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > Interior Finishes at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-20 | 3 | 160 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-17-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > Interior Finishes at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-19 | 2 | 169 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-17-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > Interior Finishes at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-20 | 3 | 169 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-17-U-FN-330 | Install Door Hardware @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-20 | 3 | 178 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-17-U-FN-340 | Install Toilet Accessories @ B/Rs - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-19 | 2 | 179 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-17-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-29 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-17-U-MP-400 | Install HVAC Trim & Control @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > MEP Trim at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-22 | 5 | 173 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-17-U-MP-440 | Install FP Sprinkler Heads @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > MEP Trim at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-22 | 5 | 173 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-17-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > Interior Finishes at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-01-21 | 2027-01-25 | 3 | 160 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-17-C-FN-130 | Install Trash Chute @ Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > Interior Finishes at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-01-26 | 2027-01-26 | 1 | 165 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-17-C-MP-100 | Install Mech Eqp @ Mech Eqp Rm #1721 - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-01-26 | 2027-02-08 | 10 | 160 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-17-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > Interior Finishes at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-01-29 | 3 | 165 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-17-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > Interior Finishes at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-02-01 | 2027-02-01 | 1 | 173 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-17-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > Interior Finishes at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-02-01 | 2027-02-03 | 3 | 171 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-17-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-02-01 | 2027-02-01 | 1 | 173 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-17-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-02-01 | 2027-02-02 | 2 | 166 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-17-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-02-01 | 2027-02-01 | 1 | 165 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-17-U-MP-410 | Install Electrical Power Trim @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > MEP Trim at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-02-01 | 2027-02-02 | 2 | 161 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-17-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-03 | 2 | 165 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-17-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-03 | 2 | 165 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-17-U-FN-390 | Install Kitchen Appliances @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-02-03 | 2027-02-04 | 2 | 167 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-17-U-MP-420 | Install Light Fixtures @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > MEP Trim at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-02-03 | 2027-02-09 | 5 | 161 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-17-U-MP-430 | Install FA & Low Voltage Devices @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > MEP Trim at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-02-03 | 2027-02-08 | 4 | 162 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-17-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > Interior Finishes at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-02-04 | 2027-02-04 | 1 | 171 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-17-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-10 | 2 | 160 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-17-U-FN-400 | Rough Cleanup @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-02-10 | 2027-02-11 | 2 | 164 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-17-U-FN-410 | Touch-up Paint @ Units - L17 | yes | Finishes and equipment | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Interior Finishes at Units at 17th Lvl | TT_Task | TK_NotStart | 2027-02-12 | 2027-02-15 | 2 | 164 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-18-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2026-12-15 | 2026-12-23 | 7 | 113 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-18-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2026-12-24 | 2026-12-28 | 2 | 138 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-18-U-FN-370 | Install Flooring & Base @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2026-12-24 | 2026-12-31 | 5 | 142 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-18-U-FN-300 | Install Shower Enclosures @ B/Rs L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2026-12-29 | 2026-12-31 | 3 | 138 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-18-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > MEP Eqp at Units at 18th Lvl | TT_Task | TK_NotStart | 2026-12-29 | 2027-01-04 | 4 | 192 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-18-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > MEP Eqp at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-20 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-18-U-FN-310 | Paint Final Coat @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-01-21 | 2027-01-26 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-18-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > Interior Finishes at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-01-29 | 3 | 155 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-18-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > Interior Finishes at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-01-28 | 2 | 168 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-18-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > Interior Finishes at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-01-29 | 3 | 168 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-18-U-FN-330 | Install Door Hardware @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-01-29 | 3 | 176 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-18-U-FN-340 | Install Toilet Accessories @ B/Rs - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-01-28 | 2 | 177 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-18-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-02-09 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-18-U-MP-400 | Install HVAC Trim & Control @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > MEP Trim at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-02-02 | 5 | 171 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-18-U-MP-440 | Install FP Sprinkler Heads @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > MEP Trim at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-02-02 | 5 | 171 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-18-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > Interior Finishes at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-02-01 | 2027-02-03 | 3 | 155 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-18-C-FN-130 | Install Trash Chute @ Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > Interior Finishes at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-02-04 | 2027-02-04 | 1 | 164 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-18-C-MP-100 | Install Elect & Low Voltage Panels @ Telecom/Elect Rm #1821- L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-02-04 | 2027-02-19 | 12 | 155 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-18-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > Interior Finishes at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-09 | 3 | 164 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-18-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > Interior Finishes at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-02-10 | 2027-02-10 | 1 | 171 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-18-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > Interior Finishes at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-02-10 | 2027-02-12 | 3 | 169 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-18-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-02-10 | 2027-02-10 | 1 | 171 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-18-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-02-10 | 2027-02-11 | 2 | 164 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-18-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-02-10 | 2027-02-11 | 2 | 164 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-18-U-MP-410 | Install Electrical Power Trim @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > MEP Trim at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-02-10 | 2027-02-11 | 2 | 159 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-18-U-FN-390 | Install Kitchen Appliances @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-02-12 | 2027-02-15 | 2 | 165 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-18-U-MP-420 | Install Light Fixtures @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > MEP Trim at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-02-12 | 2027-02-18 | 5 | 159 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-18-U-MP-430 | Install FA & Low Voltage Devices @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > MEP Trim at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-02-12 | 2027-02-17 | 4 | 160 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-18-U-FN-400 | Rough Cleanup @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-02-19 | 2027-02-22 | 2 | 162 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-18-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-02-22 | 2027-02-22 | 1 | 155 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-18-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-02-24 | 2 | 155 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-18-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-02-24 | 2 | 155 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-18-U-FN-410 | Touch-up Paint @ Units - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Interior Finishes at Units at 18th Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-02-24 | 2 | 162 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-18-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L18 | yes | Finishes and equipment | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > Interior Finishes at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-02-25 | 1 | 161 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-19-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2026-12-23 | 2027-01-04 | 7 | 112 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-19-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-01-05 | 2027-01-06 | 2 | 139 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-19-U-FN-370 | Install Flooring & Base @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-01-05 | 2027-01-11 | 5 | 143 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-19-U-FN-300 | Install Shower Enclosures @ B/Rs L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-11 | 3 | 139 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-19-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > MEP Eqp at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-12 | 4 | 191 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-19-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > MEP Eqp at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-29 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-19-U-FN-310 | Paint Final Coat @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-02-01 | 2027-02-04 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-19-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > Interior Finishes at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-09 | 3 | 153 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-19-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > Interior Finishes at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-08 | 2 | 166 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-19-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > Interior Finishes at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-09 | 3 | 166 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-19-U-FN-330 | Install Door Hardware @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-09 | 3 | 174 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-19-U-FN-340 | Install Toilet Accessories @ B/Rs - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-08 | 2 | 175 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-19-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-18 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-19-U-MP-400 | Install HVAC Trim & Control @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > MEP Trim at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-11 | 5 | 169 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-19-U-MP-440 | Install FP Sprinkler Heads @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > MEP Trim at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-11 | 5 | 169 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-19-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > Interior Finishes at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-02-10 | 2027-02-12 | 3 | 153 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-19-C-FN-130 | Install Trash Chute @ Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > Interior Finishes at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-02-15 | 2027-02-15 | 1 | 162 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-19-C-MP-100 | Install Elect & Low Voltage Panels @ Telecom/Elect Rm #1921- L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-02-15 | 2027-03-02 | 12 | 153 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-19-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > Interior Finishes at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-18 | 3 | 162 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-19-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > Interior Finishes at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-02-19 | 2027-02-19 | 1 | 169 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-19-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > Interior Finishes at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-02-19 | 2027-02-23 | 3 | 167 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-19-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-02-19 | 2027-02-19 | 1 | 169 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-19-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-02-19 | 2027-02-22 | 2 | 162 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-19-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-02-19 | 2027-02-22 | 2 | 162 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-19-U-MP-410 | Install Electrical Power Trim @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > MEP Trim at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-02-19 | 2027-02-22 | 2 | 157 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-19-U-FN-390 | Install Kitchen Appliances @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-02-24 | 2 | 163 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-19-U-MP-420 | Install Light Fixtures @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > MEP Trim at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-03-01 | 5 | 157 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-19-U-MP-430 | Install FA & Low Voltage Devices @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > MEP Trim at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-02-26 | 4 | 158 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-19-U-FN-400 | Rough Cleanup @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-03-02 | 2027-03-03 | 2 | 160 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-19-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-03 | 1 | 153 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-19-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-03-04 | 2027-03-05 | 2 | 153 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-19-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-03-04 | 2027-03-05 | 2 | 153 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-19-U-FN-410 | Touch-up Paint @ Units - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Interior Finishes at Units at 19th Lvl | TT_Task | TK_NotStart | 2027-03-04 | 2027-03-05 | 2 | 160 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-19-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L19 | yes | Finishes and equipment | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > Interior Finishes at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-08 | 1 | 159 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-20-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-12 | 7 | 111 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-20-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-01-13 | 2027-01-14 | 2 | 140 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-20-U-FN-370 | Install Flooring & Base @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-01-13 | 2027-01-19 | 5 | 144 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-20-U-FN-300 | Install Shower Enclosures @ B/Rs L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-01-15 | 2027-01-19 | 3 | 140 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-20-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > MEP Eqp at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-01-15 | 2027-01-20 | 4 | 190 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-20-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > MEP Eqp at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-02-09 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-20-U-FN-310 | Paint Final Coat @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-02-10 | 2027-02-15 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-20-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > Interior Finishes at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-18 | 3 | 154 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-20-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > Interior Finishes at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-17 | 2 | 163 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-20-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > Interior Finishes at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-18 | 3 | 163 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-20-U-FN-330 | Install Door Hardware @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-18 | 3 | 172 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-20-U-FN-340 | Install Toilet Accessories @ B/Rs - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-17 | 2 | 173 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-20-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-03-01 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-20-U-MP-400 | Install HVAC Trim & Control @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > MEP Trim at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-22 | 5 | 167 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-20-U-MP-440 | Install FP Sprinkler Heads @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > MEP Trim at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-22 | 5 | 167 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-20-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > Interior Finishes at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-02-19 | 2027-02-23 | 3 | 154 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-20-C-FN-130 | Install Trash Chute @ Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > Interior Finishes at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-02-24 | 2027-02-24 | 1 | 159 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-20-C-MP-100 | Install Mech Eqp @ Mech Eqp Rm #2021 - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-02-24 | 2027-03-09 | 10 | 154 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-20-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > Interior Finishes at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-03-01 | 3 | 159 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-20-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > Interior Finishes at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-03-02 | 2027-03-02 | 1 | 167 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-20-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > Interior Finishes at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-03-02 | 2027-03-04 | 3 | 165 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-20-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-03-02 | 2027-03-02 | 1 | 167 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-20-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-03-02 | 2027-03-03 | 2 | 160 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-20-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-03-02 | 2027-03-02 | 1 | 159 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-20-U-MP-410 | Install Electrical Power Trim @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > MEP Trim at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-03-02 | 2027-03-03 | 2 | 155 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-20-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-04 | 2 | 159 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-20-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-04 | 2 | 159 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-20-U-FN-390 | Install Kitchen Appliances @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-03-04 | 2027-03-05 | 2 | 161 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-20-U-MP-420 | Install Light Fixtures @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > MEP Trim at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-03-04 | 2027-03-10 | 5 | 155 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-20-U-MP-430 | Install FA & Low Voltage Devices @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > MEP Trim at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-03-04 | 2027-03-09 | 4 | 156 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-20-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > Interior Finishes at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-03-05 | 2027-03-05 | 1 | 165 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-20-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-03-10 | 2027-03-11 | 2 | 154 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-20-U-FN-400 | Rough Cleanup @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-12 | 2 | 158 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-20-U-FN-410 | Touch-up Paint @ Units - L20 | yes | Finishes and equipment | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Interior Finishes at Units at 20th Lvl | TT_Task | TK_NotStart | 2027-03-15 | 2027-03-16 | 2 | 158 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-21-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-20 | 7 | 110 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-21-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-01-21 | 2027-01-22 | 2 | 141 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-21-U-FN-370 | Install Flooring & Base @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-01-21 | 2027-01-27 | 5 | 145 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-21-U-FN-300 | Install Shower Enclosures @ B/Rs L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-01-25 | 2027-01-27 | 3 | 141 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-21-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > MEP Eqp at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-01-25 | 2027-01-28 | 4 | 189 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-21-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > MEP Eqp at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-18 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-21-U-FN-310 | Paint Final Coat @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-02-19 | 2027-02-24 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-21-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > Interior Finishes at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-03-01 | 3 | 149 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-21-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > Interior Finishes at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-02-26 | 2 | 162 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-21-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > Interior Finishes at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-03-01 | 3 | 162 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-21-U-FN-330 | Install Door Hardware @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-03-01 | 3 | 170 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-21-U-FN-340 | Install Toilet Accessories @ B/Rs - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-02-26 | 2 | 171 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-21-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-03-10 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-21-U-MP-400 | Install HVAC Trim & Control @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > MEP Trim at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-03-03 | 5 | 165 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-21-U-MP-440 | Install FP Sprinkler Heads @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > MEP Trim at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-03-03 | 5 | 165 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-21-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > Interior Finishes at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-03-02 | 2027-03-04 | 3 | 149 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-21-C-FN-130 | Install Trash Chute @ Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > Interior Finishes at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-03-05 | 2027-03-05 | 1 | 158 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-21-C-MP-100 | Install Low Voltage Panels @ Telecom Rm #2121- L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-03-05 | 2027-03-22 | 12 | 149 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-21-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > Interior Finishes at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-10 | 3 | 158 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-21-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > Interior Finishes at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-11 | 1 | 165 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-21-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > Interior Finishes at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-15 | 3 | 163 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-21-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-11 | 1 | 165 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-21-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-12 | 2 | 158 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-21-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-12 | 2 | 158 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-21-U-MP-410 | Install Electrical Power Trim @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > MEP Trim at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-12 | 2 | 153 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-21-U-FN-390 | Install Kitchen Appliances @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-03-15 | 2027-03-16 | 2 | 159 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-21-U-MP-420 | Install Light Fixtures @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > MEP Trim at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-03-15 | 2027-03-19 | 5 | 153 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-21-U-MP-430 | Install FA & Low Voltage Devices @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > MEP Trim at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-03-15 | 2027-03-18 | 4 | 154 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-21-U-FN-400 | Rough Cleanup @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-03-22 | 2027-03-23 | 2 | 156 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-21-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-03-23 | 2027-03-23 | 1 | 149 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-21-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-25 | 2 | 149 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-21-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-25 | 2 | 149 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-21-U-FN-410 | Touch-up Paint @ Units - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Interior Finishes at Units at 21st Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-25 | 2 | 156 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-21-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L21 | yes | Finishes and equipment | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > Interior Finishes at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-03-26 | 1 | 155 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-22-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-01-28 | 7 | 109 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-22-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-01-29 | 2027-02-01 | 2 | 142 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-22-U-FN-370 | Install Flooring & Base @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-01-29 | 2027-02-04 | 5 | 146 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-22-U-FN-300 | Install Shower Enclosures @ B/Rs L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-04 | 3 | 142 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-22-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > MEP Eqp at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-05 | 4 | 188 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-22-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > MEP Eqp at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-03-01 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-22-U-FN-310 | Paint Final Coat @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-02 | 2027-03-05 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-22-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > Interior Finishes at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-10 | 3 | 147 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-22-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > Interior Finishes at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-09 | 2 | 160 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-22-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > Interior Finishes at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-10 | 3 | 160 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-22-U-FN-330 | Install Door Hardware @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-10 | 3 | 168 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-22-U-FN-340 | Install Toilet Accessories @ B/Rs - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-09 | 2 | 169 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-22-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-19 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-22-U-MP-400 | Install HVAC Trim & Control @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > MEP Trim at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-12 | 5 | 163 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-22-U-MP-440 | Install FP Sprinkler Heads @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > MEP Trim at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-12 | 5 | 163 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-22-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > Interior Finishes at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-15 | 3 | 147 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-22-C-FN-130 | Install Trash Chute @ Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > Interior Finishes at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-16 | 2027-03-16 | 1 | 156 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-22-C-MP-100 | Install Elect & Panels & Stack Meters @ Stack Vault #2221 - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-16 | 2027-03-31 | 12 | 147 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-22-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > Interior Finishes at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-19 | 3 | 156 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-22-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > Interior Finishes at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-22 | 2027-03-22 | 1 | 163 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-22-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > Interior Finishes at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-22 | 2027-03-24 | 3 | 161 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-22-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-22 | 2027-03-22 | 1 | 163 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-22-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-22 | 2027-03-23 | 2 | 156 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-22-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-22 | 2027-03-23 | 2 | 156 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-22-U-MP-410 | Install Electrical Power Trim @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > MEP Trim at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-22 | 2027-03-23 | 2 | 151 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-22-U-FN-390 | Install Kitchen Appliances @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-25 | 2 | 157 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-22-U-MP-420 | Install Light Fixtures @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > MEP Trim at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-30 | 5 | 151 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-22-U-MP-430 | Install FA & Low Voltage Devices @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > MEP Trim at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-29 | 4 | 152 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-22-U-FN-400 | Rough Cleanup @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-03-31 | 2027-04-01 | 2 | 154 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-22-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-01 | 1 | 147 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-22-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-04-02 | 2027-04-05 | 2 | 147 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-22-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-04-02 | 2027-04-05 | 2 | 147 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-22-U-FN-410 | Touch-up Paint @ Units - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Interior Finishes at Units at 22nd Lvl | TT_Task | TK_NotStart | 2027-04-02 | 2027-04-05 | 2 | 154 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-22-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L22 | yes | Finishes and equipment | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > Interior Finishes at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-06 | 1 | 153 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-23-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-01-28 | 2027-02-05 | 7 | 108 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-23-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-02-08 | 2027-02-09 | 2 | 143 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-23-U-FN-370 | Install Flooring & Base @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-02-08 | 2027-02-12 | 5 | 147 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-23-U-FN-300 | Install Shower Enclosures @ B/Rs L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-02-10 | 2027-02-12 | 3 | 143 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-23-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > MEP Eqp at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-02-10 | 2027-02-15 | 4 | 187 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-23-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > MEP Eqp at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-03-10 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-23-U-FN-310 | Paint Final Coat @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-16 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-23-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > Interior Finishes at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-19 | 3 | 148 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-23-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > Interior Finishes at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-18 | 2 | 157 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-23-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > Interior Finishes at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-19 | 3 | 157 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-23-U-FN-330 | Install Door Hardware @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-19 | 3 | 166 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-23-U-FN-340 | Install Toilet Accessories @ B/Rs - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-18 | 2 | 167 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-23-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-30 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-23-U-MP-400 | Install HVAC Trim & Control @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > MEP Trim at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-23 | 5 | 161 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-23-U-MP-440 | Install FP Sprinkler Heads @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > MEP Trim at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-23 | 5 | 161 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-23-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > Interior Finishes at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-22 | 2027-03-24 | 3 | 148 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-23-C-FN-130 | Install Trash Chute @ Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > Interior Finishes at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-25 | 2027-03-25 | 1 | 153 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-23-C-MP-100 | Install Mech Eqp @ Mech Eqp Rm #2321 - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-25 | 2027-04-07 | 10 | 148 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-23-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > Interior Finishes at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-03-30 | 3 | 153 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-23-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > Interior Finishes at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-31 | 2027-03-31 | 1 | 161 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-23-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > Interior Finishes at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-31 | 2027-04-02 | 3 | 159 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-23-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-31 | 2027-03-31 | 1 | 161 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-23-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-31 | 2027-04-01 | 2 | 154 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-23-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-31 | 2027-03-31 | 1 | 153 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-23-U-MP-410 | Install Electrical Power Trim @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > MEP Trim at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-03-31 | 2027-04-01 | 2 | 149 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-23-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-02 | 2 | 153 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-23-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-02 | 2 | 153 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-23-U-FN-390 | Install Kitchen Appliances @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-04-02 | 2027-04-05 | 2 | 155 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-23-U-MP-420 | Install Light Fixtures @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > MEP Trim at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-04-02 | 2027-04-08 | 5 | 149 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-23-U-MP-430 | Install FA & Low Voltage Devices @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > MEP Trim at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-04-02 | 2027-04-07 | 4 | 150 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-23-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > Interior Finishes at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-04-05 | 2027-04-05 | 1 | 159 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-23-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-04-08 | 2027-04-09 | 2 | 148 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-23-U-FN-400 | Rough Cleanup @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-12 | 2 | 152 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-23-U-FN-410 | Touch-up Paint @ Units - L23 | yes | Finishes and equipment | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Interior Finishes at Units at 23rd Lvl | TT_Task | TK_NotStart | 2027-04-13 | 2027-04-14 | 2 | 152 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-24-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-15 | 7 | 107 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-24-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-17 | 2 | 144 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-24-U-FN-370 | Install Flooring & Base @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-22 | 5 | 148 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-24-U-FN-300 | Install Shower Enclosures @ B/Rs L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-02-18 | 2027-02-22 | 3 | 144 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-24-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > MEP Eqp at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-02-18 | 2027-02-23 | 4 | 186 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-24-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > MEP Eqp at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-19 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-24-U-FN-310 | Paint Final Coat @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-03-22 | 2027-03-25 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-24-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > Interior Finishes at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-03-30 | 3 | 143 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-24-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > Interior Finishes at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-03-29 | 2 | 156 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-24-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > Interior Finishes at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-03-30 | 3 | 156 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-24-U-FN-330 | Install Door Hardware @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-03-30 | 3 | 164 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-24-U-FN-340 | Install Toilet Accessories @ B/Rs - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-03-29 | 2 | 165 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-24-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-04-08 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-24-U-MP-400 | Install HVAC Trim & Control @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > MEP Trim at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-04-01 | 5 | 159 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-24-U-MP-440 | Install FP Sprinkler Heads @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > MEP Trim at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-04-01 | 5 | 159 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-24-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > Interior Finishes at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-03-31 | 2027-04-02 | 3 | 143 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-24-C-FN-130 | Install Trash Chute @ Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > Interior Finishes at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-04-05 | 2027-04-05 | 1 | 152 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-24-C-MP-100 | Install Elect & Low Voltage Panels @ Telecom/Elect Rm #2421- L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-04-05 | 2027-04-20 | 12 | 143 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-24-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > Interior Finishes at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-08 | 3 | 152 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-24-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > Interior Finishes at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-09 | 1 | 159 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-24-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > Interior Finishes at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-13 | 3 | 157 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-24-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-09 | 1 | 159 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-24-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-12 | 2 | 152 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-24-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-12 | 2 | 152 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-24-U-MP-410 | Install Electrical Power Trim @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > MEP Trim at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-12 | 2 | 147 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-24-U-FN-390 | Install Kitchen Appliances @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-04-13 | 2027-04-14 | 2 | 153 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-24-U-MP-420 | Install Light Fixtures @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > MEP Trim at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-04-13 | 2027-04-19 | 5 | 147 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-24-U-MP-430 | Install FA & Low Voltage Devices @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > MEP Trim at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-04-13 | 2027-04-16 | 4 | 148 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-24-U-FN-400 | Rough Cleanup @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-04-20 | 2027-04-21 | 2 | 150 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-24-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-04-21 | 2027-04-21 | 1 | 143 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-24-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-04-22 | 2027-04-23 | 2 | 143 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-24-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-04-22 | 2027-04-23 | 2 | 143 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-24-U-FN-410 | Touch-up Paint @ Units - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Interior Finishes at Units at 24th Lvl | TT_Task | TK_NotStart | 2027-04-22 | 2027-04-23 | 2 | 150 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-24-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L24 | yes | Finishes and equipment | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > Interior Finishes at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-04-26 | 1 | 149 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-25-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-02-15 | 2027-02-23 | 7 | 106 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-25-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-02-24 | 2027-02-25 | 2 | 145 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-25-U-FN-370 | Install Flooring & Base @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-02-24 | 2027-03-02 | 5 | 149 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-25-U-FN-300 | Install Shower Enclosures @ B/Rs L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-02-26 | 2027-03-02 | 3 | 145 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-25-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > MEP Eqp at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-02-26 | 2027-03-03 | 4 | 185 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-25-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > MEP Eqp at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-30 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-25-U-FN-310 | Paint Final Coat @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-03-31 | 2027-04-05 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-25-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > Interior Finishes at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-08 | 3 | 141 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-25-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > Interior Finishes at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-07 | 2 | 154 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-25-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > Interior Finishes at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-08 | 3 | 154 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-25-U-FN-330 | Install Door Hardware @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-08 | 3 | 162 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-25-U-FN-340 | Install Toilet Accessories @ B/Rs - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-07 | 2 | 163 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-25-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-19 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-25-U-MP-400 | Install HVAC Trim & Control @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > MEP Trim at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-12 | 5 | 157 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-25-U-MP-440 | Install FP Sprinkler Heads @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > MEP Trim at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-12 | 5 | 157 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-25-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > Interior Finishes at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-13 | 3 | 141 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-25-C-FN-130 | Install Trash Chute @ Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > Interior Finishes at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-04-14 | 2027-04-14 | 1 | 150 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-25-C-MP-100 | Install Elect & Panels & Stack Meters @ Stack Vault #2521 - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-04-14 | 2027-04-29 | 12 | 141 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-25-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > Interior Finishes at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-04-15 | 2027-04-19 | 3 | 150 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-25-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > Interior Finishes at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-04-20 | 2027-04-20 | 1 | 157 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-25-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > Interior Finishes at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-04-20 | 2027-04-22 | 3 | 155 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-25-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-04-20 | 2027-04-20 | 1 | 157 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-25-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-04-20 | 2027-04-21 | 2 | 150 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-25-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-04-20 | 2027-04-21 | 2 | 150 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-25-U-MP-410 | Install Electrical Power Trim @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > MEP Trim at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-04-20 | 2027-04-21 | 2 | 145 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-25-U-FN-390 | Install Kitchen Appliances @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-04-22 | 2027-04-23 | 2 | 151 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-25-U-MP-420 | Install Light Fixtures @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > MEP Trim at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-04-22 | 2027-04-28 | 5 | 145 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-25-U-MP-430 | Install FA & Low Voltage Devices @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > MEP Trim at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-04-22 | 2027-04-27 | 4 | 146 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-25-U-FN-400 | Rough Cleanup @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-04-29 | 2027-04-30 | 2 | 148 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-25-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-04-30 | 2027-04-30 | 1 | 141 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-25-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-05-03 | 2027-05-04 | 2 | 141 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-25-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-05-03 | 2027-05-04 | 2 | 141 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-25-U-FN-410 | Touch-up Paint @ Units - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Interior Finishes at Units at 25th Lvl | TT_Task | TK_NotStart | 2027-05-03 | 2027-05-04 | 2 | 148 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-25-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L25 | yes | Finishes and equipment | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > Interior Finishes at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-05 | 1 | 147 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-26-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-03-03 | 7 | 105 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-26-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-03-04 | 2027-03-05 | 2 | 146 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-26-U-FN-370 | Install Flooring & Base @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-03-04 | 2027-03-10 | 5 | 150 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-26-U-FN-300 | Install Shower Enclosures @ B/Rs L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-10 | 3 | 146 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-26-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > MEP Eqp at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-11 | 4 | 184 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-26-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > MEP Eqp at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-04-08 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-26-U-FN-310 | Paint Final Coat @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-14 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-26-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > Interior Finishes at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-04-15 | 2027-04-19 | 3 | 142 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-26-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > Interior Finishes at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-04-15 | 2027-04-16 | 2 | 151 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-26-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > Interior Finishes at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-04-15 | 2027-04-19 | 3 | 151 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-26-U-FN-330 | Install Door Hardware @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-04-15 | 2027-04-19 | 3 | 160 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-26-U-FN-340 | Install Toilet Accessories @ B/Rs - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-04-15 | 2027-04-16 | 2 | 161 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-26-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-04-15 | 2027-04-28 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-26-U-MP-400 | Install HVAC Trim & Control @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > MEP Trim at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-04-15 | 2027-04-21 | 5 | 155 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-26-U-MP-440 | Install FP Sprinkler Heads @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > MEP Trim at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-04-15 | 2027-04-21 | 5 | 155 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-26-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > Interior Finishes at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-04-20 | 2027-04-22 | 3 | 142 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-26-C-FN-130 | Install Trash Chute @ Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > Interior Finishes at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-04-23 | 2027-04-23 | 1 | 147 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-26-C-MP-100 | Install Mech Eqp @ Mech Eqp Rm #2621- L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-04-23 | 2027-05-06 | 10 | 142 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-26-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > Interior Finishes at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-04-28 | 3 | 147 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-26-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > Interior Finishes at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-04-29 | 2027-04-29 | 1 | 155 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-26-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > Interior Finishes at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-04-29 | 2027-05-03 | 3 | 153 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-26-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-04-29 | 2027-04-29 | 1 | 155 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-26-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-04-29 | 2027-04-30 | 2 | 148 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-26-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-04-29 | 2027-04-29 | 1 | 147 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-26-U-MP-410 | Install Electrical Power Trim @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > MEP Trim at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-04-29 | 2027-04-30 | 2 | 143 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-26-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-04-30 | 2027-05-03 | 2 | 147 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-26-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-04-30 | 2027-05-03 | 2 | 147 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-26-U-FN-390 | Install Kitchen Appliances @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-05-03 | 2027-05-04 | 2 | 149 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-26-U-MP-420 | Install Light Fixtures @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > MEP Trim at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-05-03 | 2027-05-07 | 5 | 143 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-26-U-MP-430 | Install FA & Low Voltage Devices @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > MEP Trim at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-05-03 | 2027-05-06 | 4 | 144 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-26-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > Interior Finishes at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-05-04 | 2027-05-04 | 1 | 153 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-26-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-05-07 | 2027-05-10 | 2 | 142 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-26-U-FN-400 | Rough Cleanup @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-11 | 2 | 146 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-26-U-FN-410 | Touch-up Paint @ Units - L26 | yes | Finishes and equipment | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Interior Finishes at Units at 26th Lvl | TT_Task | TK_NotStart | 2027-05-12 | 2027-05-13 | 2 | 146 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-27-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-11 | 7 | 104 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-27-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-03-12 | 2027-03-15 | 2 | 147 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-27-U-FN-370 | Install Flooring & Base @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-03-12 | 2027-03-18 | 5 | 151 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-27-U-FN-300 | Install Shower Enclosures @ B/Rs L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-03-16 | 2027-03-18 | 3 | 147 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-27-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > MEP Eqp at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-03-16 | 2027-03-19 | 4 | 183 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-27-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > MEP Eqp at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-19 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-27-U-FN-310 | Paint Final Coat @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-04-20 | 2027-04-23 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-27-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > Interior Finishes at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-04-28 | 3 | 137 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-27-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > Interior Finishes at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-04-27 | 2 | 150 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-27-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > Interior Finishes at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-04-28 | 3 | 150 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-27-U-FN-330 | Install Door Hardware @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-04-28 | 3 | 158 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-27-U-FN-340 | Install Toilet Accessories @ B/Rs - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-04-27 | 2 | 159 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-27-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-05-07 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-27-U-MP-400 | Install HVAC Trim & Control @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > MEP Trim at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-04-30 | 5 | 153 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-27-U-MP-440 | Install FP Sprinkler Heads @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > MEP Trim at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-04-30 | 5 | 153 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-27-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > Interior Finishes at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-04-29 | 2027-05-03 | 3 | 137 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-27-C-FN-130 | Install Trash Chute @ Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > Interior Finishes at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-05-04 | 2027-05-04 | 1 | 146 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-27-C-MP-100 | Install Low Voltage Panels @ Telecom Rm #2721- L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-05-04 | 2027-05-19 | 12 | 137 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-27-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > Interior Finishes at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-07 | 3 | 146 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-27-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > Interior Finishes at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-10 | 1 | 153 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-27-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > Interior Finishes at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-12 | 3 | 151 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-27-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-10 | 1 | 153 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-27-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-11 | 2 | 146 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-27-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-11 | 2 | 146 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-27-U-MP-410 | Install Electrical Power Trim @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > MEP Trim at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-11 | 2 | 141 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-27-U-FN-390 | Install Kitchen Appliances @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-05-12 | 2027-05-13 | 2 | 147 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-27-U-MP-420 | Install Light Fixtures @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > MEP Trim at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-05-12 | 2027-05-18 | 5 | 141 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-27-U-MP-430 | Install FA & Low Voltage Devices @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > MEP Trim at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-05-12 | 2027-05-17 | 4 | 142 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-27-U-FN-400 | Rough Cleanup @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-05-20 | 2 | 144 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-27-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-05-20 | 2027-05-20 | 1 | 137 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-27-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-05-21 | 2027-05-24 | 2 | 137 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-27-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-05-21 | 2027-05-24 | 2 | 137 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-27-U-FN-410 | Touch-up Paint @ Units - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Interior Finishes at Units at 27th Lvl | TT_Task | TK_NotStart | 2027-05-21 | 2027-05-24 | 2 | 144 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-27-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L27 | yes | Finishes and equipment | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > Interior Finishes at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-05-25 | 1 | 143 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-28-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-19 | 7 | 103 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-28-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-03-22 | 2027-03-23 | 2 | 148 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-28-U-FN-370 | Install Flooring & Base @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-03-22 | 2027-03-26 | 5 | 152 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-28-U-FN-300 | Install Shower Enclosures @ B/Rs L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-26 | 3 | 148 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-28-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > MEP Eqp at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-29 | 4 | 182 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-28-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > MEP Eqp at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-04-15 | 2027-04-28 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-28-U-FN-310 | Paint Final Coat @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-04-29 | 2027-05-04 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-28-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > Interior Finishes at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-07 | 3 | 135 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-28-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > Interior Finishes at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-06 | 2 | 148 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-28-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > Interior Finishes at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-07 | 3 | 148 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-28-U-FN-330 | Install Door Hardware @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-07 | 3 | 156 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-28-U-FN-340 | Install Toilet Accessories @ B/Rs - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-06 | 2 | 157 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-28-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-18 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-28-U-MP-400 | Install HVAC Trim & Control @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > MEP Trim at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-11 | 5 | 151 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-28-U-MP-440 | Install FP Sprinkler Heads @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > MEP Trim at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-11 | 5 | 151 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-28-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > Interior Finishes at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-12 | 3 | 135 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-28-C-FN-130 | Install Trash Chute @ Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > Interior Finishes at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-05-13 | 2027-05-13 | 1 | 144 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-28-C-MP-100 | Install Elect Panels & Stack Meters @ Stack Vault #2821- L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-05-13 | 2027-05-28 | 12 | 135 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-28-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > Interior Finishes at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-05-14 | 2027-05-18 | 3 | 144 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-28-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > Interior Finishes at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-05-19 | 1 | 151 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-28-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > Interior Finishes at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-05-21 | 3 | 149 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-28-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-05-19 | 1 | 151 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-28-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-05-20 | 2 | 144 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-28-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-05-20 | 2 | 144 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-28-U-MP-410 | Install Electrical Power Trim @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > MEP Trim at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-05-20 | 2 | 139 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-28-U-FN-390 | Install Kitchen Appliances @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-05-21 | 2027-05-24 | 2 | 145 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-28-U-MP-420 | Install Light Fixtures @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > MEP Trim at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-05-21 | 2027-05-27 | 5 | 139 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-28-U-MP-430 | Install FA & Low Voltage Devices @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > MEP Trim at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-05-21 | 2027-05-26 | 4 | 140 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-28-U-FN-400 | Rough Cleanup @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-05-28 | 2027-06-01 | 2 | 142 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-28-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-06-01 | 2027-06-01 | 1 | 135 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-28-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-06-02 | 2027-06-03 | 2 | 135 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-28-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-06-02 | 2027-06-03 | 2 | 135 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-28-U-FN-410 | Touch-up Paint @ Units - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Interior Finishes at Units at 28th Lvl | TT_Task | TK_NotStart | 2027-06-02 | 2027-06-03 | 2 | 142 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-28-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L28 | yes | Finishes and equipment | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > Interior Finishes at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-06-04 | 2027-06-04 | 1 | 141 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-29-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-03-19 | 2027-03-29 | 7 | 102 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-29-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-03-30 | 2027-03-31 | 2 | 149 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-29-U-FN-370 | Install Flooring & Base @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-03-30 | 2027-04-05 | 5 | 153 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-29-U-FN-300 | Install Shower Enclosures @ B/Rs L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-05 | 3 | 149 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-29-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > MEP Eqp at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-06 | 4 | 181 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-29-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > MEP Eqp at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-05-07 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-29-U-FN-310 | Paint Final Coat @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-13 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-29-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > Interior Finishes at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-05-14 | 2027-05-18 | 3 | 136 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-29-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > Interior Finishes at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-05-14 | 2027-05-17 | 2 | 145 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-29-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > Interior Finishes at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-05-14 | 2027-05-18 | 3 | 145 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-29-U-FN-330 | Install Door Hardware @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-05-14 | 2027-05-18 | 3 | 154 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-29-U-FN-340 | Install Toilet Accessories @ B/Rs - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-05-14 | 2027-05-17 | 2 | 155 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-29-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-05-14 | 2027-05-27 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-29-U-MP-400 | Install HVAC Trim & Control @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > MEP Trim at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-05-14 | 2027-05-20 | 5 | 149 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-29-U-MP-440 | Install FP Sprinkler Heads @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > MEP Trim at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-05-14 | 2027-05-20 | 5 | 149 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-29-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > Interior Finishes at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-05-21 | 3 | 136 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-29-C-FN-130 | Install Trash Chute @ Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > Interior Finishes at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-05-24 | 2027-05-24 | 1 | 141 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-29-C-MP-100 | Install Mech Eqp @ Mech Eqp Rm #2921 - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-05-24 | 2027-06-07 | 10 | 136 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-29-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > Interior Finishes at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-05-27 | 3 | 141 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-29-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > Interior Finishes at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-05-28 | 2027-05-28 | 1 | 149 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-29-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > Interior Finishes at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-05-28 | 2027-06-02 | 3 | 147 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-29-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-05-28 | 2027-05-28 | 1 | 149 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-29-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-05-28 | 2027-06-01 | 2 | 142 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-29-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-05-28 | 2027-05-28 | 1 | 141 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-29-U-MP-410 | Install Electrical Power Trim @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > MEP Trim at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-05-28 | 2027-06-01 | 2 | 137 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-29-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-06-01 | 2027-06-02 | 2 | 141 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-29-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-06-01 | 2027-06-02 | 2 | 141 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-29-U-FN-390 | Install Kitchen Appliances @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-06-02 | 2027-06-03 | 2 | 143 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-29-U-MP-420 | Install Light Fixtures @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > MEP Trim at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-06-02 | 2027-06-08 | 5 | 137 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-29-U-MP-430 | Install FA & Low Voltage Devices @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > MEP Trim at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-06-02 | 2027-06-07 | 4 | 138 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-29-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > Interior Finishes at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-06-03 | 2027-06-03 | 1 | 147 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-29-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-06-08 | 2027-06-09 | 2 | 136 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-29-U-FN-400 | Rough Cleanup @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-06-09 | 2027-06-10 | 2 | 140 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-29-U-FN-410 | Touch-up Paint @ Units - L29 | yes | Finishes and equipment | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Interior Finishes at Units at 29th Lvl | TT_Task | TK_NotStart | 2027-06-11 | 2027-06-14 | 2 | 140 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-30-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-03-29 | 2027-04-06 | 7 | 101 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-30-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-04-07 | 2027-04-08 | 2 | 150 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-30-U-FN-370 | Install Flooring & Base @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-04-07 | 2027-04-13 | 5 | 154 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-30-U-FN-300 | Install Shower Enclosures @ B/Rs L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-13 | 3 | 150 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-30-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > MEP Eqp at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-14 | 4 | 180 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-30-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > MEP Eqp at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-18 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-30-U-FN-310 | Paint Final Coat @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-05-24 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-30-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > Interior Finishes at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-05-27 | 3 | 131 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-30-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > Interior Finishes at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-05-26 | 2 | 144 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-30-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > Interior Finishes at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-05-27 | 3 | 144 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-30-U-FN-330 | Install Door Hardware @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-05-27 | 3 | 152 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-30-U-FN-340 | Install Toilet Accessories @ B/Rs - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-05-26 | 2 | 153 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-30-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-06-08 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-30-U-MP-400 | Install HVAC Trim & Control @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > MEP Trim at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-06-01 | 5 | 147 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-30-U-MP-440 | Install FP Sprinkler Heads @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > MEP Trim at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-06-01 | 5 | 147 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-30-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > Interior Finishes at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-05-28 | 2027-06-02 | 3 | 131 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-30-C-FN-130 | Install Trash Chute @ Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > Interior Finishes at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-06-03 | 2027-06-03 | 1 | 140 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-30-C-MP-100 | Install Elect & Low Voltage Panels @ Telecom/Elect Rm #3021- L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-06-03 | 2027-06-18 | 12 | 131 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-30-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > Interior Finishes at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-06-04 | 2027-06-08 | 3 | 140 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-30-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > Interior Finishes at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-06-09 | 2027-06-09 | 1 | 147 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-30-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > Interior Finishes at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-06-09 | 2027-06-11 | 3 | 145 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-30-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-06-09 | 2027-06-09 | 1 | 147 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-30-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-06-09 | 2027-06-10 | 2 | 140 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-30-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-06-09 | 2027-06-10 | 2 | 140 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-30-U-MP-410 | Install Electrical Power Trim @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > MEP Trim at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-06-09 | 2027-06-10 | 2 | 135 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-30-U-FN-390 | Install Kitchen Appliances @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-06-11 | 2027-06-14 | 2 | 141 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-30-U-MP-420 | Install Light Fixtures @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > MEP Trim at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-06-11 | 2027-06-17 | 5 | 135 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-30-U-MP-430 | Install FA & Low Voltage Devices @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > MEP Trim at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-06-11 | 2027-06-16 | 4 | 136 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-30-U-FN-400 | Rough Cleanup @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-06-18 | 2027-06-21 | 2 | 138 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-30-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-06-21 | 2027-06-21 | 1 | 131 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-30-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-06-22 | 2027-06-23 | 2 | 131 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-30-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-06-22 | 2027-06-23 | 2 | 131 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-30-U-FN-410 | Touch-up Paint @ Units - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Interior Finishes at Units at 30th Lvl | TT_Task | TK_NotStart | 2027-06-22 | 2027-06-23 | 2 | 138 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-30-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L30 | yes | Finishes and equipment | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > Interior Finishes at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-24 | 1 | 137 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-31-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-14 | 7 | 100 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-31-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-04-15 | 2027-04-16 | 2 | 151 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-31-U-FN-370 | Install Flooring & Base @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-04-15 | 2027-04-21 | 5 | 155 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-31-U-FN-300 | Install Shower Enclosures @ B/Rs L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-04-19 | 2027-04-21 | 3 | 151 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-31-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > MEP Eqp at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-04-19 | 2027-04-22 | 4 | 179 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-31-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > MEP Eqp at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-05-14 | 2027-05-27 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-31-U-FN-310 | Paint Final Coat @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-05-28 | 2027-06-03 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-31-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > Interior Finishes at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-06-04 | 2027-06-08 | 3 | 129 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-31-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > Interior Finishes at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-06-04 | 2027-06-07 | 2 | 142 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-31-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > Interior Finishes at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-06-04 | 2027-06-08 | 3 | 142 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-31-U-FN-330 | Install Door Hardware @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-06-04 | 2027-06-08 | 3 | 150 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-31-U-FN-340 | Install Toilet Accessories @ B/Rs - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-06-04 | 2027-06-07 | 2 | 151 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-31-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-06-04 | 2027-06-17 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-31-U-MP-400 | Install HVAC Trim & Control @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > MEP Trim at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-06-04 | 2027-06-10 | 5 | 145 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-31-U-MP-440 | Install FP Sprinkler Heads @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > MEP Trim at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-06-04 | 2027-06-10 | 5 | 145 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-31-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > Interior Finishes at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-06-09 | 2027-06-11 | 3 | 129 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-31-C-FN-130 | Install Trash Chute @ Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > Interior Finishes at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-06-14 | 2027-06-14 | 1 | 138 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-31-C-MP-100 | Install Elect & Low Voltage Panels @ Telecom/Elect Rm #3121- L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-06-14 | 2027-06-29 | 12 | 129 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-31-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > Interior Finishes at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-06-15 | 2027-06-17 | 3 | 138 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-31-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > Interior Finishes at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-06-18 | 2027-06-18 | 1 | 145 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-31-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > Interior Finishes at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-06-18 | 2027-06-22 | 3 | 143 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-31-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-06-18 | 2027-06-18 | 1 | 145 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-31-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-06-18 | 2027-06-21 | 2 | 138 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-31-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-06-18 | 2027-06-21 | 2 | 138 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-31-U-MP-410 | Install Electrical Power Trim @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > MEP Trim at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-06-18 | 2027-06-21 | 2 | 133 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-31-U-FN-390 | Install Kitchen Appliances @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-06-22 | 2027-06-23 | 2 | 139 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-31-U-MP-420 | Install Light Fixtures @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > MEP Trim at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-06-22 | 2027-06-28 | 5 | 133 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-31-U-MP-430 | Install FA & Low Voltage Devices @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > MEP Trim at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-06-22 | 2027-06-25 | 4 | 134 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-31-U-FN-400 | Rough Cleanup @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-06-30 | 2 | 136 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-31-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-06-30 | 2027-06-30 | 1 | 129 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-31-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-02 | 2 | 129 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-31-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-02 | 2 | 129 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-31-U-FN-410 | Touch-up Paint @ Units - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Interior Finishes at Units at 31st Lvl | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-02 | 2 | 136 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-31-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L31 | yes | Finishes and equipment | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > Interior Finishes at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2027-07-06 | 2027-07-06 | 1 | 135 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-32-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-04-14 | 2027-04-22 | 7 | 99 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-32-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-04-23 | 2027-04-26 | 2 | 152 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-32-U-FN-370 | Install Flooring & Base @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-04-23 | 2027-04-29 | 5 | 156 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-32-U-FN-300 | Install Shower Enclosures @ B/Rs L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-04-27 | 2027-04-29 | 3 | 152 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-32-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > MEP Eqp at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-04-27 | 2027-04-30 | 4 | 178 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-32-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > MEP Eqp at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-05-25 | 2027-06-08 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-32-U-FN-310 | Paint Final Coat @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-09 | 2027-06-14 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-32-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > Interior Finishes at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-15 | 2027-06-17 | 3 | 130 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-32-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > Interior Finishes at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-15 | 2027-06-16 | 2 | 139 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-32-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > Interior Finishes at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-15 | 2027-06-17 | 3 | 139 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-32-U-FN-330 | Install Door Hardware @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-15 | 2027-06-17 | 3 | 148 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-32-U-FN-340 | Install Toilet Accessories @ B/Rs - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-15 | 2027-06-16 | 2 | 149 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-32-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-15 | 2027-06-28 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-32-U-MP-400 | Install HVAC Trim & Control @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > MEP Trim at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-15 | 2027-06-21 | 5 | 143 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-32-U-MP-440 | Install FP Sprinkler Heads @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > MEP Trim at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-15 | 2027-06-21 | 5 | 143 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-32-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > Interior Finishes at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-18 | 2027-06-22 | 3 | 130 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-32-C-FN-130 | Install Trash Chute @ Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > Interior Finishes at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-23 | 2027-06-23 | 1 | 135 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-32-C-MP-100 | Install Mech Eqp @ Mech Eqp Rm #3221 - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-23 | 2027-07-07 | 10 | 130 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-32-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > Interior Finishes at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-28 | 3 | 135 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-32-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > Interior Finishes at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-06-29 | 1 | 143 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-32-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > Interior Finishes at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-07-01 | 3 | 141 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-32-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-06-29 | 1 | 143 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-32-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-06-30 | 2 | 136 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-32-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-06-29 | 1 | 135 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-32-U-MP-410 | Install Electrical Power Trim @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > MEP Trim at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-06-30 | 2 | 131 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-32-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-30 | 2027-07-01 | 2 | 135 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-32-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-06-30 | 2027-07-01 | 2 | 135 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-32-U-FN-390 | Install Kitchen Appliances @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-02 | 2 | 137 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-32-U-MP-420 | Install Light Fixtures @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > MEP Trim at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-08 | 5 | 131 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-32-U-MP-430 | Install FA & Low Voltage Devices @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > MEP Trim at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-07 | 4 | 132 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-32-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > Interior Finishes at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-07-02 | 2027-07-02 | 1 | 141 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-32-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2027-07-08 | 2027-07-09 | 2 | 130 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-32-U-FN-400 | Rough Cleanup @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-12 | 2 | 134 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-32-U-FN-410 | Touch-up Paint @ Units - L32 | yes | Finishes and equipment | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Interior Finishes at Units at 32nd Lvl | TT_Task | TK_NotStart | 2027-07-13 | 2027-07-14 | 2 | 134 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-33-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-04-22 | 2027-04-30 | 7 | 98 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-33-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-05-03 | 2027-05-04 | 2 | 153 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-33-U-FN-370 | Install Flooring & Base @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-05-03 | 2027-05-07 | 5 | 157 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-33-U-FN-300 | Install Shower Enclosures @ B/Rs L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-07 | 3 | 153 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-33-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > MEP Eqp at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-10 | 4 | 177 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-33-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > MEP Eqp at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-06-04 | 2027-06-17 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-33-U-FN-310 | Paint Final Coat @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-06-18 | 2027-06-23 | 4 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-33-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > Interior Finishes at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-28 | 3 | 125 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-33-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > Interior Finishes at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-25 | 2 | 138 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-33-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > Interior Finishes at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-28 | 3 | 138 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-33-U-FN-330 | Install Door Hardware @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-28 | 3 | 146 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-33-U-FN-340 | Install Toilet Accessories @ B/Rs - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-25 | 2 | 147 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-33-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-07-08 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-33-U-MP-400 | Install HVAC Trim & Control @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > MEP Trim at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-30 | 5 | 141 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-33-U-MP-440 | Install FP Sprinkler Heads @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > MEP Trim at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-30 | 5 | 141 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-33-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > Interior Finishes at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-07-01 | 3 | 125 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-33-C-FN-130 | Install Trash Chute @ Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > Interior Finishes at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-02 | 2027-07-02 | 1 | 134 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-33-C-MP-100 | Install Low Voltage Panels @ Telecom Rm #3321- L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-02 | 2027-07-20 | 12 | 125 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-33-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > Interior Finishes at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-06 | 2027-07-08 | 3 | 134 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-33-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > Interior Finishes at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-09 | 1 | 141 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-33-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > Interior Finishes at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-13 | 3 | 139 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-33-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-09 | 1 | 141 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-33-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-12 | 2 | 134 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-33-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-12 | 2 | 134 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-33-U-MP-410 | Install Electrical Power Trim @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > MEP Trim at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-12 | 2 | 129 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-33-U-FN-390 | Install Kitchen Appliances @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-13 | 2027-07-14 | 2 | 135 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-33-U-MP-420 | Install Light Fixtures @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > MEP Trim at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-13 | 2027-07-19 | 5 | 129 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-33-U-MP-430 | Install FA & Low Voltage Devices @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > MEP Trim at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-13 | 2027-07-16 | 4 | 130 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-33-U-FN-400 | Rough Cleanup @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-20 | 2027-07-21 | 2 | 132 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-33-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-21 | 2027-07-21 | 1 | 125 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-33-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-07-23 | 2 | 125 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-33-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-07-23 | 2 | 125 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-33-U-FN-410 | Touch-up Paint @ Units - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Interior Finishes at Units at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-07-23 | 2 | 132 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-33-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L33 | yes | Finishes and equipment | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > Interior Finishes at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2027-07-26 | 2027-07-26 | 1 | 131 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-34-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-04-30 | 2027-05-10 | 7 | 97 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-34-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-05-11 | 2027-05-12 | 2 | 152 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-34-U-FN-370 | Install Flooring & Base @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-05-11 | 2027-05-17 | 5 | 158 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-34-U-FN-300 | Install Shower Enclosures @ B/Rs L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-05-13 | 2027-05-17 | 3 | 152 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-34-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > MEP Eqp at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-05-13 | 2027-05-18 | 4 | 176 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-34-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > MEP Eqp at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-06-15 | 2027-06-28 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-34-U-FN-310 | Paint Final Coat @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-07-02 | 4 | 123 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-34-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > Interior Finishes at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-07-06 | 2027-07-08 | 3 | 123 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-34-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > Interior Finishes at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-07-06 | 2027-07-07 | 2 | 136 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-34-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > Interior Finishes at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-07-06 | 2027-07-08 | 3 | 136 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-34-U-FN-330 | Install Door Hardware @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-07-06 | 2027-07-08 | 3 | 144 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-34-U-FN-340 | Install Toilet Accessories @ B/Rs - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-07-06 | 2027-07-07 | 2 | 145 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-34-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-07-06 | 2027-07-19 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-34-U-MP-400 | Install HVAC Trim & Control @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > MEP Trim at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-07-06 | 2027-07-12 | 5 | 139 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-34-U-MP-440 | Install FP Sprinkler Heads @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > MEP Trim at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-07-06 | 2027-07-12 | 5 | 139 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-34-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > Interior Finishes at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-13 | 3 | 123 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-34-C-FN-130 | Install Trash Chute @ Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > Interior Finishes at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-07-14 | 2027-07-14 | 1 | 132 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-34-C-MP-100 | Install Elect Panels & Stack Meters @ Stack Vault #3421- L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-07-14 | 2027-07-29 | 12 | 123 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-34-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > Interior Finishes at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-19 | 3 | 132 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-34-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > Interior Finishes at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-07-20 | 2027-07-20 | 1 | 139 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-34-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > Interior Finishes at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-07-20 | 2027-07-22 | 3 | 137 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-34-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-07-20 | 2027-07-20 | 1 | 139 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-34-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-07-20 | 2027-07-21 | 2 | 132 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-34-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-07-20 | 2027-07-21 | 2 | 132 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-34-U-MP-410 | Install Electrical Power Trim @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > MEP Trim at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-07-20 | 2027-07-21 | 2 | 127 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-34-U-FN-390 | Install Kitchen Appliances @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-07-23 | 2 | 133 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-34-U-MP-420 | Install Light Fixtures @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > MEP Trim at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-07-28 | 5 | 127 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-34-U-MP-430 | Install FA & Low Voltage Devices @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > MEP Trim at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-07-27 | 4 | 128 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-34-U-FN-400 | Rough Cleanup @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-07-29 | 2027-07-30 | 2 | 130 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-34-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-07-30 | 2027-07-30 | 1 | 123 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-34-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-03 | 2 | 123 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-34-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-03 | 2 | 123 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-34-U-FN-410 | Touch-up Paint @ Units - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Interior Finishes at Units at 34th Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-03 | 2 | 130 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-34-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L34 | yes | Finishes and equipment | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > Interior Finishes at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2027-08-04 | 2027-08-04 | 1 | 129 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-35-U-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-18 | 7 | 96 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-35-U-FN-290 | Install Vanities & Mirrors @ B/Rs - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-05-20 | 2 | 96 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-35-U-FN-370 | Install Flooring & Base @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-05-25 | 5 | 159 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-35-U-FN-300 | Install Shower Enclosures @ B/Rs L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-05-21 | 2027-05-25 | 3 | 96 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-35-U-MP-210 | Install Plumbing Fixtures @ B/Rs - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > MEP Eqp at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-05-21 | 2027-05-26 | 4 | 175 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-35-U-MP-200 | Install Mech Heat Pumps & Eqp @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > MEP Eqp at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-07-08 | 10 | 66 | Interior MEPs & Finishes | MEP Eqp at Units
Phased TCO | C-35-U-FN-310 | Paint Final Coat @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-14 | 4 | 66 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-35-C-FN-100 | Hang Drywall @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > Interior Finishes at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-19 | 3 | 66 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-35-C-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > Interior Finishes at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-16 | 2 | 70 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-35-C-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > Interior Finishes at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-19 | 3 | 70 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-35-U-FN-330 | Install Door Hardware @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-19 | 3 | 142 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-35-U-FN-340 | Install Toilet Accessories @ B/Rs - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-16 | 2 | 143 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-35-U-FN-350 | Install Kitchen Cabinets & Countertops @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-28 | 10 | 125 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-35-U-MP-400 | Install HVAC Trim & Control @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > MEP Trim at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-21 | 5 | 137 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-35-U-MP-440 | Install FP Sprinkler Heads @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > MEP Trim at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-21 | 5 | 137 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-35-C-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > Interior Finishes at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-07-20 | 2027-07-22 | 3 | 66 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-35-C-FN-130 | Install Trash Chute @ Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > Interior Finishes at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-07-23 | 2027-07-23 | 1 | 66 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-35-C-MP-100 | Install Elect Panels @ Elect Rm #3521- L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-07-23 | 2027-08-09 | 12 | 121 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-35-C-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > Interior Finishes at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-07-26 | 2027-07-28 | 3 | 66 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-35-C-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > Interior Finishes at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-07-29 | 2027-07-29 | 1 | 137 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-35-C-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > Interior Finishes at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-07-29 | 2027-08-02 | 3 | 135 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-35-C-MP-110 | Install Fire Extinguisher Cabinets @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-07-29 | 2027-07-29 | 1 | 137 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-35-C-MP-120 | Install HVAC Trim @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-07-29 | 2027-07-30 | 2 | 66 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-35-C-MP-140 | Install FP Sprinkler Heads @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-07-29 | 2027-07-30 | 2 | 130 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-35-U-MP-410 | Install Electrical Power Trim @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > MEP Trim at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-07-29 | 2027-07-30 | 2 | 125 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-35-U-FN-390 | Install Kitchen Appliances @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-03 | 2 | 131 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-35-U-MP-420 | Install Light Fixtures @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > MEP Trim at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-06 | 5 | 125 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-35-U-MP-430 | Install FA & Low Voltage Devices @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > MEP Trim at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-05 | 4 | 126 | Interior MEPs & Finishes | MEP Trim at Units
Phased TCO | C-35-U-FN-400 | Rough Cleanup @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-08-09 | 2027-08-10 | 2 | 128 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-35-C-MP-150 | Install Electrical Power Trim @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-08-10 | 2027-08-10 | 1 | 121 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-35-C-MP-130 | Install FA & Low Voltage Devices @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-08-11 | 2027-08-12 | 2 | 121 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-35-C-MP-160 | Install Light Fixtures @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > MEP Eqp & Trim at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-08-11 | 2027-08-12 | 2 | 121 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & Corridor
Phased TCO | C-35-U-FN-410 | Touch-up Paint @ Units - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Interior Finishes at Units at 35th Lvl | TT_Task | TK_NotStart | 2027-08-11 | 2027-08-12 | 2 | 128 | Interior MEPs & Finishes | Interior Finishes at Units
Phased TCO | C-35-C-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L35 | yes | Finishes and equipment | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > Interior Finishes at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2027-08-13 | 2027-08-13 | 1 | 127 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-36-IN-MP-400 | Install Mech EFs @ Indoor - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > MEP Eqp & Trim at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-05-13 | 2027-05-14 | 2 | 107 | Interior MEPs & Finishes | MEP Eqp & Trim at Indoor
Phased TCO | C-36-IN-MP-200 | Inspect MEP Rough @ Indoor - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior Wall Framing & MEP Rough at 36th Pool Lvl > MEP Risers & Rough at Indoor 36th Pool Lvl > MEP Rough at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-05-19 | 1 | 100 | Interior MEPs & Finishes | MEP Rough at Indoor
Phased TCO | C-36-IN-FN-280 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-10 | 2027-06-11 | 2 | 103 | Interior MEPs & Finishes | Interior Finishes at Indoor
Phased TCO | C-36-IN-FN-290 | Install Vanities & Mirrors @ B/Rs - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-14 | 2027-06-14 | 1 | 103 | Interior MEPs & Finishes | Interior Finishes at Indoor
Phased TCO | C-36-IN-FN-310 | Paint Final Coat @ Indoor - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-15 | 2027-06-17 | 3 | 103 | Interior MEPs & Finishes | Interior Finishes at Indoor
Phased TCO | C-36-IN-MP-410 | Install Plumbing Fixtures @ B/Rs - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > MEP Eqp & Trim at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-15 | 2027-06-16 | 2 | 111 | Interior MEPs & Finishes | MEP Eqp & Trim at Indoor
Phased TCO | C-36-IN-FN-330 | Install Door Hardware @ Indoor - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-18 | 2027-06-21 | 2 | 111 | Interior MEPs & Finishes | Interior Finishes at Indoor
Phased TCO | C-36-IN-FN-340 | Install Toilet Accessories @ B/Rs - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-18 | 2027-06-18 | 1 | 112 | Interior MEPs & Finishes | Interior Finishes at Indoor
Phased TCO | C-36-IN-MP-420 | Install HVAC Trim & Control @ Indoor - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > MEP Eqp & Trim at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-18 | 2027-06-22 | 3 | 107 | Interior MEPs & Finishes | MEP Eqp & Trim at Indoor
Phased TCO | C-36-IN-MP-430 | Install Electrical Power Trim @ Indoor - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > MEP Eqp & Trim at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-18 | 2027-06-21 | 2 | 105 | Interior MEPs & Finishes | MEP Eqp & Trim at Indoor
Phased TCO | C-36-IN-MP-440 | Install Light Fixtures @ Indoor - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > MEP Eqp & Trim at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-18 | 2027-06-22 | 3 | 107 | Interior MEPs & Finishes | MEP Eqp & Trim at Indoor
Phased TCO | C-36-IN-MP-450 | Install FA & Low Voltage Devices @ Indoor - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > MEP Eqp & Trim at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-22 | 2027-06-24 | 3 | 105 | Interior MEPs & Finishes | MEP Eqp & Trim at Indoor
Phased TCO | C-36-IN-MP-460 | Install FP Sprinkler Heads @ Indoor - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > MEP Eqp & Trim at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-22 | 2027-06-23 | 2 | 109 | Interior MEPs & Finishes | MEP Eqp & Trim at Indoor
Phased TCO | C-36-IN-MP-470 | Install Steam Eqp @ Steam Rms #3608 & #3609 - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > MEP Eqp & Trim at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-23 | 2027-07-07 | 10 | 100 | Interior MEPs & Finishes | MEP Eqp & Trim at Indoor
Phased TCO | C-36-IN-FN-400 | Rough Cleanup @ Indoor - L36 | yes | Finishes and equipment | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Interior Finishes at Indoor at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-07-08 | 2027-07-09 | 2 | 100 | Interior MEPs & Finishes | Interior Finishes at Indoor
Phased TCO | C-01-U-PC-900 | Partial MEP Systems Inspections @ L1 | yes | Inspection and contractor punch | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Units Partial Inspections & Punchout & Key Delivery at 1st Lvl | TT_Task | TK_NotStart | 2027-07-27 | 2027-08-09 | 10 | 14 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-01-U-PC-910 | Subcontractor Punch List & Punch Paint @ L1 | yes | Inspection and contractor punch | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Units Partial Inspections & Punchout & Key Delivery at 1st Lvl | TT_Task | TK_NotStart | 2027-08-10 | 2027-08-30 | 15 | 79 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-01-U-PC-920 | GC Punchlist @ L1 | yes | Inspection and contractor punch | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Units Partial Inspections & Punchout & Key Delivery at 1st Lvl | TT_Task | TK_NotStart | 2027-08-31 | 2027-09-07 | 5 | 79 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-02-U-PC-900 | Partial MEP Systems Inspections @ L2 | yes | Inspection and contractor punch | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 2nd Lvl | TT_Task | TK_NotStart | 2027-06-28 | 2027-07-06 | 6 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-02-U-PC-910 | Subcontractor Punch List & Punch Paint @ L2 | yes | Inspection and contractor punch | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 2nd Lvl | TT_Task | TK_NotStart | 2027-07-07 | 2027-07-20 | 10 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-02-U-PC-920 | GC Punchlist @ L2 | yes | Inspection and contractor punch | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 2nd Lvl | TT_Task | TK_NotStart | 2027-07-21 | 2027-07-26 | 4 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-03-U-PC-900 | Partial MEP Systems Inspections @ L3 | yes | Inspection and contractor punch | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 3rd Lvl | TT_Task | TK_NotStart | 2027-07-02 | 2027-07-12 | 6 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-03-U-PC-910 | Subcontractor Punch List & Punch Paint @ L3 | yes | Inspection and contractor punch | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 3rd Lvl | TT_Task | TK_NotStart | 2027-07-13 | 2027-07-26 | 10 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-03-U-PC-920 | GC Punchlist @ L3 | yes | Inspection and contractor punch | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 3rd Lvl | TT_Task | TK_NotStart | 2027-07-27 | 2027-07-30 | 4 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-04-U-PC-900 | Partial MEP Systems Inspections @ L4 | yes | Inspection and contractor punch | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > Units Partial Inspections & Punchout & Key Delivery at 4th Lvl | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-16 | 6 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-04-U-PC-910 | Subcontractor Punch List & Punch Paint @ L4 | yes | Inspection and contractor punch | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > Units Partial Inspections & Punchout & Key Delivery at 4th Lvl | TT_Task | TK_NotStart | 2027-07-19 | 2027-07-30 | 10 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-04-U-PC-920 | GC Punchlist @ L4 | yes | Inspection and contractor punch | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > Units Partial Inspections & Punchout & Key Delivery at 4th Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-05 | 4 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-05-U-PC-900 | Partial MEP Systems Inspections @ L5 | yes | Inspection and contractor punch | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > Units Partial Inspections & Punchout & Key Delivery at 5th Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-22 | 6 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-05-U-PC-910 | Subcontractor Punch List & Punch Paint @ L5 | yes | Inspection and contractor punch | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > Units Partial Inspections & Punchout & Key Delivery at 5th Lvl | TT_Task | TK_NotStart | 2027-07-23 | 2027-08-05 | 10 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-05-U-PC-920 | GC Punchlist @ L5 | yes | Inspection and contractor punch | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > Units Partial Inspections & Punchout & Key Delivery at 5th Lvl | TT_Task | TK_NotStart | 2027-08-06 | 2027-08-11 | 4 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-06-U-PC-900 | Partial MEP Systems Inspections @ L6 | yes | Inspection and contractor punch | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > Units Partial Inspections & Punchout & Key Delivery at 6th Lvl | TT_Task | TK_NotStart | 2027-07-21 | 2027-07-28 | 6 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-06-U-PC-910 | Subcontractor Punch List & Punch Paint @ L6 | yes | Inspection and contractor punch | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > Units Partial Inspections & Punchout & Key Delivery at 6th Lvl | TT_Task | TK_NotStart | 2027-07-29 | 2027-08-11 | 10 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-06-U-PC-920 | GC Punchlist @ L6 | yes | Inspection and contractor punch | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > Units Partial Inspections & Punchout & Key Delivery at 6th Lvl | TT_Task | TK_NotStart | 2027-08-12 | 2027-08-17 | 4 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-07-U-PC-900 | Partial MEP Systems Inspections @ Units - L7 | yes | Inspection and contractor punch | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Units Partial Inspections & Punchout & Key Delivery at 7th Lvl | TT_Task | TK_NotStart | 2027-07-26 | 2027-08-03 | 7 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-07-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L7 | yes | Inspection and contractor punch | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Units Partial Inspections & Punchout & Key Delivery at 7th Lvl | TT_Task | TK_NotStart | 2027-08-04 | 2027-08-17 | 10 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-07-U-PC-920 | GC Punchlist @ Units - L7 | yes | Inspection and contractor punch | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Units Partial Inspections & Punchout & Key Delivery at 7th Lvl | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-24 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-08-U-PC-900 | Partial MEP Systems Inspections @ Units - L8 | yes | Inspection and contractor punch | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Units Partial Inspections & Punchout & Key Delivery at 8th Lvl | TT_Task | TK_NotStart | 2027-07-30 | 2027-08-09 | 7 | 1 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-08-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L8 | yes | Inspection and contractor punch | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Units Partial Inspections & Punchout & Key Delivery at 8th Lvl | TT_Task | TK_NotStart | 2027-08-10 | 2027-08-23 | 10 | 1 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-08-U-PC-920 | GC Punchlist @ Units - L8 | yes | Inspection and contractor punch | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Units Partial Inspections & Punchout & Key Delivery at 8th Lvl | TT_Task | TK_NotStart | 2027-08-24 | 2027-08-30 | 5 | 1 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-09-U-PC-900 | Partial MEP Systems Inspections @ Units - L9 | yes | Inspection and contractor punch | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Units Partial Inspections & Punchout & Key Delivery at 9th Lvl | TT_Task | TK_NotStart | 2027-08-05 | 2027-08-13 | 7 | 2 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-09-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L9 | yes | Inspection and contractor punch | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Units Partial Inspections & Punchout & Key Delivery at 9th Lvl | TT_Task | TK_NotStart | 2027-08-16 | 2027-08-27 | 10 | 2 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-09-U-PC-920 | GC Punchlist @ Units - L9 | yes | Inspection and contractor punch | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Units Partial Inspections & Punchout & Key Delivery at 9th Lvl | TT_Task | TK_NotStart | 2027-08-30 | 2027-09-03 | 5 | 2 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-10-U-PC-900 | Partial MEP Systems Inspections @ Units - L10 | yes | Inspection and contractor punch | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Units Partial Inspections & Punchout & Key Delivery at 10th Lvl | TT_Task | TK_NotStart | 2027-08-11 | 2027-08-19 | 7 | 3 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-10-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L10 | yes | Inspection and contractor punch | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Units Partial Inspections & Punchout & Key Delivery at 10th Lvl | TT_Task | TK_NotStart | 2027-08-20 | 2027-09-02 | 10 | 3 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-10-U-PC-920 | GC Punchlist @ Units - L10 | yes | Inspection and contractor punch | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Units Partial Inspections & Punchout & Key Delivery at 10th Lvl | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-10 | 5 | 3 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-11-U-PC-900 | Partial MEP Systems Inspections @ Units - L11 | yes | Inspection and contractor punch | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Units Partial Inspections & Punchout & Key Delivery at 11th Lvl | TT_Task | TK_NotStart | 2027-08-17 | 2027-08-25 | 7 | 4 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-11-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L11 | yes | Inspection and contractor punch | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Units Partial Inspections & Punchout & Key Delivery at 11th Lvl | TT_Task | TK_NotStart | 2027-08-26 | 2027-09-09 | 10 | 4 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-11-U-PC-920 | GC Punchlist @ Units - L11 | yes | Inspection and contractor punch | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Units Partial Inspections & Punchout & Key Delivery at 11th Lvl | TT_Task | TK_NotStart | 2027-09-10 | 2027-09-16 | 5 | 4 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-12-U-PC-900 | Partial MEP Systems Inspections @ Units - L12 | yes | Inspection and contractor punch | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Units Partial Inspections & Punchout & Key Delivery at 12th Lvl | TT_Task | TK_NotStart | 2027-08-23 | 2027-08-31 | 7 | 5 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-12-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L12 | yes | Inspection and contractor punch | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Units Partial Inspections & Punchout & Key Delivery at 12th Lvl | TT_Task | TK_NotStart | 2027-09-01 | 2027-09-15 | 10 | 5 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-12-U-PC-920 | GC Punchlist @ Units - L12 | yes | Inspection and contractor punch | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Units Partial Inspections & Punchout & Key Delivery at 12th Lvl | TT_Task | TK_NotStart | 2027-09-16 | 2027-09-22 | 5 | 5 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-14-U-PC-900 | Partial MEP Systems Inspections @ Units - L14 | yes | Inspection and contractor punch | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Units Partial Inspections & Punchout & Key Delivery at 14th Lvl | TT_Task | TK_NotStart | 2027-08-27 | 2027-09-07 | 7 | 6 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-14-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L14 | yes | Inspection and contractor punch | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Units Partial Inspections & Punchout & Key Delivery at 14th Lvl | TT_Task | TK_NotStart | 2027-09-08 | 2027-09-21 | 10 | 6 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-14-U-PC-920 | GC Punchlist @ Units - L14 | yes | Inspection and contractor punch | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Units Partial Inspections & Punchout & Key Delivery at 14th Lvl | TT_Task | TK_NotStart | 2027-09-22 | 2027-09-28 | 5 | 6 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-15-U-PC-900 | Partial MEP Systems Inspections @ Units - L15 | yes | Inspection and contractor punch | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Units Partial Inspections & Punchout & Key Delivery at 15th Lvl | TT_Task | TK_NotStart | 2027-09-02 | 2027-09-13 | 7 | 7 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-15-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L15 | yes | Inspection and contractor punch | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Units Partial Inspections & Punchout & Key Delivery at 15th Lvl | TT_Task | TK_NotStart | 2027-09-14 | 2027-09-27 | 10 | 7 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-15-U-PC-920 | GC Punchlist @ Units - L15 | yes | Inspection and contractor punch | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Units Partial Inspections & Punchout & Key Delivery at 15th Lvl | TT_Task | TK_NotStart | 2027-09-28 | 2027-10-04 | 5 | 7 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-16-U-PC-900 | Partial MEP Systems Inspections @ Units - L16 | yes | Inspection and contractor punch | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Units Partial Inspections & Punchout & Key Delivery at 16th Lvl | TT_Task | TK_NotStart | 2027-09-09 | 2027-09-17 | 7 | 8 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-16-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L16 | yes | Inspection and contractor punch | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Units Partial Inspections & Punchout & Key Delivery at 16th Lvl | TT_Task | TK_NotStart | 2027-09-20 | 2027-10-01 | 10 | 8 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-16-U-PC-920 | GC Punchlist @ Units - L16 | yes | Inspection and contractor punch | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Units Partial Inspections & Punchout & Key Delivery at 16th Lvl | TT_Task | TK_NotStart | 2027-10-04 | 2027-10-08 | 5 | 8 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-17-U-PC-900 | Partial MEP Systems Inspections @ Units - L17 | yes | Inspection and contractor punch | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Units Partial Inspections & Punchout & Key Delivery at 17th Lvl | TT_Task | TK_NotStart | 2027-09-15 | 2027-09-23 | 7 | 9 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-17-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L17 | yes | Inspection and contractor punch | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Units Partial Inspections & Punchout & Key Delivery at 17th Lvl | TT_Task | TK_NotStart | 2027-09-24 | 2027-10-07 | 10 | 9 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-17-U-PC-920 | GC Punchlist @ Units - L17 | yes | Inspection and contractor punch | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Units Partial Inspections & Punchout & Key Delivery at 17th Lvl | TT_Task | TK_NotStart | 2027-10-08 | 2027-10-14 | 5 | 9 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-18-U-PC-900 | Partial MEP Systems Inspections @ Units - L18 | yes | Inspection and contractor punch | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Units Partial Inspections & Punchout & Key Delivery at 18th Lvl | TT_Task | TK_NotStart | 2027-09-21 | 2027-09-29 | 7 | 10 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-18-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L18 | yes | Inspection and contractor punch | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Units Partial Inspections & Punchout & Key Delivery at 18th Lvl | TT_Task | TK_NotStart | 2027-09-30 | 2027-10-13 | 10 | 10 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-18-U-PC-920 | GC Punchlist @ Units - L18 | yes | Inspection and contractor punch | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Units Partial Inspections & Punchout & Key Delivery at 18th Lvl | TT_Task | TK_NotStart | 2027-10-14 | 2027-10-20 | 5 | 10 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-19-U-PC-900 | Partial MEP Systems Inspections @ Units - L19 | yes | Inspection and contractor punch | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Units Partial Inspections & Punchout & Key Delivery at 19th Lvl | TT_Task | TK_NotStart | 2027-09-27 | 2027-10-05 | 7 | 11 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-19-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L19 | yes | Inspection and contractor punch | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Units Partial Inspections & Punchout & Key Delivery at 19th Lvl | TT_Task | TK_NotStart | 2027-10-06 | 2027-10-19 | 10 | 11 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-19-U-PC-920 | GC Punchlist @ Units - L19 | yes | Inspection and contractor punch | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Units Partial Inspections & Punchout & Key Delivery at 19th Lvl | TT_Task | TK_NotStart | 2027-10-20 | 2027-10-26 | 5 | 11 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-20-U-PC-900 | Partial MEP Systems Inspections @ Units - L20 | yes | Inspection and contractor punch | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Units Partial Inspections & Punchout & Key Delivery at 20th Lvl | TT_Task | TK_NotStart | 2027-10-01 | 2027-10-11 | 7 | 12 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-20-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L20 | yes | Inspection and contractor punch | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Units Partial Inspections & Punchout & Key Delivery at 20th Lvl | TT_Task | TK_NotStart | 2027-10-12 | 2027-10-25 | 10 | 12 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-20-U-PC-920 | GC Punchlist @ Units - L20 | yes | Inspection and contractor punch | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Units Partial Inspections & Punchout & Key Delivery at 20th Lvl | TT_Task | TK_NotStart | 2027-10-26 | 2027-11-01 | 5 | 12 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-21-U-PC-900 | Partial MEP Systems Inspections @ Units - L21 | yes | Inspection and contractor punch | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Units Partial Inspections & Punchout & Key Delivery at 21st Lvl | TT_Task | TK_NotStart | 2027-10-07 | 2027-10-15 | 7 | 13 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-21-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L21 | yes | Inspection and contractor punch | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Units Partial Inspections & Punchout & Key Delivery at 21st Lvl | TT_Task | TK_NotStart | 2027-10-18 | 2027-10-29 | 10 | 13 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-21-U-PC-920 | GC Punchlist @ Units - L21 | yes | Inspection and contractor punch | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Units Partial Inspections & Punchout & Key Delivery at 21st Lvl | TT_Task | TK_NotStart | 2027-11-01 | 2027-11-05 | 5 | 13 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-22-U-PC-900 | Partial MEP Systems Inspections @ Units - L22 | yes | Inspection and contractor punch | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 22nd Lvl | TT_Task | TK_NotStart | 2027-10-13 | 2027-10-21 | 7 | 14 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-22-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L22 | yes | Inspection and contractor punch | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 22nd Lvl | TT_Task | TK_NotStart | 2027-10-22 | 2027-11-04 | 10 | 14 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-22-U-PC-920 | GC Punchlist @ Units - L22 | yes | Inspection and contractor punch | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 22nd Lvl | TT_Task | TK_NotStart | 2027-11-05 | 2027-11-11 | 5 | 14 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-23-U-PC-900 | Partial MEP Systems Inspections @ Units - L23 | yes | Inspection and contractor punch | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 23rd Lvl | TT_Task | TK_NotStart | 2027-10-19 | 2027-10-27 | 7 | 15 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-23-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L23 | yes | Inspection and contractor punch | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 23rd Lvl | TT_Task | TK_NotStart | 2027-10-28 | 2027-11-10 | 10 | 15 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-23-U-PC-920 | GC Punchlist @ Units - L23 | yes | Inspection and contractor punch | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 23rd Lvl | TT_Task | TK_NotStart | 2027-11-11 | 2027-11-17 | 5 | 15 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-24-U-PC-900 | Partial MEP Systems Inspections @ Units - L24 | yes | Inspection and contractor punch | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Units Partial Inspections & Punchout & Key Delivery at 24th Lvl | TT_Task | TK_NotStart | 2027-10-25 | 2027-11-02 | 7 | 16 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-24-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L24 | yes | Inspection and contractor punch | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Units Partial Inspections & Punchout & Key Delivery at 24th Lvl | TT_Task | TK_NotStart | 2027-11-03 | 2027-11-16 | 10 | 16 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-24-U-PC-920 | GC Punchlist @ Units - L24 | yes | Inspection and contractor punch | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Units Partial Inspections & Punchout & Key Delivery at 24th Lvl | TT_Task | TK_NotStart | 2027-11-17 | 2027-11-23 | 5 | 16 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-25-U-PC-900 | Partial MEP Systems Inspections @ Units - L25 | yes | Inspection and contractor punch | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Units Partial Inspections & Punchout & Key Delivery at 25th Lvl | TT_Task | TK_NotStart | 2027-10-29 | 2027-11-08 | 7 | 17 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-25-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L25 | yes | Inspection and contractor punch | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Units Partial Inspections & Punchout & Key Delivery at 25th Lvl | TT_Task | TK_NotStart | 2027-11-09 | 2027-11-22 | 10 | 17 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-25-U-PC-920 | GC Punchlist @ Units - L25 | yes | Inspection and contractor punch | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Units Partial Inspections & Punchout & Key Delivery at 25th Lvl | TT_Task | TK_NotStart | 2027-11-23 | 2027-12-01 | 5 | 17 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-26-U-PC-900 | Partial MEP Systems Inspections @ Units - L26 | yes | Inspection and contractor punch | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Units Partial Inspections & Punchout & Key Delivery at 26th Lvl | TT_Task | TK_NotStart | 2027-11-04 | 2027-11-12 | 7 | 18 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-26-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L26 | yes | Inspection and contractor punch | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Units Partial Inspections & Punchout & Key Delivery at 26th Lvl | TT_Task | TK_NotStart | 2027-11-15 | 2027-11-30 | 10 | 18 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-26-U-PC-920 | GC Punchlist @ Units - L26 | yes | Inspection and contractor punch | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Units Partial Inspections & Punchout & Key Delivery at 26th Lvl | TT_Task | TK_NotStart | 2027-12-01 | 2027-12-07 | 5 | 18 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-27-U-PC-900 | Partial MEP Systems Inspections @ Units - L27 | yes | Inspection and contractor punch | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Units Partial Inspections & Punchout & Key Delivery at 27th Lvl | TT_Task | TK_NotStart | 2027-11-10 | 2027-11-18 | 7 | 19 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-27-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L27 | yes | Inspection and contractor punch | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Units Partial Inspections & Punchout & Key Delivery at 27th Lvl | TT_Task | TK_NotStart | 2027-11-19 | 2027-12-06 | 10 | 19 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-27-U-PC-920 | GC Punchlist @ Units - L27 | yes | Inspection and contractor punch | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Units Partial Inspections & Punchout & Key Delivery at 27th Lvl | TT_Task | TK_NotStart | 2027-12-07 | 2027-12-13 | 5 | 19 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-28-U-PC-900 | Partial MEP Systems Inspections @ Units - L28 | yes | Inspection and contractor punch | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Units Partial Inspections & Punchout & Key Delivery at 28th Lvl | TT_Task | TK_NotStart | 2027-11-16 | 2027-11-24 | 7 | 20 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-28-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L28 | yes | Inspection and contractor punch | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Units Partial Inspections & Punchout & Key Delivery at 28th Lvl | TT_Task | TK_NotStart | 2027-11-29 | 2027-12-10 | 10 | 20 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-28-U-PC-920 | GC Punchlist @ Units - L28 | yes | Inspection and contractor punch | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Units Partial Inspections & Punchout & Key Delivery at 28th Lvl | TT_Task | TK_NotStart | 2027-12-13 | 2027-12-17 | 5 | 20 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-29-U-PC-900 | Partial MEP Systems Inspections @ Units - L29 | yes | Inspection and contractor punch | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Units Partial Inspections & Punchout & Key Delivery at 29th Lvl | TT_Task | TK_NotStart | 2027-11-22 | 2027-12-02 | 7 | 21 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-29-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L29 | yes | Inspection and contractor punch | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Units Partial Inspections & Punchout & Key Delivery at 29th Lvl | TT_Task | TK_NotStart | 2027-12-03 | 2027-12-16 | 10 | 21 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-29-U-PC-920 | GC Punchlist @ Units - L29 | yes | Inspection and contractor punch | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Units Partial Inspections & Punchout & Key Delivery at 29th Lvl | TT_Task | TK_NotStart | 2027-12-17 | 2027-12-23 | 5 | 21 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-30-U-PC-900 | Partial MEP Systems Inspections @ Units - L30 | yes | Inspection and contractor punch | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Units Partial Inspections & Punchout & Key Delivery at 30th Lvl | TT_Task | TK_NotStart | 2027-11-30 | 2027-12-08 | 7 | 22 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-30-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L30 | yes | Inspection and contractor punch | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Units Partial Inspections & Punchout & Key Delivery at 30th Lvl | TT_Task | TK_NotStart | 2027-12-09 | 2027-12-22 | 10 | 22 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-30-U-PC-920 | GC Punchlist @ Units - L30 | yes | Inspection and contractor punch | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Units Partial Inspections & Punchout & Key Delivery at 30th Lvl | TT_Task | TK_NotStart | 2027-12-23 | 2027-12-30 | 5 | 22 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-31-U-PC-900 | Partial MEP Systems Inspections @ Units - L31 | yes | Inspection and contractor punch | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Units Partial Inspections & Punchout & Key Delivery at 31st Lvl | TT_Task | TK_NotStart | 2027-12-06 | 2027-12-14 | 7 | 23 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-31-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L31 | yes | Inspection and contractor punch | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Units Partial Inspections & Punchout & Key Delivery at 31st Lvl | TT_Task | TK_NotStart | 2027-12-15 | 2027-12-29 | 10 | 23 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-31-U-PC-920 | GC Punchlist @ Units - L31 | yes | Inspection and contractor punch | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Units Partial Inspections & Punchout & Key Delivery at 31st Lvl | TT_Task | TK_NotStart | 2027-12-30 | 2028-01-06 | 5 | 23 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-32-U-PC-900 | Partial MEP Systems Inspections @ Units - L32 | yes | Inspection and contractor punch | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 32nd Lvl | TT_Task | TK_NotStart | 2027-12-10 | 2027-12-20 | 7 | 24 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-32-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L32 | yes | Inspection and contractor punch | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 32nd Lvl | TT_Task | TK_NotStart | 2027-12-21 | 2028-01-05 | 10 | 24 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-32-U-PC-920 | GC Punchlist @ Units - L32 | yes | Inspection and contractor punch | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 32nd Lvl | TT_Task | TK_NotStart | 2028-01-06 | 2028-01-12 | 5 | 24 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-33-U-PC-900 | Partial MEP Systems Inspections @ Units - L33 | yes | Inspection and contractor punch | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 33rd Lvl | TT_Task | TK_NotStart | 2027-12-16 | 2027-12-27 | 7 | 25 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-33-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L33 | yes | Inspection and contractor punch | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 33rd Lvl | TT_Task | TK_NotStart | 2027-12-28 | 2028-01-11 | 10 | 25 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-33-U-PC-920 | GC Punchlist @ Units - L33 | yes | Inspection and contractor punch | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 33rd Lvl | TT_Task | TK_NotStart | 2028-01-12 | 2028-01-18 | 5 | 25 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-34-U-PC-900 | Partial MEP Systems Inspections @ Units - L34 | yes | Inspection and contractor punch | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Units Partial Inspections & Punchout & Key Delivery at 34th Lvl | TT_Task | TK_NotStart | 2027-12-22 | 2028-01-03 | 7 | 26 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-34-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L34 | yes | Inspection and contractor punch | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Units Partial Inspections & Punchout & Key Delivery at 34th Lvl | TT_Task | TK_NotStart | 2028-01-04 | 2028-01-17 | 10 | 26 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-34-U-PC-920 | GC Punchlist @ Units - L34 | yes | Inspection and contractor punch | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Units Partial Inspections & Punchout & Key Delivery at 34th Lvl | TT_Task | TK_NotStart | 2028-01-18 | 2028-01-24 | 5 | 26 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-35-U-PC-900 | Partial MEP Systems Inspections @ Units - L35 | yes | Inspection and contractor punch | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Units Partial Inspections & Punchout & Key Delivery at 35th Lvl | TT_Task | TK_NotStart | 2027-12-29 | 2028-01-07 | 7 | 27 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-35-U-PC-910 | Subcontractor Punch List & Punch Paint @ Units - L35 | yes | Inspection and contractor punch | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Units Partial Inspections & Punchout & Key Delivery at 35th Lvl | TT_Task | TK_NotStart | 2028-01-10 | 2028-01-21 | 10 | 27 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-35-U-PC-920 | GC Punchlist @ Units - L35 | yes | Inspection and contractor punch | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Units Partial Inspections & Punchout & Key Delivery at 35th Lvl | TT_Task | TK_NotStart | 2028-01-24 | 2028-01-28 | 5 | 27 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-36-IN-PC-900 | Partial MEP Systems Inspections @ Indoor - L36 | yes | Inspection and contractor punch | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Units Partial Inspections & Punchout & Key Delivery at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-25 | 2027-07-01 | 5 | 105 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery at Indoor
Phased TCO | C-36-IN-PC-910 | Subcontractor Punch List & Punch Paint @ Indoor - L36 | yes | Inspection and contractor punch | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Units Partial Inspections & Punchout & Key Delivery at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-07-12 | 2027-07-30 | 15 | 100 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery at Indoor
Phased TCO | C-36-IN-PC-920 | GC Punchlist @ Indoor - L36 | yes | Inspection and contractor punch | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Units Partial Inspections & Punchout & Key Delivery at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-06 | 5 | 100 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery at Indoor
Phased TCO | C-01-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L1 | yes | Final clean and Owner punch | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Elev Lobby & Corridors at 1st Lvl > Interior Finishes at Elev Lobby & Corridors at 1st Lvl | TT_Task | TK_NotStart | 2027-07-27 | 2027-07-27 | 1 | 115 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridors
Phased TCO | C-01-U-PC-930 | Final Cleanup @ L1 | yes | Final clean and Owner punch | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Units Partial Inspections & Punchout & Key Delivery at 1st Lvl | TT_Task | TK_NotStart | 2027-09-08 | 2027-09-14 | 5 | 79 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-01-U-PC-940 | Touch-up Paint @ L1 | yes | Final clean and Owner punch | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Units Partial Inspections & Punchout & Key Delivery at 1st Lvl | TT_Task | TK_NotStart | 2027-09-15 | 2027-09-16 | 2 | 79 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-01-U-PC-950 | Owner/Arch Punch List @ L1 | yes | Final clean and Owner punch | 1 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Units Partial Inspections & Punchout & Key Delivery at 1st Lvl | TT_Task | TK_NotStart | 2027-09-22 | 2027-09-28 | 5 | 76 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-02-U-PC-930 | Final Cleanup @ L2 | yes | Final clean and Owner punch | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 2nd Lvl | TT_Task | TK_NotStart | 2027-07-27 | 2027-07-30 | 4 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-02-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L2 | yes | Final clean and Owner punch | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 2nd Lvl > Interior Finishes at Elev Lobby & Corridor at 2nd Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-02 | 1 | 0 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-02-U-PC-950 | Owner/Arch Punch List @ L2 | yes | Final clean and Owner punch | 2 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Units & Common Areas at 2nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 2nd Lvl | TT_Task | TK_NotStart | 2027-08-03 | 2027-08-06 | 4 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-03-U-PC-930 | Final Cleanup @ L3 | yes | Final clean and Owner punch | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 3rd Lvl | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-05 | 4 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-03-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L3 | yes | Final clean and Owner punch | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 3rd Lvl > Interior Finishes at Elev Lobby & Corridor at 3rd Lvl | TT_Task | TK_NotStart | 2027-08-06 | 2027-08-06 | 1 | 0 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-03-U-PC-950 | Owner/Arch Punch List @ L3 | yes | Final clean and Owner punch | 3 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Units at 3rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 3rd Lvl | TT_Task | TK_NotStart | 2027-08-09 | 2027-08-12 | 4 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-04-U-PC-930 | Final Cleanup @ L4 | yes | Final clean and Owner punch | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > Units Partial Inspections & Punchout & Key Delivery at 4th Lvl | TT_Task | TK_NotStart | 2027-08-06 | 2027-08-11 | 4 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-04-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L4 | yes | Final clean and Owner punch | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 4th Lvl > Interior Finishes at Elev Lobby & Corridor at 4th Lvl | TT_Task | TK_NotStart | 2027-08-12 | 2027-08-12 | 1 | 0 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-04-U-PC-950 | Owner/Arch Punch List @ L4 | yes | Final clean and Owner punch | 4 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Units at 4th Lvl > Units Partial Inspections & Punchout & Key Delivery at 4th Lvl | TT_Task | TK_NotStart | 2027-08-13 | 2027-08-18 | 4 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-05-U-PC-930 | Final Cleanup @ L5 | yes | Final clean and Owner punch | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > Units Partial Inspections & Punchout & Key Delivery at 5th Lvl | TT_Task | TK_NotStart | 2027-08-12 | 2027-08-17 | 4 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-05-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L5 | yes | Final clean and Owner punch | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 5th Lvl > Interior Finishes at Elev Lobby & Corridor at 5th Lvl | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-18 | 1 | 0 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-05-U-PC-950 | Owner/Arch Punch List @ L5 | yes | Final clean and Owner punch | 5 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Units at 5th Lvl > Units Partial Inspections & Punchout & Key Delivery at 5th Lvl | TT_Task | TK_NotStart | 2027-08-19 | 2027-08-24 | 4 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-06-U-PC-930 | Final Cleanup @ L6 | yes | Final clean and Owner punch | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > Units Partial Inspections & Punchout & Key Delivery at 6th Lvl | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-23 | 4 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-06-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L6 | yes | Final clean and Owner punch | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 6th Lvl > Interior Finishes at Elev Lobby & Corridor at 6th Lvl | TT_Task | TK_NotStart | 2027-08-24 | 2027-08-24 | 1 | 0 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-06-U-PC-950 | Owner/Arch Punch List @ L6 | yes | Final clean and Owner punch | 6 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Units at 6th Lvl > Units Partial Inspections & Punchout & Key Delivery at 6th Lvl | TT_Task | TK_NotStart | 2027-08-25 | 2027-08-30 | 4 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-07-U-PC-930 | Final Cleanup @ Units - L7 | yes | Final clean and Owner punch | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Units Partial Inspections & Punchout & Key Delivery at 7th Lvl | TT_Task | TK_NotStart | 2027-08-25 | 2027-08-27 | 3 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-07-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L7 | yes | Final clean and Owner punch | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 7th Lvl > Interior Finishes at Elev Lobby & Corridor at 7th Lvl | TT_Task | TK_NotStart | 2027-08-30 | 2027-08-30 | 1 | 0 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-07-U-PC-950 | Owner/Arch Punch List @ L7 | yes | Final clean and Owner punch | 7 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 7th Lvl > Interior MEPs & Finishes at Units 7th Lvl > Units Partial Inspections & Punchout & Key Delivery at 7th Lvl | TT_Task | TK_NotStart | 2027-08-31 | 2027-09-07 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-08-U-PC-930 | Final Cleanup @ Units - L8 | yes | Final clean and Owner punch | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Units Partial Inspections & Punchout & Key Delivery at 8th Lvl | TT_Task | TK_NotStart | 2027-08-31 | 2027-09-02 | 3 | 1 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-08-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L8 | yes | Final clean and Owner punch | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 8th Lvl > Interior Finishes at Elev Lobby & Corridor at 8th Lvl | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-03 | 1 | 1 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-08-U-PC-950 | Owner/Arch Punch List @ L8 | yes | Final clean and Owner punch | 8 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 8th Lvl > Interior MEPs & Finishes at Units 8th Lvl > Units Partial Inspections & Punchout & Key Delivery at 8th Lvl | TT_Task | TK_NotStart | 2027-09-08 | 2027-09-14 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-09-U-PC-930 | Final Cleanup @ Units - L9 | yes | Final clean and Owner punch | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Units Partial Inspections & Punchout & Key Delivery at 9th Lvl | TT_Task | TK_NotStart | 2027-09-07 | 2027-09-09 | 3 | 2 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-09-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L9 | yes | Final clean and Owner punch | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 9th Lvl > Interior Finishes at Elev Lobby & Corridor at 9th Lvl | TT_Task | TK_NotStart | 2027-09-10 | 2027-09-10 | 1 | 2 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-09-U-PC-950 | Owner/Arch Punch List @ L9 | yes | Final clean and Owner punch | 9 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 9th Lvl > Interior MEPs & Finishes at Units 9th Lvl > Units Partial Inspections & Punchout & Key Delivery at 9th Lvl | TT_Task | TK_NotStart | 2027-09-15 | 2027-09-21 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-10-U-PC-930 | Final Cleanup @ Units - L10 | yes | Final clean and Owner punch | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Units Partial Inspections & Punchout & Key Delivery at 10th Lvl | TT_Task | TK_NotStart | 2027-09-13 | 2027-09-15 | 3 | 3 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-10-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L10 | yes | Final clean and Owner punch | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 10th Lvl > Interior Finishes at Elev Lobby & Corridor at 10th Lvl | TT_Task | TK_NotStart | 2027-09-16 | 2027-09-16 | 1 | 3 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-10-U-PC-950 | Owner/Arch Punch List @ L10 | yes | Final clean and Owner punch | 10 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 10th Lvl > Interior MEPs & Finishes at Units 10th Lvl > Units Partial Inspections & Punchout & Key Delivery at 10th Lvl | TT_Task | TK_NotStart | 2027-09-22 | 2027-09-28 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-11-U-PC-930 | Final Cleanup @ Units - L11 | yes | Final clean and Owner punch | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Units Partial Inspections & Punchout & Key Delivery at 11th Lvl | TT_Task | TK_NotStart | 2027-09-17 | 2027-09-21 | 3 | 4 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-11-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L11 | yes | Final clean and Owner punch | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 11th Lvl > Interior Finishes at Elev Lobby & Corridor at 11th Lvl | TT_Task | TK_NotStart | 2027-09-22 | 2027-09-22 | 1 | 4 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-11-U-PC-950 | Owner/Arch Punch List @ L11 | yes | Final clean and Owner punch | 11 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 11th Lvl > Interior MEPs & Finishes at Units 11th Lvl > Units Partial Inspections & Punchout & Key Delivery at 11th Lvl | TT_Task | TK_NotStart | 2027-09-29 | 2027-10-05 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-12-U-PC-930 | Final Cleanup @ Units - L12 | yes | Final clean and Owner punch | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Units Partial Inspections & Punchout & Key Delivery at 12th Lvl | TT_Task | TK_NotStart | 2027-09-23 | 2027-09-27 | 3 | 5 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-12-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L12 | yes | Final clean and Owner punch | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 12th Lvl > Interior Finishes at Elev Lobby & Corridor at 12th Lvl | TT_Task | TK_NotStart | 2027-09-28 | 2027-09-28 | 1 | 5 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-12-U-PC-950 | Owner/Arch Punch List @ L12 | yes | Final clean and Owner punch | 12 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 12th Lvl > Interior MEPs & Finishes at Units 12th Lvl > Units Partial Inspections & Punchout & Key Delivery at 12th Lvl | TT_Task | TK_NotStart | 2027-10-06 | 2027-10-12 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-14-U-PC-930 | Final Cleanup @ Units - L14 | yes | Final clean and Owner punch | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Units Partial Inspections & Punchout & Key Delivery at 14th Lvl | TT_Task | TK_NotStart | 2027-09-29 | 2027-10-01 | 3 | 6 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-14-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L14 | yes | Final clean and Owner punch | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 14th Lvl > Interior Finishes at Elev Lobby & Corridor at 14th Lvl | TT_Task | TK_NotStart | 2027-10-04 | 2027-10-04 | 1 | 6 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-14-U-PC-950 | Owner/Arch Punch List @ L14 | yes | Final clean and Owner punch | 14 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 14th Lvl > Interior MEPs & Finishes at Units 14th Lvl > Units Partial Inspections & Punchout & Key Delivery at 14th Lvl | TT_Task | TK_NotStart | 2027-10-13 | 2027-10-19 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-15-U-PC-930 | Final Cleanup @ Units - L15 | yes | Final clean and Owner punch | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Units Partial Inspections & Punchout & Key Delivery at 15th Lvl | TT_Task | TK_NotStart | 2027-10-05 | 2027-10-07 | 3 | 7 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-15-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L15 | yes | Final clean and Owner punch | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 15th Lvl > Interior Finishes at Elev Lobby & Corridor at 15th Lvl | TT_Task | TK_NotStart | 2027-10-08 | 2027-10-08 | 1 | 7 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-15-U-PC-950 | Owner/Arch Punch List @ L15 | yes | Final clean and Owner punch | 15 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 15th Lvl > Interior MEPs & Finishes at Units 15th Lvl > Units Partial Inspections & Punchout & Key Delivery at 15th Lvl | TT_Task | TK_NotStart | 2027-10-20 | 2027-10-26 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-16-U-PC-930 | Final Cleanup @ Units - L16 | yes | Final clean and Owner punch | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Units Partial Inspections & Punchout & Key Delivery at 16th Lvl | TT_Task | TK_NotStart | 2027-10-11 | 2027-10-13 | 3 | 8 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-16-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L16 | yes | Final clean and Owner punch | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 16th Lvl > Interior Finishes at Elev Lobby & Corridor at 16th Lvl | TT_Task | TK_NotStart | 2027-10-14 | 2027-10-14 | 1 | 8 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-16-U-PC-950 | Owner/Arch Punch List @ L16 | yes | Final clean and Owner punch | 16 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 16th Lvl > Interior MEPs & Finishes at Units 16th Lvl > Units Partial Inspections & Punchout & Key Delivery at 16th Lvl | TT_Task | TK_NotStart | 2027-10-27 | 2027-11-02 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-17-U-PC-930 | Final Cleanup @ Units - L17 | yes | Final clean and Owner punch | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Units Partial Inspections & Punchout & Key Delivery at 17th Lvl | TT_Task | TK_NotStart | 2027-10-15 | 2027-10-19 | 3 | 9 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-17-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L17 | yes | Final clean and Owner punch | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 17th Lvl > Interior Finishes at Elev Lobby & Corridor at 17th Lvl | TT_Task | TK_NotStart | 2027-10-20 | 2027-10-20 | 1 | 9 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-17-U-PC-950 | Owner/Arch Punch List @ L17 | yes | Final clean and Owner punch | 17 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 17th Lvl > Interior MEPs & Finishes at Units 17th Lvl > Units Partial Inspections & Punchout & Key Delivery at 17th Lvl | TT_Task | TK_NotStart | 2027-11-03 | 2027-11-09 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-18-U-PC-930 | Final Cleanup @ Units - L18 | yes | Final clean and Owner punch | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Units Partial Inspections & Punchout & Key Delivery at 18th Lvl | TT_Task | TK_NotStart | 2027-10-21 | 2027-10-25 | 3 | 10 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-18-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L18 | yes | Final clean and Owner punch | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 18th Lvl > Interior Finishes at Elev Lobby & Corridor at 18th Lvl | TT_Task | TK_NotStart | 2027-10-26 | 2027-10-26 | 1 | 10 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-18-U-PC-950 | Owner/Arch Punch List @ L18 | yes | Final clean and Owner punch | 18 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 18th Lvl > Interior MEPs & Finishes at Units 18th Lvl > Units Partial Inspections & Punchout & Key Delivery at 18th Lvl | TT_Task | TK_NotStart | 2027-11-10 | 2027-11-16 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-19-U-PC-930 | Final Cleanup @ Units - L19 | yes | Final clean and Owner punch | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Units Partial Inspections & Punchout & Key Delivery at 19th Lvl | TT_Task | TK_NotStart | 2027-10-27 | 2027-10-29 | 3 | 11 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-19-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L19 | yes | Final clean and Owner punch | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 19th Lvl > Interior Finishes at Elev Lobby & Corridor at 19th Lvl | TT_Task | TK_NotStart | 2027-11-01 | 2027-11-01 | 1 | 11 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-19-U-PC-950 | Owner/Arch Punch List @ L19 | yes | Final clean and Owner punch | 19 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 19th Lvl > Interior MEPs & Finishes at Units 19th Lvl > Units Partial Inspections & Punchout & Key Delivery at 19th Lvl | TT_Task | TK_NotStart | 2027-11-17 | 2027-11-23 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-20-U-PC-930 | Final Cleanup @ Units - L20 | yes | Final clean and Owner punch | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Units Partial Inspections & Punchout & Key Delivery at 20th Lvl | TT_Task | TK_NotStart | 2027-11-02 | 2027-11-04 | 3 | 12 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-20-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L20 | yes | Final clean and Owner punch | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 20th Lvl > Interior Finishes at Elev Lobby & Corridor at 20th Lvl | TT_Task | TK_NotStart | 2027-11-05 | 2027-11-05 | 1 | 12 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-20-U-PC-950 | Owner/Arch Punch List @ L20 | yes | Final clean and Owner punch | 20 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 20th Lvl > Interior MEPs & Finishes at Units 20th Lvl > Units Partial Inspections & Punchout & Key Delivery at 20th Lvl | TT_Task | TK_NotStart | 2027-11-24 | 2027-12-02 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-21-U-PC-930 | Final Cleanup @ Units - L21 | yes | Final clean and Owner punch | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Units Partial Inspections & Punchout & Key Delivery at 21st Lvl | TT_Task | TK_NotStart | 2027-11-08 | 2027-11-10 | 3 | 13 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-21-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L21 | yes | Final clean and Owner punch | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 21st Lvl > Interior Finishes at Elev Lobby & Corridor at 21st Lvl | TT_Task | TK_NotStart | 2027-11-11 | 2027-11-11 | 1 | 13 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-21-U-PC-950 | Owner/Arch Punch List @ L21 | yes | Final clean and Owner punch | 21 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 21st Lvl > Interior MEPs & Finishes at Units 21st Lvl > Units Partial Inspections & Punchout & Key Delivery at 21st Lvl | TT_Task | TK_NotStart | 2027-12-03 | 2027-12-09 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-22-U-PC-930 | Final Cleanup @ Units - L22 | yes | Final clean and Owner punch | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 22nd Lvl | TT_Task | TK_NotStart | 2027-11-12 | 2027-11-16 | 3 | 14 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-22-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L22 | yes | Final clean and Owner punch | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 22nd Lvl > Interior Finishes at Elev Lobby & Corridor at 22nd Lvl | TT_Task | TK_NotStart | 2027-11-17 | 2027-11-17 | 1 | 14 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-22-U-PC-950 | Owner/Arch Punch List @ L22 | yes | Final clean and Owner punch | 22 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 22nd Lvl > Interior MEPs & Finishes at Units 22nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 22nd Lvl | TT_Task | TK_NotStart | 2027-12-10 | 2027-12-16 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-23-U-PC-930 | Final Cleanup @ Units - L23 | yes | Final clean and Owner punch | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 23rd Lvl | TT_Task | TK_NotStart | 2027-11-18 | 2027-11-22 | 3 | 15 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-23-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L23 | yes | Final clean and Owner punch | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 23rd Lvl > Interior Finishes at Elev Lobby & Corridor at 23rd Lvl | TT_Task | TK_NotStart | 2027-11-23 | 2027-11-23 | 1 | 15 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-23-U-PC-950 | Owner/Arch Punch List @ L23 | yes | Final clean and Owner punch | 23 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 23rd Lvl > Interior MEPs & Finishes at Units 23rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 23rd Lvl | TT_Task | TK_NotStart | 2027-12-17 | 2027-12-23 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-24-U-PC-930 | Final Cleanup @ Units - L24 | yes | Final clean and Owner punch | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Units Partial Inspections & Punchout & Key Delivery at 24th Lvl | TT_Task | TK_NotStart | 2027-11-24 | 2027-11-30 | 3 | 16 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-24-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L24 | yes | Final clean and Owner punch | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 24th Lvl > Interior Finishes at Elev Lobby & Corridor at 24th Lvl | TT_Task | TK_NotStart | 2027-12-01 | 2027-12-01 | 1 | 16 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-24-U-PC-950 | Owner/Arch Punch List @ L24 | yes | Final clean and Owner punch | 24 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 24th Lvl > Interior MEPs & Finishes at Units 24th Lvl > Units Partial Inspections & Punchout & Key Delivery at 24th Lvl | TT_Task | TK_NotStart | 2027-12-27 | 2028-01-03 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-25-U-PC-930 | Final Cleanup @ Units - L25 | yes | Final clean and Owner punch | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Units Partial Inspections & Punchout & Key Delivery at 25th Lvl | TT_Task | TK_NotStart | 2027-12-02 | 2027-12-06 | 3 | 17 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-25-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L25 | yes | Final clean and Owner punch | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 25th Lvl > Interior Finishes at Elev Lobby & Corridor at 25th Lvl | TT_Task | TK_NotStart | 2027-12-07 | 2027-12-07 | 1 | 17 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-25-U-PC-950 | Owner/Arch Punch List @ L25 | yes | Final clean and Owner punch | 25 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 25th Lvl > Interior MEPs & Finishes at Units 25th Lvl > Units Partial Inspections & Punchout & Key Delivery at 25th Lvl | TT_Task | TK_NotStart | 2028-01-04 | 2028-01-10 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-26-U-PC-930 | Final Cleanup @ Units - L26 | yes | Final clean and Owner punch | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Units Partial Inspections & Punchout & Key Delivery at 26th Lvl | TT_Task | TK_NotStart | 2027-12-08 | 2027-12-10 | 3 | 18 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-26-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L26 | yes | Final clean and Owner punch | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 26th Lvl > Interior Finishes at Elev Lobby & Corridor at 26th Lvl | TT_Task | TK_NotStart | 2027-12-13 | 2027-12-13 | 1 | 18 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-26-U-PC-950 | Owner/Arch Punch List @ L26 | yes | Final clean and Owner punch | 26 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 26th Lvl > Interior MEPs & Finishes at Units 26th Lvl > Units Partial Inspections & Punchout & Key Delivery at 26th Lvl | TT_Task | TK_NotStart | 2028-01-11 | 2028-01-17 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-27-U-PC-930 | Final Cleanup @ Units - L27 | yes | Final clean and Owner punch | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Units Partial Inspections & Punchout & Key Delivery at 27th Lvl | TT_Task | TK_NotStart | 2027-12-14 | 2027-12-16 | 3 | 19 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-27-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L27 | yes | Final clean and Owner punch | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 27th Lvl > Interior Finishes at Elev Lobby & Corridor at 27th Lvl | TT_Task | TK_NotStart | 2027-12-17 | 2027-12-17 | 1 | 19 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-27-U-PC-950 | Owner/Arch Punch List @ L27 | yes | Final clean and Owner punch | 27 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 27th Lvl > Interior MEPs & Finishes at Units 27th Lvl > Units Partial Inspections & Punchout & Key Delivery at 27th Lvl | TT_Task | TK_NotStart | 2028-01-18 | 2028-01-24 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-28-U-PC-930 | Final Cleanup @ Units - L28 | yes | Final clean and Owner punch | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Units Partial Inspections & Punchout & Key Delivery at 28th Lvl | TT_Task | TK_NotStart | 2027-12-20 | 2027-12-22 | 3 | 20 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-28-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L28 | yes | Final clean and Owner punch | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 28th Lvl > Interior Finishes at Elev Lobby & Corridor at 28th Lvl | TT_Task | TK_NotStart | 2027-12-23 | 2027-12-23 | 1 | 20 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-28-U-PC-950 | Owner/Arch Punch List @ L28 | yes | Final clean and Owner punch | 28 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 28th Lvl > Interior MEPs & Finishes at Units 28th Lvl > Units Partial Inspections & Punchout & Key Delivery at 28th Lvl | TT_Task | TK_NotStart | 2028-01-25 | 2028-01-31 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-29-U-PC-930 | Final Cleanup @ Units - L29 | yes | Final clean and Owner punch | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Units Partial Inspections & Punchout & Key Delivery at 29th Lvl | TT_Task | TK_NotStart | 2027-12-27 | 2027-12-29 | 3 | 21 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-29-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L29 | yes | Final clean and Owner punch | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 29th Lvl > Interior Finishes at Elev Lobby & Corridor at 29th Lvl | TT_Task | TK_NotStart | 2027-12-30 | 2027-12-30 | 1 | 21 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-29-U-PC-950 | Owner/Arch Punch List @ L29 | yes | Final clean and Owner punch | 29 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 29th Lvl > Interior MEPs & Finishes at Units 29th Lvl > Units Partial Inspections & Punchout & Key Delivery at 29th Lvl | TT_Task | TK_NotStart | 2028-02-01 | 2028-02-07 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-30-U-PC-930 | Final Cleanup @ Units - L30 | yes | Final clean and Owner punch | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Units Partial Inspections & Punchout & Key Delivery at 30th Lvl | TT_Task | TK_NotStart | 2028-01-03 | 2028-01-05 | 3 | 22 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-30-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L30 | yes | Final clean and Owner punch | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 30th Lvl > Interior Finishes at Elev Lobby & Corridor at 30th Lvl | TT_Task | TK_NotStart | 2028-01-06 | 2028-01-06 | 1 | 22 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-30-U-PC-950 | Owner/Arch Punch List @ L30 | yes | Final clean and Owner punch | 30 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 30th Lvl > Interior MEPs & Finishes at Units 30th Lvl > Units Partial Inspections & Punchout & Key Delivery at 30th Lvl | TT_Task | TK_NotStart | 2028-02-08 | 2028-02-14 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-31-U-PC-930 | Final Cleanup @ Units - L31 | yes | Final clean and Owner punch | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Units Partial Inspections & Punchout & Key Delivery at 31st Lvl | TT_Task | TK_NotStart | 2028-01-07 | 2028-01-11 | 3 | 23 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-31-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L31 | yes | Final clean and Owner punch | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 31st Lvl > Interior Finishes at Elev Lobby & Corridor at 31st Lvl | TT_Task | TK_NotStart | 2028-01-12 | 2028-01-12 | 1 | 23 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-31-U-PC-950 | Owner/Arch Punch List @ L31 | yes | Final clean and Owner punch | 31 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 31st Lvl > Interior MEPs & Finishes at Units 31st Lvl > Units Partial Inspections & Punchout & Key Delivery at 31st Lvl | TT_Task | TK_NotStart | 2028-02-15 | 2028-02-21 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-32-U-PC-930 | Final Cleanup @ Units - L32 | yes | Final clean and Owner punch | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 32nd Lvl | TT_Task | TK_NotStart | 2028-01-13 | 2028-01-17 | 3 | 24 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-32-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L32 | yes | Final clean and Owner punch | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 32nd Lvl > Interior Finishes at Elev Lobby & Corridor at 32nd Lvl | TT_Task | TK_NotStart | 2028-01-18 | 2028-01-18 | 1 | 24 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-32-U-PC-950 | Owner/Arch Punch List @ L32 | yes | Final clean and Owner punch | 32 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 32nd Lvl > Interior MEPs & Finishes at Units 32nd Lvl > Units Partial Inspections & Punchout & Key Delivery at 32nd Lvl | TT_Task | TK_NotStart | 2028-02-22 | 2028-02-28 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-33-U-PC-930 | Final Cleanup @ Units - L33 | yes | Final clean and Owner punch | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 33rd Lvl | TT_Task | TK_NotStart | 2028-01-19 | 2028-01-21 | 3 | 25 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-33-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L33 | yes | Final clean and Owner punch | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 33rd Lvl > Interior Finishes at Elev Lobby & Corridor at 33rd Lvl | TT_Task | TK_NotStart | 2028-01-24 | 2028-01-24 | 1 | 25 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-33-U-PC-950 | Owner/Arch Punch List @ L33 | yes | Final clean and Owner punch | 33 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 33rd Lvl > Interior MEPs & Finishes at Units 33rd Lvl > Units Partial Inspections & Punchout & Key Delivery at 33rd Lvl | TT_Task | TK_NotStart | 2028-02-29 | 2028-03-06 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-34-U-PC-930 | Final Cleanup @ Units - L34 | yes | Final clean and Owner punch | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Units Partial Inspections & Punchout & Key Delivery at 34th Lvl | TT_Task | TK_NotStart | 2028-01-25 | 2028-01-27 | 3 | 26 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-34-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L34 | yes | Final clean and Owner punch | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 34th Lvl > Interior Finishes at Elev Lobby & Corridor at 34th Lvl | TT_Task | TK_NotStart | 2028-01-28 | 2028-01-28 | 1 | 26 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-34-U-PC-950 | Owner/Arch Punch List @ L34 | yes | Final clean and Owner punch | 34 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 34th Lvl > Interior MEPs & Finishes at Units 34th Lvl > Units Partial Inspections & Punchout & Key Delivery at 34th Lvl | TT_Task | TK_NotStart | 2028-03-07 | 2028-03-13 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-35-U-PC-930 | Final Cleanup @ Units - L35 | yes | Final clean and Owner punch | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Units Partial Inspections & Punchout & Key Delivery at 35th Lvl | TT_Task | TK_NotStart | 2028-01-31 | 2028-02-02 | 3 | 27 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-35-C-FN-190 | Final Cleanup @ Elev Lobby & Corr - L35 | yes | Final clean and Owner punch | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes Elev Lobby & Corridor at 35th Lvl > Interior Finishes at Elev Lobby & Corridor at 35th Lvl | TT_Task | TK_NotStart | 2028-02-03 | 2028-02-03 | 1 | 27 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby & Corridor
Phased TCO | C-35-U-PC-950 | Owner/Arch Punch List @ L35 | yes | Final clean and Owner punch | 35 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 35th Lvl > Interior MEPs & Finishes at Units 35th Lvl > Units Partial Inspections & Punchout & Key Delivery at 35th Lvl | TT_Task | TK_NotStart | 2028-03-14 | 2028-03-20 | 5 | 0 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery
Phased TCO | C-36-IN-PC-930 | Final Cleanup @ Indoor - L36 | yes | Final clean and Owner punch | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Units Partial Inspections & Punchout & Key Delivery at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-09 | 2027-08-13 | 5 | 100 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery at Indoor
Phased TCO | C-36-IN-PC-940 | Touchup Paint @ Indoor - L36 | yes | Final clean and Owner punch | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Units Partial Inspections & Punchout & Key Delivery at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-16 | 2027-08-17 | 2 | 100 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery at Indoor
Phased TCO | C-36-IN-PC-950 | Owner/Arch Punch List @ Indoor - L36 | yes | Final clean and Owner punch | 36 |  | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes at Indoor 36th Pool Lvl > Units Partial Inspections & Punchout & Key Delivery at Indoor 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-24 | 5 | 100 | Interior MEPs & Finishes | Units Partial Inspections & Punchout & Key Delivery at Indoor
Phased TCO | C-00-PL-100 | Install & Report Test Piles @ Site | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Piling Work | TT_Task | TK_NotStart | 2025-11-11 | 2025-12-10 | 20 | 0 | Building Structure | Piling Work
Phased TCO | C-00-ST-100 | Excavate Entire Lot 3' ft @ Site | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2025-11-11 | 2025-12-03 | 15 | 22 | Building Structure | Foundation Work
Phased TCO | C-00-WL-100 | Install Perm Wells @ Site | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2025-12-04 | 2025-12-17 | 10 | 22 | Building Structure | Foundation Work
Phased TCO | C-00-PL-200 | Install Production Piles @ Bldg | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Piling Work | TT_Task | TK_NotStart | 2025-12-11 | 2026-01-16 | 25 | 0 | Building Structure | Piling Work
Phased TCO | C-00-PL-300 | Cut-off Piles @ Site | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Piling Work | TT_Task | TK_NotStart | 2026-01-19 | 2026-01-23 | 5 | 0 | Building Structure | Piling Work
Phased TCO | C-00-ST-200 | Form PIle Caps @ Foundations | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2026-01-21 | 2026-01-27 | 5 | 0 | Building Structure | Foundation Work
Phased TCO | C-00-ST-210 | Rebar Pile Caps @ Foundations | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2026-01-26 | 2026-02-06 | 10 | 0 | Building Structure | Foundation Work
Phased TCO | C-00-ST-220 | Pour Pile Caps @ Foundations | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2026-02-09 | 2026-02-10 | 2 | 0 | Building Structure | Foundation Work
Phased TCO | C-00-ST-300 | Rebar Shear Walls @ Foundations | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2026-02-11 | 2026-02-24 | 10 | 0 | Building Structure | Foundation Work
Phased TCO | C-00-ST-310 | Form Shear Walls @ Foundations | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2026-02-25 | 2026-02-27 | 3 | 0 | Building Structure | Foundation Work
Phased TCO | C-00-ST-320 | Pour Shear Walls @ Foundations | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2026-03-02 | 2026-03-03 | 2 | 0 | Building Structure | Foundation Work
Phased TCO | C-00-ST-400 | Form Grade Beams @ Foundations | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2026-03-04 | 2026-03-05 | 2 | 0 | Building Structure | Foundation Work
Phased TCO | C-00-ST-410 | Rebar Grade Beams @ Foundations | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2026-03-06 | 2026-03-12 | 5 | 0 | Building Structure | Foundation Work
Phased TCO | C-00-ST-420 | Pour Grade Beams @ Foundations | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2026-03-13 | 2026-03-13 | 1 | 0 | Building Structure | Foundation Work
Phased TCO | C-00-ST-500 | F/R/P 1st Lift Columns @ Foundations - L1 | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2026-03-16 | 2026-03-20 | 5 | 0 | Building Structure | Foundation Work
Phased TCO | C-00-ST-600 | Backfill & Compact @ Foundations | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Subsurface Structure > Foundation Work | TT_Task | TK_NotStart | 2026-03-20 | 2026-03-23 | 2 | 0 | Building Structure | Foundation Work
Phased TCO | C-00-MP-310 | FPL Ductbank Design Fee Payment | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Superstructure > U/G MEPs & SOG at 1st Lvl > FPL Vault SOG - Early Work | TT_Task | TK_NotStart | 2026-04-09 | 2026-04-09 | 1 | 0 | Building Structure | FPL Vault SOG - Early Work
Phased TCO | C-00-MP-320 | FPL Ductbank Design | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Superstructure > U/G MEPs & SOG at 1st Lvl > FPL Vault SOG - Early Work | TT_Task | TK_NotStart | 2026-04-10 | 2026-08-10 | 85 | 0 | Building Structure | FPL Vault SOG - Early Work
Phased TCO | C-00-MP-300 | Install U/G Electrical @ FPL Vault Area | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Superstructure > U/G MEPs & SOG at 1st Lvl > FPL Vault SOG - Early Work | TT_Task | TK_NotStart | 2026-08-11 | 2026-08-31 | 15 | 43 | Building Structure | FPL Vault SOG - Early Work
Phased TCO | C-00-MP-330 | FPL Ductbank Bidding Work Process | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Superstructure > U/G MEPs & SOG at 1st Lvl > FPL Vault SOG - Early Work | TT_Task | TK_NotStart | 2026-08-11 | 2026-10-20 | 50 | 0 | Building Structure | FPL Vault SOG - Early Work
Phased TCO | C-00-MP-340 | FPL Ductbank Work | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Superstructure > U/G MEPs & SOG at 1st Lvl > FPL Vault SOG - Early Work | TT_Task | TK_NotStart | 2026-10-21 | 2027-02-22 | 85 | 0 | Building Structure | FPL Vault SOG - Early Work
Phased TCO | C-00-MP-100 | Install U/G Plumbing @ Subsurface | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Superstructure > U/G MEPs & SOG at 1st Lvl | TT_Task | TK_NotStart | 2027-02-01 | 2027-02-19 | 15 | 0 | Building Structure | U/G MEPs & SOG
Phased TCO | C-00-MP-110 | Install U/G Electrical @ Subsurface | no |  | 0 | level outside the configured range | CONSTRUCTION > Building Structure > Building Superstructure > U/G MEPs & SOG at 1st Lvl | TT_Task | TK_NotStart | 2027-02-15 | 2027-03-05 | 15 | 0 | Building Structure | U/G MEPs & SOG
Phased TCO | C-01-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-05-14 | 2026-05-18 | 3 | 68 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-01-ST-310 | Apply Vapor Barrier Under S.O.G. @ FPL Vault #118 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Building Superstructure > U/G MEPs & SOG at 1st Lvl > FPL Vault SOG - Early Work | TT_Task | TK_NotStart | 2026-09-01 | 2026-09-01 | 1 | 43 | Building Structure | FPL Vault SOG - Early Work
Phased TCO | C-01-ST-320 | F/R/P S.O.G. @ FPL Vault #118 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Building Superstructure > U/G MEPs & SOG at 1st Lvl > FPL Vault SOG - Early Work | TT_Task | TK_NotStart | 2026-09-02 | 2026-09-04 | 3 | 43 | Building Structure | FPL Vault SOG - Early Work
Phased TCO | C-01-ST-330 | Lay CMU Walls @ FPL Vault #118 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Building Superstructure > U/G MEPs & SOG at 1st Lvl > FPL Vault SOG - Early Work | TT_Task | TK_NotStart | 2026-09-08 | 2026-09-10 | 3 | 43 | Building Structure | FPL Vault SOG - Early Work
Phased TCO | C-01-MP-MP-100 | Prep Room to Receive FPL Work @ FPL Vault #118 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > FPL Vault #118 at 1st Lvl | TT_Task | TK_NotStart | 2026-09-11 | 2026-10-08 | 20 | 43 | Interior MEPs & Finishes | FPL Vault #118
Phased TCO | C-01-MP-MP-110 | Verify Vault by FPL Work @ FPL Vault #118 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > FPL Vault #118 at 1st Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-29 | 15 | 43 | Interior MEPs & Finishes | FPL Vault #118
Phased TCO | C-01-MP-MP-120 | Coordinate & Schedule with FPL for Work @ FPL Vault #118 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > FPL Vault #118 at 1st Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-12-21 | 35 | 43 | Interior MEPs & Finishes | FPL Vault #118
Phased TCO | C-01-MP-130 | Install Grease (GI-1) & Solid (SI-1) Interceptors & Piping @ Subsurface | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Building Superstructure > U/G MEPs & SOG at 1st Lvl | TT_Task | TK_NotStart | 2027-02-22 | 2027-03-05 | 10 | 0 | Building Structure | U/G MEPs & SOG
Phased TCO | C-01-MP-MP-130 | FPL Work @ FPL Vault #118 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > FPL Vault #118 at 1st Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-06-22 | 85 | 0 | Interior MEPs & Finishes | FPL Vault #118
Phased TCO | C-01-ST-200 | Apply Vapor Barrier Under S.O.G. @ L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Building Superstructure > U/G MEPs & SOG at 1st Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-10 | 3 | 0 | Building Structure | U/G MEPs & SOG
Phased TCO | C-01-ST-210 | F/R/P S.O.G. @ L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Building Superstructure > U/G MEPs & SOG at 1st Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-18 | 6 | 0 | Building Structure | U/G MEPs & SOG
Phased TCO | C-01-PG-MP-200 | Install Plumbing Floor Drains @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > MEP Eqp & Trim at Parking & Drop-Offat 1st Lvl | TT_Task | TK_NotStart | 2027-04-28 | 2027-04-30 | 3 | 96 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking & Drop-Offat
Phased TCO | C-01-PG-MP-210 | Install Mech GEFs @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > MEP Eqp & Trim at Parking & Drop-Offat 1st Lvl | TT_Task | TK_NotStart | 2027-05-17 | 2027-05-21 | 5 | 46 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking & Drop-Offat
Phased TCO | C-01-KT-100 | Kitchen Buildout @ L1 (Place Holder) | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Work in Lobby Restaurant- Place Holders | TT_Task | TK_NotStart | 2027-06-01 | 2027-11-17 | 120 | 0 | Interior MEPs & Finishes | Work in Lobby Restaurant- Place Holders
Phased TCO | C-01-LB-100 | Lobby & Restaurant Buildout @ L1 (Place Holder) | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Lobby/Future Space/Packages at 1st Lvl > Work in Lobby Restaurant- Place Holders | TT_Task | TK_NotStart | 2027-06-01 | 2027-11-17 | 120 | 0 | Interior MEPs & Finishes | Work in Lobby Restaurant- Place Holders
Phased TCO | C-01-MP-MP-200 | Prep Room to Receive FC Eqp @ Fire Command #112 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Command #112 at 1st Lvl | TT_Task | TK_NotStart | 2027-06-01 | 2027-06-21 | 15 | 13 | Interior MEPs & Finishes | Fire Command #112
Phased TCO | C-01-MP-MP-300 | Prep Room to Receive Pump Eqp @ Fire Pump Rm #116 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Pump Rm #116 at 1st Lvl | TT_Task | TK_NotStart | 2027-06-01 | 2027-06-21 | 15 | 17 | Interior MEPs & Finishes | Fire Pump Rm #116
Phased TCO | C-01-MP-MP-500 | Prep Room to Receive Trash Eqp @ Trash Rms #115 & #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Trash Rms #115 & #122 at 1st Lvl | TT_Task | TK_NotStart | 2027-06-01 | 2027-06-21 | 15 | 17 | Interior MEPs & Finishes | Trash Rms #115 & #122
Phased TCO | C-01-PG-EV-100 | Install Car Elevators @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-06-01 | 2027-09-08 | 70 | 76 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Phased TCO | C-01-PG-FN-110 | Frame GWB Ceilings @ Drop-Off - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-06-16 | 2027-06-22 | 5 | 7 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Phased TCO | C-01-PG-FN-120 | Hang GWB Ceilings @ Drop-Off - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-06-21 | 2027-06-25 | 5 | 7 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Phased TCO | C-01-MP-MP-210 | Install Mech A/C Eqp @ Fire Command #112 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Command #112 at 1st Lvl | TT_Task | TK_NotStart | 2027-06-22 | 2027-06-23 | 2 | 13 | Interior MEPs & Finishes | Fire Command #112
Phased TCO | C-01-MP-MP-310 | F/R/P Pump Pads @ Fire Pump Rm #116 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Pump Rm #116 at 1st Lvl | TT_Task | TK_NotStart | 2027-06-22 | 2027-06-23 | 2 | 17 | Interior MEPs & Finishes | Fire Pump Rm #116
Phased TCO | C-01-MP-MP-400 | Prep Room to Receive Pump Eqp @ Domestic Water #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Domestic Water Rm #121 at 1st Lvl | TT_Task | TK_NotStart | 2027-06-22 | 2027-07-13 | 15 | 113 | Interior MEPs & Finishes | Domestic Water Rm #121
Phased TCO | C-01-MP-MP-510 | Install Floor Drains (GDs) @ Trash Rms #115 & #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Trash Rms #115 & #122 at 1st Lvl | TT_Task | TK_NotStart | 2027-06-22 | 2027-06-23 | 2 | 17 | Interior MEPs & Finishes | Trash Rms #115 & #122
Phased TCO | C-01-MP-MP-220 | Install Electrical Panels @ Fire Command #112 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Command #112 at 1st Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-30 | 5 | 13 | Interior MEPs & Finishes | Fire Command #112
Phased TCO | C-01-MP-MP-320 | Install Floor Drain (FD) @ Fire Pump Rm #116 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Pump Rm #116 at 1st Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-24 | 1 | 17 | Interior MEPs & Finishes | Fire Pump Rm #116
Phased TCO | C-01-MP-MP-520 | Install Mech A/C Eqp @ Trash Rms #115 & #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Trash Rms #115 & #122 at 1st Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-29 | 4 | 17 | Interior MEPs & Finishes | Trash Rms #115 & #122
Phased TCO | C-01-PG-FN-130 | Tape & Finish GWB Ceilings @ Drop-Off - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-29 | 4 | 7 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Phased TCO | C-01-MP-MP-330 | Apply Waterproofing @ Fire Pump Rm #116 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Pump Rm #116 at 1st Lvl | TT_Task | TK_NotStart | 2027-06-25 | 2027-06-28 | 2 | 17 | Interior MEPs & Finishes | Fire Pump Rm #116
Phased TCO | C-01-MP-MP-340 | Install Mech A/C Eqp @ Fire Pump Rm #116 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Pump Rm #116 at 1st Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-06-30 | 2 | 17 | Interior MEPs & Finishes | Fire Pump Rm #116
Phased TCO | C-01-MP-MP-530 | Install MEP Trim @ Trash Rms #115 & #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Trash Rms #115 & #122 at 1st Lvl | TT_Task | TK_NotStart | 2027-06-30 | 2027-07-09 | 7 | 17 | Interior MEPs & Finishes | Trash Rms #115 & #122
Phased TCO | C-01-PG-FN-140 | Install Bollards @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-06-30 | 2027-07-01 | 2 | 20 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Phased TCO | C-01-PG-FN-150 | Install Metal Canopy @ Drop-Off - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-06-30 | 2027-07-12 | 8 | 110 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Phased TCO | C-01-PG-FN-160 | Stucco @ Drop-off & Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-06-30 | 2027-07-21 | 15 | 7 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Phased TCO | C-01-MP-MP-230 | Install Fire Alarm FA/V-CP & FACP & FAPS Panels @ Fire Command #112 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Command #112 at 1st Lvl | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-22 | 15 | 13 | Interior MEPs & Finishes | Fire Command #112
Phased TCO | C-01-MP-MP-240 | Install Generator Switch (SS) & Status Panel (GENAN) @ Fire Command #112 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Command #112 at 1st Lvl | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-08 | 5 | 23 | Interior MEPs & Finishes | Fire Command #112
Phased TCO | C-01-MP-MP-350 | Install & Connect Fire Pumps @ Fire Pump Rm #116 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Pump Rm #116 at 1st Lvl | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-22 | 15 | 17 | Interior MEPs & Finishes | Fire Pump Rm #116
Phased TCO | C-01-MP-MP-540 | Install Trash Eqp @ Trash Rms #115 & #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Trash Rms #115 & #122 at 1st Lvl | TT_Task | TK_NotStart | 2027-07-12 | 2027-07-21 | 8 | 17 | Interior MEPs & Finishes | Trash Rms #115 & #122
Phased TCO | C-01-PG-FN-170 | Install Porcelain Tiles @ Drop-Off - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-07-13 | 2027-07-26 | 10 | 110 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Phased TCO | C-01-MP-MP-410 | F/R/P Pump Pads @ Domestic Water #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Domestic Water Rm #121 at 1st Lvl | TT_Task | TK_NotStart | 2027-07-14 | 2027-07-15 | 2 | 113 | Interior MEPs & Finishes | Domestic Water Rm #121
Phased TCO | C-01-MP-MP-420 | Install Floor Drain (FD) @ Domestic Water #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Domestic Water Rm #121 at 1st Lvl | TT_Task | TK_NotStart | 2027-07-16 | 2027-07-16 | 1 | 113 | Interior MEPs & Finishes | Domestic Water Rm #121
Phased TCO | C-01-MP-MP-430 | Apply Waterproofing @ Domestic Water #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Domestic Water Rm #121 at 1st Lvl | TT_Task | TK_NotStart | 2027-07-19 | 2027-07-20 | 2 | 113 | Interior MEPs & Finishes | Domestic Water Rm #121
Phased TCO | C-01-MP-MP-440 | Install Mech A/C & GEF Eqp @ Dometic Water #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Domestic Water Rm #121 at 1st Lvl | TT_Task | TK_NotStart | 2027-07-21 | 2027-07-22 | 2 | 113 | Interior MEPs & Finishes | Domestic Water Rm #121
Phased TCO | C-01-PG-FN-180 | Paint @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-07-28 | 5 | 7 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Phased TCO | C-01-PG-FN-190 | Lightweight Concrete Cladding (DEKKO) @ Drop-off - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-08-04 | 10 | 107 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Phased TCO | C-01-PG-MP-220 | Install Mech Condensing Units @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > MEP Eqp & Trim at Parking & Drop-Offat 1st Lvl | TT_Task | TK_NotStart | 2027-07-22 | 2027-07-26 | 3 | 9 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking & Drop-Offat
Phased TCO | C-01-MP-MP-250 | Install SCU & Head-End Control Panels @ Fire Command #112 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Command #112 at 1st Lvl | TT_Task | TK_NotStart | 2027-07-23 | 2027-07-29 | 5 | 13 | Interior MEPs & Finishes | Fire Command #112
Phased TCO | C-01-MP-MP-260 | Install MEP Trim @ Fire Command #112 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Command #112 at 1st Lvl | TT_Task | TK_NotStart | 2027-07-23 | 2027-08-02 | 7 | 16 | Interior MEPs & Finishes | Fire Command #112
Phased TCO | C-01-MP-MP-360 | Install MEP Trim @ Fire Pump Rm #116 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Pump Rm #116 at 1st Lvl | TT_Task | TK_NotStart | 2027-07-23 | 2027-07-29 | 5 | 17 | Interior MEPs & Finishes | Fire Pump Rm #116
Phased TCO | C-01-MP-MP-450 | Install & Connect Dometic Pumps @ Dometic Water #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Domestic Water Rm #121 at 1st Lvl | TT_Task | TK_NotStart | 2027-07-23 | 2027-08-12 | 15 | 113 | Interior MEPs & Finishes | Domestic Water Rm #121
Phased TCO | C-01-PG-FN-200 | Install Column Protection & Pipe Guards @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-07-29 | 2027-08-03 | 4 | 101 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Phased TCO | C-01-PG-FN-210 | Install Fire Extinguisher Cabinet (FEC) @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-07-29 | 2027-07-29 | 1 | 111 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Phased TCO | C-01-PG-MP-230 | Install Light Fixtures @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > MEP Eqp & Trim at Parking & Drop-Offat 1st Lvl | TT_Task | TK_NotStart | 2027-07-29 | 2027-08-04 | 5 | 7 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking & Drop-Offat
Phased TCO | C-01-ES-100 | Fine Grade @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-07-30 | 2027-08-05 | 5 | 112 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Phased TCO | C-01-MP-MP-270 | Install Elevator ANN Panel (ELAN) @ Fire Command #112 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Command #112 at 1st Lvl | TT_Task | TK_NotStart | 2027-07-30 | 2027-08-05 | 5 | 13 | Interior MEPs & Finishes | Fire Command #112
Phased TCO | C-01-MP-MP-370 | Install & Pump Controller & Gas Sub Meters @ Fire Pump Rm #116 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Pump Rm #116 at 1st Lvl | TT_Task | TK_NotStart | 2027-07-30 | 2027-08-04 | 4 | 17 | Interior MEPs & Finishes | Fire Pump Rm #116
Phased TCO | C-01-PG-MP-240 | Install Electrical Power Trim @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > MEP Eqp & Trim at Parking & Drop-Offat 1st Lvl | TT_Task | TK_NotStart | 2027-08-05 | 2027-08-09 | 3 | 7 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking & Drop-Offat
Phased TCO | C-01-ES-110 | F/R/P Planters @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-08-06 | 2027-08-23 | 12 | 112 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Phased TCO | C-01-ES-120 | Install Electrical Rough @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-08-06 | 2027-08-12 | 5 | 124 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Phased TCO | C-01-MP-MP-280 | Install BDA Panel @ Fire Command #112 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Fire Command #112 at 1st Lvl | TT_Task | TK_NotStart | 2027-08-06 | 2027-08-10 | 3 | 13 | Interior MEPs & Finishes | Fire Command #112
Phased TCO | C-01-MP-MP-460 | Install MEP Trim @ Domestic Water #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Domestic Water Rm #121 at 1st Lvl | TT_Task | TK_NotStart | 2027-08-09 | 2027-08-13 | 5 | 113 | Interior MEPs & Finishes | Domestic Water Rm #121
Phased TCO | C-01-PG-MP-250 | Install FP Sprinkler Heads @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > MEP Eqp & Trim at Parking & Drop-Offat 1st Lvl | TT_Task | TK_NotStart | 2027-08-10 | 2027-08-12 | 3 | 7 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking & Drop-Offat
Phased TCO | C-01-PG-MP-260 | Install FA & Low Voltage Devices (CCTV-Access Ctrl-PA) @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > MEP Eqp & Trim at Parking & Drop-Offat 1st Lvl | TT_Task | TK_NotStart | 2027-08-13 | 2027-08-18 | 4 | 7 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking & Drop-Offat
Phased TCO | C-01-MP-MP-470 | Install & Pump Controller @ Dometic Water #122 - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > MEP Eqp at MEP Rooms at 1st Lvl > Domestic Water Rm #121 at 1st Lvl | TT_Task | TK_NotStart | 2027-08-16 | 2027-08-18 | 3 | 113 | Interior MEPs & Finishes | Domestic Water Rm #121
Phased TCO | C-01-ES-130 | Install Irrigation Mainlines & Laterals Rough @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-08-17 | 2027-08-30 | 10 | 112 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Phased TCO | C-01-ES-140 | Install Drainage @ Planters - E. & S. Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-08-24 | 2027-09-02 | 8 | 122 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Phased TCO | C-01-ES-150 | Form & Pour Conc Curbs & Gutters @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-08-31 | 2027-09-14 | 10 | 112 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Phased TCO | C-01-ES-160 | Form & Pour Sidewalks @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-09-08 | 2027-09-17 | 8 | 112 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Phased TCO | C-01-PG-FN-220 | Apply Waterproofing & Seal Concrete @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-09-09 | 2027-09-13 | 3 | 76 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Phased TCO | C-01-PG-FN-230 | Apply Pavement Markings @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-09-14 | 2027-09-15 | 2 | 76 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Phased TCO | C-01-PG-FN-240 | Install Signage @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-09-16 | 2027-09-17 | 2 | 76 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Phased TCO | C-01-ES-170 | Install Metal Bike Racks @ E. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-09-20 | 2027-09-20 | 1 | 150 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Phased TCO | C-01-ES-180 | Apply Stucco @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-09-20 | 2027-09-27 | 6 | 112 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Phased TCO | C-01-PG-FN-250 | Final Cleanup @ Parking - L1 | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 1st Lvl > Interior MEPs & Finishes at Parking & Drop-Off at 1st Lvl > Interior Finishes at Parking & Drop-Off at 1st Lvl | TT_Task | TK_NotStart | 2027-09-20 | 2027-09-21 | 2 | 76 | Interior MEPs & Finishes | Interior Finishes at Parking & Drop-Off
Phased TCO | C-01-ES-190 | Paint Stucco @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-09-28 | 2027-09-29 | 2 | 112 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Phased TCO | C-01-ES-200 | Lay Concrete & Stone Pavers & Tiles @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-09-30 | 2027-10-21 | 16 | 112 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Phased TCO | C-01-ES-210 | Building Signage @ Planter - S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-09-30 | 2027-10-06 | 5 | 134 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Phased TCO | C-01-ES-220 | Fill Soil Mix @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-09-30 | 2027-10-04 | 3 | 115 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Phased TCO | C-01-ES-230 | Sod & Plant Trees & Shrubs @ Planters - E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-10-05 | 2027-10-18 | 10 | 115 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Phased TCO | C-01-ES-240 | Install Signage @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-10-07 | 2027-10-12 | 4 | 134 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Phased TCO | C-01-ES-250 | Plant Trees & Landscaping @ SW 2nd Ave - West Site | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-10-22 | 2027-11-08 | 12 | 112 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Phased TCO | C-01-ES-260 | Asphalt Pavement @ SW 11th St & 2nd Ave | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-11-09 | 2027-11-11 | 3 | 115 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Phased TCO | C-01-ES-270 | Install Irrigation Spray Sprinkler & Controls @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-11-09 | 2027-11-11 | 3 | 112 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Phased TCO | C-01-ES-280 | Install Tree Grates @ E. & S. Bldg Surroundings | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-11-12 | 2027-11-12 | 1 | 112 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Phased TCO | C-01-ES-290 | Install Tree Up-Lighting @ SW 2nd Ave - West Site | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-11-15 | 2027-11-16 | 2 | 112 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Phased TCO | C-01-ES-300 | Apply Pavement Markings @ SW 11th St & 2nd Ave | no |  | 1 | has a level but matches no band rule | CONSTRUCTION > Exterior Site Improvements at Building Surroundings | TT_Task | TK_NotStart | 2027-11-17 | 2027-11-18 | 2 | 112 | Exterior Site Improvements at Building Surroundings | Exterior Site Improvements at Building Surroundings
Phased TCO | C-02-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-06-01 | 2026-06-03 | 3 | 60 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-02-PG-MP-100 | Install Plumbing Rough @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > MEP Rough at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2026-06-29 | 2026-07-07 | 6 | 74 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-02-PG-MP-110 | Install Fire Protection Rough @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > MEP Rough at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2026-07-06 | 2026-07-13 | 6 | 236 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-02-PG-MP-120 | Install Plumbing Floor Drains @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > MEP Rough at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2026-07-06 | 2026-07-09 | 4 | 241 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-02-PG-MP-130 | Install Electrical Rough @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > MEP Rough at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2026-07-07 | 2026-07-14 | 6 | 236 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-02-PG-MP-140 | Install FA & Low Voltage Rough @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > MEP Rough at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2026-07-10 | 2026-07-16 | 5 | 236 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-02-PG-MP-200 | Install Mech Condensing Units @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > MEP Eqp & Trim at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2026-07-15 | 2026-07-17 | 3 | 259 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-02-PG-MP-150 | Inspect MEP Rough @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > MEP Rough at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2026-07-17 | 2026-07-17 | 1 | 236 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-02-PG-FN-110 | Paint @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > Interior Finishes at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2026-07-20 | 2026-07-23 | 4 | 236 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-02-PG-FN-120 | Install Column Protection & Pipe Guards @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > Interior Finishes at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2026-07-24 | 2026-07-28 | 3 | 245 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-02-PG-FN-130 | Install Fire Extinguisher Cabinet (FEC) @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > Interior Finishes at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2026-07-24 | 2026-07-24 | 1 | 247 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-02-PG-FN-140 | Install Parking Stacker Lifts @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > Interior Finishes at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2026-07-24 | 2026-08-10 | 12 | 236 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-02-PG-FN-150 | Apply Waterproofing/ Seal Concrete @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > Interior Finishes at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-11 | 2026-08-12 | 2 | 236 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-02-PG-FN-160 | Install Wheel Stops @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > Interior Finishes at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-13 | 2026-08-17 | 3 | 236 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-02-PG-FN-170 | Apply Pavement Markings @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > Interior Finishes at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-18 | 2026-08-19 | 2 | 236 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-02-PG-FN-180 | Install Signage @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > Interior Finishes at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-20 | 2026-08-21 | 2 | 305 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-02-PG-MP-210 | Install Light Fixtures @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > MEP Eqp & Trim at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-20 | 2026-08-25 | 4 | 236 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-02-PG-MP-220 | Install Electrical Power Trim @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > MEP Eqp & Trim at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-26 | 2026-08-27 | 2 | 236 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-02-PG-MP-230 | Install FP Sprinkler Heads @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > MEP Eqp & Trim at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2026-08-28 | 2026-09-01 | 3 | 236 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-02-PG-MP-240 | Install FA & Low Voltage Devices (CCTV-Access Ctrl-PA) @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > MEP Eqp & Trim at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-02 | 2026-09-04 | 3 | 236 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-02-PG-FN-190 | Final Cleanup @ Parking - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > Interior MEPs & Finishes at Parking at 2nd Lvl > Interior Finishes at Parking at 2nd Lvl | TT_Task | TK_NotStart | 2026-09-08 | 2026-09-09 | 2 | 295 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-02-MP-MP-100 | Prep Room (MEP Rough & Finishes) to Receive Elect Panels & Eqp @ Main Elect/MDF #235 - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > MEP Eqp at MEP Rooms at 2nd Lvl > Main Electrical & MDF Room #235 at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-29 | 15 | 128 | Interior MEPs & Finishes | Main Electrical & MDF Room #235
Phased TCO | C-02-MP-MP-200 | Prep Room (MEP Rough & Finishes) to Receive Gen Eqp @ Generator #234 - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > MEP Eqp at MEP Rooms at 2nd Lvl > Generator Room #234 at 2nd Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-19 | 15 | 201 | Interior MEPs & Finishes | Generator Room #234
Phased TCO | C-02-MP-MP-210 | F/R/P Generator Pad @ Generator #234 - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > MEP Eqp at MEP Rooms at 2nd Lvl > Generator Room #234 at 2nd Lvl | TT_Task | TK_NotStart | 2026-11-20 | 2026-11-23 | 2 | 201 | Interior MEPs & Finishes | Generator Room #234
Phased TCO | C-02-MP-MP-220 | Setup Generator & Sub-Base Tank @ Generator #234 - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > MEP Eqp at MEP Rooms at 2nd Lvl > Generator Room #234 at 2nd Lvl | TT_Task | TK_NotStart | 2026-12-15 | 2026-12-21 | 5 | 188 | Interior MEPs & Finishes | Generator Room #234
Phased TCO | C-02-MP-MP-230 | Close CMU Wall Opening @ Generator #234 - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > MEP Eqp at MEP Rooms at 2nd Lvl > Generator Room #234 at 2nd Lvl | TT_Task | TK_NotStart | 2026-12-22 | 2026-12-23 | 2 | 188 | Interior MEPs & Finishes | Generator Room #234
Phased TCO | C-02-MP-MP-240 | Install Mech Exhaust Fan (GEF) @ Generator #234 - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > MEP Eqp at MEP Rooms at 2nd Lvl > Generator Room #234 at 2nd Lvl | TT_Task | TK_NotStart | 2026-12-24 | 2026-12-28 | 2 | 214 | Interior MEPs & Finishes | Generator Room #234
Phased TCO | C-02-MP-MP-110 | Install Electrical Switchgear & Boards & Panels @ Main Elect/MDF #235 - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > MEP Eqp at MEP Rooms at 2nd Lvl > Main Electrical & MDF Room #235 at 2nd Lvl | TT_Task | TK_NotStart | 2027-01-11 | 2027-02-26 | 35 | 81 | Interior MEPs & Finishes | Main Electrical & MDF Room #235
Phased TCO | C-02-RF-100 | Install Roof Drain Base @ North Roof (CL 2-5/D-E) - L3 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at North Side at (CL 1-2/D-E) - 2nd Lvl | TT_Task | TK_NotStart | 2027-02-01 | 2027-02-01 | 1 | 56 | Exterior Envelope | Roofing at North Side at (CL 1-2/D-E)
Phased TCO | C-02-RF-110 | Tapered Insulation @ North Roof (CL 1-2/D-E) - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at North Side at (CL 1-2/D-E) - 2nd Lvl | TT_Task | TK_NotStart | 2027-02-02 | 2027-02-02 | 1 | 56 | Exterior Envelope | Roofing at North Side at (CL 1-2/D-E)
Phased TCO | C-02-RF-120 | Apply Roofing Membrane & Flashing @ North Roof (CL 1-2/D-E) - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at North Side at (CL 1-2/D-E) - 2nd Lvl | TT_Task | TK_NotStart | 2027-02-03 | 2027-02-05 | 3 | 56 | Exterior Envelope | Roofing at North Side at (CL 1-2/D-E)
Phased TCO | C-02-RF-130 | Install Overflow Scupper @ North Roof (CL 1-2/D-E) - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at North Side at (CL 1-2/D-E) - 2nd Lvl | TT_Task | TK_NotStart | 2027-02-08 | 2027-02-08 | 1 | 56 | Exterior Envelope | Roofing at North Side at (CL 1-2/D-E)
Phased TCO | C-02-RF-210 | Tapered Insulation @ North Roof (CL 7-8/F-G) - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at North Side at (CL 7-8/F-G) - 2nd Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-09 | 1 | 56 | Exterior Envelope | Roofing at North Side at (CL 7-8/F-G)
Phased TCO | C-02-RF-220 | Apply Roofing Membrane & Flashing @ North Roof (CL 7-8/F-G) - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at North Side at (CL 7-8/F-G) - 2nd Lvl | TT_Task | TK_NotStart | 2027-02-10 | 2027-02-12 | 3 | 56 | Exterior Envelope | Roofing at North Side at (CL 7-8/F-G)
Phased TCO | C-02-RF-230 | Install Overflow Scuppers @ North Roof (CL 7-8/F-G) - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at North Side at (CL 7-8/F-G) - 2nd Lvl | TT_Task | TK_NotStart | 2027-02-15 | 2027-02-15 | 1 | 56 | Exterior Envelope | Roofing at North Side at (CL 7-8/F-G)
Phased TCO | C-02-MP-MP-250 | Install MEP Connections for Generator @ Generator #234 - L2 | no |  | 2 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 2nd Lvl > MEP Eqp at MEP Rooms at 2nd Lvl > Generator Room #234 at 2nd Lvl | TT_Task | TK_NotStart | 2027-03-01 | 2027-04-09 | 30 | 143 | Interior MEPs & Finishes | Generator Room #234
Phased TCO | C-03-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-06-16 | 2026-06-18 | 3 | 56 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-03-PG-MP-100 | Install Plumbing Rough @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Rough at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2026-07-15 | 2026-07-22 | 6 | 69 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-03-PG-MP-110 | Install Fire Protection Rough @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Rough at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2026-07-21 | 2026-07-28 | 6 | 227 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-03-PG-MP-120 | Install Plumbing Floor Drains @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Rough at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2026-07-21 | 2026-07-24 | 4 | 232 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-03-PG-MP-130 | Install Electrical Rough @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Rough at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2026-07-22 | 2026-07-29 | 6 | 227 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-03-PG-MP-140 | Install FA & Low Voltage Rough @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Rough at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2026-07-27 | 2026-07-31 | 5 | 227 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-03-PG-MP-200 | Install Mech Condensing Units @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Eqp & Trim at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2026-07-30 | 2026-08-03 | 3 | 250 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-03-PG-MP-150 | Inspect MEP Rough @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Rough at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-03 | 2026-08-03 | 1 | 227 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-03-PG-FN-110 | Paint @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > Interior Finishes at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-04 | 2026-08-07 | 4 | 227 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-03-PG-FN-120 | Install Column Protection & Pipe Guards @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > Interior Finishes at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-10 | 2026-08-12 | 3 | 236 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-03-PG-FN-130 | Install Fire Extinguisher Cabinet (FEC) @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > Interior Finishes at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-10 | 2026-08-10 | 1 | 238 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-03-PG-FN-140 | Install Parking Stacker Lifts @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > Interior Finishes at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-10 | 2026-08-25 | 12 | 227 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-03-PG-FN-150 | Apply Waterproofing/ Seal Concrete @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > Interior Finishes at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-26 | 2026-08-27 | 2 | 227 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-03-PG-FN-160 | Install Wheel Stops @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > Interior Finishes at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2026-08-28 | 2026-09-01 | 3 | 227 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-03-PG-FN-170 | Apply Pavement Markings @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > Interior Finishes at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-02 | 2026-09-03 | 2 | 227 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-03-PG-FN-180 | Install Signage @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > Interior Finishes at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-04 | 2026-09-08 | 2 | 296 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-03-PG-MP-210 | Install Light Fixtures @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Eqp & Trim at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-04 | 2026-09-10 | 4 | 227 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-03-PG-MP-220 | Install Electrical Power Trim @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Eqp & Trim at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-11 | 2026-09-14 | 2 | 227 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-03-PG-MP-230 | Install FP Sprinkler Heads @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Eqp & Trim at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-17 | 3 | 228 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-03-PG-MP-250 | Install EV Charge Stations @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Eqp & Trim at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-18 | 4 | 227 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-03-PG-MP-240 | Install FA & Low Voltage Devices (CCTV-Access Ctrl-PA) @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > MEP Eqp & Trim at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-21 | 2026-09-23 | 3 | 227 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-03-EX-210x | Apply Waterproofing & Install Tiles @ Balconies - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 3rd to 7th Lvl | TT_Task | TK_NotStart | 2026-09-22 | 2026-09-25 | 4 | 200 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 3rd to
Phased TCO | C-03-PG-FN-190 | Final Cleanup @ Parking - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 3rd Lvl > Interior MEPs & Finishes at Parking at 3rd Lvl > Interior Finishes at Parking at 3rd Lvl | TT_Task | TK_NotStart | 2026-09-24 | 2026-09-25 | 2 | 285 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-03-EX-230x | Install Balcony Glass Railings @ Balconies - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 3rd to 7th Lvl | TT_Task | TK_NotStart | 2026-11-03 | 2026-11-09 | 5 | 200 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 3rd to
Phased TCO | C-03-RF-100 | Install Roof Drain Bases @ North Roof (CL 2-5/D-E) - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at North Side at (CL 2-5/D-E) - 3rd Lvl | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-17 | 2 | 56 | Exterior Envelope | Roofing at North Side at (CL 2-5/D-E)
Phased TCO | C-03-RF-110 | Tapered Insulation @ North Roof (CL 2-5/D-E) - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at North Side at (CL 2-5/D-E) - 3rd Lvl | TT_Task | TK_NotStart | 2027-02-18 | 2027-02-22 | 3 | 56 | Exterior Envelope | Roofing at North Side at (CL 2-5/D-E)
Phased TCO | C-03-RF-120 | Apply Roofing Membrane & Flashing @ North Roof (CL 2-5/D-E) - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at North Side at (CL 2-5/D-E) - 3rd Lvl | TT_Task | TK_NotStart | 2027-02-23 | 2027-03-03 | 7 | 56 | Exterior Envelope | Roofing at North Side at (CL 2-5/D-E)
Phased TCO | C-03-RF-130 | Install Overflow Scuppers @ North Roof (CL 2-5/D-E) - L3 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at North Side at (CL 2-5/D-E) - 3rd Lvl | TT_Task | TK_NotStart | 2027-03-04 | 2027-03-05 | 2 | 56 | Exterior Envelope | Roofing at North Side at (CL 2-5/D-E)
Phased TCO | C-03-RF-200 | Install Roof Drain Base @ West Roof (CL 7-8/A-B) - L7 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at West Side at (CL 7-8/A-B) - 7th Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-08 | 1 | 56 | Exterior Envelope | Roofing at West Side at (CL 7-8/A-B)
Phased TCO | C-03-RF-210 | Tapered Insulation @ West Roof (CL 7-8/A-B) - L7 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at West Side at (CL 7-8/A-B) - 7th Lvl | TT_Task | TK_NotStart | 2027-03-09 | 2027-03-10 | 2 | 56 | Exterior Envelope | Roofing at West Side at (CL 7-8/A-B)
Phased TCO | C-03-RF-220 | Apply Roofing Membrane & Flashing @ West Roof (CL 7-8/A-B) - L7 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at West Side at (CL 7-8/A-B) - 7th Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-17 | 5 | 56 | Exterior Envelope | Roofing at West Side at (CL 7-8/A-B)
Phased TCO | C-03-RF-230 | Install Overflow Scuppers @ West Roof (CL 7-8/A-B) - L7 | no |  | 3 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at West Side at (CL 7-8/A-B) - 7th Lvl | TT_Task | TK_NotStart | 2027-03-18 | 2027-03-18 | 1 | 56 | Exterior Envelope | Roofing at West Side at (CL 7-8/A-B)
Phased TCO | C-04-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-06-26 | 2026-06-30 | 3 | 55 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-04-PG-MP-100 | Install Plumbing Rough @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > MEP Rough at Parking at 4th Lvl | TT_Task | TK_NotStart | 2026-07-27 | 2026-08-03 | 6 | 67 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-04-PG-MP-110 | Install Fire Protection Rough @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > MEP Rough at Parking at 4th Lvl | TT_Task | TK_NotStart | 2026-07-31 | 2026-08-07 | 6 | 223 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-04-PG-MP-120 | Install Plumbing Floor Drains @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > MEP Rough at Parking at 4th Lvl | TT_Task | TK_NotStart | 2026-07-31 | 2026-08-05 | 4 | 228 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-04-PG-MP-130 | Install Electrical Rough @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > MEP Rough at Parking at 4th Lvl | TT_Task | TK_NotStart | 2026-08-03 | 2026-08-10 | 6 | 223 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-04-PG-MP-140 | Install FA & Low Voltage Rough @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > MEP Rough at Parking at 4th Lvl | TT_Task | TK_NotStart | 2026-08-06 | 2026-08-12 | 5 | 223 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-04-PG-MP-200 | Install Mech Condensing Units @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > MEP Eqp & Trim at Parking at 4th Lvl | TT_Task | TK_NotStart | 2026-08-11 | 2026-08-13 | 3 | 246 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-04-PG-MP-150 | Inspect MEP Rough @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > MEP Rough at Parking at 4th Lvl | TT_Task | TK_NotStart | 2026-08-13 | 2026-08-13 | 1 | 223 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-04-PG-FN-110 | Paint @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > Interior Finishes at Parking at 4th Lvl | TT_Task | TK_NotStart | 2026-08-14 | 2026-08-19 | 4 | 223 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-04-PG-FN-120 | Install Column Protection & Pipe Guards @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > Interior Finishes at Parking at 4th Lvl | TT_Task | TK_NotStart | 2026-08-20 | 2026-08-24 | 3 | 232 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-04-PG-FN-130 | Install Fire Extinguisher Cabinet (FEC) @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > Interior Finishes at Parking at 4th Lvl | TT_Task | TK_NotStart | 2026-08-20 | 2026-08-20 | 1 | 234 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-04-PG-FN-140 | Install Parking Stacker Lifts @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > Interior Finishes at Parking at 4th Lvl | TT_Task | TK_NotStart | 2026-08-20 | 2026-09-04 | 12 | 223 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-04-PG-FN-150 | Apply Waterproofing/ Seal Concrete @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > Interior Finishes at Parking at 4th Lvl | TT_Task | TK_NotStart | 2026-09-08 | 2026-09-09 | 2 | 223 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-04-PG-FN-160 | Install Wheel Stops @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > Interior Finishes at Parking at 4th Lvl | TT_Task | TK_NotStart | 2026-09-10 | 2026-09-14 | 3 | 223 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-04-PG-FN-170 | Apply Pavement Markings @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > Interior Finishes at Parking at 4th Lvl | TT_Task | TK_NotStart | 2026-09-15 | 2026-09-16 | 2 | 223 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-04-PG-FN-180 | Install Signage @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > Interior Finishes at Parking at 4th Lvl | TT_Task | TK_NotStart | 2026-09-17 | 2026-09-18 | 2 | 290 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-04-PG-MP-210 | Install Light Fixtures @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > MEP Eqp & Trim at Parking at 4th Lvl | TT_Task | TK_NotStart | 2026-09-17 | 2026-09-22 | 4 | 223 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-04-PG-MP-220 | Install Electrical Power Trim @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > MEP Eqp & Trim at Parking at 4th Lvl | TT_Task | TK_NotStart | 2026-09-23 | 2026-09-24 | 2 | 223 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-04-PG-MP-230 | Install FP Sprinkler Heads @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > MEP Eqp & Trim at Parking at 4th Lvl | TT_Task | TK_NotStart | 2026-09-25 | 2026-09-29 | 3 | 223 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-04-EX-210x | Apply Waterproofing & Install Tiles @ Balconies - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 3rd to 7th Lvl | TT_Task | TK_NotStart | 2026-09-28 | 2026-10-01 | 4 | 200 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 3rd to
Phased TCO | C-04-PG-MP-240 | Install FA & Low Voltage Devices (CCTV-Access Ctrl-PA) @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > MEP Eqp & Trim at Parking at 4th Lvl | TT_Task | TK_NotStart | 2026-09-30 | 2026-10-02 | 3 | 223 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-04-PG-FN-190 | Final Cleanup @ Parking - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 4th Lvl > Interior MEPs & Finishes at Parking at 4th Lvl > Interior Finishes at Parking at 4th Lvl | TT_Task | TK_NotStart | 2026-10-05 | 2026-10-06 | 2 | 280 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-04-EX-230x | Install Balcony Glass Railings @ Balconies - L4 | no |  | 4 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 3rd to 7th Lvl | TT_Task | TK_NotStart | 2026-11-10 | 2026-11-16 | 5 | 200 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 3rd to
Phased TCO | C-05-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-07-06 | 2026-07-08 | 3 | 57 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-05-PG-MP-100 | Install Plumbing Rough @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > MEP Rough at Parking at 5th Lvl | TT_Task | TK_NotStart | 2026-08-04 | 2026-08-11 | 6 | 67 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-05-PG-MP-110 | Install Fire Protection Rough @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > MEP Rough at Parking at 5th Lvl | TT_Task | TK_NotStart | 2026-08-10 | 2026-08-17 | 6 | 220 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-05-PG-MP-120 | Install Plumbing Floor Drains @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > MEP Rough at Parking at 5th Lvl | TT_Task | TK_NotStart | 2026-08-10 | 2026-08-13 | 4 | 225 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-05-PG-MP-130 | Install Electrical Rough @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > MEP Rough at Parking at 5th Lvl | TT_Task | TK_NotStart | 2026-08-11 | 2026-08-18 | 6 | 220 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-05-PG-MP-140 | Install FA & Low Voltage Rough @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > MEP Rough at Parking at 5th Lvl | TT_Task | TK_NotStart | 2026-08-14 | 2026-08-20 | 5 | 220 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-05-PG-MP-200 | Install Mech Condensing Units @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > MEP Eqp & Trim at Parking at 5th Lvl | TT_Task | TK_NotStart | 2026-08-19 | 2026-08-21 | 3 | 243 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-05-PG-MP-150 | Inspect MEP Rough @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > MEP Rough at Parking at 5th Lvl | TT_Task | TK_NotStart | 2026-08-21 | 2026-08-21 | 1 | 220 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-05-PG-FN-110 | Paint @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > Interior Finishes at Parking at 5th Lvl | TT_Task | TK_NotStart | 2026-08-24 | 2026-08-27 | 4 | 220 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-05-PG-FN-120 | Install Column Protection & Pipe Guards @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > Interior Finishes at Parking at 5th Lvl | TT_Task | TK_NotStart | 2026-08-28 | 2026-09-01 | 3 | 229 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-05-PG-FN-130 | Install Fire Extinguisher Cabinet (FEC) @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > Interior Finishes at Parking at 5th Lvl | TT_Task | TK_NotStart | 2026-08-28 | 2026-08-28 | 1 | 231 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-05-PG-FN-140 | Install Parking Stacker Lifts @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > Interior Finishes at Parking at 5th Lvl | TT_Task | TK_NotStart | 2026-08-28 | 2026-09-15 | 12 | 220 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-05-PG-FN-150 | Apply Waterproofing/ Seal Concrete @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > Interior Finishes at Parking at 5th Lvl | TT_Task | TK_NotStart | 2026-09-16 | 2026-09-17 | 2 | 220 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-05-PG-FN-160 | Install Wheel Stops @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > Interior Finishes at Parking at 5th Lvl | TT_Task | TK_NotStart | 2026-09-18 | 2026-09-22 | 3 | 220 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-05-PG-FN-170 | Apply Pavement Markings @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > Interior Finishes at Parking at 5th Lvl | TT_Task | TK_NotStart | 2026-09-23 | 2026-09-24 | 2 | 220 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-05-PG-FN-180 | Install Signage @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > Interior Finishes at Parking at 5th Lvl | TT_Task | TK_NotStart | 2026-09-25 | 2026-09-28 | 2 | 286 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-05-PG-MP-210 | Install Light Fixtures @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > MEP Eqp & Trim at Parking at 5th Lvl | TT_Task | TK_NotStart | 2026-09-25 | 2026-09-30 | 4 | 220 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-05-PG-MP-220 | Install Electrical Power Trim @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > MEP Eqp & Trim at Parking at 5th Lvl | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-02 | 2 | 220 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-05-EX-210x | Apply Waterproofing & Install Tiles @ Balconies - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 3rd to 7th Lvl | TT_Task | TK_NotStart | 2026-10-02 | 2026-10-07 | 4 | 200 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 3rd to
Phased TCO | C-05-PG-MP-230 | Install FP Sprinkler Heads @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > MEP Eqp & Trim at Parking at 5th Lvl | TT_Task | TK_NotStart | 2026-10-05 | 2026-10-07 | 3 | 220 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-05-PG-MP-240 | Install FA & Low Voltage Devices (CCTV-Access Ctrl-PA) @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > MEP Eqp & Trim at Parking at 5th Lvl | TT_Task | TK_NotStart | 2026-10-08 | 2026-10-12 | 3 | 220 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-05-PG-FN-190 | Final Cleanup @ Parking - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 5th Lvl > Interior MEPs & Finishes at Parking at 5th Lvl > Interior Finishes at Parking at 5th Lvl | TT_Task | TK_NotStart | 2026-10-13 | 2026-10-14 | 2 | 276 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-05-EX-230x | Install Balcony Glass Railings @ Balconies - L5 | no |  | 5 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 3rd to 7th Lvl | TT_Task | TK_NotStart | 2026-11-17 | 2026-11-23 | 5 | 200 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 3rd to
Phased TCO | C-06-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-07-13 | 2026-07-15 | 3 | 59 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-06-PG-MP-100 | Install Plumbing Rough @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > MEP Rough at Parking at 6th Lvl | TT_Task | TK_NotStart | 2026-08-10 | 2026-08-17 | 6 | 219 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-06-PG-MP-110 | Install Fire Protection Rough @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > MEP Rough at Parking at 6th Lvl | TT_Task | TK_NotStart | 2026-08-14 | 2026-08-21 | 6 | 219 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-06-PG-MP-120 | Install Plumbing Floor Drains @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > MEP Rough at Parking at 6th Lvl | TT_Task | TK_NotStart | 2026-08-14 | 2026-08-19 | 4 | 224 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-06-PG-MP-130 | Install Electrical Rough @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > MEP Rough at Parking at 6th Lvl | TT_Task | TK_NotStart | 2026-08-17 | 2026-08-24 | 6 | 219 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-06-PG-MP-140 | Install FA & Low Voltage Rough @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > MEP Rough at Parking at 6th Lvl | TT_Task | TK_NotStart | 2026-08-20 | 2026-08-26 | 5 | 219 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-06-PG-MP-200 | Install Mech Condensing Units @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > MEP Eqp & Trim at Parking at 6th Lvl | TT_Task | TK_NotStart | 2026-08-25 | 2026-08-27 | 3 | 242 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-06-PG-MP-150 | Inspect MEP Rough @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > MEP Rough at Parking at 6th Lvl | TT_Task | TK_NotStart | 2026-08-27 | 2026-08-27 | 1 | 219 | Interior MEPs & Finishes | MEP Rough at Parking
Phased TCO | C-06-PG-FN-110 | Paint @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > Interior Finishes at Parking at 6th Lvl | TT_Task | TK_NotStart | 2026-08-28 | 2026-09-02 | 4 | 219 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-06-PG-FN-120 | Install Column Protection & Pipe Guards @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > Interior Finishes at Parking at 6th Lvl | TT_Task | TK_NotStart | 2026-09-03 | 2026-09-08 | 3 | 228 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-06-PG-FN-130 | Install Fire Extinguisher Cabinet (FEC) @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > Interior Finishes at Parking at 6th Lvl | TT_Task | TK_NotStart | 2026-09-03 | 2026-09-03 | 1 | 230 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-06-PG-FN-140 | Install Parking Stacker Lifts @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > Interior Finishes at Parking at 6th Lvl | TT_Task | TK_NotStart | 2026-09-03 | 2026-09-21 | 12 | 219 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-06-PG-FN-150 | Apply Waterproofing/ Seal Concrete @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > Interior Finishes at Parking at 6th Lvl | TT_Task | TK_NotStart | 2026-09-22 | 2026-09-23 | 2 | 219 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-06-PG-FN-160 | Install Wheel Stops @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > Interior Finishes at Parking at 6th Lvl | TT_Task | TK_NotStart | 2026-09-24 | 2026-09-28 | 3 | 219 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-06-PG-FN-170 | Apply Pavement Markings @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > Interior Finishes at Parking at 6th Lvl | TT_Task | TK_NotStart | 2026-09-29 | 2026-09-30 | 2 | 219 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-06-PG-FN-180 | Install Signage @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > Interior Finishes at Parking at 6th Lvl | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-02 | 2 | 284 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-06-PG-MP-210 | Install Light Fixtures @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > MEP Eqp & Trim at Parking at 6th Lvl | TT_Task | TK_NotStart | 2026-10-01 | 2026-10-06 | 4 | 219 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-06-PG-MP-220 | Install Electrical Power Trim @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > MEP Eqp & Trim at Parking at 6th Lvl | TT_Task | TK_NotStart | 2026-10-07 | 2026-10-08 | 2 | 219 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-06-EX-210x | Apply Waterproofing & Install Tiles @ Balconies - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 3rd to 7th Lvl | TT_Task | TK_NotStart | 2026-10-08 | 2026-10-13 | 4 | 200 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 3rd to
Phased TCO | C-06-PG-MP-230 | Install FP Sprinkler Heads @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > MEP Eqp & Trim at Parking at 6th Lvl | TT_Task | TK_NotStart | 2026-10-09 | 2026-10-13 | 3 | 219 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-06-PG-MP-240 | Install FA & Low Voltage Devices (CCTV-Access Ctrl-PA) @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > MEP Eqp & Trim at Parking at 6th Lvl | TT_Task | TK_NotStart | 2026-10-14 | 2026-10-16 | 3 | 219 | Interior MEPs & Finishes | MEP Eqp & Trim at Parking
Phased TCO | C-06-PG-FN-190 | Final Cleanup @ Parking - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 6th Lvl > Interior MEPs & Finishes at Parking at 6th Lvl > Interior Finishes at Parking at 6th Lvl | TT_Task | TK_NotStart | 2026-10-19 | 2026-10-20 | 2 | 274 | Interior MEPs & Finishes | Interior Finishes at Parking
Phased TCO | C-06-EX-230x | Install Balcony Glass Railings @ Balconies - L6 | no |  | 6 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 3rd to 7th Lvl | TT_Task | TK_NotStart | 2026-11-24 | 2026-12-02 | 5 | 200 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 3rd to
Phased TCO | C-07-ST-200 | F/R/P Planter Walls @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Building Superstructure > Structure at 7th Lvl | TT_Task | TK_NotStart | 2026-06-18 | 2026-07-16 | 20 | 222 | Building Structure | Structure
Phased TCO | C-07-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-07-20 | 2026-07-22 | 3 | 61 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-07-EX-210x | Apply Waterproofing & Install Tiles @ Balconies - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 3rd to 7th Lvl | TT_Task | TK_NotStart | 2026-10-14 | 2026-10-19 | 4 | 200 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 3rd to
Phased TCO | C-07-EX-230x | Install Balcony Glass Railings @ Balconies - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 3rd to 7th Lvl | TT_Task | TK_NotStart | 2026-12-03 | 2026-12-09 | 5 | 200 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 3rd to
Phased TCO | C-07-RD-100 | Install Pluming Rough @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > MEP Rough at Outdoors at th Lvl | TT_Task | TK_NotStart | 2027-04-23 | 2027-05-03 | 7 | 11 | Exterior Envelope | MEP Rough at Outdoors at th Lvl
Phased TCO | C-07-RD-110 | Install Electrical & LV Rough @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > MEP Rough at Outdoors at th Lvl | TT_Task | TK_NotStart | 2027-05-04 | 2027-05-13 | 8 | 11 | Exterior Envelope | MEP Rough at Outdoors at th Lvl
Phased TCO | C-07-RD-200 | Install Exercise Unit Structural Base @ Fitness Area - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Roofing & Planter Walls at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-05-14 | 2027-05-14 | 1 | 11 | Exterior Envelope | Roofing & Planter Walls at Roof Deck
Phased TCO | C-07-RD-220 | Install Roof Drain Bases @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Roofing & Planter Walls at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-05-17 | 2027-05-21 | 5 | 11 | Exterior Envelope | Roofing & Planter Walls at Roof Deck
Phased TCO | C-07-RD-230 | F/R/P Topping Slabs @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Roofing & Planter Walls at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-05-24 | 2027-06-07 | 10 | 11 | Exterior Envelope | Roofing & Planter Walls at Roof Deck
Phased TCO | C-07-RD-240 | Apply Fluid Membrane @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Roofing & Planter Walls at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-06-08 | 2027-06-16 | 7 | 11 | Exterior Envelope | Roofing & Planter Walls at Roof Deck
Phased TCO | C-07-RD-250 | Install Drain Mats @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Roofing & Planter Walls at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-06-17 | 2027-06-23 | 5 | 11 | Exterior Envelope | Roofing & Planter Walls at Roof Deck
Phased TCO | C-07-RD-300 | Install Stone Tile Flooring @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Finishes & Flooring at Roof Deck 7th Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-07-15 | 15 | 11 | Exterior Envelope | Finishes & Flooring at Roof Deck
Phased TCO | C-07-RD-400 | Install Drainage @ Planters - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Planters at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-07-16 | 2027-07-29 | 10 | 11 | Exterior Envelope | Planters at Roof Deck
Phased TCO | C-07-RD-410 | Apply Waterproofing Membrane @ Planters - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Planters at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-07-30 | 2027-08-09 | 7 | 11 | Exterior Envelope | Planters at Roof Deck
Phased TCO | C-07-RD-420 | Install Electrical Rough @ Planters - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Planters at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-08-10 | 2027-08-16 | 5 | 24 | Exterior Envelope | Planters at Roof Deck
Phased TCO | C-07-RD-430 | Install Irrigation & Prping & Valves @ Planters - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Planters at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-08-10 | 2027-08-19 | 8 | 11 | Exterior Envelope | Planters at Roof Deck
Phased TCO | C-07-RD-440 | Apply Stucco @ Planters - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Planters at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-08-20 | 2027-08-26 | 5 | 11 | Exterior Envelope | Planters at Roof Deck
Phased TCO | C-07-RD-450 | Paint Stucco @ Planters - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Planters at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-08-27 | 2027-09-02 | 5 | 11 | Exterior Envelope | Planters at Roof Deck
Phased TCO | C-07-RD-370 | Install Perimeter Railing @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Finishes & Flooring at Roof Deck 7th Lvl | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-17 | 10 | 40 | Exterior Envelope | Finishes & Flooring at Roof Deck
Phased TCO | C-07-RD-460 | Fill Soil Mix @ Planters - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Planters at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-10 | 5 | 11 | Exterior Envelope | Planters at Roof Deck
Phased TCO | C-07-RD-470 | Plant Trees & Shrubs @ Planters - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Planters at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-09-13 | 2027-10-01 | 15 | 11 | Exterior Envelope | Planters at Roof Deck
Phased TCO | C-07-RD-310 | Install Pergola with Angled Louvers @ Treatment Area - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Finishes & Flooring at Roof Deck 7th Lvl | TT_Task | TK_NotStart | 2027-10-04 | 2027-10-08 | 5 | 11 | Exterior Envelope | Finishes & Flooring at Roof Deck
Phased TCO | C-07-RD-480 | Install Irrigation Trim @ Planters - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Planters at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-10-04 | 2027-10-05 | 2 | 25 | Exterior Envelope | Planters at Roof Deck
Phased TCO | C-07-RD-490 | Install Lighting @ Planters - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Planters at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-10-06 | 2027-10-08 | 3 | 25 | Exterior Envelope | Planters at Roof Deck
Phased TCO | C-07-RD-320 | Install Wood Decking @ Yoga - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Finishes & Flooring at Roof Deck 7th Lvl | TT_Task | TK_NotStart | 2027-10-11 | 2027-10-20 | 8 | 11 | Exterior Envelope | Finishes & Flooring at Roof Deck
Phased TCO | C-07-RD-330 | Install Privacy Screen @ Treatment Area - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Finishes & Flooring at Roof Deck 7th Lvl | TT_Task | TK_NotStart | 2027-10-11 | 2027-10-12 | 2 | 23 | Exterior Envelope | Finishes & Flooring at Roof Deck
Phased TCO | C-07-RD-340 | Pour-in-Place Rubber Flooring @ Fitness Area - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Finishes & Flooring at Roof Deck 7th Lvl | TT_Task | TK_NotStart | 2027-10-21 | 2027-10-22 | 2 | 11 | Exterior Envelope | Finishes & Flooring at Roof Deck
Phased TCO | C-07-RD-350 | Install Exercise Unit @ Fitness Area - Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Finishes & Flooring at Roof Deck 7th Lvl | TT_Task | TK_NotStart | 2027-10-25 | 2027-10-25 | 1 | 14 | Exterior Envelope | Finishes & Flooring at Roof Deck
Phased TCO | C-07-RD-360 | Install Synthetic Turf @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Finishes & Flooring at Roof Deck 7th Lvl | TT_Task | TK_NotStart | 2027-10-25 | 2027-10-27 | 3 | 11 | Exterior Envelope | Finishes & Flooring at Roof Deck
Phased TCO | C-07-RD-260 | Install Roof Drain Strainers @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Roofing & Planter Walls at Roof Deck at 7th Lvl | TT_Task | TK_NotStart | 2027-10-28 | 2027-10-28 | 1 | 11 | Exterior Envelope | Roofing & Planter Walls at Roof Deck
Phased TCO | C-07-RD-380 | Install FF&Es @ Roof Deck - L7 | no |  | 7 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Outdoor Area at 7th Lvl > Finishes & Flooring at Roof Deck 7th Lvl | TT_Task | TK_NotStart | 2027-10-29 | 2027-11-02 | 3 | 11 | Exterior Envelope | Finishes & Flooring at Roof Deck
Phased TCO | C-08-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L8 | no |  | 8 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-07-27 | 2026-07-28 | 2 | 63 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-08-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L8 | no |  | 8 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 8th to 14th Lvl | TT_Task | TK_NotStart | 2026-10-30 | 2026-11-04 | 4 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 8th to
Phased TCO | C-08-EX-230 | Install Balcony Glass Railings @ Balconies - L8 | no |  | 8 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 8th to 14th Lvl | TT_Task | TK_NotStart | 2026-12-21 | 2026-12-28 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 8th to
Phased TCO | C-09-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L9 | no |  | 9 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-08-04 | 2026-08-05 | 2 | 62 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-09-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L9 | no |  | 9 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 8th to 14th Lvl | TT_Task | TK_NotStart | 2026-11-05 | 2026-11-10 | 4 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 8th to
Phased TCO | C-09-EX-230 | Install Balcony Glass Railings @ Balconies - L9 | no |  | 9 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 8th to 14th Lvl | TT_Task | TK_NotStart | 2026-12-29 | 2027-01-05 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 8th to
Phased TCO | C-10-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L10 | no |  | 10 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-08-11 | 2026-08-12 | 2 | 62 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-10-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L10 | no |  | 10 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 8th to 14th Lvl | TT_Task | TK_NotStart | 2026-11-11 | 2026-11-16 | 4 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 8th to
Phased TCO | C-10-EX-230 | Install Balcony Glass Railings @ Balconies - L10 | no |  | 10 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 8th to 14th Lvl | TT_Task | TK_NotStart | 2027-01-06 | 2027-01-12 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 8th to
Phased TCO | C-11-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L11 | no |  | 11 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-08-18 | 2026-08-19 | 2 | 62 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-11-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L11 | no |  | 11 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 8th to 14th Lvl | TT_Task | TK_NotStart | 2026-11-17 | 2026-11-20 | 4 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 8th to
Phased TCO | C-11-EX-230 | Install Balcony Glass Railings @ Balconies - L11 | no |  | 11 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 8th to 14th Lvl | TT_Task | TK_NotStart | 2027-01-13 | 2027-01-19 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 8th to
Phased TCO | C-12-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L12 | no |  | 12 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-08-25 | 2026-08-26 | 2 | 62 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-12-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L12 | no |  | 12 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 8th to 14th Lvl | TT_Task | TK_NotStart | 2026-11-23 | 2026-11-30 | 4 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 8th to
Phased TCO | C-12-EX-230 | Install Balcony Glass Railings @ Balconies - L12 | no |  | 12 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 8th to 14th Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-01-26 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 8th to
Phased TCO | C-14-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L14 | no |  | 14 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-09-01 | 2026-09-02 | 2 | 62 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-14-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L14 | no |  | 14 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 8th to 14th Lvl | TT_Task | TK_NotStart | 2026-12-01 | 2026-12-04 | 4 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 8th to
Phased TCO | C-14-EX-230 | Install Balcony Glass Railings @ Balconies - L14 | no |  | 14 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 8th to 14th Lvl | TT_Task | TK_NotStart | 2027-01-27 | 2027-02-02 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 8th to
Phased TCO | C-15-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L15 | no |  | 15 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-09-09 | 2026-09-10 | 2 | 62 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-15-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L15 | no |  | 15 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 15th to 20th Lvl | TT_Task | TK_NotStart | 2026-12-15 | 2026-12-18 | 4 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 15th to
Phased TCO | C-15-EX-230 | Install Balcony Glass Railings @ Balconies - L15 | no |  | 15 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 15th to 20th Lvl | TT_Task | TK_NotStart | 2027-02-03 | 2027-02-09 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 15th to
Phased TCO | C-16-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L16 | no |  | 16 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-09-16 | 2026-09-17 | 2 | 62 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-16-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L16 | no |  | 16 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 15th to 20th Lvl | TT_Task | TK_NotStart | 2026-12-21 | 2026-12-24 | 4 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 15th to
Phased TCO | C-16-EX-230 | Install Balcony Glass Railings @ Balconies - L16 | no |  | 16 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 15th to 20th Lvl | TT_Task | TK_NotStart | 2027-02-10 | 2027-02-16 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 15th to
Phased TCO | C-17-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L17 | no |  | 17 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-09-23 | 2026-09-24 | 2 | 62 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-17-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L17 | no |  | 17 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 15th to 20th Lvl | TT_Task | TK_NotStart | 2026-12-28 | 2026-12-31 | 4 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 15th to
Phased TCO | C-17-EX-230 | Install Balcony Glass Railings @ Balconies - L17 | no |  | 17 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 15th to 20th Lvl | TT_Task | TK_NotStart | 2027-02-17 | 2027-02-23 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 15th to
Phased TCO | C-18-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L18 | no |  | 18 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-09-30 | 2026-10-01 | 2 | 62 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-18-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L18 | no |  | 18 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 15th to 20th Lvl | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-07 | 4 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 15th to
Phased TCO | C-18-EX-230 | Install Balcony Glass Railings @ Balconies - L18 | no |  | 18 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 15th to 20th Lvl | TT_Task | TK_NotStart | 2027-02-24 | 2027-03-02 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 15th to
Phased TCO | C-19-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L19 | no |  | 19 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-10-07 | 2026-10-08 | 2 | 62 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-19-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L19 | no |  | 19 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 15th to 20th Lvl | TT_Task | TK_NotStart | 2027-01-08 | 2027-01-13 | 4 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 15th to
Phased TCO | C-19-EX-230 | Install Balcony Glass Railings @ Balconies - L19 | no |  | 19 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 15th to 20th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-09 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 15th to
Phased TCO | C-20-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L20 | no |  | 20 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-10-14 | 2026-10-15 | 2 | 62 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-20-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L20 | no |  | 20 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 15th to 20th Lvl | TT_Task | TK_NotStart | 2027-01-14 | 2027-01-19 | 4 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 15th to
Phased TCO | C-20-EX-230 | Install Balcony Glass Railings @ Balconies - L20 | no |  | 20 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 15th to 20th Lvl | TT_Task | TK_NotStart | 2027-03-10 | 2027-03-16 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 15th to
Phased TCO | C-21-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L21 | no |  | 21 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-10-21 | 2026-10-22 | 2 | 62 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-21-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L21 | no |  | 21 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 21st to 26th Lvl | TT_Task | TK_NotStart | 2027-01-28 | 2027-02-02 | 4 | 189 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 21st to
Phased TCO | C-21-EX-230 | Install Balcony Glass Railings @ Balconies - L21 | no |  | 21 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 21st to 26th Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-23 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 21st to
Phased TCO | C-22-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L22 | no |  | 22 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-10-28 | 2026-10-29 | 2 | 62 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-22-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L22 | no |  | 22 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 21st to 26th Lvl | TT_Task | TK_NotStart | 2027-02-03 | 2027-02-08 | 4 | 189 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 21st to
Phased TCO | C-22-EX-230 | Install Balcony Glass Railings @ Balconies - L22 | no |  | 22 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 21st to 26th Lvl | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-30 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 21st to
Phased TCO | C-23-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L23 | no |  | 23 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-11-04 | 2026-11-05 | 2 | 62 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-23-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L23 | no |  | 23 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 21st to 26th Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-12 | 4 | 189 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 21st to
Phased TCO | C-23-EX-230 | Install Balcony Glass Railings @ Balconies - L23 | no |  | 23 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 21st to 26th Lvl | TT_Task | TK_NotStart | 2027-03-31 | 2027-04-06 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 21st to
Phased TCO | C-24-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L24 | no |  | 24 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-11-11 | 2026-11-12 | 2 | 62 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-24-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L24 | no |  | 24 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 21st to 26th Lvl | TT_Task | TK_NotStart | 2027-02-15 | 2027-02-18 | 4 | 189 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 21st to
Phased TCO | C-24-EX-230 | Install Balcony Glass Railings @ Balconies - L24 | no |  | 24 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 21st to 26th Lvl | TT_Task | TK_NotStart | 2027-04-07 | 2027-04-13 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 21st to
Phased TCO | C-25-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L25 | no |  | 25 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-11-18 | 2026-11-19 | 2 | 62 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-25-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L25 | no |  | 25 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 21st to 26th Lvl | TT_Task | TK_NotStart | 2027-02-19 | 2027-02-24 | 4 | 189 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 21st to
Phased TCO | C-25-EX-230 | Install Balcony Glass Railings @ Balconies - L25 | no |  | 25 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 21st to 26th Lvl | TT_Task | TK_NotStart | 2027-04-14 | 2027-04-20 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 21st to
Phased TCO | C-26-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L26 | no |  | 26 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-11-25 | 2026-11-30 | 2 | 62 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-26-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L26 | no |  | 26 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 21st to 26th Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-03-02 | 4 | 189 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 21st to
Phased TCO | C-26-EX-230 | Install Balcony Glass Railings @ Balconies - L26 | no |  | 26 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 21st to 26th Lvl | TT_Task | TK_NotStart | 2027-04-21 | 2027-04-27 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 21st to
Phased TCO | C-27-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L27 | no |  | 27 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-12-04 | 2026-12-07 | 2 | 62 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-27-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L27 | no |  | 27 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 27th to 32nd Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-16 | 4 | 183 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 27th to
Phased TCO | C-27-EX-230 | Install Balcony Glass Railings @ Balconies - L27 | no |  | 27 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 27th to 32nd Lvl | TT_Task | TK_NotStart | 2027-04-28 | 2027-05-04 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 27th to
Phased TCO | C-28-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L28 | no |  | 28 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-12-11 | 2026-12-14 | 2 | 62 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-28-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L28 | no |  | 28 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 27th to 32nd Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-22 | 4 | 183 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 27th to
Phased TCO | C-28-EX-230 | Install Balcony Glass Railings @ Balconies - L28 | no |  | 28 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 27th to 32nd Lvl | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-11 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 27th to
Phased TCO | C-29-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L29 | no |  | 29 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-12-21 | 2026-12-22 | 2 | 61 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-29-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L29 | no |  | 29 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 27th to 32nd Lvl | TT_Task | TK_NotStart | 2027-03-23 | 2027-03-26 | 4 | 183 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 27th to
Phased TCO | C-29-EX-230 | Install Balcony Glass Railings @ Balconies - L29 | no |  | 29 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 27th to 32nd Lvl | TT_Task | TK_NotStart | 2027-05-12 | 2027-05-18 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 27th to
Phased TCO | C-30-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L30 | no |  | 30 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2026-12-29 | 2026-12-30 | 2 | 61 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-30-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L30 | no |  | 30 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 27th to 32nd Lvl | TT_Task | TK_NotStart | 2027-03-29 | 2027-04-01 | 4 | 183 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 27th to
Phased TCO | C-30-EX-230 | Install Balcony Glass Railings @ Balconies - L30 | no |  | 30 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 27th to 32nd Lvl | TT_Task | TK_NotStart | 2027-05-19 | 2027-05-25 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 27th to
Phased TCO | C-31-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L31 | no |  | 31 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2027-01-07 | 2027-01-08 | 2 | 60 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-31-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L31 | no |  | 31 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 27th to 32nd Lvl | TT_Task | TK_NotStart | 2027-04-02 | 2027-04-07 | 4 | 183 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 27th to
Phased TCO | C-31-EX-230 | Install Balcony Glass Railings @ Balconies - L31 | no |  | 31 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 27th to 32nd Lvl | TT_Task | TK_NotStart | 2027-05-26 | 2027-06-02 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 27th to
Phased TCO | C-32-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L32 | no |  | 32 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2027-01-18 | 2027-01-19 | 2 | 58 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-32-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L32 | no |  | 32 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 27th to 32nd Lvl | TT_Task | TK_NotStart | 2027-04-08 | 2027-04-13 | 4 | 183 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 27th to
Phased TCO | C-32-EX-230 | Install Balcony Glass Railings @ Balconies - L32 | no |  | 32 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 27th to 32nd Lvl | TT_Task | TK_NotStart | 2027-06-03 | 2027-06-09 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 27th to
Phased TCO | C-33-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L33 | no |  | 33 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2027-01-20 | 2027-01-21 | 2 | 61 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-33-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L33 | no |  | 33 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 33rd to Roof Lvl | TT_Task | TK_NotStart | 2027-04-14 | 2027-04-19 | 4 | 183 | Exterior Envelope | Exterior Balconies & Elevations (Drops)
Phased TCO | C-33-EX-230 | Install Balcony Glass Railings @ Balconies - L33 | no |  | 33 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 33rd to Roof Lvl | TT_Task | TK_NotStart | 2027-06-10 | 2027-06-16 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops)
Phased TCO | C-34-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L34 | no |  | 34 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2027-01-28 | 2027-01-29 | 2 | 60 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-34-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L34 | no |  | 34 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 33rd to Roof Lvl | TT_Task | TK_NotStart | 2027-04-20 | 2027-04-23 | 4 | 183 | Exterior Envelope | Exterior Balconies & Elevations (Drops)
Phased TCO | C-34-EX-230 | Install Balcony Glass Railings @ Balconies - L34 | no |  | 34 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 33rd to Roof Lvl | TT_Task | TK_NotStart | 2027-06-17 | 2027-06-23 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops)
Phased TCO | C-35-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ L35 | no |  | 35 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2027-02-05 | 2027-02-08 | 2 | 59 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-35-EX-210 | Apply Waterproofing & Install Tiles @ Balconies - L35 | no |  | 35 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 33rd to Roof Lvl | TT_Task | TK_NotStart | 2027-04-26 | 2027-04-29 | 4 | 183 | Exterior Envelope | Exterior Balconies & Elevations (Drops)
Phased TCO | C-35-EX-230 | Install Balcony Glass Railings @ Balconies - L35 | no |  | 35 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 33rd to Roof Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-30 | 5 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops)
Phased TCO | C-36-MP-160 | Install MEP Inserts & Sleeves at Elevated Slab @ 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-01-15 | 2027-01-18 | 2 | 0 | Building Structure | Structure at Lower
Phased TCO | C-36-MP-500 | Prep Pad & Set Mech DOUA-1 Unit @ Mech Eqp Rm #3611 - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Mech Eqp Rm #3611 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-01-22 | 2027-01-26 | 3 | 0 | Exterior Envelope | MEP Work at Mech Eqp Rm #3611
Phased TCO | C-36-ST-200 | Lay Parapet Walls @ 36th Pool Level | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-02-04 | 2027-02-10 | 5 | 72 | Building Structure | Structure at Lower
Phased TCO | C-36-ST-210 | F/R/P Planter Walls @ 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Lower & 36th Pool Lvl | TT_Task | TK_NotStart | 2027-02-11 | 2027-02-24 | 10 | 72 | Building Structure | Structure at Lower
Phased TCO | C-36-ST-300 | Remove Reshoring & Grind/Prep Ceiling Slab @ 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Shoring Removals & Slab Preparation | TT_Task | TK_NotStart | 2027-02-16 | 2027-02-16 | 1 | 101 | Building Structure | Shoring Removals & Slab Preparation
Phased TCO | C-36-MP-510 | Prep Room & Housekeeping Pads to Receive Eqp @ Mech Eqp Rm #3611 - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Mech Eqp Rm #3611 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-02-26 | 2027-03-11 | 10 | 98 | Exterior Envelope | MEP Work at Mech Eqp Rm #3611
Phased TCO | C-36-MP-520 | Install Stands/ & Supports for Mech Eqp & Piping @ Mech Eqp Rm #3611 - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Mech Eqp Rm #3611 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-03-12 | 2027-03-18 | 5 | 98 | Exterior Envelope | MEP Work at Mech Eqp Rm #3611
Phased TCO | C-36-MP-530 | Set Mech CWP-1 & CWP-2 & CTP-1 & CTP-2 & EFs Eqp @ Mech Eqp Rm #3611 - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Mech Eqp Rm #3611 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-03-19 | 2027-03-25 | 5 | 98 | Exterior Envelope | MEP Work at Mech Eqp Rm #3611
Phased TCO | C-36-MP-540 | Install Mech Heat Pump & VFDs @ Mech Eqp Rm #3611 - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Mech Eqp Rm #3611 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-03-31 | 4 | 112 | Exterior Envelope | MEP Work at Mech Eqp Rm #3611
Phased TCO | C-36-MP-550 | Install Mech Eqp Refrig Piping & Ductwork @ Mech Eqp Rm #3611 - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Mech Eqp Rm #3611 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-05-06 | 30 | 98 | Exterior Envelope | MEP Work at Mech Eqp Rm #3611
Phased TCO | C-36-RF-200 | Install AD Drain Bases @ Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Pool Deck at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-03-31 | 2027-04-02 | 3 | 48 | Exterior Envelope | Roofing at Pool Deck
Phased TCO | C-36-RF-210 | Install Alum Trellises Base Plates @ Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Pool Deck at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-04-05 | 2027-04-07 | 3 | 48 | Exterior Envelope | Roofing at Pool Deck
Phased TCO | C-36-RF-220 | Apply Waterproofing Membrane @ Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Pool Deck at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-04-08 | 2027-04-16 | 7 | 48 | Exterior Envelope | Roofing at Pool Deck
Phased TCO | C-36-RF-230 | Pour Light Weight Concrete Topping @ Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Pool Deck at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-04-19 | 2027-04-28 | 8 | 48 | Exterior Envelope | Roofing at Pool Deck
Phased TCO | C-36-MP-560 | Install Electrical for Mech Eqp @ Mech Eqp Rm #3611 - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Mech Eqp Rm #3611 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-04-21 | 2027-05-11 | 15 | 98 | Exterior Envelope | MEP Work at Mech Eqp Rm #3611
Phased TCO | C-36-PD-300 | Install Drainage @ Planters - Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Planters at Pool Deck - 36th Pool Lvl | TT_Task | TK_NotStart | 2027-04-29 | 2027-05-14 | 12 | 151 | Exterior Envelope | Planters at Pool Deck
Phased TCO | C-36-PD-800 | Install Plumbing Rough @ Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > MEP Work at Pool Deck at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-04-29 | 2027-05-19 | 15 | 119 | Exterior Envelope | MEP Work at Pool Deck
Phased TCO | C-36-RF-240 | Install Roof Drain Strainers @ Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Pool Deck at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-04-29 | 2027-04-30 | 2 | 48 | Exterior Envelope | Roofing at Pool Deck
Phased TCO | C-36-PD-310 | Apply Waterproofing Membrane @ Planters - Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Planters at Pool Deck - 36th Pool Lvl | TT_Task | TK_NotStart | 2027-05-17 | 2027-05-26 | 8 | 151 | Exterior Envelope | Planters at Pool Deck
Phased TCO | C-36-PL-200 | Install MEP Rough @ Swim Spa Eqp Rm #3610 - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-05-20 | 2027-06-17 | 20 | 119 | Exterior Envelope | Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602
Phased TCO | C-36-PD-320 | Install Electrical Rough @ Planters - Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Planters at Pool Deck - 36th Pool Lvl | TT_Task | TK_NotStart | 2027-05-27 | 2027-06-07 | 7 | 186 | Exterior Envelope | Planters at Pool Deck
Phased TCO | C-36-PD-330 | Install Irrigation Piping & Valves @ Planters - Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Planters at Pool Deck - 36th Pool Lvl | TT_Task | TK_NotStart | 2027-05-27 | 2027-06-10 | 10 | 151 | Exterior Envelope | Planters at Pool Deck
Phased TCO | C-36-LB-FN-100 | Hang Drywall @ Elev Lobby & Corr - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > Interior Finishes at Elev Lobby at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-10 | 2027-06-11 | 2 | 103 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby
Phased TCO | C-36-LB-FN-120 | Frame GWB Drop Ceiling @ Elev Lobby & Corr - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > Interior Finishes at Elev Lobby at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-10 | 2027-06-11 | 2 | 100 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby
Phased TCO | C-36-PD-340 | Apply Stucco @ Planters - Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Planters at Pool Deck - 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-11 | 2027-06-28 | 12 | 151 | Exterior Envelope | Planters at Pool Deck
Phased TCO | C-36-LB-FN-110 | Tape & Finish Drywall @ Elev Lobby & Corr - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > Interior Finishes at Elev Lobby at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-14 | 2027-06-14 | 1 | 103 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby
Phased TCO | C-36-LB-MP-210 | Install Mech Heat Pump @ Elev Lobby - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > MEP Eqp & Trim at Elev Lobby & MEP Rooms at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-14 | 2027-06-16 | 3 | 100 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & MEP Rooms
Phased TCO | C-36-LB-FN-130 | Install Trash Chute @ Corr - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > Interior Finishes at Elev Lobby at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-15 | 2027-06-15 | 1 | 103 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby
Phased TCO | C-36-LB-MP-200 | Install Elect & Low Voltage Panels @ Telecom/Elect Rm #3601- L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > MEP Eqp & Trim at Elev Lobby & MEP Rooms at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-15 | 2027-07-06 | 15 | 122 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & MEP Rooms
Phased TCO | C-36-LB-FN-140 | Hang/Tape/Finish GWB Drop Ceiling @ Elev Lobby & Corr - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > Interior Finishes at Elev Lobby at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-17 | 2027-06-18 | 2 | 100 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby
Phased TCO | C-36-PL-210 | Apply Waterproofing Membrane @ Swim Spa Eqp Rm #3610 - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-18 | 2027-06-23 | 4 | 119 | Exterior Envelope | Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602
Phased TCO | C-36-LB-FN-150 | Paint Drywall & GWB Ceilings @ Elev Lobby & Corr - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > Interior Finishes at Elev Lobby at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-21 | 2027-06-22 | 2 | 100 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby
Phased TCO | C-36-LB-FN-160 | Install Interior Signage @ Elev Lobby & Corr - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > Interior Finishes at Elev Lobby at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-23 | 2027-06-23 | 1 | 136 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby
Phased TCO | C-36-LB-FN-170 | Install Flooring & Base @ Elev Lobby & Corr - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > Interior Finishes at Elev Lobby at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-23 | 2027-06-25 | 3 | 134 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby
Phased TCO | C-36-LB-MP-220 | Install HVAC Trim @ Elev Lobby - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > MEP Eqp & Trim at Elev Lobby & MEP Rooms at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-23 | 2027-06-28 | 4 | 131 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & MEP Rooms
Phased TCO | C-36-PL-220 | Install Pool Equipment Curbs & Housekeeping Pads @ Swim Spa Eqp Rm #3610 - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-29 | 4 | 119 | Exterior Envelope | Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602
Phased TCO | C-36-LB-MP-240 | Install FP Sprinkler Heads @ Elev Lobby - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > MEP Eqp & Trim at Elev Lobby & MEP Rooms at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-06-30 | 2 | 131 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & MEP Rooms
Phased TCO | C-36-PD-350 | Paint Stucco @ Planters - Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Planters at Pool Deck - 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-29 | 2027-07-06 | 5 | 151 | Exterior Envelope | Planters at Pool Deck
Phased TCO | C-36-PL-230 | Setup Pool Equipment @ Swim Spa Eqp Rm #3610 - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-06-30 | 2027-07-28 | 20 | 119 | Exterior Envelope | Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602
Phased TCO | C-36-LB-MP-230 | Install FA & Low Voltage Devices @ Elev Lobby - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > MEP Eqp & Trim at Elev Lobby & MEP Rooms at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-07-07 | 2027-07-08 | 2 | 122 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & MEP Rooms
Phased TCO | C-36-PD-360 | Fill Soil Mix @ Planters - Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Planters at Pool Deck - 36th Pool Lvl | TT_Task | TK_NotStart | 2027-07-07 | 2027-07-13 | 5 | 166 | Exterior Envelope | Planters at Pool Deck
Phased TCO | C-36-LB-MP-250 | Install Electrical Power Trim @ Elev Lobby - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > MEP Eqp & Trim at Elev Lobby & MEP Rooms at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-12 | 2 | 122 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & MEP Rooms
Phased TCO | C-36-LB-MP-260 | Install Light Fixtures @ Elev Lobby - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > MEP Eqp & Trim at Elev Lobby & MEP Rooms at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-07-12 | 2027-07-14 | 3 | 122 | Interior MEPs & Finishes | MEP Eqp & Trim at Elev Lobby & MEP Rooms
Phased TCO | C-36-PD-370 | Plant Trees & Shrubs @ Planters - Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Planters at Pool Deck - 36th Pool Lvl | TT_Task | TK_NotStart | 2027-07-14 | 2027-08-10 | 20 | 166 | Exterior Envelope | Planters at Pool Deck
Phased TCO | C-36-LB-FN-180 | Touch-up Paint @ Elev Lobby & Corr - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > Interior Finishes at Elev Lobby at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-15 | 1 | 122 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby
Phased TCO | C-36-PL-240 | Install Plumbing Piping & Connections @ Swim Spa Eqp Rm #3610 - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-08-11 | 20 | 119 | Exterior Envelope | Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602
Phased TCO | C-36-LB-FN-190 | Final Cleanup @ Elev Lobby & Corr - L36 | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Interior MEPs & Finishes > Interior MEPs & Finishes at 36th Pool Lvl > Interior MEPs & Finishes Elev Lobby at 36th Pool Lvl > Interior Finishes at Elev Lobby at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-07-16 | 2027-07-16 | 1 | 122 | Interior MEPs & Finishes | Interior Finishes at Elev Lobby
Phased TCO | C-36-PL-260 | Electrical Connections @ Swim Spa Eqp Rm #3610 - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-06 | 2027-08-13 | 6 | 163 | Exterior Envelope | Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602
Phased TCO | C-36-PL-100 | Apply Waterproofing @ Pool - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Swim Spa Pool Work at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-10 | 2027-08-13 | 4 | 119 | Exterior Envelope | Swim Spa Pool Work
Phased TCO | C-36-PD-380 | Install Irrigation Trim @ Planters - Outdoor Rooftop - Roof Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Planters at Pool Deck - 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-11 | 2027-08-12 | 2 | 174 | Exterior Envelope | Planters at Pool Deck
Phased TCO | C-36-PL-250 | Install Gas Detection @ Swim Spa Eqp Rm #3610 - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602 at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-12 | 2027-08-18 | 5 | 160 | Exterior Envelope | Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602
Phased TCO | C-36-PD-390 | Install Lighting @ Planters - Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Planters at Pool Deck - 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-13 | 2027-08-19 | 5 | 174 | Exterior Envelope | Planters at Pool Deck
Phased TCO | C-36-JC-400 | Apply Waterproofing @ Jacuzzi - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Jacuzzi Work at 36th Pool Lvl > Jacuzzi at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-16 | 2027-08-17 | 2 | 159 | Exterior Envelope | Jacuzzi
Phased TCO | C-36-PL-110 | Install Trench Drains & Grated Gutters @ Pool - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Swim Spa Pool Work at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-16 | 2027-08-19 | 4 | 119 | Exterior Envelope | Swim Spa Pool Work
Phased TCO | C-36-JC-410 | Install Jacuzzi Surface Finish @ Jacuzzi - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Jacuzzi Work at 36th Pool Lvl > Jacuzzi at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-24 | 5 | 159 | Exterior Envelope | Jacuzzi
Phased TCO | C-36-PL-270 | Pool Equipment Installation Complete @ Swim Spa Eqp Rm #3610 - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602 at 36th Pool Lvl | TT_FinMile | TK_NotStart | 2027-08-18 | 2027-08-18 | 0 | 160 | Exterior Envelope | Pool Equipment at Swim Spa & Eqp Rms #3610 & #3602
Phased TCO | C-36-PD-100 | Lay Tile Pavers @ Pool Deck - 36th pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Pool Deck Finishes at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-20 | 2027-09-10 | 15 | 119 | Exterior Envelope | Pool Deck Finishes
Phased TCO | C-36-PL-130 | Install Pool Surface Finish @ Pool - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Swim Spa Pool Work at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-20 | 2027-09-02 | 10 | 149 | Exterior Envelope | Swim Spa Pool Work
Phased TCO | C-36-JC-420 | Install Grab Rails & Accessories @ Jacuzzi - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Jacuzzi Work at 36th Pool Lvl > Jacuzzi at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-23 | 2027-08-24 | 2 | 159 | Exterior Envelope | Jacuzzi
Phased TCO | C-36-JC-430 | Install Light Fixtures @ Jacuzzi - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Jacuzzi Work at 36th Pool Lvl > Jacuzzi at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-08-23 | 2027-08-23 | 1 | 160 | Exterior Envelope | Jacuzzi
Phased TCO | C-36-PD-110 | Erect Pergola (Trellis) Structure & Finishes @ Pool Deck - 36th pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Pool Deck Finishes at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-13 | 2027-10-01 | 15 | 119 | Exterior Envelope | Pool Deck Finishes
Phased TCO | C-36-PD-120 | Install Plunge Bucket Shower & Pergola @ Pool Deck - 36th pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Pool Deck Finishes at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-13 | 2027-09-16 | 4 | 155 | Exterior Envelope | Pool Deck Finishes
Phased TCO | C-36-PD-810 | Install Electrical & Low Voltage Rough @ Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > MEP Work at Pool Deck at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-13 | 2027-09-24 | 10 | 132 | Exterior Envelope | MEP Work at Pool Deck
Phased TCO | C-36-PL-150 | Install Pool Handrails & Grab Rails & Accessories @ Pool - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Swim Spa Pool Work at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-13 | 2027-09-14 | 2 | 142 | Exterior Envelope | Swim Spa Pool Work
Phased TCO | C-36-PL-140 | Install Light Fixtures @ Pool - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Swim Spa Pool Work at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-09-27 | 2027-09-28 | 2 | 132 | Exterior Envelope | Swim Spa Pool Work
Phased TCO | C-36-PD-130 | Install Perimeter Glass Railings @ Pool Deck - 36th pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Pool Deck Finishes at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-10-04 | 2027-10-15 | 10 | 119 | Exterior Envelope | Pool Deck Finishes
Phased TCO | C-36-PD-140 | Install Signage @ Pool Deck - 36th pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Pool Deck Finishes at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-10-04 | 2027-10-06 | 3 | 141 | Exterior Envelope | Pool Deck Finishes
Phased TCO | C-36-PD-150 | Install Bar Millwork & Appliances/Eqp @ Pool Bar - Pool Deck - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Pool Deck Finishes at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-10-04 | 2027-10-15 | 10 | 134 | Exterior Envelope | Pool Deck Finishes
Phased TCO | C-36-PD-160 | Install Greenscreen Metal Trellis Along Face of N. Walls @ Pool Deck - 36th pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Pool Deck Finishes at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-10-04 | 2027-10-13 | 8 | 136 | Exterior Envelope | Pool Deck Finishes
Phased TCO | C-36-PD-170 | Install Light Fixtures & Power Trim @ Pool Deck - 36th pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Pool Deck Finishes at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-10-18 | 2027-10-21 | 4 | 128 | Exterior Envelope | Pool Deck Finishes
Phased TCO | C-36-PL-700 | Fill Pool @ Pool - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Swim Spa Startup & Certification at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-10-18 | 2027-10-19 | 2 | 119 | Exterior Envelope | Swim Spa Startup & Certification
Phased TCO | C-36-JC-900 | Fill Jacuzzi @ Jacuzzi - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Jacuzzi Work at 36th Pool Lvl > Jacuzzi Startup at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-10-20 | 2027-10-20 | 1 | 120 | Exterior Envelope | Jacuzzi Startup
Phased TCO | C-36-PL-710 | Start-up Pool Equipment @ Pool - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Swim Spa Startup & Certification at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-10-20 | 2027-10-21 | 2 | 119 | Exterior Envelope | Swim Spa Startup & Certification
Phased TCO | C-36-JC-910 | Start-up Jacuzzi Equipment @ Jacuzzi - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Jacuzzi Work at 36th Pool Lvl > Jacuzzi Startup at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-10-21 | 2027-10-22 | 2 | 120 | Exterior Envelope | Jacuzzi Startup
Phased TCO | C-36-PD-180 | Install FA & Low Voltage Devices @ Pool Deck - 36th pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Pool Deck Finishes at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-10-22 | 2027-10-25 | 2 | 128 | Exterior Envelope | Pool Deck Finishes
Phased TCO | C-36-PL-720 | Balance & Test Pool Water @ Pool - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Swim Spa Startup & Certification at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-10-22 | 2027-10-26 | 3 | 119 | Exterior Envelope | Swim Spa Startup & Certification
Phased TCO | C-36-JC-920 | Balance & Test Jacuzzi Water @ Jacuzzi - 36th Pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Jacuzzi Work at 36th Pool Lvl > Jacuzzi Startup at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-10-25 | 2027-10-25 | 1 | 120 | Exterior Envelope | Jacuzzi Startup
Phased TCO | C-36-PD-190 | Install FF&Es @ Pool Deck - 36th pool Lvl | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Pool Deck Finishes at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-10-26 | 2027-10-27 | 2 | 128 | Exterior Envelope | Pool Deck Finishes
Phased TCO | C-36-PL-730 | Dept. of Health Inspection & Certification of Pool & Jacuzzi | no |  | 36 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Outdoor MEPs & Finishes at 7th & 36th Pool Lvl > Pool & Pool Deck at 36th Pool Lvl > Swim Spa Pool at 36th Pool Level > Swim Spa Startup & Certification at 36th Pool Lvl | TT_Task | TK_NotStart | 2027-10-27 | 2027-11-09 | 10 | 119 | Exterior Envelope | Swim Spa Startup & Certification
Phased TCO | C-37-ST-200 | Lay Parapet Walls @ Roof Level | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Building Structure > Building Superstructure > Structure at Roof Lvl | TT_Task | TK_NotStart | 2027-02-09 | 2027-02-17 | 7 | 0 | Building Structure | Structure at Roof Lvl
Phased TCO | C-37-RF-200 | Install Roof Drain Bases @ Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Roof Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-02-26 | 2 | 0 | Exterior Envelope | Roofing at Roof Lvl
Phased TCO | C-37-MP-100 | Install Roof Stands & Supports for Roof Mech Eqp @ East Mech Eqp Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at East Mech Eqp Area at Roof Lvl | TT_Task | TK_NotStart | 2027-03-01 | 2027-03-08 | 6 | 0 | Exterior Envelope | MEP Work at East Mech Eqp Area at Roof Lvl
Phased TCO | C-37-MP-300 | Install Roof Stands & Supports & Pedestals for CT-1 & CT-2 & Piping @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Task | TK_NotStart | 2027-03-09 | 2027-03-16 | 6 | 0 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Phased TCO | C-37-MP-310 | Set Isolators & Support Rails @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-23 | 5 | 12 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Phased TCO | C-37-RF-210 | Pour Light Weight Concrete @ Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Roof Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-25 | 7 | 0 | Exterior Envelope | Roofing at Roof Lvl
Phased TCO | C-37-RF-220 | Apply Single Ply Roofing Membrane & Flashing & Trim @ Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Roof Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-04-08 | 10 | 0 | Exterior Envelope | Roofing at Roof Lvl
Phased TCO | C-37-MP-320 | Set Cooling Towers CT-1 & CT-2 @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-13 | 3 | 0 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Phased TCO | C-37-RF-230 | Install Roof Drain Strainers @ Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Roof Lvl | TT_Task | TK_NotStart | 2027-04-09 | 2027-04-09 | 1 | 61 | Exterior Envelope | Roofing at Roof Lvl
Phased TCO | C-37-MP-110 | Set Mech DOAU-2 on Curbs @ East Mech Eqp Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at East Mech Eqp Area at Roof Lvl | TT_Task | TK_NotStart | 2027-04-12 | 2027-04-15 | 4 | 0 | Exterior Envelope | MEP Work at East Mech Eqp Area at Roof Lvl
Phased TCO | C-37-MP-330 | Install Mech Eqp Refrig Piping @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Task | TK_NotStart | 2027-04-14 | 2027-06-02 | 35 | 74 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Phased TCO | C-37-MP-220 | Install Mech Eqp Refrig Piping & Ductwork @ East Mech Eqp Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at East Mech Eqp Area at Roof Lvl | TT_Task | TK_NotStart | 2027-04-16 | 2027-05-20 | 25 | 88 | Exterior Envelope | MEP Work at East Mech Eqp Area at Roof Lvl
Phased TCO | C-37-MP-230 | Install Mech CUs on Walls @ East Mech Eqp Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at East Mech Eqp Area at Roof Lvl | TT_Task | TK_NotStart | 2027-04-16 | 2027-04-26 | 7 | 91 | Exterior Envelope | MEP Work at East Mech Eqp Area at Roof Lvl
Phased TCO | C-37-MP-240 | Set Stair Pressurization Fan SPF-01-02 @ East Mech Eqp Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at East Mech Eqp Area at Roof Lvl | TT_Task | TK_NotStart | 2027-04-16 | 2027-04-20 | 3 | 98 | Exterior Envelope | MEP Work at East Mech Eqp Area at Roof Lvl
Phased TCO | C-37-MP-260 | Install Mech VFDs @ East Mech Eqp Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at East Mech Eqp Area at Roof Lvl | TT_Task | TK_NotStart | 2027-04-21 | 2027-04-22 | 2 | 98 | Exterior Envelope | MEP Work at East Mech Eqp Area at Roof Lvl
Phased TCO | C-37-MP-270 | Install Electrical for Mech Eqp @ East Mech Eqp Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at East Mech Eqp Area at Roof Lvl | TT_Task | TK_NotStart | 2027-04-28 | 2027-05-25 | 20 | 88 | Exterior Envelope | MEP Work at East Mech Eqp Area at Roof Lvl
Phased TCO | C-37-MP-280 | Install FPL Stacked M/U Air Intake Duct @ East Mech Eqp Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at East Mech Eqp Area at Roof Lvl | TT_Task | TK_NotStart | 2027-04-30 | 2027-05-10 | 7 | 98 | Exterior Envelope | MEP Work at East Mech Eqp Area at Roof Lvl
Phased TCO | C-37-MP-340 | Install Electrical for Mech Eqp @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Task | TK_NotStart | 2027-05-17 | 2027-06-07 | 15 | 74 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Phased TCO | C-37-MP-350 | Erect Ladders and Platforms @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Rsrc | TK_NotStart | 2027-06-08 | 2027-06-14 | 5 | 74 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Phased TCO | C-37-MP-600 | Prepare Room to Receive MEP Eqp @ Boiler Rm #3701 | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Boiler Rm #3702 at Roof Lvl | TT_Task | TK_NotStart | 2027-06-14 | 2027-07-12 | 20 | 115 | Exterior Envelope | MEP Work at Boiler Rm #3702 at Roof Lvl
Phased TCO | C-37-MP-360 | Check Fan Rotation @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Rsrc | TK_NotStart | 2027-06-15 | 2027-06-15 | 1 | 74 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Phased TCO | C-37-MP-370 | Secure & Start Fill of Mech System @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Rsrc | TK_NotStart | 2027-06-16 | 2027-06-18 | 3 | 74 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Phased TCO | C-37-MP-380 | Confirm Operational Status of CW Pumps @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Rsrc | TK_NotStart | 2027-06-21 | 2027-06-22 | 2 | 74 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Phased TCO | C-37-MP-390 | Start Water Circulation @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Rsrc | TK_NotStart | 2027-06-23 | 2027-06-24 | 2 | 74 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Phased TCO | C-37-MP-400 | Start CT1-1 & CT-2 Flushing @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Rsrc | TK_NotStart | 2027-06-25 | 2027-07-06 | 7 | 74 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Phased TCO | C-37-MP-410 | Run Cooling Tower @ Cooling Towers Area - Roof Lvl | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at West Cooling Towers Area at Roof Lvl | TT_Rsrc | TK_NotStart | 2027-07-07 | 2027-07-13 | 5 | 74 | Exterior Envelope | MEP Work at West Cooling Towers Area at Roof Lvl
Phased TCO | C-37-MP-610 | F/R/P Boiler Pad @ Boiler Rm #3701 | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Boiler Rm #3702 at Roof Lvl | TT_Task | TK_NotStart | 2027-07-13 | 2027-07-14 | 2 | 115 | Exterior Envelope | MEP Work at Boiler Rm #3702 at Roof Lvl
Phased TCO | C-37-MP-620 | Install Floor Drain (FD) Base @ Boiler Rm #3701 | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Boiler Rm #3702 at Roof Lvl | TT_Task | TK_NotStart | 2027-07-15 | 2027-07-15 | 1 | 115 | Exterior Envelope | MEP Work at Boiler Rm #3702 at Roof Lvl
Phased TCO | C-37-MP-630 | Apply Waterproofing @ Boiler Rm #3701 | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Boiler Rm #3702 at Roof Lvl | TT_Task | TK_NotStart | 2027-07-16 | 2027-07-19 | 2 | 115 | Exterior Envelope | MEP Work at Boiler Rm #3702 at Roof Lvl
Phased TCO | C-37-MP-640 | Setup & Connect Boiler @ Boiler Rm #3701 | no |  | 37 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Boiler Rm #3702 at Roof Lvl | TT_Task | TK_NotStart | 2027-07-20 | 2027-08-16 | 20 | 115 | Exterior Envelope | MEP Work at Boiler Rm #3702 at Roof Lvl
Phased TCO | C-38-RF-200 | Install Roof Drain Bases @ Upper Roof Lvl | no |  | 38 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Upper Roof Lvl | TT_Task | TK_NotStart | 2027-02-24 | 2027-02-24 | 1 | 0 | Exterior Envelope | Roofing at Upper Roof Lvl
Phased TCO | C-38-MP-100 | Install Roof Stands & Supports for Roof Mech Eqp @ Upper Roof Lvl | no |  | 38 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Upper Roof Lvl | TT_Task | TK_NotStart | 2027-02-25 | 2027-03-02 | 4 | 55 | Exterior Envelope | MEP Work at Upper Roof Lvl
Phased TCO | C-38-RF-210 | Pour Light Weight Concrete @ Upper Roof Lvl | no |  | 38 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Upper Roof Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-05 | 3 | 55 | Exterior Envelope | Roofing at Upper Roof Lvl
Phased TCO | C-38-RF-220 | Apply Single Ply Roofing Membrane & Flashing & Trim @ Upper Roof Lvl | no |  | 38 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Upper Roof Lvl | TT_Task | TK_NotStart | 2027-03-08 | 2027-03-12 | 5 | 55 | Exterior Envelope | Roofing at Upper Roof Lvl
Phased TCO | C-38-MP-110 | Install Mech VRV-CUs @ Upper Roof Lvl | no |  | 38 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Upper Roof Lvl | TT_Task | TK_NotStart | 2027-03-15 | 2027-03-19 | 5 | 94 | Exterior Envelope | MEP Work at Upper Roof Lvl
Phased TCO | C-38-RF-230 | Install Roof Drain Strainers @ Upper Roof Lvl | no |  | 38 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > Roofing at Roofs > Roofing at Upper Roof Lvl | TT_Task | TK_NotStart | 2027-03-15 | 2027-03-15 | 1 | 79 | Exterior Envelope | Roofing at Upper Roof Lvl
Phased TCO | C-38-MP-130 | Set Stair Pressurization Fan SPF-02-02 @ Upper Roof Lvl | no |  | 38 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Upper Roof Lvl | TT_Task | TK_NotStart | 2027-03-22 | 2027-03-25 | 4 | 94 | Exterior Envelope | MEP Work at Upper Roof Lvl
Phased TCO | C-38-MP-140 | Set Mech Fans SVF-01-01 & SVF-01-02 @ Upper Roof Lvl | no |  | 38 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Upper Roof Lvl | TT_Task | TK_NotStart | 2027-03-26 | 2027-03-31 | 4 | 94 | Exterior Envelope | MEP Work at Upper Roof Lvl
Phased TCO | C-38-MP-150 | Set Mech Fans SEF-01 & TEF-01 @ Upper Roof Lvl | no |  | 38 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Upper Roof Lvl | TT_Task | TK_NotStart | 2027-04-01 | 2027-04-06 | 4 | 94 | Exterior Envelope | MEP Work at Upper Roof Lvl
Phased TCO | C-38-MP-160 | Install Mech Eqp Refrig Piping & Ductwork @ Upper Roof Lvl | no |  | 38 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Upper Roof Lvl | TT_Task | TK_NotStart | 2027-04-07 | 2027-05-11 | 25 | 94 | Exterior Envelope | MEP Work at Upper Roof Lvl
Phased TCO | C-38-MP-170 | Install Electrical for Mech Eqp @ Upper Roof Lvl | no |  | 38 | has a level but matches no band rule | CONSTRUCTION > Exterior Envelope > MEPs & Eqp Work at Roofs > MEP Work at Upper Roof Lvl | TT_Task | TK_NotStart | 2027-05-04 | 2027-05-17 | 10 | 94 | Exterior Envelope | MEP Work at Upper Roof Lvl
Phased TCO | C-SU-130 | City of Miami Dryrun Approval (by Owner) | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > MOT Permitting & Setup | TT_Task | TK_NotStart | 2025-10-22 | 2026-05-26 | 150 | 44 | Site Utilities | MOT Permitting & Setup
Phased TCO | MOB-1000 | Mobilization & Temp Facilities | no |  |  | no level in the Activity ID | CONSTRUCTION > Mobilization & Site Preparation | TT_Task | TK_NotStart | 2025-10-22 | 2025-10-30 | 7 | 0 | Mobilization & Site Preparation | Mobilization & Site Preparation
Phased TCO | PR-MS-100 | Notice-to-Proceed (N.T.P.) | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Contract Milestones | TT_Mile | TK_NotStart | 2025-10-22 | 2025-10-22 | 0 | 0 | Contract Milestones | Contract Milestones
Phased TCO | PR-PS-800 | Overall Project Duration (N.T.P. to T.C.O.) | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Project Duration Summary (Cal Days) | TT_LOE | TK_NotStart | 2025-10-22 | 2028-03-20 | 881 | 0 | Project Duration Summary (Cal Days) | Project Duration Summary (Cal Days)
Phased TCO | PR-PS-900 | Overall Project Duration (N.T.P. to C.O.) | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Project Duration Summary (Cal Days) | TT_LOE | TK_NotStart | 2025-10-22 | 2028-05-21 | 943 | 0 | Project Duration Summary (Cal Days) | Project Duration Summary (Cal Days)
Phased TCO | S-0-100 | Start of Submittals | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 | TT_Mile | TK_NotStart | 2025-10-22 | 2025-10-22 | 0 | 6 |  | SUBMITTALS & PROCUREMENT1
Phased TCO | MOB-1010 | Prepare Site & Building Pad | no |  |  | no level in the Activity ID | CONSTRUCTION > Mobilization & Site Preparation | TT_Task | TK_NotStart | 2025-10-31 | 2025-11-10 | 7 | 0 | Mobilization & Site Preparation | Mobilization & Site Preparation
Phased TCO | S-03-100 | Prep & Submit Concrete Mix | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 03 - Concrete > Concrete Mix | TT_Task | TK_NotStart | 2025-11-19 | 2025-12-04 | 10 | 21 | DIV 03 - Concrete | Concrete Mix
Phased TCO | S-03-200 | Prep & Submit Rebar | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 03 - Concrete > Rebar | TT_Task | TK_NotStart | 2025-11-19 | 2025-12-04 | 10 | 6 | DIV 03 - Concrete | Rebar
Phased TCO | S-03-300 | Prep & Submit Formwork | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 03 - Concrete > Formwork | TT_Task | TK_NotStart | 2025-11-19 | 2025-12-04 | 10 | 21 | DIV 03 - Concrete | Formwork
Phased TCO | S-04-100 | Prep & Submit CMU | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 04 - Masonry > CMU | TT_Task | TK_NotStart | 2025-11-19 | 2025-12-04 | 10 | 176 | DIV 04 - Masonry | CMU
Phased TCO | S-26-200 | Prep & Submit Switchgear | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Switchgear | TT_Task | TK_NotStart | 2025-11-19 | 2026-01-19 | 40 | 118 | DIV 26 - Electrical | Switchgear
Phased TCO | R-03-100 | Review & Approve Concrete Mix | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 03 - Concrete > Concrete Mix | TT_Task | TK_NotStart | 2025-12-05 | 2025-12-18 | 10 | 21 | DIV 03 - Concrete | Concrete Mix
Phased TCO | R-03-200 | Review & Approve Rebar | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 03 - Concrete > Rebar | TT_Task | TK_NotStart | 2025-12-05 | 2025-12-18 | 10 | 6 | DIV 03 - Concrete | Rebar
Phased TCO | R-03-300 | Review & Approve Formwork | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 03 - Concrete > Formwork | TT_Task | TK_NotStart | 2025-12-05 | 2025-12-18 | 10 | 21 | DIV 03 - Concrete | Formwork
Phased TCO | R-04-100 | Review & Approve CMU | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 04 - Masonry > CMU | TT_Task | TK_NotStart | 2025-12-05 | 2025-12-18 | 10 | 176 | DIV 04 - Masonry | CMU
Phased TCO | S-03-400 | Prep & Submit Post Tension Calculations - L2 | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 03 - Concrete > Post Tension | TT_Task | TK_NotStart | 2025-12-05 | 2026-01-05 | 20 | 16 | DIV 03 - Concrete | Post Tension
Phased TCO | S-23-100 | Prep & Submit Mechanical SD | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > Mechanical SD | TT_Task | TK_NotStart | 2025-12-05 | 2026-02-02 | 40 | 159 | DIV 23 - HVAC | Mechanical SD
Phased TCO | F-03-200 | Fab & Deliver Rebar | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 03 - Concrete > Rebar | TT_Task | TK_NotStart | 2025-12-19 | 2026-01-12 | 15 | 6 | DIV 03 - Concrete | Rebar
Phased TCO | S-26-100 | Prep & Submit Electrical SD | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Electrical SD | TT_Task | TK_NotStart | 2025-12-19 | 2026-02-16 | 40 | 147 | DIV 26 - Electrical | Electrical SD
Phased TCO | R-03-400 | Review & Approve Post Tension Calculations - L2 | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 03 - Concrete > Post Tension | TT_Task | TK_NotStart | 2026-01-06 | 2026-01-19 | 10 | 16 | DIV 03 - Concrete | Post Tension
Phased TCO | S-08-100 | Prep & Submit Windows & Storefronts | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Windows & Storefronts | TT_Task | TK_NotStart | 2026-01-06 | 2026-02-16 | 30 | 87 | DIV 08 - Openings | Windows & Storefronts
Phased TCO | S-22-100 | Prep & Submit Plumbing SD | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Plumbing SD | TT_Task | TK_NotStart | 2026-01-06 | 2026-03-02 | 40 | 222 | DIV 22 - Plumbing | Plumbing SD
Phased TCO | S-26-300 | Prep & Submit Generator | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Generator | TT_Task | TK_NotStart | 2026-01-06 | 2026-02-16 | 30 | 188 | DIV 26 - Electrical | Generator
Phased TCO | S-26-400 | Prep & Submit Electrical Panels | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Electrical Panels | TT_Task | TK_NotStart | 2026-01-06 | 2026-03-02 | 40 | 171 | DIV 26 - Electrical | Electrical Panels
Phased TCO | F-03-400 | Fab & Deliver Post Tension Tendons - L2 | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 03 - Concrete > Post Tension | TT_Task | TK_NotStart | 2026-01-20 | 2026-03-02 | 30 | 16 | DIV 03 - Concrete | Post Tension
Phased TCO | R-26-200 | Review & Approve Switchgear | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Switchgear | TT_Task | TK_NotStart | 2026-01-20 | 2026-02-02 | 10 | 118 | DIV 26 - Electrical | Switchgear
Phased TCO | S-08-200 | Prep & Submit Door Frames | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Door Frames | TT_Task | TK_NotStart | 2026-01-20 | 2026-02-16 | 20 | 185 | DIV 08 - Openings | Door Frames
Phased TCO | S-14-100 | Prep & Submit Elevators | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 14 - Conveying Systems > Elevator | TT_Task | TK_NotStart | 2026-01-20 | 2026-03-16 | 40 | 140 | DIV 14 - Conveying Systems | Elevator
Phased TCO | S-23-200 | Prep & Submit Cooling Towers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > Cooling Towers | TT_Task | TK_NotStart | 2026-01-20 | 2026-03-16 | 40 | 131 | DIV 23 - HVAC | Cooling Towers
Phased TCO | S-23-300 | Prep & Submit DOAUs | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > Rooftop DOAUs | TT_Task | TK_NotStart | 2026-01-20 | 2026-03-16 | 40 | 86 | DIV 23 - HVAC | Rooftop DOAUs
Phased TCO | S-23-400 | Prep & Submit Heat Pumps & ACs & CUs | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > ACs & CUs | TT_Task | TK_NotStart | 2026-01-20 | 2026-03-02 | 30 | 142 | DIV 23 - HVAC | ACs & CUs
Phased TCO | S-23-500 | Prep & Submit VFDs | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > VFDs | TT_Task | TK_NotStart | 2026-01-20 | 2026-03-02 | 30 | 293 | DIV 23 - HVAC | VFDs
Phased TCO | F-26-200 | Fab & Deliver Switchgear | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Switchgear | TT_Task | TK_NotStart | 2026-02-03 | 2026-11-12 | 200 | 118 | DIV 26 - Electrical | Switchgear
Phased TCO | R-23-100 | Review & Approve Mechanical SD | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > Mechanical SD | TT_Task | TK_NotStart | 2026-02-03 | 2026-02-16 | 10 | 159 | DIV 23 - HVAC | Mechanical SD
Phased TCO | R-08-100 | Review & Approve Windows & Storefronts & Revisions | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Windows & Storefronts | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-02 | 10 | 87 | DIV 08 - Openings | Windows & Storefronts
Phased TCO | R-08-200 | Review & Approve Door Frames | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Door Frames | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-02 | 10 | 185 | DIV 08 - Openings | Door Frames
Phased TCO | R-26-100 | Review & Approve Electrical SD | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Electrical SD | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-02 | 10 | 147 | DIV 26 - Electrical | Electrical SD
Phased TCO | R-26-300 | Review & Approve Generator | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Generator | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-02 | 10 | 188 | DIV 26 - Electrical | Generator
Phased TCO | S-08-300 | Prep & Submit Doors | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Doors | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-16 | 20 | 155 | DIV 08 - Openings | Doors
Phased TCO | S-10-400 | Prep & Submit Shower Enclosures | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Shower Enclosures | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-16 | 20 | 158 | DIV 10 - Specialties | Shower Enclosures
Phased TCO | S-14-200 | Prep & Submit Trash Chute | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 14 - Conveying Systems > Trash Chute | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-30 | 30 | 200 | DIV 14 - Conveying Systems | Trash Chute
Phased TCO | S-14-300 | Prep & Submit Car Lifts | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 14 - Conveying Systems > Car Lifts | TT_Task | TK_NotStart | 2026-02-17 | 2026-04-13 | 40 | 233 | DIV 14 - Conveying Systems | Car Lifts
Phased TCO | S-21-100 | Prep & Submit Fire Pump | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 21 - Fire Suppression > Fire Pump | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-30 | 30 | 246 | DIV 21 - Fire Suppression | Fire Pump
Phased TCO | S-21-200 | Prep & Submit Fire Spinkler SD | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 21 - Fire Suppression > Fire Suppression | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-30 | 30 | 244 | DIV 21 - Fire Suppression | Fire Suppression
Phased TCO | S-22-200 | Prep & Submit Domestic Pump | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Domestic Pump | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-16 | 20 | 367 | DIV 22 - Plumbing | Domestic Pump
Phased TCO | S-22-300 | Prep & Submit Plumbing Fixtures | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Plumbing Fixtures | TT_Task | TK_NotStart | 2026-02-17 | 2026-04-27 | 50 | 199 | DIV 22 - Plumbing | Plumbing Fixtures
Phased TCO | S-26-500 | Prep & Submit Light Fixtures | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Light Fixtures | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-30 | 30 | 232 | DIV 26 - Electrical | Light Fixtures
Phased TCO | S-26-600 | Prep & Submit EV Charge Stations | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > EV Charging Stations | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-16 | 20 | 264 | DIV 26 - Electrical | EV Charging Stations
Phased TCO | S-27-100 | Prep & Submit Low Voltage | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 27 - Communications > Low Voltage | TT_Task | TK_NotStart | 2026-02-17 | 2026-04-13 | 40 | 191 | DIV 27 - Communications | Low Voltage
Phased TCO | S-27-200 | Prep & Submit BDA | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 27 - Communications > BDA | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-16 | 20 | 287 | DIV 27 - Communications | BDA
Phased TCO | S-28-100 | Prep & Submit Fire Alarm | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 28 - Electronic Safety & Security > Fire Alarm | TT_Task | TK_NotStart | 2026-02-17 | 2026-04-13 | 40 | 192 | DIV 28 - Electronic Safety & Security | Fire Alarm
Phased TCO | S-33-100 | Prep & Submit Water | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 33 - Utilities > Water | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-30 | 30 | 216 | DIV 33 - Utilities | Water
Phased TCO | S-33-200 | Prep & Submit Drainage | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 33 - Utilities > Drainage | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-30 | 30 | 241 | DIV 33 - Utilities | Drainage
Phased TCO | S-33-300 | Prep & Submit Fire | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 33 - Utilities > Fire | TT_Task | TK_NotStart | 2026-02-17 | 2026-03-30 | 30 | 264 | DIV 33 - Utilities | Fire
Phased TCO | F-08-100 | Fab & Deliver Windows & Storefronts | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Windows & Storefronts | TT_Task | TK_NotStart | 2026-03-03 | 2026-05-26 | 60 | 87 | DIV 08 - Openings | Windows & Storefronts
Phased TCO | F-08-200 | Fab & Deliver Door Frames | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Door Frames | TT_Task | TK_NotStart | 2026-03-03 | 2026-05-11 | 50 | 185 | DIV 08 - Openings | Door Frames
Phased TCO | F-26-300 | Fab & Deliver Generator | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Generator | TT_Task | TK_NotStart | 2026-03-03 | 2026-12-14 | 200 | 188 | DIV 26 - Electrical | Generator
Phased TCO | R-22-100 | Review & Approve Plumbing SD | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Plumbing SD | TT_Task | TK_NotStart | 2026-03-03 | 2026-03-16 | 10 | 222 | DIV 22 - Plumbing | Plumbing SD
Phased TCO | R-23-400 | Review & Approve Heat Pumps & ACs & CUs | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > ACs & CUs | TT_Task | TK_NotStart | 2026-03-03 | 2026-03-16 | 10 | 142 | DIV 23 - HVAC | ACs & CUs
Phased TCO | R-23-500 | Review & Approve VFDs | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > VFDs | TT_Task | TK_NotStart | 2026-03-03 | 2026-03-16 | 10 | 293 | DIV 23 - HVAC | VFDs
Phased TCO | R-26-400 | Review & Approve Electrical Panels | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Electrical Panels | TT_Task | TK_NotStart | 2026-03-03 | 2026-03-16 | 10 | 171 | DIV 26 - Electrical | Electrical Panels
Phased TCO | S-05-100 | Prep & Submit Misc Metals | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 05 - Metals > Misc Metals | TT_Task | TK_NotStart | 2026-03-03 | 2026-04-13 | 30 | 363 | DIV 05 - Metals | Misc Metals
Phased TCO | S-06-200 | Prep & Submit Kitchen Cabinets & Vanities | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 06 - Wood and Plastics > Kitchen Cabinets & Vanities | TT_Task | TK_NotStart | 2026-03-03 | 2026-04-27 | 40 | 126 | DIV 06 - Wood and Plastics | Kitchen Cabinets & Vanities
Phased TCO | C-CR-100 | F/R/P Foundations @ Tower Crane | no |  |  | no level in the Activity ID | CONSTRUCTION > Hoisting Equipment > Tower Crane | TT_Task | TK_NotStart | 2026-03-04 | 2026-03-19 | 12 | 2 | Hoisting Equipment | Tower Crane
Phased TCO | DES-KL-100 | Final Design - Lobby/Kitchen | no |  |  | no level in the Activity ID | SPECIAL DESIGN & PERMITTING > Lobby & Kitchen Design & Permit Revisions | TT_Task | TK_NotStart | 2026-03-11 | 2026-08-27 | 120 | 161 | Lobby & Kitchen Design & Permit Revisions | Lobby & Kitchen Design & Permit Revisions
Phased TCO | F-23-400 | Fab & Deliver Heat Pumps & ACs & CUs | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > ACs & CUs | TT_Task | TK_NotStart | 2026-03-17 | 2026-07-22 | 90 | 142 | DIV 23 - HVAC | ACs & CUs
Phased TCO | F-23-500 | Fab & Deliver VFDs | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > VFDs | TT_Task | TK_NotStart | 2026-03-17 | 2026-07-08 | 80 | 293 | DIV 23 - HVAC | VFDs
Phased TCO | F-26-400 | Fab & Deliver Electrical Panels | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Electrical Panels | TT_Task | TK_NotStart | 2026-03-17 | 2026-10-01 | 140 | 171 | DIV 26 - Electrical | Electrical Panels
Phased TCO | R-08-300 | Review & Approve Doors | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Doors | TT_Task | TK_NotStart | 2026-03-17 | 2026-03-30 | 10 | 155 | DIV 08 - Openings | Doors
Phased TCO | R-10-400 | Review & Approve Shower Enclosures | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Shower Enclosures | TT_Task | TK_NotStart | 2026-03-17 | 2026-03-30 | 10 | 158 | DIV 10 - Specialties | Shower Enclosures
Phased TCO | R-14-100 | Review & Approve Elevators | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 14 - Conveying Systems > Elevator | TT_Task | TK_NotStart | 2026-03-17 | 2026-03-30 | 10 | 140 | DIV 14 - Conveying Systems | Elevator
Phased TCO | R-22-200 | Review & Approve Domestic Pump | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Domestic Pump | TT_Task | TK_NotStart | 2026-03-17 | 2026-03-30 | 10 | 367 | DIV 22 - Plumbing | Domestic Pump
Phased TCO | R-23-200 | Review & Approve Cooling Towers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > Cooling Towers | TT_Task | TK_NotStart | 2026-03-17 | 2026-03-30 | 10 | 131 | DIV 23 - HVAC | Cooling Towers
Phased TCO | R-23-300 | Review & Approve DOAUs | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > Rooftop DOAUs | TT_Task | TK_NotStart | 2026-03-17 | 2026-03-30 | 10 | 86 | DIV 23 - HVAC | Rooftop DOAUs
Phased TCO | R-26-600 | Review & Approve EV Charge Stations | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > EV Charging Stations | TT_Task | TK_NotStart | 2026-03-17 | 2026-03-30 | 10 | 264 | DIV 26 - Electrical | EV Charging Stations
Phased TCO | R-27-200 | Review & Approve BDA | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 27 - Communications > BDA | TT_Task | TK_NotStart | 2026-03-17 | 2026-03-30 | 10 | 287 | DIV 27 - Communications | BDA
Phased TCO | S-05-110 | Prep & Submit Trellises | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 05 - Metals > Trelllises | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-27 | 30 | 398 | DIV 05 - Metals | Trelllises
Phased TCO | S-06-100 | Prep & Submit Millwork (Pool Bar) | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 06 - Wood and Plastics > Millwork (Pool Bar) | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-27 | 30 | 408 | DIV 06 - Wood and Plastics | Millwork (Pool Bar)
Phased TCO | S-07-100 | Prep & Submit Roofing | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 07 - Thermal and Moisture Protection > Roofing | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-27 | 30 | 209 | DIV 07 - Thermal and Moisture Protection | Roofing
Phased TCO | S-08-400 | Prep & Submit Door Hardware | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Door Hardware | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-27 | 30 | 212 | DIV 08 - Openings | Door Hardware
Phased TCO | S-09-100 | Prep & Submit Toilet Tiles | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Toilet Tiles | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-13 | 20 | 152 | DIV 09 - Finishes | Toilet Tiles
Phased TCO | S-09-200 | Prep & Submit LVT Flooring | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > LVT Flooring | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-13 | 20 | 160 | DIV 09 - Finishes | LVT Flooring
Phased TCO | S-09-300 | Prep & Submit Hardscape Pavers - L1 | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Hardscape Pavers - L1 | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-13 | 20 | 414 | DIV 09 - Finishes | Hardscape Pavers - L1
Phased TCO | S-09-400 | Prep & Submit Pool Deck Pavers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Pool Deck Pavers | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-13 | 20 | 393 | DIV 09 - Finishes | Pool Deck Pavers
Phased TCO | S-09-500 | Prep & Submit Wood Deck Flooring | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Wood Deck - L7 | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-13 | 20 | 320 | DIV 09 - Finishes | Wood Deck - L7
Phased TCO | S-10-100 | Prep & Submit Toilet Accessories | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Toilet Accessories | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-13 | 20 | 231 | DIV 10 - Specialties | Toilet Accessories
Phased TCO | S-10-200 | Prep & Submit Toilet Partitions | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Toilet Partitions | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-13 | 20 | 231 | DIV 10 - Specialties | Toilet Partitions
Phased TCO | S-10-300 | Prep & Submit Fire Extinguishers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Fire Extinguishers | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-13 | 20 | 253 | DIV 10 - Specialties | Fire Extinguishers
Phased TCO | S-13-100 | Prep & Submit Swim Spa Pool Eqp | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 13 - Special Construction > Swim Spa Pool | TT_Task | TK_NotStart | 2026-03-17 | 2026-05-26 | 50 | 244 | DIV 13 - Special Construction | Swim Spa Pool
Phased TCO | S-13-200 | Prep & Submit Jacuzzi Eqp | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 13 - Special Construction > Jacuzzi | TT_Task | TK_NotStart | 2026-03-17 | 2026-05-26 | 50 | 379 | DIV 13 - Special Construction | Jacuzzi
Phased TCO | S-22-400 | Prep & Submit Grease Interceptors | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Grease Interceptors | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-27 | 30 | 117 | DIV 22 - Plumbing | Grease Interceptors
Phased TCO | S-22-500 | Prep & Submit Trench Drains | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Trench Drains | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-13 | 20 | 191 | DIV 22 - Plumbing | Trench Drains
Phased TCO | S-22-600 | Prep & Submit Water Heaters | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Heat Heaters | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-13 | 20 | 229 | DIV 22 - Plumbing | Heat Heaters
Phased TCO | S-22-700 | Prep & Submit Boiler | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Boilers | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-27 | 30 | 336 | DIV 22 - Plumbing | Boilers
Phased TCO | S-22-800 | Prep & Submit Backflow Preventer | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Backflow Preventer | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-13 | 20 | 407 | DIV 22 - Plumbing | Backflow Preventer
Phased TCO | S-23-600 | Prep & Submit HVAC Controls | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > HVAC Control | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-27 | 30 | 203 | DIV 23 - HVAC | HVAC Control
Phased TCO | S-23-700 | Prep & Submit Grilles & Diffusers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > Grilles & Diffusers | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-27 | 30 | 213 | DIV 23 - HVAC | Grilles & Diffusers
Phased TCO | S-26-700 | Prep & Submit Site Lighting | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Site Lighting | TT_Task | TK_NotStart | 2026-03-17 | 2026-04-27 | 30 | 436 | DIV 26 - Electrical | Site Lighting
Phased TCO | C-CR-200 | Erect Crane @ Tower Crane | no |  |  | no level in the Activity ID | CONSTRUCTION > Hoisting Equipment > Tower Crane | TT_Task | TK_NotStart | 2026-03-20 | 2026-03-26 | 5 | 268 | Hoisting Equipment | Tower Crane
Phased TCO | PR-MS-500 | Subsurface Structure Complete | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2026-03-23 | 2026-03-23 | 0 | 0 | Interim Milestones | Interim Milestones
Phased TCO | F-08-300 | Fab & Deliver Doors | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Doors | TT_Task | TK_NotStart | 2026-03-31 | 2026-06-23 | 60 | 155 | DIV 08 - Openings | Doors
Phased TCO | F-10-400 | Fab & Deliver Shower Enclosures | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Shower Enclosures | TT_Task | TK_NotStart | 2026-03-31 | 2026-07-08 | 70 | 158 | DIV 10 - Specialties | Shower Enclosures
Phased TCO | F-14-100 | Fab & Deliver Elevators | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 14 - Conveying Systems > Elevator | TT_Task | TK_NotStart | 2026-03-31 | 2026-11-12 | 160 | 140 | DIV 14 - Conveying Systems | Elevator
Phased TCO | F-22-200 | Fab & Deliver Domestic Pump | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Domestic Pump | TT_Task | TK_NotStart | 2026-03-31 | 2026-07-22 | 80 | 367 | DIV 22 - Plumbing | Domestic Pump
Phased TCO | F-23-200 | Fab & Deliver Cooling Towers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > Cooling Towers | TT_Task | TK_NotStart | 2026-03-31 | 2026-10-01 | 130 | 131 | DIV 23 - HVAC | Cooling Towers
Phased TCO | F-23-300 | Fab & Deliver DOAUs | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > Rooftop DOAUs | TT_Task | TK_NotStart | 2026-03-31 | 2026-09-17 | 120 | 86 | DIV 23 - HVAC | Rooftop DOAUs
Phased TCO | F-26-600 | Fab & Deliver EV Charge Stations | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > EV Charging Stations | TT_Task | TK_NotStart | 2026-03-31 | 2026-07-22 | 80 | 264 | DIV 26 - Electrical | EV Charging Stations
Phased TCO | F-27-200 | Fab & Deliver BDA System | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 27 - Communications > BDA | TT_Task | TK_NotStart | 2026-03-31 | 2026-07-08 | 70 | 287 | DIV 27 - Communications | BDA
Phased TCO | R-14-200 | Review & Approve Trash Chute | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 14 - Conveying Systems > Trash Chute | TT_Task | TK_NotStart | 2026-03-31 | 2026-04-13 | 10 | 200 | DIV 14 - Conveying Systems | Trash Chute
Phased TCO | R-21-100 | Review & Approve Fire Pump | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 21 - Fire Suppression > Fire Pump | TT_Task | TK_NotStart | 2026-03-31 | 2026-04-13 | 10 | 246 | DIV 21 - Fire Suppression | Fire Pump
Phased TCO | R-21-200 | Review & Approve Fire Spinkler SD | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 21 - Fire Suppression > Fire Suppression | TT_Task | TK_NotStart | 2026-03-31 | 2026-04-13 | 10 | 244 | DIV 21 - Fire Suppression | Fire Suppression
Phased TCO | R-26-500 | Review & Approve Light Fixtures | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Light Fixtures | TT_Task | TK_NotStart | 2026-03-31 | 2026-04-13 | 10 | 232 | DIV 26 - Electrical | Light Fixtures
Phased TCO | R-33-100 | Review & Approve Water | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 33 - Utilities > Water | TT_Task | TK_NotStart | 2026-03-31 | 2026-04-13 | 10 | 216 | DIV 33 - Utilities | Water
Phased TCO | R-33-200 | Review & Approve Drainage | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 33 - Utilities > Drainage | TT_Task | TK_NotStart | 2026-03-31 | 2026-04-13 | 10 | 241 | DIV 33 - Utilities | Drainage
Phased TCO | R-33-300 | Review & Approve Fire | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 33 - Utilities > Fire | TT_Task | TK_NotStart | 2026-03-31 | 2026-04-13 | 10 | 264 | DIV 33 - Utilities | Fire
Phased TCO | F-14-200 | Fab & Deliver Trash Chute | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 14 - Conveying Systems > Trash Chute | TT_Task | TK_NotStart | 2026-04-14 | 2026-09-02 | 100 | 200 | DIV 14 - Conveying Systems | Trash Chute
Phased TCO | F-21-100 | Fab & Deliver Fire Pump | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 21 - Fire Suppression > Fire Pump | TT_Task | TK_NotStart | 2026-04-14 | 2026-08-05 | 80 | 246 | DIV 21 - Fire Suppression | Fire Pump
Phased TCO | F-21-1200 | Fab & Deliver Fire Spinkler Heads | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 21 - Fire Suppression > Fire Suppression | TT_Task | TK_NotStart | 2026-04-14 | 2026-07-08 | 60 | 244 | DIV 21 - Fire Suppression | Fire Suppression
Phased TCO | F-26-500 | Fab & Deliver Light Fixtures | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Light Fixtures | TT_Task | TK_NotStart | 2026-04-14 | 2026-07-22 | 70 | 232 | DIV 26 - Electrical | Light Fixtures
Phased TCO | F-33-100 | Fab & Deliver Water Piping | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 33 - Utilities > Water | TT_Task | TK_NotStart | 2026-04-14 | 2026-06-16 | 45 | 216 | DIV 33 - Utilities | Water
Phased TCO | F-33-200 | Fab & Deliver Drainage Piping & Structures | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 33 - Utilities > Drainage | TT_Task | TK_NotStart | 2026-04-14 | 2026-06-16 | 45 | 241 | DIV 33 - Utilities | Drainage
Phased TCO | F-33-300 | Fab & Deliver Fire Lines | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 33 - Utilities > Fire | TT_Task | TK_NotStart | 2026-04-14 | 2026-06-16 | 45 | 264 | DIV 33 - Utilities | Fire
Phased TCO | R-05-100 | Review & Approve Misc Metals | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 05 - Metals > Misc Metals | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 363 | DIV 05 - Metals | Misc Metals
Phased TCO | R-09-100 | Review & Approve Toilet Tiles | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Toilet Tiles | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 152 | DIV 09 - Finishes | Toilet Tiles
Phased TCO | R-09-200 | Review & Approve LVT Flooring | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > LVT Flooring | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 160 | DIV 09 - Finishes | LVT Flooring
Phased TCO | R-09-300 | Review & Approve Hardscape Pavers - L1 | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Hardscape Pavers - L1 | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 414 | DIV 09 - Finishes | Hardscape Pavers - L1
Phased TCO | R-09-400 | Review & Approve Pool Deck Pavers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Pool Deck Pavers | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 393 | DIV 09 - Finishes | Pool Deck Pavers
Phased TCO | R-09-500 | Review & Approve Wood Deck Flooring | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Wood Deck - L7 | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 320 | DIV 09 - Finishes | Wood Deck - L7
Phased TCO | R-10-100 | Review & Approve Toilet Accessories | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Toilet Accessories | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 231 | DIV 10 - Specialties | Toilet Accessories
Phased TCO | R-10-200 | Review & Approve Toilet Partitions | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Toilet Partitions | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 231 | DIV 10 - Specialties | Toilet Partitions
Phased TCO | R-10-300 | Review & Approve Fire Extinguishers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Fire Extinguishers | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 253 | DIV 10 - Specialties | Fire Extinguishers
Phased TCO | R-14-300 | Review & Approve Car Lifts | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 14 - Conveying Systems > Car Lifts | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 233 | DIV 14 - Conveying Systems | Car Lifts
Phased TCO | R-22-500 | Review & Approve Trench Drains | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Trench Drains | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 191 | DIV 22 - Plumbing | Trench Drains
Phased TCO | R-22-600 | Review & Approve Water Heaters | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Heat Heaters | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 229 | DIV 22 - Plumbing | Heat Heaters
Phased TCO | R-22-800 | Review & Approve Backflow Preventer | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Backflow Preventer | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 407 | DIV 22 - Plumbing | Backflow Preventer
Phased TCO | R-27-100 | Review & Approve Low Voltage | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 27 - Communications > Low Voltage | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 191 | DIV 27 - Communications | Low Voltage
Phased TCO | R-28-100 | Review & Approve Fire Alarm | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 28 - Electronic Safety & Security > Fire Alarm | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 192 | DIV 28 - Electronic Safety & Security | Fire Alarm
Phased TCO | S-09-600 | Prep & Submit Paint | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Paint | TT_Task | TK_NotStart | 2026-04-14 | 2026-04-27 | 10 | 188 | DIV 09 - Finishes | Paint
Phased TCO | S-11-100 | Prep & Submit Kitchen Appliances | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 11 - Equipment > Appliances | TT_Task | TK_NotStart | 2026-04-14 | 2026-05-26 | 30 | 183 | DIV 11 - Equipment | Appliances
Phased TCO | S-32-100 | Prep & Submit Irrigation | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 32 - Exterior Site Improvements > Irrigation | TT_Task | TK_NotStart | 2026-04-14 | 2026-05-26 | 30 | 267 | DIV 32 - Exterior Site Improvements | Irrigation
Phased TCO | S-32-200 | Prep & Submit Landscaping | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 32 - Exterior Site Improvements > Landscape | TT_Task | TK_NotStart | 2026-04-14 | 2026-05-26 | 30 | 270 | DIV 32 - Exterior Site Improvements | Landscape
Phased TCO | S-32-300 | Prep & Submit Parking Signage | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 32 - Exterior Site Improvements > Parking Signage | TT_Task | TK_NotStart | 2026-04-14 | 2026-05-26 | 30 | 315 | DIV 32 - Exterior Site Improvements | Parking Signage
Phased TCO | F-05-100 | Fab & Deliver Misc Metals | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 05 - Metals > Misc Metals | TT_Task | TK_NotStart | 2026-04-28 | 2026-07-22 | 60 | 363 | DIV 05 - Metals | Misc Metals
Phased TCO | F-09-100 | Fab & Deliver Toilet Tiles | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Toilet Tiles | TT_Task | TK_NotStart | 2026-04-28 | 2026-07-08 | 50 | 152 | DIV 09 - Finishes | Toilet Tiles
Phased TCO | F-09-200 | Fab & Deliver LVT Flooring | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > LVT Flooring | TT_Task | TK_NotStart | 2026-04-28 | 2026-07-08 | 50 | 160 | DIV 09 - Finishes | LVT Flooring
Phased TCO | F-09-300 | Fab & Deliver Hardscape Pavers - L1 | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Hardscape Pavers - L1 | TT_Task | TK_NotStart | 2026-04-28 | 2026-07-22 | 60 | 414 | DIV 09 - Finishes | Hardscape Pavers - L1
Phased TCO | F-09-400 | Fab & Deliver Pool Deck Pavers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Pool Deck Pavers | TT_Task | TK_NotStart | 2026-04-28 | 2026-07-22 | 60 | 393 | DIV 09 - Finishes | Pool Deck Pavers
Phased TCO | F-09-500 | Fab & Deliver Wood Deck Flooring | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Wood Deck - L7 | TT_Task | TK_NotStart | 2026-04-28 | 2026-07-22 | 60 | 320 | DIV 09 - Finishes | Wood Deck - L7
Phased TCO | F-10-100 | Fab & Deliver Toilet Accessories | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Toilet Accessories | TT_Task | TK_NotStart | 2026-04-28 | 2026-07-22 | 60 | 231 | DIV 10 - Specialties | Toilet Accessories
Phased TCO | F-10-200 | Fab & Deliver Toilet Partitions | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Toilet Partitions | TT_Task | TK_NotStart | 2026-04-28 | 2026-07-22 | 60 | 231 | DIV 10 - Specialties | Toilet Partitions
Phased TCO | F-10-300 | Fab & Deliver Fire Extinguishers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 10 - Specialties > Fire Extinguishers | TT_Task | TK_NotStart | 2026-04-28 | 2026-06-23 | 40 | 253 | DIV 10 - Specialties | Fire Extinguishers
Phased TCO | F-14-300 | Fab & Deliver Car Lifts | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 14 - Conveying Systems > Car Lifts | TT_Task | TK_NotStart | 2026-04-28 | 2026-10-15 | 120 | 233 | DIV 14 - Conveying Systems | Car Lifts
Phased TCO | F-22-500 | Fab & Deliver Trench Drains | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Trench Drains | TT_Task | TK_NotStart | 2026-04-28 | 2026-07-22 | 60 | 191 | DIV 22 - Plumbing | Trench Drains
Phased TCO | F-22-600 | Fab & Deliver Water Heaters | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Heat Heaters | TT_Task | TK_NotStart | 2026-04-28 | 2026-07-22 | 60 | 229 | DIV 22 - Plumbing | Heat Heaters
Phased TCO | F-22-800 | Fab & Deliver Backflow Preventer | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Backflow Preventer | TT_Task | TK_NotStart | 2026-04-28 | 2026-07-22 | 60 | 407 | DIV 22 - Plumbing | Backflow Preventer
Phased TCO | F-27-100 | Fab & Deliver Low Voltage Panels & Devices | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 27 - Communications > Low Voltage | TT_Task | TK_NotStart | 2026-04-28 | 2026-09-02 | 90 | 191 | DIV 27 - Communications | Low Voltage
Phased TCO | F-28-100 | Fab & Deliver Fire Alarm Command Panel (FACP) | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 28 - Electronic Safety & Security > Fire Alarm | TT_Task | TK_NotStart | 2026-04-28 | 2026-10-15 | 120 | 192 | DIV 28 - Electronic Safety & Security | Fire Alarm
Phased TCO | F-28-110 | Fab & Deliver Fire Alarm Devices | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 28 - Electronic Safety & Security > Fire Alarm | TT_Task | TK_NotStart | 2026-04-28 | 2026-08-19 | 80 | 214 | DIV 28 - Electronic Safety & Security | Fire Alarm
Phased TCO | R-05-110 | Review & Approve Trellises | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 05 - Metals > Trelllises | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 398 | DIV 05 - Metals | Trelllises
Phased TCO | R-06-100 | Review & Approve Millwork (Pool Bar) | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 06 - Wood and Plastics > Millwork (Pool Bar) | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 408 | DIV 06 - Wood and Plastics | Millwork (Pool Bar)
Phased TCO | R-06-200 | Review & Approve Kitchen Cabinets & Vanities | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 06 - Wood and Plastics > Kitchen Cabinets & Vanities | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 126 | DIV 06 - Wood and Plastics | Kitchen Cabinets & Vanities
Phased TCO | R-07-100 | Review & Approve Roofing | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 07 - Thermal and Moisture Protection > Roofing | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 209 | DIV 07 - Thermal and Moisture Protection | Roofing
Phased TCO | R-08-400 | Review & Approve Door Hardware | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Door Hardware | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 212 | DIV 08 - Openings | Door Hardware
Phased TCO | R-09-600 | Review & Approve Paint | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 09 - Finishes > Paint | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 188 | DIV 09 - Finishes | Paint
Phased TCO | R-22-300 | Review & Approve Plumbing Fixtures | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Plumbing Fixtures | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 199 | DIV 22 - Plumbing | Plumbing Fixtures
Phased TCO | R-22-400 | Review & Approve Grease Interceptors | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Grease Interceptors | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 117 | DIV 22 - Plumbing | Grease Interceptors
Phased TCO | R-22-700 | Review & Approve Boiler | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Boilers | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 336 | DIV 22 - Plumbing | Boilers
Phased TCO | R-23-600 | Review & Approve HVAC Controls | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > HVAC Control | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 203 | DIV 23 - HVAC | HVAC Control
Phased TCO | R-23-700 | Review & Approve Grilles & Diffusers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > Grilles & Diffusers | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 213 | DIV 23 - HVAC | Grilles & Diffusers
Phased TCO | R-26-700 | Review & Approve Site Lighting | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Site Lighting | TT_Task | TK_NotStart | 2026-04-28 | 2026-05-11 | 10 | 436 | DIV 26 - Electrical | Site Lighting
Phased TCO | F-05-110 | Fab & Deliver Trellises | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 05 - Metals > Trelllises | TT_Task | TK_NotStart | 2026-05-12 | 2026-08-05 | 60 | 398 | DIV 05 - Metals | Trelllises
Phased TCO | F-06-100 | Fab & Deliver Millwork (Pool Bar) | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 06 - Wood and Plastics > Millwork (Pool Bar) | TT_Task | TK_NotStart | 2026-05-12 | 2026-09-02 | 80 | 408 | DIV 06 - Wood and Plastics | Millwork (Pool Bar)
Phased TCO | F-06-200 | Fab & Deliver Kitchen Cabinets & Vanities | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 06 - Wood and Plastics > Kitchen Cabinets & Vanities | TT_Task | TK_NotStart | 2026-05-12 | 2026-08-19 | 70 | 126 | DIV 06 - Wood and Plastics | Kitchen Cabinets & Vanities
Phased TCO | F-07-100 | Fab & Deliver Roofing | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 07 - Thermal and Moisture Protection > Roofing | TT_Task | TK_NotStart | 2026-05-12 | 2026-06-23 | 30 | 209 | DIV 07 - Thermal and Moisture Protection | Roofing
Phased TCO | F-08-400 | Fab & Deliver Door Hardware | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 08 - Openings > Door Hardware | TT_Task | TK_NotStart | 2026-05-12 | 2026-08-19 | 70 | 212 | DIV 08 - Openings | Door Hardware
Phased TCO | F-22-300 | Fab & Deliver Plumbing Fixtures | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Plumbing Fixtures | TT_Task | TK_NotStart | 2026-05-12 | 2026-09-02 | 80 | 199 | DIV 22 - Plumbing | Plumbing Fixtures
Phased TCO | F-22-400 | Fab & Deliver Grease Interceptors | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Grease Interceptors | TT_Task | TK_NotStart | 2026-05-12 | 2026-09-02 | 80 | 117 | DIV 22 - Plumbing | Grease Interceptors
Phased TCO | F-22-700 | Fab & Deliver Boiler | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 22 - Plumbing > Boilers | TT_Task | TK_NotStart | 2026-05-12 | 2026-09-02 | 80 | 336 | DIV 22 - Plumbing | Boilers
Phased TCO | F-23-600 | Fab & Deliver HVAC Controls | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > HVAC Control | TT_Task | TK_NotStart | 2026-05-12 | 2026-09-02 | 80 | 203 | DIV 23 - HVAC | HVAC Control
Phased TCO | F-23-700 | Fab & Deliver Grilles & Diffusers | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 23 - HVAC > Grilles & Diffusers | TT_Task | TK_NotStart | 2026-05-12 | 2026-08-19 | 70 | 213 | DIV 23 - HVAC | Grilles & Diffusers
Phased TCO | F-26-700 | Fab & Deliver Site Lighting | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 26 - Electrical > Site Lighting | TT_Task | TK_NotStart | 2026-05-12 | 2026-08-05 | 60 | 436 | DIV 26 - Electrical | Site Lighting
Phased TCO | C-BH-100 | Install Buckhoists - 1st Lift | no |  |  | no level in the Activity ID | CONSTRUCTION > Hoisting Equipment > Buckhoists | TT_Task | TK_NotStart | 2026-05-14 | 2026-05-28 | 10 | 11 | Hoisting Equipment | Buckhoists
Phased TCO | C-SU-100 | Prep & Submit WM Drawings for Permiitting | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > MOT Permitting & Setup | TT_Task | TK_NotStart | 2026-05-27 | 2026-08-26 | 65 | 44 | Site Utilities | MOT Permitting & Setup
Phased TCO | R-11-100 | Review & Approve Kitchen Appliances | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 11 - Equipment > Appliances | TT_Task | TK_NotStart | 2026-05-27 | 2026-06-09 | 10 | 183 | DIV 11 - Equipment | Appliances
Phased TCO | R-13-100 | Review & Approve Swim Spa Pool Eqp | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 13 - Special Construction > Swim Spa Pool | TT_Task | TK_NotStart | 2026-05-27 | 2026-06-09 | 10 | 244 | DIV 13 - Special Construction | Swim Spa Pool
Phased TCO | R-13-200 | Review & Approve Jacuzzi Eqp | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 13 - Special Construction > Jacuzzi | TT_Task | TK_NotStart | 2026-05-27 | 2026-06-09 | 10 | 379 | DIV 13 - Special Construction | Jacuzzi
Phased TCO | R-32-100 | Review & Approve Irrigation | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 32 - Exterior Site Improvements > Irrigation | TT_Task | TK_NotStart | 2026-05-27 | 2026-06-09 | 10 | 267 | DIV 32 - Exterior Site Improvements | Irrigation
Phased TCO | R-32-200 | Review & Approve Landscaping | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 32 - Exterior Site Improvements > Landscape | TT_Task | TK_NotStart | 2026-05-27 | 2026-06-09 | 10 | 270 | DIV 32 - Exterior Site Improvements | Landscape
Phased TCO | R-32-300 | Review & Approve Parking Signage | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 32 - Exterior Site Improvements > Parking Signage | TT_Task | TK_NotStart | 2026-05-27 | 2026-06-09 | 10 | 315 | DIV 32 - Exterior Site Improvements | Parking Signage
Phased TCO | F-11-100 | Fab & Deliver Kitchen Appliances | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 11 - Equipment > Appliances | TT_Task | TK_NotStart | 2026-06-10 | 2026-10-01 | 80 | 183 | DIV 11 - Equipment | Appliances
Phased TCO | F-13-100 | Fab & Deliver Swim Spa Pool Eqp | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 13 - Special Construction > Swim Spa Pool | TT_Task | TK_NotStart | 2026-06-10 | 2026-10-29 | 100 | 244 | DIV 13 - Special Construction | Swim Spa Pool
Phased TCO | F-13-200 | Fab & Deliver Jacuzzi Eqp | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 13 - Special Construction > Jacuzzi | TT_Task | TK_NotStart | 2026-06-10 | 2026-10-01 | 80 | 379 | DIV 13 - Special Construction | Jacuzzi
Phased TCO | F-32-100 | Fab & Deliver Irrigation | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 32 - Exterior Site Improvements > Irrigation | TT_Task | TK_NotStart | 2026-06-10 | 2026-08-05 | 40 | 267 | DIV 32 - Exterior Site Improvements | Irrigation
Phased TCO | F-32-200 | Procure Landscaping | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 32 - Exterior Site Improvements > Landscape | TT_Task | TK_NotStart | 2026-06-10 | 2026-09-02 | 60 | 270 | DIV 32 - Exterior Site Improvements | Landscape
Phased TCO | F-32-300 | Fab & Deliver Parking Signage | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 32 - Exterior Site Improvements > Parking Signage | TT_Task | TK_NotStart | 2026-06-10 | 2026-08-05 | 40 | 315 | DIV 32 - Exterior Site Improvements | Parking Signage
Phased TCO | C-BH-200 | Install Buckhoists - 2nd Lift | no |  |  | no level in the Activity ID | CONSTRUCTION > Hoisting Equipment > Buckhoists | TT_Task | TK_NotStart | 2026-07-13 | 2026-07-16 | 4 | 5 | Hoisting Equipment | Buckhoists
Phased TCO | C-S1-EX-200x | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies & Ext Elev - L3 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 3rd to 7th Lvl | TT_Task | TK_NotStart | 2026-08-24 | 2026-09-21 | 20 | 200 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 3rd to
Phased TCO | C-BH-300 | Install Buckhoists - 3rd Lift | no |  |  | no level in the Activity ID | CONSTRUCTION > Hoisting Equipment > Buckhoists | TT_Task | TK_NotStart | 2026-08-25 | 2026-08-28 | 4 | 5 | Hoisting Equipment | Buckhoists
Phased TCO | C-SU-110 | Pull City Permit for Water | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > MOT Permitting & Setup | TT_Task | TK_NotStart | 2026-08-27 | 2026-11-30 | 65 | 44 | Site Utilities | MOT Permitting & Setup
Phased TCO | MS-KL-110 | Kitchen/Lobby Subcontract Procurement | no |  |  | no level in the Activity ID | SPECIAL DESIGN & PERMITTING > Lobby & Kitchen Design & Permit Revisions | TT_Task | TK_NotStart | 2026-08-28 | 2026-10-09 | 30 | 161 | Lobby & Kitchen Design & Permit Revisions | Lobby & Kitchen Design & Permit Revisions
Phased TCO | PMT-KL-100 | Master Permit Revision | no |  |  | no level in the Activity ID | SPECIAL DESIGN & PERMITTING > Lobby & Kitchen Design & Permit Revisions | TT_Task | TK_NotStart | 2026-08-28 | 2027-02-18 | 120 | 319 | Lobby & Kitchen Design & Permit Revisions | Lobby & Kitchen Design & Permit Revisions
Phased TCO | C-S2-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies & Ext Elev - L8 to L14 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 8th to 14th Lvl | TT_Task | TK_NotStart | 2026-10-06 | 2026-10-29 | 18 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 8th to
Phased TCO | C-S1-EX-220x | Paint Stucco Walls & Ceilings @ Balconies & Ext Elev - L3 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 3rd to 7th Lvl | TT_Task | TK_NotStart | 2026-10-20 | 2026-11-02 | 10 | 200 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 3rd to
Phased TCO | C-BH-400 | Install Buckhoists - 4th Lift | no |  |  | no level in the Activity ID | CONSTRUCTION > Hoisting Equipment > Buckhoists | TT_Task | TK_NotStart | 2026-10-21 | 2026-10-26 | 4 | 5 | Hoisting Equipment | Buckhoists
Phased TCO | C-S3-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies & Ext Elev - L15 to L20 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 15th to 20th Lvl | TT_Task | TK_NotStart | 2026-11-17 | 2026-12-14 | 18 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 15th to
Phased TCO | MS-KL-100 | Kitchen/Lobby Permit Received | no |  |  | no level in the Activity ID | SPECIAL DESIGN & PERMITTING > Lobby & Kitchen Design & Permit Revisions | TT_FinMile | TK_NotStart | 2026-11-24 | 2026-11-24 | 0 | 0 | Lobby & Kitchen Design & Permit Revisions | Lobby & Kitchen Design & Permit Revisions
Phased TCO | S-06-210 | Prep & Submit Millwork (Common Areas) | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 06 - Wood and Plastics > Millwork (Common Areas) | TT_Task | TK_NotStart | 2026-11-25 | 2027-01-11 | 30 | 0 | DIV 06 - Wood and Plastics | Millwork (Common Areas)
Phased TCO | S-11-110 | Prep & Submit Food Service Equipment | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 11 - Equipment > Food Service Equipment | TT_Task | TK_NotStart | 2026-11-25 | 2027-01-11 | 30 | 9 | DIV 11 - Equipment | Food Service Equipment
Phased TCO | C-SU-120 | Permit MOT Road Lanes Closure @ SW 11th St & 2nd Ave - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > MOT Permitting & Setup | TT_Task | TK_NotStart | 2026-12-01 | 2027-01-20 | 35 | 44 | Site Utilities | MOT Permitting & Setup
Phased TCO | C-S2-EX-220 | Paint Stucco Walls & Ceilings @ Balconies & Ext Elev - L8 to L14 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 8th to 14th Lvl | TT_Task | TK_NotStart | 2026-12-07 | 2026-12-18 | 10 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 8th to
Phased TCO | C-S4-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies & Ext Elev - L21 to L26 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 21st to 26th Lvl | TT_Task | TK_NotStart | 2027-01-04 | 2027-01-27 | 18 | 189 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 21st to
Phased TCO | R-06-210 | Review & Approve Millwork (Common Areas) | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 06 - Wood and Plastics > Millwork (Common Areas) | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-25 | 10 | 0 | DIV 06 - Wood and Plastics | Millwork (Common Areas)
Phased TCO | R-11-110 | Review & Approve Food Service Equipment | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 11 - Equipment > Food Service Equipment | TT_Task | TK_NotStart | 2027-01-12 | 2027-01-25 | 10 | 9 | DIV 11 - Equipment | Food Service Equipment
Phased TCO | C-BH-500 | Install Buckhoists - 5th Lift | no |  |  | no level in the Activity ID | CONSTRUCTION > Hoisting Equipment > Buckhoists | TT_Task | TK_NotStart | 2027-01-20 | 2027-01-25 | 4 | 3 | Hoisting Equipment | Buckhoists
Phased TCO | C-S3-EX-220 | Paint Stucco Walls & Ceilings @ Balconies & Ext Elev - L15 to L20 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 15th to 20th Lvl | TT_Task | TK_NotStart | 2027-01-20 | 2027-02-02 | 10 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 15th to
Phased TCO | F-06-210 | Fab & Deliver Millwork (Common Areas) | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 06 - Wood and Plastics > Millwork (Common Areas) | TT_Task | TK_NotStart | 2027-01-26 | 2027-05-28 | 89 | 0 | DIV 06 - Wood and Plastics | Millwork (Common Areas)
Phased TCO | F-11-110 | Fab & Deliver Food Service Equipment | no |  |  | no level in the Activity ID | SUBMITTALS & PROCUREMENT1 > DIV 11 - Equipment > Food Service Equipment | TT_Task | TK_NotStart | 2027-01-26 | 2027-05-17 | 80 | 9 | DIV 11 - Equipment | Food Service Equipment
Phased TCO | PR-MS-520 | Structure Top out | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2027-01-29 | 2027-01-29 | 0 | 76 | Interim Milestones | Interim Milestones
Phased TCO | C-SU-200 | Order & Setup MOT @ SW 11th St & 2nd Ave - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > MOT Permitting & Setup | TT_Task | TK_NotStart | 2027-02-01 | 2027-02-12 | 10 | 37 | Site Utilities | MOT Permitting & Setup
Phased TCO | C-S5-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies & Ext Elev - L27 to L32 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 27th to 32nd Lvl | TT_Task | TK_NotStart | 2027-02-15 | 2027-03-10 | 18 | 183 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 27th to
Phased TCO | C-SU-210 | Demo & Sawcut Exist Asphalt Pavement & Sidewalk @ SW 11th St & 2nd Ave - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > MOT Permitting & Setup | TT_Task | TK_NotStart | 2027-02-15 | 2027-02-26 | 10 | 37 | Site Utilities | MOT Permitting & Setup
Phased TCO | C-SU-600 | Excavate for Water Piping @ East - Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities | TT_Task | TK_NotStart | 2027-02-23 | 2027-03-02 | 6 | 37 | Site Utilities | Water Site Utilities
Phased TCO | C-RF-EX-700 | Prep Surface for Stucco @ Roof Elevations | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 33rd to Roof Lvl | TT_Task | TK_NotStart | 2027-02-24 | 2027-03-01 | 4 | 48 | Exterior Envelope | Exterior Balconies & Elevations (Drops)
Phased TCO | C-RF-EX-710 | Apply Stucco Scratch/Brown/Finish Coats @ Roof Elevations | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 33rd to Roof Lvl | TT_Task | TK_NotStart | 2027-02-24 | 2027-03-09 | 10 | 48 | Exterior Envelope | Exterior Balconies & Elevations (Drops)
Phased TCO | C-S4-EX-220 | Paint Stucco Walls & Ceilings @ Balconies & Ext Elev - L21 to L26 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 21st to 26th Lvl | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-16 | 10 | 193 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 21st to
Phased TCO | C-SU-610 | Install Water Main Crossings @ SW 11th St - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities | TT_Task | TK_NotStart | 2027-03-03 | 2027-03-12 | 8 | 37 | Site Utilities | Water Site Utilities
Phased TCO | C-RF-EX-770 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Ext Elevations - L1 & L2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Elevations at L1 & L2 | TT_Task | TK_NotStart | 2027-03-10 | 2027-03-23 | 10 | 48 | Exterior Envelope | Exterior Elevations at L1 & L2
Phased TCO | C-S6-EX-200 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Balconies & Ext Elev - L33 to Roof | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 33rd to Roof Lvl | TT_Task | TK_NotStart | 2027-03-11 | 2027-03-26 | 12 | 195 | Exterior Envelope | Exterior Balconies & Elevations (Drops)
Phased TCO | C-EV12-100 | Set Divider & Hoist Beams @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-03-15 | 2027-03-17 | 3 | 55 | Vertical Conveying | Elevators #3 & #4
Phased TCO | C-SU-620 | Install Water Main Crossings @ SW 2nd Ave - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities | TT_Task | TK_NotStart | 2027-03-15 | 2027-03-30 | 12 | 37 | Site Utilities | Water Site Utilities
Phased TCO | C-RF-EX-730 | Paint Stucco @ Roof Elevations | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 33rd to Roof Lvl | TT_Task | TK_NotStart | 2027-03-17 | 2027-03-22 | 4 | 54 | Exterior Envelope | Exterior Balconies & Elevations (Drops)
Phased TCO | C-EV12-110 | Build Car Sling & Stack Rails @Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-03-18 | 2027-04-07 | 15 | 55 | Vertical Conveying | Elevators #3 & #4
Phased TCO | PR-MS-510 | S.O.G Complete | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2027-03-18 | 2027-03-18 | 0 | 0 | Interim Milestones | Interim Milestones
Phased TCO | C-RF-EX-790 | Paint Stucco @ Ext Elevations - L1 & L2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Elevations at L1 & L2 | TT_Task | TK_NotStart | 2027-03-24 | 2027-03-30 | 5 | 48 | Exterior Envelope | Exterior Elevations at L1 & L2
Phased TCO | C-EV12-120 | Set Door Jambs @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-03-31 | 2027-04-13 | 10 | 55 | Vertical Conveying | Elevators #3 & #4
Phased TCO | C-EV12-130 | Install Door Frames & Blocking & Controllers @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-04-06 | 2027-04-26 | 15 | 55 | Vertical Conveying | Elevators #3 & #4
Phased TCO | C-N-EX-350 | Install Exterior Decorative Metal Louvers @ North Elev - L2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation (Facade) Louvers & Lighting & Signage > Exterior Elevation (Facade) Louvers | TT_Task | TK_NotStart | 2027-04-07 | 2027-04-09 | 3 | 230 | Exterior Envelope | Exterior Elevation (Facade) Louvers
Phased TCO | C-EV12-170 | Set Elev Equipment & Mech A/C @ Machine Room -Roof Lvl | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-04-08 | 2027-04-19 | 8 | 79 | Vertical Conveying | Elevators #3 & #4
Phased TCO | C-E-EX-350 | Install Exterior Decorative Metal Louvers @ East Elev - L2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation (Facade) Louvers & Lighting & Signage > Exterior Elevation (Facade) Louvers | TT_Task | TK_NotStart | 2027-04-12 | 2027-04-20 | 7 | 230 | Exterior Envelope | Exterior Elevation (Facade) Louvers
Phased TCO | C-S5-EX-220 | Paint Stucco Walls & Ceilings @ Balconies & Ext Elev - L27 to L32 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 27th to 32nd Lvl | TT_Task | TK_NotStart | 2027-04-14 | 2027-04-27 | 10 | 185 | Exterior Envelope | Exterior Balconies & Elevations (Drops) at 27th to
Phased TCO | PR-MS-570 | Exterior Glazing Complete | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2027-04-14 | 2027-04-14 | 0 | 56 | Interim Milestones | Interim Milestones
Phased TCO | C-CR-300 | Remove Crane @ Tower Crane | no |  |  | no level in the Activity ID | CONSTRUCTION > Hoisting Equipment > Tower Crane | TT_Task | TK_NotStart | 2027-04-16 | 2027-04-22 | 5 | 0 | Hoisting Equipment | Tower Crane
Phased TCO | C-EV12-140 | Set Equipment & Drop Lines @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-04-21 | 2027-05-04 | 10 | 55 | Vertical Conveying | Elevators #3 & #4
Phased TCO | C-S-EX-450 | Install Exterior Decorative Metal Louvers @ South Elev - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation (Facade) Louvers & Lighting & Signage > Exterior Elevation (Facade) Louvers | TT_Task | TK_NotStart | 2027-04-21 | 2027-05-12 | 16 | 230 | Exterior Envelope | Exterior Elevation (Facade) Louvers
Phased TCO | PR-MS-550 | Tower Crane Removed | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2027-04-22 | 2027-04-22 | 0 | 0 | Interim Milestones | Interim Milestones
Phased TCO | C-SU-300 | Install Sewer Lateral @ SW 11th St - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Sewer Site Utilities | TT_Task | TK_NotStart | 2027-04-23 | 2027-04-29 | 5 | 15 | Site Utilities | Sewer Site Utilities
Phased TCO | C-SU-400 | Install Drainage Trench Drains @ South - On-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Drainage Site Utilities | TT_Task | TK_NotStart | 2027-04-23 | 2027-05-10 | 12 | 0 | Site Utilities | Drainage Site Utilities
Phased TCO | C-S6-EX-220 | Paint Stucco Walls & Ceilings @ Balconies & Ext Elev - L33 to Roof | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Balconies & Drops > Exterior Balconies & Elevations (Drops) at 33rd to Roof Lvl | TT_Task | TK_NotStart | 2027-04-30 | 2027-05-07 | 6 | 183 | Exterior Envelope | Exterior Balconies & Elevations (Drops)
Phased TCO | C-EV12-150 | Install Elevator Pit Equipment & Work @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-05-05 | 2027-05-11 | 5 | 55 | Vertical Conveying | Elevators #3 & #4
Phased TCO | PR-MS-590 | Complete Exterior Stucco & Paint Work | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2027-05-07 | 2027-05-07 | 0 | 359 | Interim Milestones | Interim Milestones
Phased TCO | C-EV12-160 | Build Cab @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-21 | 10 | 55 | Vertical Conveying | Elevators #3 & #4
Phased TCO | C-N-EX-440 | Install Exterior Facade Lighting @ North Elev | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation (Facade) Louvers & Lighting & Signage > Exterior Elevation (Facade) Lighting | TT_Task | TK_NotStart | 2027-05-10 | 2027-05-21 | 10 | 183 | Exterior Envelope | Exterior Elevation (Facade) Lighting
Phased TCO | C-SU-410 | Install Drainage HDPE Pipes & Structures @ South - On-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Drainage Site Utilities | TT_Task | TK_NotStart | 2027-05-11 | 2027-06-01 | 15 | 13 | Site Utilities | Drainage Site Utilities
Phased TCO | C-SU-420 | Install Drainage Trench Drain @ East - On-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Drainage Site Utilities | TT_Task | TK_NotStart | 2027-05-11 | 2027-05-20 | 8 | 0 | Site Utilities | Drainage Site Utilities
Phased TCO | C-S-EX-550 | Install Exterior Decorative Metal Louvers @ South Elev - L2 (Comeback) | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation (Facade) Louvers & Lighting & Signage > Exterior Elevation (Facade) Louvers | TT_Task | TK_NotStart | 2027-05-13 | 2027-05-21 | 7 | 230 | Exterior Envelope | Exterior Elevation (Facade) Louvers
Phased TCO | C-EV12-180 | Install Traveling Cable & Robe Cabs @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-05-17 | 2027-05-28 | 10 | 55 | Vertical Conveying | Elevators #3 & #4
Phased TCO | C-EV12-190 | Install Hoistway Wiring & Switches & Call Station & Fixtures @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-05-20 | 2027-06-03 | 10 | 55 | Vertical Conveying | Elevators #3 & #4
Phased TCO | C-SU-310 | Install Sewer Manholes, Piping, & Cleanouts @ SW 2nd Ave - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Sewer Site Utilities | TT_Task | TK_NotStart | 2027-05-21 | 2027-06-11 | 15 | 0 | Site Utilities | Sewer Site Utilities
Phased TCO | C-EV34-100 | Set Divider & Hoist Beams @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-05-24 | 2027-05-26 | 3 | 61 | Vertical Conveying | Elevators #1 & #2
Phased TCO | C-W-EX-440 | Install Exterior Facade Lighting @ West Elev | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation (Facade) Louvers & Lighting & Signage > Exterior Elevation (Facade) Lighting | TT_Task | TK_NotStart | 2027-05-24 | 2027-06-02 | 7 | 183 | Exterior Envelope | Exterior Elevation (Facade) Lighting
Phased TCO | C-EV34-110 | Build Car Sling & Stack Rails @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-05-27 | 2027-06-17 | 15 | 61 | Vertical Conveying | Elevators #1 & #2
Phased TCO | C-E-EX-440 | Install Exterior Facade Lighting @ East Elev | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation (Facade) Louvers & Lighting & Signage > Exterior Elevation (Facade) Lighting | TT_Task | TK_NotStart | 2027-06-03 | 2027-06-10 | 6 | 183 | Exterior Envelope | Exterior Elevation (Facade) Lighting
Phased TCO | C-EV12-300 | Partial Fire Alarm Integration @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-06-04 | 2027-06-10 | 5 | 55 | Vertical Conveying | Elevators #3 & #4
Phased TCO | C-EV34-120 | Set Door Jambs @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-06-10 | 2027-06-23 | 10 | 61 | Vertical Conveying | Elevators #1 & #2
Phased TCO | C-EV12-310 | Adjust & Align ELev. Doors @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-06-11 | 2027-06-18 | 6 | 55 | Vertical Conveying | Elevators #3 & #4
Phased TCO | C-S-EX-440 | Install Exterior Facade Lighting @ South Elev | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation (Facade) Louvers & Lighting & Signage > Exterior Elevation (Facade) Lighting | TT_Task | TK_NotStart | 2027-06-11 | 2027-06-24 | 10 | 183 | Exterior Envelope | Exterior Elevation (Facade) Lighting
Phased TCO | C-SU-320 | F/RP Concrete Slab at Sewer Laterals @ SW 11th St - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Sewer Site Utilities | TT_Task | TK_NotStart | 2027-06-14 | 2027-06-25 | 10 | 0 | Site Utilities | Sewer Site Utilities
Phased TCO | C-SU-430 | Install Drainage HDPE Pipes & Structure @ SW 11th St - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Drainage Site Utilities | TT_Task | TK_NotStart | 2027-06-14 | 2027-06-18 | 5 | 5 | Site Utilities | Drainage Site Utilities
Phased TCO | C-SU-500 | Install Fire Lines @ East - On-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Fire Lines | TT_Task | TK_NotStart | 2027-06-14 | 2027-06-25 | 10 | 13 | Site Utilities | Fire Lines
Phased TCO | C-EV34-130 | Install Door Frames & Blocking & Controllers @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-06-16 | 2027-07-07 | 15 | 61 | Vertical Conveying | Elevators #1 & #2
Phased TCO | C-EV12-320 | In-House Test Elevator @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-06-21 | 2027-06-23 | 3 | 55 | Vertical Conveying | Elevators #3 & #4
Phased TCO | C-SU-440 | Install Drainage HDPE Pipes & Structures @ East - On-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Drainage Site Utilities | TT_Task | TK_NotStart | 2027-06-21 | 2027-07-02 | 10 | 130 | Site Utilities | Drainage Site Utilities
Phased TCO | PR-MS-530 | Temp For Test (FPL Power) | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_Task | TK_NotStart | 2027-06-23 | 2027-06-27 | 5 | 0 | Interim Milestones | Interim Milestones
Phased TCO | C-EV12-330 | Elevator Burn-in Time @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_Task | TK_NotStart | 2027-06-24 | 2027-06-25 | 2 | 55 | Vertical Conveying | Elevators #3 & #4
Phased TCO | C-EV12-340 | Elevators Ready for Construction Use @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #3 & #4 | TT_FinMile | TK_NotStart | 2027-06-25 | 2027-06-25 | 0 | 55 | Vertical Conveying | Elevators #3 & #4
Phased TCO | C-RF-EX-750 | Install Exterior Facade Lighting @ Roof Elevations | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation (Facade) Louvers & Lighting & Signage > Exterior Elevation (Facade) Lighting | TT_Task | TK_NotStart | 2027-06-25 | 2027-07-06 | 7 | 183 | Exterior Envelope | Exterior Elevation (Facade) Lighting
Phased TCO | PR-MS-540 | Permanent Power Available | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2027-06-27 | 2027-06-27 | 0 | 0 | Interim Milestones | Interim Milestones
Phased TCO | C-BH-600 | Remove Buckhoists | no |  |  | no level in the Activity ID | CONSTRUCTION > Hoisting Equipment > Buckhoists | TT_Task | TK_NotStart | 2027-06-28 | 2027-07-19 | 15 | 55 | Hoisting Equipment | Buckhoists
Phased TCO | C-SR1-100 | Prep Concrete & CMU Surface @ East Stair #1 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Stairs > Stair #1 - East | TT_Task | TK_NotStart | 2027-06-28 | 2027-07-19 | 15 | 105 | Vertical Conveying | Stair #1 - East
Phased TCO | C-SU-510 | Install FDCs @ East - On-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Fire Lines | TT_Task | TK_NotStart | 2027-06-28 | 2027-07-02 | 5 | 13 | Site Utilities | Fire Lines
Phased TCO | C-SU-900 | Backfill & Compact Utilities @ SW 11th St & 2nd Ave - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > MOT Permitting & Setup | TT_Task | TK_NotStart | 2027-06-28 | 2027-07-08 | 8 | 0 | Site Utilities | MOT Permitting & Setup
Phased TCO | PR-PC-100 | Generator Test (Lvl 1-14) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_Task | TK_NotStart | 2027-06-28 | 2027-07-02 | 5 | 140 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | C-EV34-140 | Set Equipment & Drop Lines @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-07-01 | 2027-07-15 | 10 | 61 | Vertical Conveying | Elevators #1 & #2
Phased TCO | C-RF-EX-760 | Install Exterior Bldg Signage @ North Elev - Roof | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation (Facade) Louvers & Lighting & Signage > Exterior Elevation (Facade) Signage | TT_Task | TK_NotStart | 2027-07-07 | 2027-07-20 | 10 | 190 | Exterior Envelope | Exterior Elevation (Facade) Signage
Phased TCO | C-SR1-110 | Install Guardrails & Handrails @ East Stair #1 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Stairs > Stair #1 - East | TT_Task | TK_NotStart | 2027-07-08 | 2027-07-28 | 15 | 120 | Vertical Conveying | Stair #1 - East
Phased TCO | C-SU-910 | Lay Limerock Base @ SW 11th St & 2nd Ave - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > MOT Permitting & Setup | TT_Task | TK_NotStart | 2027-07-09 | 2027-07-16 | 6 | 0 | Site Utilities | MOT Permitting & Setup
Phased TCO | PR-PC-130 | Start-up HVAC Cooling Towers & DAOUs Equipment | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_Task | TK_NotStart | 2027-07-14 | 2027-07-20 | 5 | 74 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | C-EV34-150 | Install Elevator Pit Equipment & Work @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-07-16 | 2027-07-22 | 5 | 61 | Vertical Conveying | Elevators #1 & #2
Phased TCO | C-SU-920 | Temporary Resurface Exit Pavement @ SW 11th St & 2nd Ave - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > MOT Permitting & Setup | TT_Task | TK_NotStart | 2027-07-19 | 2027-07-22 | 4 | 0 | Site Utilities | MOT Permitting & Setup
Phased TCO | PR-MS-580 | Buckhoists Removed | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2027-07-19 | 2027-07-19 | 0 | 78 | Interim Milestones | Interim Milestones
Phased TCO | C-BH1-EX-100 | Lay Exterior CMU & Balcony Edges @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Exterior Envelope at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-07-20 | 2027-07-22 | 3 | 55 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L2 to L7
Phased TCO | C-SR2-100 | Prep Concrete & CMU Surface @ West Stair #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Stairs > Stair #2 - West | TT_Task | TK_NotStart | 2027-07-20 | 2027-08-09 | 15 | 105 | Vertical Conveying | Stair #2 - West
Phased TCO | C-BH1-FN-100 | Install Remaining Drywall Framing @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Wall Framing at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-07-21 | 2027-07-27 | 5 | 55 | Comeback Work at Buckhoist Area Units | Wall Framing at Comeback Units at L2 to L7
Phased TCO | C-EV34-160 | Build Cab @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-07-21 | 2027-08-03 | 10 | 61 | Vertical Conveying | Elevators #1 & #2
Phased TCO | C-S-EX-560 | Install Exterior Bldg Signage @ South Elev - L2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Exterior Envelope > Exterior Facade at Elevations > Exterior Elevation (Facade) Louvers & Lighting & Signage > Exterior Elevation (Facade) Signage | TT_Task | TK_NotStart | 2027-07-21 | 2027-07-30 | 8 | 190 | Exterior Envelope | Exterior Elevation (Facade) Signage
Phased TCO | C-BH1-EX-110 | Install Exterior Glazing @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Exterior Envelope at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-07-22 | 2027-07-26 | 3 | 57 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L2 to L7
Phased TCO | C-BH1-MP-100 | Install Remaining MEP Rough @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > MEP Rough at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-07-22 | 2027-08-04 | 10 | 55 | Comeback Work at Buckhoist Area Units | MEP Rough at Comeback Units at L2 to L7
Phased TCO | C-SU-700 | Perform Flush & Pressure & Chloronation Tests @ Water | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities > Water Testing | TT_Task | TK_NotStart | 2027-07-23 | 2027-07-29 | 5 | 2 | Site Utilities | Water Testing
Phased TCO | C-SU-800 | Prep As-Built Submittal | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities > Conveyance Process | TT_Task | TK_NotStart | 2027-07-23 | 2027-08-05 | 10 | 0 | Site Utilities | Conveyance Process
Phased TCO | C-SU-930 | Remove MOT @ SW 11th St & 2nd Ave - Off-Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > MOT Permitting & Setup | TT_Task | TK_NotStart | 2027-07-23 | 2027-07-29 | 5 | 112 | Site Utilities | MOT Permitting & Setup
Phased TCO | C-BH1-EX-120 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Comeback Balconies - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Exterior Envelope at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-07-27 | 2027-08-05 | 8 | 71 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L2 to L7
Phased TCO | C-BH1-FN-110 | Install Door Frames @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Wall Framing at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-07-27 | 2027-07-28 | 2 | 62 | Comeback Work at Buckhoist Area Units | Wall Framing at Comeback Units at L2 to L7
Phased TCO | C-BH2-EX-100 | Lay Exterior CMU & Balcony Edges @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Exterior Envelope at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-07-27 | 2027-07-29 | 3 | 57 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L8 to L15
Phased TCO | C-BH2-FN-100 | Install Remaining Drywall Framing @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Wall Framing at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-07-28 | 2027-08-03 | 5 | 57 | Comeback Work at Buckhoist Area Units | Wall Framing at Comeback Units at L8 to L15
Phased TCO | C-EV34-180 | Install Traveling Cable & Robe Cabs @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-07-28 | 2027-08-10 | 10 | 61 | Vertical Conveying | Elevators #1 & #2
Phased TCO | C-BH2-EX-110 | Install Exterior Glazing @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Exterior Envelope at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-07-29 | 2027-08-02 | 3 | 69 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L8 to L15
Phased TCO | C-BH2-MP-100 | Install Remaining MEP Rough @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > MEP Rough at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-07-29 | 2027-08-11 | 10 | 57 | Comeback Work at Buckhoist Area Units | MEP Rough at Comeback Units at L8 to L15
Phased TCO | C-BH3-MP-100 | Install Remaining MEP Rough @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > MEP Rough at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-07-29 | 2027-08-11 | 10 | 76 | Comeback Work at Buckhoist Area Units | MEP Rough at Comeback Units at L16 to L25
Phased TCO | C-SR1-120 | Install Stair Doors & Hardware @ East Stair #1 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Stairs > Stair #1 - East | TT_Task | TK_NotStart | 2027-07-29 | 2027-08-06 | 7 | 120 | Vertical Conveying | Stair #1 - East
Phased TCO | C-SR2-110 | Install Guardrails & Handrails @ West Stair #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Stairs > Stair #2 - West | TT_Task | TK_NotStart | 2027-07-29 | 2027-08-18 | 15 | 105 | Vertical Conveying | Stair #2 - West
Phased TCO | PR-MS-560 | Complete Site Utilities Work | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2027-07-29 | 2027-07-29 | 0 | 165 | Interim Milestones | Interim Milestones
Phased TCO | C-SU-710 | Provide Pressure Test Report by WASD/City | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities > Water Testing | TT_Task | TK_NotStart | 2027-07-30 | 2027-08-05 | 5 | 2 | Site Utilities | Water Testing
Phased TCO | PR-MS-610 | Complete Exterior Elevations Work | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2027-07-30 | 2027-07-30 | 0 | 275 | Interim Milestones | Interim Milestones
Phased TCO | C-BH3-FN-100 | Install Remaining Drywall Framing @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Wall Framing at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-06 | 5 | 76 | Comeback Work at Buckhoist Area Units | Wall Framing at Comeback Units at L16 to L25
Phased TCO | C-EV34-190 | Install Hoistway Wiring & Switches & Call Station & Fixtures @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-13 | 10 | 61 | Vertical Conveying | Elevators #1 & #2
Phased TCO | PR-PC-200 | Fire Damper Testing (Lvl 1-14) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_Task | TK_NotStart | 2027-08-02 | 2027-08-13 | 10 | 66 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | C-BH2-EX-120 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Comeback Balconies - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Exterior Envelope at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-08-03 | 2027-08-12 | 8 | 69 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L8 to L15
Phased TCO | C-BH2-FN-110 | Install Door Frames @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Wall Framing at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-08-03 | 2027-08-04 | 2 | 63 | Comeback Work at Buckhoist Area Units | Wall Framing at Comeback Units at L8 to L15
Phased TCO | C-BH3-EX-100 | Lay Exterior CMU & Balcony Edges @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Exterior Envelope at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-03 | 2027-08-05 | 3 | 71 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L16 to L25
Phased TCO | C-BH1-MP-110 | Inspect MEP Rough @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > MEP Rough at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-05 | 2027-08-06 | 2 | 55 | Comeback Work at Buckhoist Area Units | MEP Rough at Comeback Units at L2 to L7
Phased TCO | C-BH3-EX-110 | Install Exterior Glazing @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Exterior Envelope at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-05 | 2027-08-09 | 3 | 71 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L16 to L25
Phased TCO | C-BH4-MP-100 | Install Remaining MEP Rough @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > MEP Rough at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-05 | 2027-08-18 | 10 | 76 | Comeback Work at Buckhoist Area Units | MEP Rough at Comeback Units at L26 to L35
Phased TCO | PR-PC-110 | Commission Fire Pump | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_Task | TK_NotStart | 2027-08-05 | 2027-09-01 | 20 | 98 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | C-BH1-EX-130 | Apply Waterproofing & Install Tiles @ Comeback Balconies - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Exterior Envelope at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-06 | 2027-08-09 | 2 | 71 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L2 to L7
Phased TCO | C-BH3-FN-110 | Install Door Frames @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Wall Framing at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-06 | 2027-08-09 | 2 | 80 | Comeback Work at Buckhoist Area Units | Wall Framing at Comeback Units at L16 to L25
Phased TCO | C-SU-720 | Perform Bact-T Test @ Water | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities > Water Testing | TT_Task | TK_NotStart | 2027-08-06 | 2027-08-10 | 3 | 2 | Site Utilities | Water Testing
Phased TCO | C-SU-810 | Review & Submit Water As-Built Submittal by EOR | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities > Conveyance Process | TT_Task | TK_NotStart | 2027-08-06 | 2027-08-19 | 10 | 0 | Site Utilities | Conveyance Process
Phased TCO | C-BH1-FN-200 | Install Drywall One Side @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-09 | 2027-08-12 | 4 | 55 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Phased TCO | C-BH4-FN-100 | Install Remaining Drywall Framing @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Wall Framing at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-09 | 2027-08-13 | 5 | 76 | Comeback Work at Buckhoist Area Units | Wall Framing at Comeback Units at L26 to L35
Phased TCO | C-SR1-130 | Install Light Fixtures & Exit Signs @ East Stair #1 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Stairs > Stair #1 - East | TT_Task | TK_NotStart | 2027-08-09 | 2027-08-17 | 7 | 166 | Vertical Conveying | Stair #1 - East
Phased TCO | C-BH1-EX-140 | Paint Stucco Walls & Ceilings @ Comeback Balconies - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Exterior Envelope at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-10 | 2027-08-11 | 2 | 71 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L2 to L7
Phased TCO | C-BH3-EX-120 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Comeback Balconies - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Exterior Envelope at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-10 | 2027-08-19 | 8 | 71 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L16 to L25
Phased TCO | C-BH3-FN-260 | Tape & Finish GWB Drop Ceilings/Soffits @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-10 | 2027-08-12 | 3 | 77 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Phased TCO | C-BH4-EX-100 | Lay Exterior CMU & Balcony Edges @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Exterior Envelope at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-10 | 2027-08-12 | 3 | 71 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L26 to L35
Phased TCO | C-BH3-FN-250 | Hang GWB Drop Ceilings/Soffits @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-11 | 2027-08-16 | 4 | 77 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Phased TCO | C-BH3-FN-270 | Hang Interior Doors @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-11 | 2027-08-12 | 2 | 77 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Phased TCO | C-BH3-FN-300 | Install Kitchen Cabinets & Countertops @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-11 | 2027-08-16 | 4 | 82 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Phased TCO | C-BH3-MP-230 | Install Light Fixtures @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > MEP Trim at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-11 | 2027-08-13 | 3 | 82 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L16 to L25
Phased TCO | C-SU-730 | Prepare Force Main & Water Clearance Letter for HRS by EOR | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities > Water Testing | TT_Task | TK_NotStart | 2027-08-11 | 2027-08-17 | 5 | 2 | Site Utilities | Water Testing
Phased TCO | C-BH1-EX-150 | Install Balcony Glass Railings @ Comeback Balconies - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Exterior Envelope at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-12 | 2027-08-16 | 3 | 71 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L2 to L7
Phased TCO | C-BH1-FN-210 | Install Drywall Insulation @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-12 | 2027-08-13 | 2 | 55 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Phased TCO | C-BH2-MP-110 | Inspect MEP Rough @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > MEP Rough at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-08-12 | 2027-08-13 | 2 | 57 | Comeback Work at Buckhoist Area Units | MEP Rough at Comeback Units at L8 to L15
Phased TCO | C-BH3-FN-230 | Frame GWB Drop Ceilings/Soffits @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-12 | 2027-08-17 | 4 | 77 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Phased TCO | C-BH3-FN-280 | Paint Drywall @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-12 | 2027-08-16 | 3 | 76 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Phased TCO | C-BH3-FN-500 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 > Bathrooms at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-12 | 2027-08-17 | 4 | 76 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L16 to L25
Phased TCO | C-BH3-MP-110 | Inspect MEP Rough @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > MEP Rough at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-12 | 2027-08-13 | 2 | 76 | Comeback Work at Buckhoist Area Units | MEP Rough at Comeback Units at L16 to L25
Phased TCO | C-BH3-MP-200 | Install HVAC Trim & Control @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > MEP Trim at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-12 | 2027-08-13 | 2 | 81 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L16 to L25
Phased TCO | C-BH3-MP-210 | Install FP Sprinkler Heads @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > MEP Trim at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-12 | 2027-08-13 | 2 | 80 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L16 to L25
Phased TCO | C-BH3-MP-220 | Install Electrical Power Trim @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > MEP Trim at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-12 | 2027-08-13 | 2 | 80 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L16 to L25
Phased TCO | C-BH4-EX-110 | Install Exterior Glazing @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Exterior Envelope at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-12 | 2027-08-16 | 3 | 71 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L26 to L35
Phased TCO | C-BH1-FN-220 | Hang Drywall @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-13 | 2027-08-17 | 3 | 55 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Phased TCO | C-BH1-FN-230 | Frame GWB Drop Ceilings/Soffits @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-13 | 2027-08-18 | 4 | 55 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Phased TCO | C-BH2-EX-130 | Apply Waterproofing & Install Tiles @ Comeback Balconies - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Exterior Envelope at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-08-13 | 2027-08-16 | 2 | 69 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L8 to L15
Phased TCO | C-BH2-FN-200 | Install Drywall One Side @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-08-13 | 2027-08-18 | 4 | 57 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Phased TCO | C-BH3-FN-240 | Tape & Finish Drywall @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-13 | 2027-08-17 | 3 | 76 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Phased TCO | C-BH3-FN-310 | Install Door Hardware @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-13 | 2027-08-16 | 2 | 81 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Phased TCO | C-BH4-FN-110 | Install Door Frames @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Wall Framing at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-13 | 2027-08-16 | 2 | 80 | Comeback Work at Buckhoist Area Units | Wall Framing at Comeback Units at L26 to L35
Phased TCO | C-BH1-FN-240 | Tape & Finish Drywall @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-16 | 2027-08-18 | 3 | 61 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Phased TCO | C-BH3-FN-200 | Install Drywall One Side @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-16 | 2027-08-19 | 4 | 76 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Phased TCO | C-BH3-FN-220 | Hang Drywall @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-16 | 2027-08-18 | 3 | 76 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Phased TCO | C-BH3-MP-240 | Install FA & Low Voltage Devices @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > MEP Trim at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-16 | 2027-08-16 | 1 | 80 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L16 to L25
Phased TCO | C-EV34-300 | Partial Fire Alarm Integration @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-08-16 | 2027-08-20 | 5 | 61 | Vertical Conveying | Elevators #1 & #2
Phased TCO | PR-PC-1120 | Fire Damper Testing (Lvl 15-36) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | TT_Task | TK_NotStart | 2027-08-16 | 2027-08-27 | 10 | 66 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2
Phased TCO | C-BH2-EX-140 | Paint Stucco Walls & Ceilings @ Comeback Balconies - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Exterior Envelope at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-08-17 | 2027-08-20 | 4 | 69 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L8 to L15
Phased TCO | C-BH3-FN-210 | Install Drywall Insulation @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-17 | 2027-08-18 | 2 | 76 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Phased TCO | C-BH3-FN-320 | Install Flooring & Base @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-17 | 2027-08-20 | 4 | 78 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Phased TCO | C-BH4-EX-120 | Prepare Surface & Stucco Walls & Ceilings & Caulk Openings @ Comeback Balconies - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Exterior Envelope at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-17 | 2027-08-26 | 8 | 71 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L26 to L35
Phased TCO | C-BH4-FN-260 | Tape & Finish GWB Drop Ceilings/Soffits @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-17 | 2027-08-19 | 3 | 77 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Phased TCO | C-BH2-FN-210 | Install Drywall Insulation @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-19 | 2 | 57 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Phased TCO | C-BH3-FN-510 | Install Vanities & Mirrors @ B/Rs - Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 > Bathrooms at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-19 | 2 | 76 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L16 to L25
Phased TCO | C-BH4-FN-250 | Hang GWB Drop Ceilings/Soffits @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-23 | 4 | 77 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Phased TCO | C-BH4-FN-270 | Hang Interior Doors @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-19 | 2 | 77 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Phased TCO | C-BH4-FN-300 | Install Kitchen Cabinets & Countertops @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-23 | 4 | 82 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Phased TCO | C-BH4-MP-230 | Install Light Fixtures @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > MEP Trim at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-20 | 3 | 82 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L26 to L35
Phased TCO | C-SR1-140 | Install Signage @ East Stair #1 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Stairs > Stair #1 - East | TT_Task | TK_NotStart | 2027-08-18 | 2027-08-20 | 3 | 170 | Vertical Conveying | Stair #1 - East
Phased TCO | C-SU-740 | HRS Certification & Release | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities > Water Testing | TT_Task | TK_NotStart | 2027-08-18 | 2027-09-15 | 20 | 2 | Site Utilities | Water Testing
Phased TCO | C-BH1-FN-250 | Hang GWB Drop Ceilings/Soffits @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-19 | 2027-08-24 | 4 | 55 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Phased TCO | C-BH2-FN-220 | Hang Drywall @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-08-19 | 2027-08-23 | 3 | 57 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Phased TCO | C-BH2-FN-230 | Frame GWB Drop Ceilings/Soffits @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-08-19 | 2027-08-24 | 4 | 57 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Phased TCO | C-BH3-FN-330 | Install Kitchen Appliances @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-19 | 2027-08-19 | 1 | 78 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Phased TCO | C-BH4-FN-230 | Frame GWB Drop Ceilings/Soffits @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-19 | 2027-08-24 | 4 | 77 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Phased TCO | C-BH4-FN-280 | Paint Drywall @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-19 | 2027-08-23 | 3 | 76 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Phased TCO | C-BH4-FN-500 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 > Bathrooms at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-19 | 2027-08-24 | 4 | 76 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L26 to L35
Phased TCO | C-BH4-MP-110 | Inspect MEP Rough @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > MEP Rough at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-19 | 2027-08-20 | 2 | 76 | Comeback Work at Buckhoist Area Units | MEP Rough at Comeback Units at L26 to L35
Phased TCO | C-BH4-MP-200 | Install HVAC Trim & Control @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > MEP Trim at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-19 | 2027-08-20 | 2 | 81 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L26 to L35
Phased TCO | C-BH4-MP-210 | Install FP Sprinkler Heads @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > MEP Trim at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-19 | 2027-08-20 | 2 | 80 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L26 to L35
Phased TCO | C-BH4-MP-220 | Install Electrical Power Trim @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > MEP Trim at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-19 | 2027-08-20 | 2 | 80 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L26 to L35
Phased TCO | C-SR2-120 | Install Stair Doors & Hardware @ West Stair #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Stairs > Stair #2 - West | TT_Task | TK_NotStart | 2027-08-19 | 2027-08-27 | 7 | 105 | Vertical Conveying | Stair #2 - West
Phased TCO | PR-PC-120 | Commission Fire Alarm System (Fire Command Work) (Lvl 1-14) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_Task | TK_NotStart | 2027-08-19 | 2027-10-14 | 40 | 7 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | PR-PC-140 | Commission Generator (Lvl 1-14) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_Task | TK_NotStart | 2027-08-19 | 2027-09-16 | 20 | 52 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | C-BH1-FN-260 | Tape & Finish GWB Drop Ceilings/Soffits @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-20 | 2027-08-24 | 3 | 55 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Phased TCO | C-BH2-FN-240 | Tape & Finish Drywall @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-08-20 | 2027-08-24 | 3 | 63 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Phased TCO | C-BH3-EX-130 | Apply Waterproofing & Install Tiles @ Comeback Balconies - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Exterior Envelope at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-20 | 2027-08-23 | 2 | 71 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L16 to L25
Phased TCO | C-BH3-FN-520 | Install Shower Enclosures @ B/Rs Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 > Bathrooms at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-20 | 2027-08-23 | 2 | 76 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L16 to L25
Phased TCO | C-BH3-FN-540 | Install Toilet Accessories @ B/Rs - Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 > Bathrooms at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-20 | 2027-08-20 | 1 | 76 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L16 to L25
Phased TCO | C-BH3-MP-530 | Install Plumbing Fixtures @ B/Rs - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 > Bathrooms at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-20 | 2027-08-23 | 2 | 76 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L16 to L25
Phased TCO | C-BH4-FN-240 | Tape & Finish Drywall @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-20 | 2027-08-24 | 3 | 76 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Phased TCO | C-BH4-FN-310 | Install Door Hardware @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-20 | 2027-08-23 | 2 | 81 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Phased TCO | C-SU-820 | Review & Approve Water As-Built Submittal by WASD | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities > Conveyance Process | TT_Task | TK_NotStart | 2027-08-20 | 2027-09-17 | 20 | 0 | Site Utilities | Conveyance Process
Phased TCO | C-BH2-EX-150 | Install Balcony Glass Railings @ Comeback Balconies - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Exterior Envelope at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-08-23 | 2027-08-25 | 3 | 69 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L8 to L15
Phased TCO | C-BH3-FN-400 | Rough Cleanup @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Interior Finishes at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-23 | 2027-08-23 | 1 | 76 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L16 to L25
Phased TCO | C-BH4-FN-200 | Install Drywall One Side @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-23 | 2027-08-26 | 4 | 76 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Phased TCO | C-BH4-FN-220 | Hang Drywall @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-23 | 2027-08-25 | 3 | 76 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Phased TCO | C-BH4-MP-240 | Install FA & Low Voltage Devices @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > MEP Trim at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-23 | 2027-08-23 | 1 | 80 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L26 to L35
Phased TCO | C-EV34-310 | Adjust & Align ELev. Doors @ Elev #1 & #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-08-23 | 2027-08-30 | 6 | 61 | Vertical Conveying | Elevators #1 & #2
Phased TCO | C-BH1-FN-270 | Hang Interior Doors @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-24 | 2027-08-25 | 2 | 55 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Phased TCO | C-BH3-EX-140 | Paint Stucco Walls & Ceilings @ Comeback Balconies - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Exterior Envelope at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-24 | 2027-08-25 | 2 | 71 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L16 to L25
Phased TCO | C-BH4-FN-210 | Install Drywall Insulation @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-24 | 2027-08-25 | 2 | 76 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Phased TCO | C-BH4-FN-320 | Install Flooring & Base @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-24 | 2027-08-27 | 4 | 78 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Phased TCO | C-BH1-FN-280 | Paint Drywall @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-25 | 2027-08-27 | 3 | 55 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Phased TCO | C-BH2-FN-250 | Hang GWB Drop Ceilings/Soffits @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-08-25 | 2027-08-30 | 4 | 57 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Phased TCO | C-BH4-FN-510 | Install Vanities & Mirrors @ B/Rs - Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 > Bathrooms at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-25 | 2027-08-26 | 2 | 76 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L26 to L35
Phased TCO | C-BH1-FN-500 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 > Bathrooms at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-26 | 2027-08-31 | 4 | 55 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L2 to L7
Phased TCO | C-BH1-MP-200 | Install HVAC Trim & Control @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > MEP Trim at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-26 | 2027-08-27 | 2 | 61 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L2 to L7
Phased TCO | C-BH2-FN-260 | Tape & Finish GWB Drop Ceilings/Soffits @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-08-26 | 2027-08-30 | 3 | 57 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Phased TCO | C-BH3-EX-150 | Install Balcony Glass Railings @ Comeback Balconies - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Exterior Envelope at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-26 | 2027-08-30 | 3 | 71 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L16 to L25
Phased TCO | C-BH4-FN-330 | Install Kitchen Appliances @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-26 | 2027-08-26 | 1 | 78 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Phased TCO | C-BH1-MP-210 | Install FP Sprinkler Heads @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > MEP Trim at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-27 | 2027-08-30 | 2 | 58 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L2 to L7
Phased TCO | C-BH4-EX-130 | Apply Waterproofing & Install Tiles @ Comeback Balconies - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Exterior Envelope at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-27 | 2027-08-30 | 2 | 71 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L26 to L35
Phased TCO | C-BH4-FN-520 | Install Shower Enclosures @ B/Rs Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 > Bathrooms at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-27 | 2027-08-30 | 2 | 76 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L26 to L35
Phased TCO | C-BH4-FN-540 | Install Toilet Accessories @ B/Rs - Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 > Bathrooms at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-27 | 2027-08-27 | 1 | 76 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L26 to L35
Phased TCO | C-BH4-MP-530 | Install Plumbing Fixtures @ B/Rs - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 > Bathrooms at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-27 | 2027-08-30 | 2 | 76 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L26 to L35
Phased TCO | C-BH1-FN-300 | Install Kitchen Cabinets & Countertops @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-30 | 2027-09-02 | 4 | 55 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Phased TCO | C-BH1-FN-310 | Install Door Hardware @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-30 | 2027-08-31 | 2 | 60 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Phased TCO | C-BH1-MP-220 | Install Electrical Power Trim @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > MEP Trim at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-30 | 2027-08-31 | 2 | 58 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L2 to L7
Phased TCO | C-BH2-FN-270 | Hang Interior Doors @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-08-30 | 2027-08-31 | 2 | 57 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Phased TCO | C-BH4-FN-400 | Rough Cleanup @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Interior Finishes at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-30 | 2027-08-30 | 1 | 76 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L26 to L35
Phased TCO | C-SR2-130 | Install Light Fixtures & Exit Signs @ West Stair #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Stairs > Stair #2 - West | TT_Task | TK_NotStart | 2027-08-30 | 2027-09-08 | 7 | 158 | Vertical Conveying | Stair #2 - West
Phased TCO | PR-PC-1110 | Fire Smoke Test (Lvl 15-36) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | TT_Task | TK_NotStart | 2027-08-30 | 2027-09-13 | 10 | 66 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2
Phased TCO | PR-PC-190 | Stair Pressurization Test | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_Task | TK_NotStart | 2027-08-30 | 2027-09-03 | 5 | 105 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | C-BH1-MP-230 | Install Light Fixtures @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > MEP Trim at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-08-31 | 2027-09-02 | 3 | 58 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L2 to L7
Phased TCO | C-BH2-FN-280 | Paint Drywall @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-08-31 | 2027-09-02 | 3 | 57 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Phased TCO | C-BH3-PC-900 | Partial MEP Systems Inspections @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Partial Inspections & Punchout at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-08-31 | 2027-09-02 | 3 | 71 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L16 to L25
Phased TCO | C-BH4-EX-140 | Paint Stucco Walls & Ceilings @ Comeback Balconies - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Exterior Envelope at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-08-31 | 2027-09-01 | 2 | 71 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L26 to L35
Phased TCO | C-EV34-320 | In-House Test Elevator @ Elev #3 & #4 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Elevators > Elevators #1 & #2 | TT_Task | TK_NotStart | 2027-08-31 | 2027-09-02 | 3 | 61 | Vertical Conveying | Elevators #1 & #2
Phased TCO | C-BH1-FN-510 | Install Vanities & Mirrors @ B/Rs - Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 > Bathrooms at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-01 | 2027-09-02 | 2 | 55 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L2 to L7
Phased TCO | C-BH1-MP-240 | Install FA & Low Voltage Devices @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > MEP Trim at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-01 | 2027-09-01 | 1 | 58 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L2 to L7
Phased TCO | C-BH2-FN-500 | Apply Waterproofing & Install Floor/Walls Tiles @ B/Rs - Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 > Bathrooms at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-01 | 2027-09-07 | 4 | 57 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L8 to L15
Phased TCO | C-BH2-MP-200 | Install HVAC Trim & Control @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > MEP Trim at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-01 | 2027-09-02 | 2 | 62 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L8 to L15
Phased TCO | C-BH2-MP-210 | Install FP Sprinkler Heads @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > MEP Trim at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-02 | 2027-09-03 | 2 | 60 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L8 to L15
Phased TCO | C-BH4-EX-150 | Install Balcony Glass Railings @ Comeback Balconies - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Exterior Envelope at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-09-02 | 2027-09-07 | 3 | 71 | Comeback Work at Buckhoist Area Units | Exterior Envelope at Comeback Units at L26 to L35
Phased TCO | C-BH1-FN-320 | Install Flooring & Base @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-09 | 4 | 55 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Phased TCO | C-BH1-FN-520 | Install Shower Enclosures @ B/Rs Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 > Bathrooms at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-07 | 2 | 55 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L2 to L7
Phased TCO | C-BH2-FN-310 | Install Door Hardware @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-07 | 2 | 61 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Phased TCO | C-BH2-MP-220 | Install Electrical Power Trim @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > MEP Trim at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-07 | 2 | 60 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L8 to L15
Phased TCO | C-BH2-MP-230 | Install Light Fixtures @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > MEP Trim at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-08 | 3 | 60 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L8 to L15
Phased TCO | C-BH3-PC-910 | Subcontractor Punch List & Punch Paint @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Partial Inspections & Punchout at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-09-03 | 2027-09-10 | 5 | 71 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L16 to L25
Phased TCO | C-BH1-FN-540 | Install Toilet Accessories @ B/Rs - Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 > Bathrooms at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-07 | 2027-09-07 | 1 | 55 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L2 to L7
Phased TCO | C-BH1-MP-530 | Install Plumbing Fixtures @ B/Rs - Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 > Bathrooms at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-07 | 2027-09-08 | 2 | 55 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L2 to L7
Phased TCO | C-BH2-MP-240 | Install FA & Low Voltage Devices @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > MEP Trim at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-07 | 2027-09-07 | 1 | 60 | Comeback Work at Buckhoist Area Units | MEP Trim at Comeback Units at L8 to L15
Phased TCO | PR-PC-210 | Fire Smoke Test (Lvl 1-14) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_Task | TK_NotStart | 2027-09-07 | 2027-09-20 | 10 | 105 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | C-BH1-FN-330 | Install Kitchen Appliances @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-08 | 2027-09-08 | 1 | 55 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Phased TCO | C-BH1-FN-400 | Rough Cleanup @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Interior Finishes at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-08 | 2027-09-08 | 1 | 55 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L2 to L7
Phased TCO | C-BH2-FN-320 | Install Flooring & Base @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-08 | 2027-09-13 | 4 | 58 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Phased TCO | C-BH2-FN-510 | Install Vanities & Mirrors @ B/Rs - Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 > Bathrooms at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-08 | 2027-09-09 | 2 | 57 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L8 to L15
Phased TCO | C-BH4-PC-900 | Partial MEP Systems Inspections @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Partial Inspections & Punchout at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-09-08 | 2027-09-10 | 3 | 71 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L26 to L35
Phased TCO | C-BH1-PC-900 | Partial MEP Systems Inspections @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Partial Inspections & Punchout at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-09 | 2027-09-13 | 3 | 55 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L2 to L7
Phased TCO | C-BH2-FN-300 | Install Kitchen Cabinets & Countertops @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-09 | 2027-09-14 | 4 | 57 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Phased TCO | C-SR2-140 | Install Signage @ West Stair #2 | no |  |  | no level in the Activity ID | CONSTRUCTION > Vertical Conveying > Stairs > Stair #2 - West | TT_Task | TK_NotStart | 2027-09-09 | 2027-09-15 | 5 | 158 | Vertical Conveying | Stair #2 - West
Phased TCO | C-BH2-FN-520 | Install Shower Enclosures @ B/Rs Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 > Bathrooms at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-10 | 2027-09-13 | 2 | 57 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L8 to L15
Phased TCO | C-BH2-FN-540 | Install Toilet Accessories @ B/Rs - Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 > Bathrooms at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-10 | 2027-09-10 | 1 | 57 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L8 to L15
Phased TCO | C-BH2-MP-530 | Install Plumbing Fixtures @ B/Rs - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 > Bathrooms at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-10 | 2027-09-13 | 2 | 57 | Comeback Work at Buckhoist Area Units | Bathrooms at Comeback Units at L8 to L15
Phased TCO | C-BH2-FN-330 | Install Kitchen Appliances @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-13 | 2027-09-13 | 1 | 57 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Phased TCO | C-BH2-FN-400 | Rough Cleanup @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Interior Finishes at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-13 | 2027-09-13 | 1 | 57 | Comeback Work at Buckhoist Area Units | Interior Finishes at Comeback Units at L8 to L15
Phased TCO | C-BH3-PC-920 | GC Punchlist @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Partial Inspections & Punchout at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-09-13 | 2027-09-16 | 4 | 71 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L16 to L25
Phased TCO | C-BH4-PC-910 | Subcontractor Punch List & Punch Paint @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Partial Inspections & Punchout at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-09-13 | 2027-09-17 | 5 | 71 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L26 to L35
Phased TCO | C-BH1-PC-910 | Subcontractor Punch List & Punch Paint @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Partial Inspections & Punchout at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-14 | 2027-09-20 | 5 | 55 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L2 to L7
Phased TCO | C-BH2-PC-900 | Partial MEP Systems Inspections @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Partial Inspections & Punchout at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-14 | 2027-09-16 | 3 | 57 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L8 to L15
Phased TCO | PR-PC-1000 | Smoke Test Report (Lvl 15-36) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | TT_Task | TK_NotStart | 2027-09-14 | 2027-09-20 | 5 | 86 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2
Phased TCO | PR-PC-1200 | Final Fire Suppression Inspections (Lvl 15-36) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | TT_Task | TK_NotStart | 2027-09-14 | 2027-09-23 | 8 | 108 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2
Phased TCO | PR-PC-1220 | Test & Balance Report (Lvl 15-36) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | TT_Task | TK_NotStart | 2027-09-14 | 2027-09-27 | 10 | 66 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2
Phased TCO | C-BH2-PC-910 | Subcontractor Punch List & Punch Paint @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Partial Inspections & Punchout at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-17 | 2027-09-23 | 5 | 57 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L8 to L15
Phased TCO | C-BH3-PC-930 | Final Cleanup @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Partial Inspections & Punchout at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-09-17 | 2027-09-17 | 1 | 71 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L16 to L25
Phased TCO | PR-PC-150 | Elevator Transfer & Load Test (Elev #1 & #2) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_Task | TK_NotStart | 2027-09-17 | 2027-09-23 | 5 | 152 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | PR-PC-160 | Elevator Transfer & Load Test (Elev #3) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_Task | TK_NotStart | 2027-09-17 | 2027-09-23 | 5 | 52 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | C-BH3-PC-940 | Touchup Paint @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Partial Inspections & Punchout at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-09-20 | 2027-09-21 | 2 | 71 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L16 to L25
Phased TCO | C-BH4-PC-920 | GC Punchlist @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Partial Inspections & Punchout at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-09-20 | 2027-09-23 | 4 | 71 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L26 to L35
Phased TCO | C-SU-630 | Install Backflow Preventers @ Drop-off Area - L1 | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities | TT_Task | TK_NotStart | 2027-09-20 | 2027-09-28 | 7 | 113 | Site Utilities | Water Site Utilities
Phased TCO | C-SU-830 | Prepare Full Conveyance Package | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities > Conveyance Process | TT_Task | TK_NotStart | 2027-09-20 | 2027-10-01 | 10 | 0 | Site Utilities | Conveyance Process
Phased TCO | C-BH1-PC-920 | GC Punchlist @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Partial Inspections & Punchout at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-21 | 2027-09-24 | 4 | 55 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L2 to L7
Phased TCO | PR-PC-220 | Smoke Test Report (Lvl 1-14) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_Task | TK_NotStart | 2027-09-21 | 2027-09-27 | 5 | 125 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | PR-PC-230 | Test & Balance Report (Lvl 1-14) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_Task | TK_NotStart | 2027-09-21 | 2027-10-04 | 10 | 105 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | PR-PC-600 | Final Fire Suppression Inspections (Lvl 1-14) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_Task | TK_NotStart | 2027-09-21 | 2027-09-30 | 8 | 147 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | C-BH2-PC-920 | GC Punchlist @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Partial Inspections & Punchout at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-24 | 2027-09-29 | 4 | 57 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L8 to L15
Phased TCO | C-BH4-PC-930 | Final Cleanup @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Partial Inspections & Punchout at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-09-24 | 2027-09-24 | 1 | 71 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L26 to L35
Phased TCO | C-BH1-PC-930 | Final Cleanup @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Partial Inspections & Punchout at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-27 | 2027-09-27 | 1 | 55 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L2 to L7
Phased TCO | C-BH4-PC-940 | Touchup Paint @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Partial Inspections & Punchout at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-09-27 | 2027-09-28 | 2 | 71 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L26 to L35
Phased TCO | C-BH1-PC-940 | Touchup Paint @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Partial Inspections & Punchout at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-28 | 2027-09-29 | 2 | 55 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L2 to L7
Phased TCO | PR-PC-1100 | Test & Balance HVAC (Lvl 15-36) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | TT_Task | TK_NotStart | 2027-09-28 | 2027-10-25 | 20 | 66 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2
Phased TCO | C-BH1-PC-950 | Owner/Arch Punch List @ Comeback Units - L2 to L7 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L2 to L7 > Partial Inspections & Punchout at Comeback Units at L2 to L7 | TT_Task | TK_NotStart | 2027-09-30 | 2027-10-06 | 5 | 55 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L2 to L7
Phased TCO | C-BH2-PC-930 | Final Cleanup @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Partial Inspections & Punchout at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-09-30 | 2027-09-30 | 1 | 57 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L8 to L15
Phased TCO | C-BH2-PC-940 | Touchup Paint @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Partial Inspections & Punchout at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-10-01 | 2027-10-04 | 2 | 57 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L8 to L15
Phased TCO | C-SU-840 | Review & Approval of Full Conveyance Package by WASD | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities > Conveyance Process | TT_Task | TK_NotStart | 2027-10-04 | 2027-11-10 | 28 | 0 | Site Utilities | Conveyance Process
Phased TCO | PR-MS-200 | Contract MS #1 (22 months): Unit Key Delivery @ L2 to L15 | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Contract Milestones | TT_FinMile | TK_NotStart | 2027-10-04 | 2027-10-04 | 0 | 44 | Contract Milestones | Contract Milestones
Phased TCO | PR-PC-240 | Test & Balance HVAC (Lvl 1-14) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_Task | TK_NotStart | 2027-10-05 | 2027-11-01 | 20 | 105 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | C-BH2-PC-950 | Owner/Arch Punch List @ Comeback Units - L8 to L15 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L8 to L15 > Partial Inspections & Punchout at Comeback Units at L8 to L15 | TT_Task | TK_NotStart | 2027-10-07 | 2027-10-13 | 5 | 55 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L8 to L15
Phased TCO | C-BH3-PC-950 | Owner/Arch Punch List @ Comeback Units - L16 to L25 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L16 to L25 > Partial Inspections & Punchout at Comeback Units at L16 to L25 | TT_Task | TK_NotStart | 2027-10-14 | 2027-10-20 | 5 | 55 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L16 to L25
Phased TCO | PR-PC-1020 | Commission Generator (Lvl 15-36) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | TT_Task | TK_NotStart | 2027-10-15 | 2027-11-11 | 20 | 22 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2
Phased TCO | PR-PC-1030 | Commission Fire Alarm System (Fire Command Work) (Lvl 15-36) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | TT_Task | TK_NotStart | 2027-10-15 | 2027-12-13 | 40 | 7 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2
Phased TCO | PR-PC-170 | Fire Alarm Testing (Lvl 1-14) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_Task | TK_NotStart | 2027-10-15 | 2027-10-28 | 10 | 37 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | C-BH4-PC-950 | Owner/Arch Punch List @ Comeback Units - L26 to L35 | no |  |  | no level in the Activity ID | CONSTRUCTION > Comeback Work at Buckhoist Area Units > Comeback Work at Buckhoist Area Units at L26 to L35 > Partial Inspections & Punchout at Comeback Units at L26 to L35 | TT_Task | TK_NotStart | 2027-10-21 | 2027-10-27 | 5 | 55 | Comeback Work at Buckhoist Area Units | Partial Inspections & Punchout at Comeback Units at L26 to L35
Phased TCO | PR-PC-1170 | Final Mechanical Inspections (Lvl 15-36) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | TT_Task | TK_NotStart | 2027-10-26 | 2027-11-22 | 20 | 66 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2
Phased TCO | PR-MS-630 | Complete Pool & Pool Deck Work at 36th Pool Level | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2027-10-27 | 2027-10-27 | 0 | 186 | Interim Milestones | Interim Milestones
Phased TCO | PR-PC-500 | Life Safety Testing & Commissioning Complete (Lvl 1-14) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_FinMile | TK_NotStart | 2027-10-28 | 2027-10-28 | 0 | 102 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | PR-PC-610 | Final FA & Low Voltage Inspections (Lvl 1-14) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_Task | TK_NotStart | 2027-10-29 | 2027-11-18 | 15 | 112 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | PR-PC-620 | Final Electrical Inspections (Lvl 1-14) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_Task | TK_NotStart | 2027-10-29 | 2027-12-06 | 25 | 102 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | PR-MS-620 | Complete Roof Deck Work at 7th Lvl | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2027-11-02 | 2027-11-02 | 0 | 180 | Interim Milestones | Interim Milestones
Phased TCO | PR-PC-630 | Final Mechanical Inspections (Lvl 1-14) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_Task | TK_NotStart | 2027-11-02 | 2027-12-01 | 20 | 105 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | C-SU-850 | Schedule & Install Water Meter @ East - Site | no |  |  | no level in the Activity ID | CONSTRUCTION > Site Utilities > Water Site Utilities > Conveyance Process | TT_Task | TK_NotStart | 2027-11-11 | 2027-11-17 | 5 | 0 | Site Utilities | Conveyance Process
Phased TCO | PR-PC-1210 | Elevator Transfer & Load Test (Elev #4) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | TT_Task | TK_NotStart | 2027-11-12 | 2027-11-18 | 5 | 22 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2
Phased TCO | PR-MS-600 | Complete Conveyance & Water Meter Work | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Interim Milestones | TT_FinMile | TK_NotStart | 2027-11-17 | 2027-11-17 | 0 | 0 | Interim Milestones | Interim Milestones
Phased TCO | PR-MS-800 | Substantial Completion (TCO#1) (11/17/27) | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Contract Milestones | TT_FinMile | TK_NotStart | 2027-11-17 | 2027-11-17 | 0 | 0 | Contract Milestones | Contract Milestones
Phased TCO | PR-PC-180 | Final Plumbing Inspections (Lvl 1-14) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_Task | TK_NotStart | 2027-11-18 | 2027-12-03 | 10 | 49 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | PR-PC-700 | Life Safety Final Complete (Lvl 1-14) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_FinMile | TK_NotStart | 2027-11-18 | 2027-11-18 | 0 | 112 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | PR-PC-900 | Final Punchout (Lvl 1-14) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_Task | TK_NotStart | 2027-11-18 | 2028-01-18 | 62 | 62 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | PR-PC-990 | Project Closeout (Lvl 1-14) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_Task | TK_NotStart | 2027-11-18 | 2028-01-18 | 62 | 62 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | PR-MS-300 | Contract MS #2 (24 months): Unit Key Delivery @ L16 to L25 | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Contract Milestones | TT_FinMile | TK_NotStart | 2027-12-01 | 2027-12-01 | 0 | 110 | Contract Milestones | Contract Milestones
Phased TCO | PR-PC-1160 | Final Plumbing Inspections (Lvl 15-36) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | TT_Task | TK_NotStart | 2027-12-06 | 2027-12-17 | 10 | 49 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2
Phased TCO | PR-PC-800 | Building Final (Lvl 1-14) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | TT_Task | TK_NotStart | 2027-12-07 | 2027-12-28 | 15 | 102 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#1
Phased TCO | PR-PC-1080 | Fire Alarm Testing (Lvl 15-36) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | TT_Task | TK_NotStart | 2027-12-14 | 2028-01-13 | 21 | 7 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2
Phased TCO | PR-PC-1150 | Life Safety Testing & Commissioning Complete | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | TT_FinMile | TK_NotStart | 2028-01-13 | 2028-01-13 | 0 | 7 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2
Phased TCO | PR-PC-1180 | Final FA & Low Voltage Inspections (Lvl 15-36) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | TT_Task | TK_NotStart | 2028-01-14 | 2028-02-03 | 15 | 17 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2
Phased TCO | PR-PC-1190 | Final Electrical Inspections (Lvl 15-36) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | TT_Task | TK_NotStart | 2028-01-14 | 2028-02-17 | 25 | 7 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2
Phased TCO | PR-MS-400 | Contract MS #3 (26 months): Unit Key Delivery @ L26 to L35 | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Contract Milestones | TT_FinMile | TK_NotStart | 2028-01-28 | 2028-01-28 | 0 | 52 | Contract Milestones | Contract Milestones
Phased TCO | PR-PC-1230 | Life Safety Final Complete (Lvl 15-36) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | TT_FinMile | TK_NotStart | 2028-02-03 | 2028-02-03 | 0 | 17 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2
Phased TCO | PR-PC-1130 | Building Final (Lvl 15-36) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | TT_Task | TK_NotStart | 2028-02-18 | 2028-03-09 | 15 | 7 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2
Phased TCO | PR-MS-910 | Substantial Completion (TCO#2) (03/21/28) | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Contract Milestones | TT_FinMile | TK_NotStart | 2028-03-20 | 2028-03-20 | 0 | 0 | Contract Milestones | Contract Milestones
Phased TCO | PR-PC-1050 | Project Closeout (Lvl 15-36) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | TT_Task | TK_NotStart | 2028-03-21 | 2028-05-21 | 62 | 0 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2
Phased TCO | PR-PC-1140 | Final Punchout (Lvl 15-36) | no |  |  | no level in the Activity ID | PROJECT FINAL TESTING & INSPECTION & CLOSEOUT > PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | TT_Task | TK_NotStart | 2028-03-21 | 2028-05-21 | 62 | 0 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2 | PROJECT FINAL TESTING & INSPECTION PHASED TCO#2
Phased TCO | PR-MS-900 | Final Completion (C.O.) (05/22/28) | no |  |  | no level in the Activity ID | PROJECT MILESTONES & SUMMARY > Contract Milestones | TT_FinMile | TK_NotStart | 2028-05-21 | 2028-05-21 | 0 | 0 | Contract Milestones | Contract Milestones

## Notes
Domus II flowline dataset
Sources | Baseline: 20251031_Domus_II_-_Baseline_Schedule_v1.0a.xer · Phased TCO: 20260421_Domus_II_Phased_TCO_Schedule.xer (data date 22-Oct-25 in both).
Generated by | flowline_lbm.py, default grouping rules for Domus II (Activity ID patterns). Same data as the published flowline report.
Bands sheet | One row per schedule, band and level. start, finish, activities and work_days are formulas over the Activities sheet; activity_ids lists the Activity IDs in that band and level, ordered by start date.
Activities sheet | One row per activity in each schedule, including those left out of the bands, with the reason in excluded_reason.
start / finish | Actual dates where the activity has progress, otherwise early dates. Neither schedule has progress loaded, so these are early dates.
work_days | Sum of original durations (hours / 8) of the activities in the band and level. Overlapping activities add up, so it can exceed the calendar span.
total_float_d | Total float from the XER, hours / 8.
Level | Taken from the Activity ID, C-<level>-…; level 0 (foundations) is outside the configured range.
WBS crosswalk | How the scheduler's WBS groups map to the flowline bands. Counts are formulas over the Activities sheet (only activities with a level). A WBS group can feed two bands, and a band can draw from several WBS groups.